## Table 1_Sched_Council_Alt_2
Table 1: APRE/ Subbasin Planning Integration, Proposed Project Schedule and Tasks
Element |  |  | Estimated Days | Start | Finish
1. Project Integration |  |  | 149 days | 2005-03-05 | 2005-07-05
| 1A. Project Management and Coordination |  | 149 days | 2005-03-05 | 2005-06-05
| 1B. Regional / Coordination / Integration |  | 116 days | 2005-03-05 | 2005-06-05
| 1C. Convene Advisory Committee (Key Entities) |  | 125 days | 2005-03-05 | 2005-06-05
| 1D. Provide Formal Reports on Results |  | 138 days | 2005-03-05 | 2005-07-05
2. Develop Information System and Tools/Conduct Workshops |  |  | 138 days | 2005-03-05 | 2005-06-05
| 2A. Refine Implementation Plan |  | 20 days | 2005-03-05 | 2005-04-05
(Establish participants. Implement plan for goal and objective development for each subbasin and long term integration)
| 2B. Guidelines / Standards for Process / Methods |  | 20 days | 2005-03-05 | 2005-04-05
(Develop final guidelines document / manual for AHA model, changes to guidelines and standards during process)
| 2C. Information System Design, Development, Support (Manage, Maintain Data and Information) |  | 115 days | 2005-03-05 | 2005-06-05
|  | Organize Current Information | 36 days | 2005-03-05 | 2005-04-05
|  | Organize information for planning, SBP (habitat), APRE (AP), Harvest (CWT, other) for planning sessions. Enter "default' values for all stocks (Hatchery and Natural) in data base. |  | 2005-03-05
|  | Develop Short and Long Term Data and Information Needs | 115 days | 2005-03-05 | 2005-06-05
|  | Identify, implement needs for data base. Plan for utilization of existing data. Develop method, tools for aggregation of objectives at subbasin, province and basin level directed at stakeholder needs (Council, NOAA, States). |  | 2005-03-05
|  | Develop policy for long term maintenance responsibilities of information system | 20 days | 2005-03-05 | 2005-04-05
| 2D. Implement Process to Integrate Regional Activities for Anadromous Stocks |  | 91 days | 2005-03-05 | 2005-06-05
|  | Conduct training workshops with technical staff on the use of tools (3 workshops) | 29 days | 2005-04-05 | 2005-04-05
|  | Plan and conduct Work Session |  | 2005-05-05 | 2005-05-05
|  | Conduct Follow-up Communication at Subbasin Level and provide products |  | 2005-05-05 | 2005-05-05
|  | Hold subbasin work sessions with co-managers and others to complete data collation (5 worksessions) | 29 days | 2005-04-05 | 2005-05-05
| 2E. Conduct Follow-up Review |  | 138 days | 2005-06-05 | 2005-06-05

## Table 2_ Budget_Council_Alt_2
Table 2: APRE/ Subbasin Planning Integration, Project Budget
|  |  | Labor | [22 empty] | Travel | [6 empty] | Supplies / Equipment/ Printing |  |  |  | Proposed Budget March through July 2005 |  |  |  | Estimated FY 04 Budget by Task | Estimated FY 05 Budget by Task
| Work Element | Work Element Title | Biometrician / Principal | Fisheries Biologist | Habitat Biologist | Hydo / Fisheries | Data Support | Data, Workshop Support | Programming (MBI) | Programming / Sub | Workshop Facilitation | 0 | 0 | 0 | Senior Project Manager | Project Coord. | Techncial Writing | Techncial Review | Facilitation | 0 | 0 | 0 | 0 | Total Hours | Labor Cost | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Office Supplies/Equipment | Field/Research Supplies/Equipment | Supplies / Equipment / Printing | Labor | Travel | Supplies, Equip, Printing | TOTALS
|  |  | L. Mobrand | McConnaha | Watson | Malone | Garrow | Other | Greg Blair | Greyweather | John Barr | 0 | 0 | 0 | Warren | Ziji / Squier | Hemming / Other | Smith | Open | 0 | 0 | 0 | 0
| Element 1A | Project Management and Coordination | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 32207 | 600 | 0 | 750 | 273 | 129 | 75 | 1827 | 100 | 0 | 0 | 100 | 32207 | 2327 | 100 | 34634
| Element 1B | Regional / Coordination / Integration | 29 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 78 | 9615.25 | 200 | 0 | 300 | 93 | 38 | 14 | 645 | 50 | 0 | 0 | 50 | 9615.25 | 645 | 50 | 10310.25
| Element 1C | Convene Advisory Committee (Key Entities) | 12 | 15 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 5100 | 0 | 0 | 750 | 91 | 38 | 25 | 904 | 150 | 0 | 0 | 150 | 5100 | 904 | 150 | 6154
| Element 1D | Provide Formal Reports on Results | 8 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 43 | 4920.75 | 0 | 0 | 112.5 | 95 | 38 | 20 | 265.5 | 100 | 0 | 0 | 100 | 4920.75 | 265.5 | 100 | 5286.25
| Element 2A | Refine Implementation Plan | 15 | 17 | 2 | 2 | 6 | 0 | 10 | 15 | 18 | 0 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 10887.25 | 0 | 0 | 562.5 | 0 | 0 | 0 | 562.5 | 50 | 50 | 0 | 100 | 10887.25 | 562.5 | 100 | 11549.75
| Element 2B | Guidelines / Standards for Process / Methods | 19 | 5 | 0 | 0 | 20 | 0 | 5 | 5 | 28 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 8759 | 0 | 0 | 112.5 | 95 | 43 | 20 | 270.5 | 100 | 0 | 0 | 100 | 8759 | 270.5 | 100 | 9129.5
| Element 2C | Information System Design, Development, Support | 204 | 84 | 70 | 95 | 335 | 0 | 394 | 464 | 0 | 0 | 0 | 0 | 18 | 11 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 1715 | 179886.75 | 600 | 165 | 562.5 | 189 | 129 | 150 | 1795.5 | 100 | 0 | 0 | 100 | 179886.75 | 1795.5 | 100 | 181782.25
| Element 2D | Implement Process to Integrate Regional Activities for Anadromous Stocks | 4.25 | 4 | 0 | 3 | 28 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 26 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.25 | 32907 | 0 | 0 | 637.5 | 0 | 0 | 0 | 637.5 | 0 | 0 | 0 | 0 | 32907 | 4145 | 1000 | 38052
| Element 2E | Conduct Other Associated Follow-up Review | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 2472 | 0 | 0 | 75 | 95 | 41 | 15 | 226 | 25 | 0 | 0 | 25 | 2472 | 226 | 25 | 2723
|  | Total Hours | 303.25 | 155 | 72 | 100 | 402 | 0 | 409 | 484 | 55 | 0 | 0 | 0 | 281 | 87 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 2416.25
|  | Total Dollars | 49126.5 | 20770 | 7416 | 13000 | 21708 | 0 | 44990 | 50820 | 4908.75 | 0 | 0 | 0 | 25079.25 | 6851.25 | 0 | 5780 | 0 | 0 | 0 | 0 | 0 | 250449.75 | 286755 | 1400 | 165 | 3862.5 | 931 | 456 | 319 | 7133.5 | 675 | 50 | 0 | 725 | 250449.75 | 11141 | 1725 | 299621 | 0 | 0
[26 empty] | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Office Supplies/Equipment | Field/Research Supplies/Equipment | Supplies / Equipment / Printing
|  |  | Title |  | Name |  | Rate / Hour | [7 empty] | 85 | [16 empty] | 0 |  |  |  | 0 |  |  | Check | 263315.75 |  | Allocation Check
|  | 33 | Biometrician / Principal |  |  |  | 162 | [24 empty] | 0 |  |  |  | 0 |  |  | Sub detail | 0
|  | 34 | Fisheries Biologist |  |  |  | 134 | [14 empty] | 37710.5 |  | 437773.2 | [7 empty] | 0 |  |  |  | 0 |  |  |  | -263315.75
|  | 35 | Habitat Biologist |  |  |  | 103 | [24 empty] | 0 |  |  |  | 0
|  | 36 | Hydo / Fisheries |  |  |  | 130 | [24 empty] | 0 |  |  |  | 0
|  | 37 | Data Support |  |  |  | 54 | [24 empty] | 0 |  |  |  | 0
|  | 38 | Data, Workshop Support |  |  |  | 75 | [24 empty] | 0 |  |  |  | 0
|  | 39 | Programming (MBI) |  |  |  | 110 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 40 | Programming / Sub |  |  |  | 105
|  | 41 | Workshop Facilitation |  |  |  | 89.25
|  | 42 | 0
|  | 43 | 0
|  | 44 | 0
|  | 45 | Senior Project Manager |  |  |  | 89.25
|  | 46 | Project Coord. |  |  |  | 78.75
|  | 47 | Techncial Writing |  |  |  | 73.5
|  | 48 | Techncial Review |  |  |  | 85
|  | 49 | Facilitation |  |  |  | 250
|  | 50 | 0
|  | 51 | 0
|  | 52 | 0
|  | 53 | 0
|  |  | Title |  |  |  | Rate / Hour
|  |  | Biometrician / Principal (MBI) |  |  |  | 162
|  |  | Fisheries Biologist (MBI) |  |  |  | 134
|  |  | Habitat Biologist (MBI) |  |  |  | 103
|  |  | Hydro / Fisheries (MBI) |  |  |  | 130
|  |  | Data Support (MBI) |  |  |  | 54
|  |  | Programming (MBI) |  |  |  | 110
|  |  | Senior Programmer |  |  |  | 115.5
|  |  | *Programmer |  |  |  | 105
|  |  | HTML / Web Designer |  |  |  | 84
|  |  | Workshop Facilitation |  |  |  | 89.25
|  |  | Senior Project Manager |  |  |  | 89.25
|  |  | Project Coord. |  |  |  | 78.75
|  |  | Technical Writing |  |  |  | 73.5
|  |  | Technical Review |  |  |  | 89.25

## Table 3_Stocklist_Council_Alt_2
Table 3: APRE/ Subbasin Planning Integration, Anadromous Stocks Included in Project
No | Stock | Natural / Hatchery | Subbasin |  |  | Province
1 | Summer Steelhead-Natural | Natural | Asotin | 6A | 0 | Blue Mountain
2 | Fall Chinook Tule-Natural | Natural | Big White Salmon | 1F | 0 | Columbia Gorge
3 | Summer Steelhead-Natural | Natural | Big White Salmon | 1F | 0 | Columbia Gorge
4 | Winter Steelhead-Natural | Natural | Big White Salmon | 1F | 0 | Columbia Gorge
5 | Spring Chinook-Natural | Natural | Clearwater | 5A | 0 | Mountain Snake
6 | Steelhead A-Natural | Natural | Clearwater | 5A | 0 | Mountain Snake
7 | Steelhead B-Natural | Natural | Clearwater | 5A | 0 | Mountain Snake
8 | Coho (Clatskanie) - Natural | Natural | Columbia Estuary | 11A | 0 | Columbia Estuary
9 | Coho (Youngs Bay)- Natural | Natural | Columbia Estuary | 11A | 0 | Columbia Estuary
10 | Winter Steelhead (Scappoose/Clatskanie) - Natural | Natural | Columbia Estuary | 11A | 0 | Columbia Estuary
11 | Winter Steelhead (Youngs Bay) - Natural | Natural | Columbia Estuary | 11A | 0 | Columbia Estuary
12 | Chum- Natural | Natural | Cowlitz | 10B | 0 | Lower Columbia
13 | Coweeman Fall Chinook-Natural | Natural | Cowlitz | 10B | 0 | Lower Columbia
14 | Fall Chinook - Natural | Natural | Deschutes | 4D | 0 | Columbia Plateau
15 | Chum- Natural | Natural | Elochoman | 11B | 0 | Columbia River Estuary
16 | Late Winter Steelhead-Natural | Natural | Elochoman | 11B | 0 | Columbia River Estuary
17 | Spring Chinook-Natural | Natural | Entiat | 9B | 0 | Columbia Cascade
18 | Steelhead-Natural | Natural | Entiat | 9B | 0 | Columbia Cascade
19 | Cutthroat-Natural | Natural | Fifteenmile Creek | 1B | 0 | Columbia Gorge
20 | Winter Steelhead-Natural | Natural | Fifteenmile Creek | 1B | 0 | Columbia Gorge
21 | Fall Chinook-Natural | Natural | Grande Ronde | 6B | 0 | Blue Mountain
22 | Spring Chinook-Natural | Natural | Grande Ronde | 6B | 0 | Blue Mountain
23 | Summer Steelhead-Natural | Natural | Grande Ronde | 6B | 0 | Blue Mountain
24 | Fall Chinook-Natural | Natural | Grays | 11C | 0 | Columbia River Estuary
25 | Late Winter Steelhead-Natural | Natural | Grays | 11C | 0 | Columbia River Estuary
26 | Searun Cutthroat- Natural | Natural | Grays | 11C | 0 | Columbia River Estuary
27 | Coho-Natural | Natural | Hood | 1C | 0 | Columbia Gorge
28 | Fall Chinook-Natural | Natural | Hood | 1C | 0 | Columbia Gorge
29 | Sea Run Cutthroat-Natural | Natural | Hood | 1C | 0 | Columbia Gorge
30 | Spring Chinook-Natural | Natural | Hood | 1C | 0 | Columbia Gorge
31 | Fall Chinook (SRB)-Natural | Natural | Imnaha | 6C | 0 | Blue Mountain
32 | Spring Chinook Natural | Natural | John Day | 4E | 0 | Columbia Plateau
33 | Summer Steelhead Natural | Natural | John Day | 4E | 0 | Columbia Plateau
34 | Coho (Early)-Natural | Natural | Kalama | 10C | 0 | Lower Columbia
35 | Coho (Late)-Natural | Natural | Kalama | 10C | 0 | Lower Columbia
36 | Fall Chinook (Tule)-Natural | Natural | Klickitat | 1D | 0 | Columbia Gorge
37 | Summer Chinook-Natural | Natural | Klickitat | 1D | 0 | Columbia Gorge
38 | Summer Steelhead-Natural | Natural | Klickitat | 1D | 0 | Columbia Gorge
39 | Winter Steelhead-Natural | Natural | Klickitat | 1D | 0 | Columbia Gorge
40 | Chum- Natural | Natural | Lewis | 10D | 0 | Lower Columbia
41 | Fall Chinook LRB-Natural | Natural | Lewis | 10D | 0 | Lower Columbia
42 | Fall Chinook Tule-Natural | Natural | Lewis | 10D | 0 | Lower Columbia
43 | Late Winter Steelhead-Natural | Natural | Lewis | 10D | 0 | Lower Columbia
44 | Searun Cutthroat-Natural | Natural | Lewis | 10D | 0 | Lower Columbia
45 | Chum (Lower Columbia Tribs) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
46 | Coho (Big/Gnat) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
47 | Coho (Gorge) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
48 | Coho (Hood River) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
49 | Fall Chinook (Tule LCR Tribs) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
50 | Winter Steelhead (Big/Gnat) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
51 | Winter Steelhead (Gorge) - Natural | Natural | Lower Columbia | 10A | 0 | Lower Columbia
52 | Spring Chinook - Natural | Natural | Salmon | 5B | 0 | Mountain Snake
53 | Steelhead A-Natural | Natural | Salmon | 5B | 0 | Mountain Snake
54 | Steelhead B-Natural | Natural | Salmon | 5B | 0 | Mountain Snake
55 | Summer Chinook - Natural | Natural | Salmon | 5B | 0 | Mountain Snake
56 | Coho - Natural | Natural | Sandy | 10E | 0 | Lower Columbia
57 | Early Fall Chinook- Natural | Natural | Sandy | 10E | 0 | Lower Columbia
58 | Late Fall Chinook - Natural | Natural | Sandy | 10E | 0 | Lower Columbia
59 | Summer Steelhead - Natural | Natural | Snake Hells Canyon | 6D | 0 | Blue Mountain
60 | Spring Chinook- Natural | Natural | Walla Walla | 4J | 0 | Columbia Plateau
61 | Summer Steelhead-Natural | Natural | Walla Walla | 4J | 0 | Columbia Plateau
62 | Chum- Natural | Natural | Washougal | 10F | 0 | Lower Columbia
63 | Late Winter Steelhead-Natural | Natural | Washougal | 10F | 0 | Lower Columbia
64 | Calapooia Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
65 | Clackamas Early Coho - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
66 | Clackamas Fall Chinook - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
67 | Clackamas Late Coho - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
68 | Luckiamute Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
69 | Molalla Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
70 | North Santiam Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
71 | Rickreall Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
72 | South Santiam Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
73 | Tualatin Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
74 | Upper Willamette Fall Chinook Non-native - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
75 | Yamhill Winter Steelhead - Natural | Natural | Willamette | 10G | 0 | Lower Columbia
76 | Fall Chinook (Tule) Natural | Natural | Wind | 1G | 0 | Columbia Gorge
77 | Fall Chinook (URB)-Natural | Natural | Wind | 1G | 0 | Columbia Gorge
78 | Summer Steelhead Natural | Natural | Wind | 1G | 0 | Columbia Gorge
79 | Winter Steelhead Natural | Natural | Wind | 1G | 0 | Columbia Gorge
80 | American River Spring Chinook-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
81 | Naches Spring Chinook-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
82 | Naches Steelhead-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
83 | Satus Steelhead-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
84 | Toppenish Steelhead-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
85 | Upper Yakima Steelhead-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
86 | Yakima Summer Chinook-Natural | Natural | Yakima | 4C | 0 | Columbia Plateau
87 | Winter Steelhead (Skamania)-Hatchery | Hatchery | Big White Salmon | 1F | 1 | Columbia Gorge
88 | Coho | Hatchery | Clearwater | 5A | 1 | Mountain Snake
89 | Fall Chinook (Big Canyon)-Integrated | Hatchery | Clearwater | 5A | 1 | Mountain Snake
90 | Fall Chinook (NP Cherry Lane)- Integrated | Hatchery | Clearwater | 5A | 1 | Mountain Snake
91 | Spring Chinook (Clearwater Hatchery)-Hatchery | Hatchery | Clearwater | 5A | 1 | Mountain Snake
92 | Spring Chinook (Dworshak)-Hatchery | Hatchery | Clearwater | 5A | 1 | Mountain Snake
93 | Spring Chinook (Kooskia)-Integrated | Hatchery | Clearwater | 5A | 1 | Mountain Snake
94 | Spring Chinook (Nez Perce) | Hatchery | Clearwater | 5A | 1 | Mountain Snake
95 | Summer Steelhead B-Run (Clearwater)- Hatchery | Hatchery | Clearwater | 5A | 1 | Mountain Snake
96 | Summer Steelhead B-Run (Dworshak)- Integrated | Hatchery | Clearwater | 5A | 1 | Mountain Snake
97 | Chum (Sea Resources)- Integrated | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
98 | Coho (Big Creek) - Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
99 | Coho (CEDC Sandy River)- Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
100 | Coho (SAFE Tanner Creek) - Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
101 | Coho (Steamboat Slough)- Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
102 | Early Coho (Sea Resources)- Integrated | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
103 | Fall Chinook (Rogue CEDC) - Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
104 | Fall Chinook (Sea Resources)- Integrated | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
105 | Fall Chinook Tule (Big Creek) - Integrated | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
106 | Grays-Deep River Coho | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
107 | Grays-Deep River Spring Chinook | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
108 | Spring Chinook CEDC (SAFE Willamette Hat.) - Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
109 | Spring Chinook CEDC (South Santiam Hat.) - Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
110 | Type N Coho (Cathlament HS - FFA) | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
111 | Winter Steelhead (Big Creek) - Hatchery | Hatchery | Columbia Estuary | 11A | 1 | Columbia Estuary
112 | Fall Chinook Tule-Hatchery | Hatchery | Columbia Gorge | 1A | 1 | Columbia Gorge
113 | Fall Chinook (Priest Rapids URB) - Integrated | Hatchery | Columbia Lower Middle | 4B | 1 | Columbia Plateau
114 | Summer Steelhead (Ringold)- Integrated | Hatchery | Columbia Lower Middle | 4B | 1 | Columbia Plateau
115 | Cowlitz Coho (Late) | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
116 | Cowlitz Fall Chinook | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
117 | Early Winter Steelhead (Chambers)-Hatchery | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
118 | Early Winter Steelhead (Coweeman)- Hatchery | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
119 | Late Winter Steelhead | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
120 | Searun Cutthroat- Integrated | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
121 | Skamania Summer Steelhead (S.F. Toutle)- Hatchery | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
122 | Spring Chinook | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
123 | Summer Steelhead Skamania-Hatchery | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
124 | Toutle Coho (Early) | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
125 | Toutle Fall Chinook | Hatchery | Cowlitz | 10B | 1 | Lower Columbia
126 | Round Butte Spring Chinook - Hatchery | Hatchery | Deschutes | 4D | 1 | Columbia Plateau
127 | Steelhead-Integrated | Hatchery | Deschutes | 4D | 1 | Columbia Plateau
128 | Warm Springs Spring Chinook- Integrated | Hatchery | Deschutes | 4D | 1 | Columbia Plateau
129 | Early Coho | Hatchery | Elochoman | 11B | 1 | Columbia Estuary
130 | Early Winter Steelhead-Hatchery | Hatchery | Elochoman | 11B | 1 | Columbia Estuary
131 | Fall Chinook | Hatchery | Elochoman | 11B | 1 | Columbia Estuary
132 | Late Coho | Hatchery | Elochoman | 11B | 1 | Columbia Estuary
133 | Late Winter Steelhead- Integrated | Hatchery | Elochoman | 11B | 1 | Columbia Estuary
134 | Summer Steelhead- Hatchery | Hatchery | Elochoman | 11B | 1 | Columbia Estuary
135 | Spring Chinook-Hatchery | Hatchery | Entiat | 9B | 1 | Columbia Cascade
136 | Spring Chinook (Captive Brood)- Catherine Creek | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
137 | Spring Chinook (Captive Brood)- Grande Ronde | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
138 | Spring Chinook (Captive Brood)- Lostine | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
139 | Spring Chinook (Catherine Creek)-Integrated | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
140 | Spring Chinook (Lostine)-Integrated | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
141 | Spring Chinook (Upper Grande Ronde)-Integrated | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
142 | Summer Steelhead (Cottonwood Creek)-Hatchery | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
143 | Summer Steelhead (Steelhead-Rainbow CrossResearch) | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
144 | Summer Steelhead- Wallowa | Hatchery | Grande Ronde | 6B | 1 | Blue Mountain
145 | Chum | Hatchery | Grays | 11C | 1 | Coumbia Estuary
146 | Early Coho | Hatchery | Grays | 11C | 1 | Coumbia Estuary
147 | Early Winter Steelhead-Hatchery | Hatchery | Grays | 11C | 1 | Coumbia Estuary
148 | Spring Chinook (Round Butte)- Integrated | Hatchery | Hood | 1C | 1 | Columbia Gorge
149 | Summer Steelhead (Native)- Integrated | Hatchery | Hood | 1C | 1 | Columbia Gorge
150 | Summer Steelhead (Skamania)- Hatchery | Hatchery | Hood | 1C | 1 | Columbia Gorge
151 | Winter Steelhead | Hatchery | Hood | 1C | 1 | Columbia Gorge
152 | Spring/Summer Chinook-Integrated | Hatchery | Imnaha | 6C | 1 | Blue Mountain
153 | Summer Steelhead-Integrated | Hatchery | Imnaha | 6C | 1 | Blue Mountain
154 | Coho (Early)-Hatchery | Hatchery | Kalama | 10C | 1 | Lower Columbia
155 | Coho (Late)-Hatchery | Hatchery | Kalama | 10C | 1 | Lower Columbia
156 | Fall Chinook | Hatchery | Kalama | 10C | 1 | Lower Columbia
157 | Spring Chinook | Hatchery | Kalama | 10C | 1 | Lower Columbia
158 | Summer Steelhead (Local) | Hatchery | Kalama | 10C | 1 | Lower Columbia
159 | Summer Steelhead (Skamania)-Hatchery | Hatchery | Kalama | 10C | 1 | Lower Columbia
160 | Winter Steelhead (Chambers)-Hatchery | Hatchery | Kalama | 10C | 1 | Lower Columbia
161 | Winter Steelhead (Local) | Hatchery | Kalama | 10C | 1 | Lower Columbia
162 | Coho N (Klickitat Hatchery)- Hatchery | Hatchery | Klickitat | 1D | 1 | Columbia Gorge
163 | Coho N (Washougal Hatchery)- Hatchery | Hatchery | Klickitat | 1D | 1 | Columbia Gorge
164 | Fall Chinook (URB)- Hatchery | Hatchery | Klickitat | 1D | 1 | Columbia Gorge
165 | Skamania Summer Steelhead- Hatchery | Hatchery | Klickitat | 1D | 1 | Columbia Gorge
166 | Spring Chinook | Hatchery | Klickitat | 1D | 1 | Columbia Gorge
167 | Early Coho | Hatchery | Lewis | 10D | 1 | Lower Columbia
168 | Early Winter Steelhead (Chambers)-Hatchery | Hatchery | Lewis | 10D | 1 | Lower Columbia
169 | Late Coho | Hatchery | Lewis | 10D | 1 | Lower Columbia
170 | Skamania Summer Steelhead (E.F. Lewis)- Hatchery | Hatchery | Lewis | 10D | 1 | Lower Columbia
171 | Skamania Summer Steelhead (N.F. Lewis)- Hatchery (Fish First-Volunteer) | Hatchery | Lewis | 10D | 1 | Lower Columbia
172 | Skamania Winter Steelhead (E.F. Lewis)- Hatchery | Hatchery | Lewis | 10D | 1 | Lower Columbia
173 | Spring Chinook-Hatchery | Hatchery | Lewis | 10D | 1 | Lower Columbia
174 | Summer Steelhead (Skamania)-Hatchery | Hatchery | Lewis | 10D | 1 | Lower Columbia
175 | Coho- Hatchery | Hatchery | Little White Salmon | 1E | 1 | Columbia Gorge
176 | Fall Chinook (URB) - Hatchery | Hatchery | Little White Salmon | 1E | 1 | Columbia Gorge
177 | Spring Chinook-Hatchery | Hatchery | Little White Salmon | 1E | 1 | Columbia Gorge
178 | Summer Steelhead (Skamania)-Hatchery | Hatchery | Little White Salmon | 1E | 1 | Columbia Gorge
179 | Chum (Duncan Creek)- Integrated | Hatchery | Lower Columbia | 10A | 1 | Lower Columbia
180 | Coho (Bonneville) - Hatchery | Hatchery | Lower Columbia | 10A | 1 | Lower Columbia
181 | Fall Chinook (Bonneville) - Hatchery | Hatchery | Lower Columbia | 10A | 1 | Lower Columbia
182 | Skamania Winter Steelhead (Salmon Cr. Netpens)- Hatchery | Hatchery | Lower Columbia | 10A | 1 | Lower Columbia
183 | Coho- Integrated | Hatchery | Methow | 9D | 1 | Columbia Cascade
184 | Spring Chinook (Methow H.)- Integrated | Hatchery | Methow | 9D | 1 | Columbia Cascade
185 | Spring Chinook (NFH)- Integrated | Hatchery | Methow | 9D | 1 | Columbia Cascade
186 | Summer Chinook- Integrated | Hatchery | Methow | 9D | 1 | Columbia Cascade
187 | Summer Steelhead (Wells)- Integrated | Hatchery | Methow | 9D | 1 | Columbia Cascade
188 | Summer Steelhead (Winthrop)- Integrated | Hatchery | Methow | 9D | 1 | Columbia Cascade
189 | Summer Chinook- Integrated | Hatchery | Okanogan | 9E | 1 | Columbia Cascade
190 | Summer Steelhead (L.Similkameen) | Hatchery | Okanogan | 9E | 1 | Columbia Cascade
191 | Summer Steelhead (Okanogan) | Hatchery | Okanogan | 9E | 1 | Columbia Cascade
192 | Lemhi River Spring Chinook | Hatchery | Salmon | 5B | 1 | Mountain Snake
193 | Redfish Lake Sockeye | Hatchery | Salmon | 5B | 1 | Mountain Snake
194 | Spring Chinook (East Fork Salmon River)- Integrated | Hatchery | Salmon | 5B | 1 | Mountain Snake
195 | Spring Chinook (Rapid River) - Hatchery | Hatchery | Salmon | 5B | 1 | Mountain Snake
196 | Spring Chinook (Upper Salmon/Sawtooth) | Hatchery | Salmon | 5B | 1 | Mountain Snake
197 | Spring Chinook (W. Fork Yankee Fork- Salmon River)- Integrated | Hatchery | Salmon | 5B | 1 | Mountain Snake
198 | Steelhead A-Run (Pahsimeroi)- Hatchery | Hatchery | Salmon | 5B | 1 | Mountain Snake
199 | Steelhead A-Run (Sawtooth)- Hatchery | Hatchery | Salmon | 5B | 1 | Mountain Snake
200 | Steelhead B (Dworshak)-Hatchery | Hatchery | Salmon | 5B | 1 | Mountain Snake
201 | Steelhead B (East Fork) - Integrated | Hatchery | Salmon | 5B | 1 | Mountain Snake
202 | Summer Chinook (Johnson Creek) | Hatchery | Salmon | 5B | 1 | Mountain Snake
203 | Summer Chinook (McCall Hatchery) | Hatchery | Salmon | 5B | 1 | Mountain Snake
204 | Summer Chinook (Pahsimeroi) | Hatchery | Salmon | 5B | 1 | Mountain Snake
205 | Coho - Hatchery | Hatchery | Sandy | 10E | 1 | Lower Columbia
206 | Spring Chinook- Integrated | Hatchery | Sandy | 10E | 1 | Lower Columbia
207 | Summer Steelhead (Skamania) - Hatchery | Hatchery | Sandy | 10E | 1 | Lower Columbia
208 | Winter Steelhead - Integrated | Hatchery | Sandy | 10E | 1 | Lower Columbia
209 | Fall Chinook (Captain John)-Integrated | Hatchery | Snake Hells Canyon | 6D | 1 | Blue Mountain
210 | Fall Chinook (IPC)- Integrated | Hatchery | Snake Hells Canyon | 6D | 1 | Blue Mountain
211 | Fall Chinook (Oxbow) | Hatchery | Snake Hells Canyon | 6D | 1 | Blue Mountain
212 | Fall Chinook (Pittsburg Landing)-Integrated | Hatchery | Snake Hells Canyon | 6D | 1 | Blue Mountain
213 | Spring Chinook - Hatchery | Hatchery | Snake Hells Canyon | 6D | 1 | Blue Mountain
214 | Summer Steelhead - Hatchery | Hatchery | Snake Hells Canyon | 6D | 1 | Blue Mountain
215 | Fall Chinook (LF)- Integrated | Hatchery | Snake Lower | 4F | 1 | Columbia Plateau
216 | Summer Steelhead (LF)- Hatchery | Hatchery | Snake Lower | 4F | 1 | Columbia Plateau
217 | Spring Chinook- Integrated | Hatchery | Tucannon | 4H | 1 | Columbia Plateau
218 | Spring Chinook-Captive Brood | Hatchery | Tucannon | 4H | 1 | Columbia Plateau
219 | Summer Steelhead (LF)-Hatchery | Hatchery | Tucannon | 4H | 1 | Columbia Plateau
220 | Summer Steelhead- Integrated | Hatchery | Tucannon | 4H | 1 | Columbia Plateau
221 | Coho- Integrated | Hatchery | Umatilla | 4I | 1 | Columbia Plateau
222 | Fall Chinook- Integrated | Hatchery | Umatilla | 4I | 1 | Columbia Plateau
223 | Spring Chinook- Integrated | Hatchery | Umatilla | 4I | 1 | Columbia Plateau
224 | Summer Steelhead- Integrated | Hatchery | Umatilla | 4I | 1 | Columbia Plateau
225 | Fall Chinook- Ringold | Hatchery | Upper Middle Columbia | 9A | 1 | Columbia Cascade
226 | Summer Chinook (Wells Hatchery) | Hatchery | Upper Middle Columbia | 9A | 1 | Columbia Cascade
227 | Summer Chinook- Hatchery | Hatchery | Upper Middle Columbia | 9A | 1 | Columbia Cascade
228 | Summer Steelhead (LF)-Hatchery | Hatchery | Walla Walla | 4J | 1 | Columbia Plateau
229 | Touchet Summer Steelhead-Endemic | Hatchery | Walla Walla | 4J | 1 | Columbia Plateau
230 | Early Winter Steelhead-Hatchery | Hatchery | Washougal | 10F | 1 | Lower Columbia
231 | Fall Chinook | Hatchery | Washougal | 10F | 1 | Lower Columbia
232 | Late Coho | Hatchery | Washougal | 10F | 1 | Lower Columbia
233 | Summer Steelhead | Hatchery | Washougal | 10F | 1 | Lower Columbia
234 | Coho- Integrated | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
235 | Sockeye | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
236 | Spring Chinook (Chiwawa R.) | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
237 | Spring Chinook (White River) | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
238 | Spring Chinook-Hatchery | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
239 | Summer Chinook | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
240 | Summer Steelhead | Hatchery | Wenatchee | 9F | 1 | Columbia Cascade
241 | Clackamas Early Coho - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
242 | Clackamas Early Winter Steelhead - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
243 | Clackamas Late Winter Steelhead - Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
244 | Clackamas Spring Chinook - Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
245 | Clackamas Summer Steelhead - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
246 | McKenzie Spring Chinook- Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
247 | McKenzie Summer Steelhead - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
248 | MF Willamette Spring Chinook - Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
249 | MF Willamette Summer Steelhead - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
250 | Molalla Spring Chinook - Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
251 | N. Santiam Spring Chinook - Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
252 | North Santiam Summer Steelhead - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
253 | South Santiam Spring Chinook - Integrated | Hatchery | Willamette | 10G | 1 | Lower Columbia
254 | South Santiam Summer Steelhead - Hatchery | Hatchery | Willamette | 10G | 1 | Lower Columbia
255 | Spring Chinook-Hatchery | Hatchery | Wind | 1G | 1 | Columbia Gorge
256 | Marion Drain Fall Chinook | Hatchery | Yakima | 4C | 1 | Columbia Plateau
257 | Naches Coho | Hatchery | Yakima | 4C | 1 | Columbia Plateau
258 | Upper Yakima Coho | Hatchery | Yakima | 4C | 1 | Columbia Plateau
259 | Upper Yakima Spring Chinook | Hatchery | Yakima | 4C | 1 | Columbia Plateau
260 | Yakima Fall Chinook | Hatchery | Yakima | 4C | 1 | Columbia Plateau