March 19, 2007

| TO: | Members Advisory Group |
| --- | --- |
| FROM: | Neil Ward (CBFWA Staff) |
| SUBJECT: | Timeline for development of 2006 SOTR |

The CBFWA staff recently completed the development of a timeline (Table 1) that identifies a completion date of September 28, 2007, for the 2006 version of the Status of the Resources Report. The date of September 28th has been selected to allow for the release of the Status of the Resources Report to coincide with the release date of the Northwest Power and Conservation Council’s (NPCC) Annual Report. The Independent Scientific Review Panel recently suggested that the information in the Status of the Resources Report and the associated web site “could serve as a source for reports of substantial geographic breadth with general treatment of specific topics, such as the NPCC’s reports to the Governors and the United States Congress.” Subsequently, the Status of the Resources Report may have the potential to be a companion document to the NPCC’s report, with the intended audience including, but not limited to, the Northwest Governors and United States Congress.

The CBFWA staff has begun to plan and coordinate efforts to ensure that the September 28th deadline is achieved. For 2006, both fish and wildlife will be represented in the report. The following are general descriptions of the various steps that will occur during the next several months to ensure delivery of a draft report on September 1st.

Wildlife

Using data (e.g., habitat units lost, habitat units gained, acquired, percent completed by species, etc.) from the Bonneville Power Administration, a draft template has been developed. The Intermountain Province and Coeur d’Alene, Pend Oreille, and Spokane subbasins were selected as pilot sites. The template for these areas has been populated and will be reviewed by the Wildlife Advisory Committee (WAC) during March and April. The CBFWA staff envisions that a final template will be approved no later than May 2007 and that a draft of the wildlife section will be completed by July 2007 for review in August.

Anadromous and Resident Fish

The CBFWA staff will work with the fish and wildlife managers, NPCC, BPA, and others from March – May 2007 to identify information that should be included in the report. From June – August 2007, the CBFWA staff will coordinate with the fish and wildlife managers to populate the templates and provide a draft report to CBFWA members for review on September 1st.

|  | March | April | May | June | July | August | September | October |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REPORT |  |  |  |  |  |  |  |  |
| Develop Template for fish and wildlife sections | Meet with BPA, NPCC, managers and other interested parties | Meet with BPA, NPCC, managers and other interested parties | Meet with BPA, NPCC, managers and other interested parties |  |  |  |  |  |
| Wildlife section |  |  | Begin wildlife section | Complete wildlife section | CBFWA Wildlife Committee review | CBFWA MAG Review | CBFWA Members approval and regional review |  |
| Fish section |  |  |  | Begin fish section | Continue working on fish section | Complete fish section | CBFWA MAG and Members approval and regional review |  |
| Final report |  |  |  |  |  |  |  | Distribute to region |
| WEB SITE |  |  |  |  |  |  |  |  |
| Fish section | Continue developing section | Section completed | Update | Update | Update | Update | Update | Update |
| Wildlife section |  |  | Plan and develop | Develop | Develop | Develop | Develop | Section completed |

H:\WORK\MAG\2007_0320\032007MAG2007SOTR.doc

# Text boxes

851 SW Sixth Avenue, Suite 260  |  Pacific First Building  |  Portland, OR 97204-1339  |  Phone: 503-229-0191 |  Fax: 503-229-0443

Coordinating and promoting effective protection and

restoration of fish, wildlife, and their

habitat in the

Columbia River Basin.

The Authority is comprised of the following tribes

and government agencies:

Burns Paiute Tribe

Coeur d’Alene Tribe

Confederated Salish and Kootenai Tribes

of the Flathead Reservation

Confederated Tribes

of the Colville Reservation

Confederated Tribes

of the Umatilla Indian Reservation

Confederated Tribes

of the Warm Springs Reservation

Confederated Tribes and Bands of the Yakama Nation

Idaho Department

of Fish and Game

Kootenai Tribe

of Idaho

Montana Department

of Fish, Wildlife and Parks

National Marine Fisheries Service

Nez Perce Tribe

Oregon Department

of Fish and Wildlife

Shoshone-Bannock Tribes of Fort Hall

Shoshone-Paiute Tribes of Duck Valley

U.S. Fish & Wildlife Service

Washington Department of Fish

and Wildlife

Coordinating Agencies

Columbia River

Inter-Tribal Fish Commission

Upper Columbia

United Tribes