Summary of proposed CSMEP work elements and products by objective for FY08, including collaborating entities.

| Objectives and Work Elements | Description of Work Products | Timing | Entities Collaborating w CSMEP | Priority |
| --- | --- | --- | --- | --- |
| 1. Develop Work Plans / Interact with Programmatic Entities |
| 1.1 Develop CSMEP Quarterly Workplans | Collaboratively prepare quarterly workplans to maximize integration and efficiency, avoid duplication of effort. | quarterly | PNAMP, BPA, NPCC, StreamNet | H-1 |
| 1.2 Quarterly Progress Reports | Quarterly reporting in PISCES of progress by objective and work element to ensure close contract monitoring. | quarterly | BPA | H-1 |
| 1.3 Preparation of Draft and Final Annual Reports | 3-level annual reports: 2-pg. exec. Summary; ~25-pg. overview w ~75-pg. appendices; hyperlinked detailed reports | annual | internal | H-5 |
| 1.4 CSMEP conference calls, meetings and workshops | Biweekly Calls: Track progress, review products, coordinate efforts. Workshops: Present results, get technical/programmatic feedback, brainstorm next steps in subgroups | biweekly calls; workshops 1-2 for half year | Calls: internal Workshops: Programmatic and Policy Feedback for part of meeting | H- 3 - 5 |
| 1.5 Coordination w PNAMP on joint activities and work products | Interact with PNAMP; Annual work planning; Synthesis of work products | planning mtgs 1X /yr | PNAMP Steering Committee | H-1 |
| 1.6 Extend application of CSMEP insights and tools to other parts of CRB and PNAMP entities | Generalize and extend qualitative and quantitative tools developed in CSMEP DQO process for use throughout CRB. Present general implications and specific analyses/tools to managers and scientists at workshops and conference symposia. | FY08 | Transfer of tools and results through CBFWA,NPCC, MAG, TRTs, PNAMP, WA Recovery Board, Model Watershed groups, AFS conferences | H-1 |
| 2. Inventory existing data relevant to questions |
| 2.1 QA on StreamNet metadata inventory for identified salmon & steelhead populations | Review new StreamNet's metadata inventories for Snake River fall Chinook, Mid-Columbia Chinook, Mid-Columbia steelhead, Upper Columbia spring Chinook and Upper Columbia steelhead | FY08 | StreamNet (separate contract); fed/state/tribal agencies with data Review State of Salmon inventory | F(H) – needed for task 3.1 5 |
| 2.2 Inventory of additional Columbia River sockeye | Support and facilitate sockeye conference at Western Division AFS Use conference to share ideas on inventory methods and data standards for sockeye stocks in US/Canada Include some coastal SK stocks | Workshop 1x/yr | DFO, Okanagan Nation Alliance, StreamNet, AFS, WDFW, IDFG, CRITFC (Jeff Fryer) | F(L) 1 |
| 2.3 Maintenance of TRT datasets | Develop (with StreamNet) a protocol to update and maintain the stock viability databases developed by the TRT’s for their viability analyses. | FY08 | StreamNet (separate contract); Technical Recovery Teams; CBFWA Data Management Framework Subcommittee (CDBMFS) | F(M) – needed for 7.1b 3 |
| 3. Organize subset of data into accessible form |
| 3.1 Maintain CSMEP web-based metadata application | Support StreamNet’s further development of the CSMEP meta-database; add new species and subbasins from task 2.1 | FY08 | StreamNet (separate contract); fed/state/tribal agencies with data | F(H) depends on task 2.1 {3} |
| 3.2 CSMEP public website maintenance | Expand user-friendly summaries of CSMEP products in hierarchical form for communication via website to multiple audiences | FY08 | CBFWA web master; link CSMEP data assessments (task 4.1) to SOTR? | H 1 |
| 3.3 Status of the Resource Report (SoTR) support | Contribute to summaries of the quality of monitoring data in the Columbia Basin to support CBFWA’s Status of the Resource Report (i.e., performance measures in addition to abundance); with focus on higher-scale aggregation for assessing subbasin/provincial objectives | FY08 | CBFWA data management group | H 1-3 |
| 3.4 Interact with groups on design and development of agency monitoring databases | Contribute to development of recommended standards for performance measures based on work done to date for decisions identified in Task 4.1 | FY08 | Regional data management processes (e.g., StreamNet, NED, PNAMP) | F(H) – links to 4.1 1 |
| 4. Evaluate ability to answer key questions with existing data |
| 4.1 Identification of priority fish management decisions/ability to answer these questions | Identification of the priority management decisions (both those made on a routine basis and those made more infrequently) in the Columbia Basin, and the monitoring and analyses required to inform those decisions across S&T and the 4Hs. Compare full set with those already addressed by CSMEP and prepare summary report. | FY08 | NPCC, NOAA, BPA, USFWS, USFS, Bor, Corps, MAG, Harvest Managers, Hatchery Managers, CBFWA Data Management Group {do at a CSMEP workshop which presents CSMEP results and asks for feedback on how decisions are made, other priority decisions} | H 3 |
| 4.2 Evaluation of existing data for identified salmon and steelhead populations | Detailed strengths & weaknesses assessments of existing monitoring information for Snake River fall Chinook, Mid-Columbia Chinook, Mid-Columbia steelhead, Upper Columbia spring Chinook and Upper Columbia steelhead. Prepare summary reports for each assessed populaiton | FY08 | USFS, BLM, OR Aquatic Inventory, OWEB, ID DEQ, PCSRF, BoR, EPA, PNAMP, tribal entities, CFBWA data management group, others | F(H) – depends on task 2.1 5 |
| 5. Collaborative monitoring program design |
| 5.1 Status & Trends | a) Complete and document CSMEP’s simulation model for assessing TRT viability criteria for spring Chinook. Prepare user guide. | FY08 | Technical Recovery Teams, ISRP/ISAB, AFS conference presentations | H 3 |
|  | b) Extend these existing CSMEP tools for assessing M&E designs to detect recovery status for steelhead | FY08 | Technical Recovery Teams | F(H) 3 |
|  | c) Work with local management groups to employ the viability and cost integration models for improving subbasin design of salmon and steelhead recovery monitoring | FY08 | Recovery planning teams for the Middle Columbia, Upper Columbia and Snake | F(H) 3-5 |
| 5.2 Hydro | Document FY06/07 CSMEP hydro analyses for Snake R steelhead (partly done) | FY08 | AFEP, NOAA-Hydro, Fish Passage Center, ISRP/ISAB | H 1-3 |
|  | Extend existing CSMEP hydro analyses to fit requirements of new BiOp (amount of new work will depend on performance stds in new BiOp) | FY08 | AFEP, NOAA-Hydro, PUDs, Fish Passage Center, ISRP/ISAB | F(H) 1-3 |
|  | Extend existing CSMEP hydro analyses to upper and mid-Columbia | FY08 | AFEP, NOAA-Hydro, PUDs, Fish Passage Center, ISRP/ISAB | F(H) 5 |
| 5.3 Habitat | a) Interact with habitat restoration programs within the Columbia Basin to help restoration managers develop action effectiveness monitoring designs/plans | FY08 | In coordination with PNAMP and ISEMP (NOAA-AA pilot projects), work with restoration managers and Model Watershed groups, (e.g. as done for the Lemhi) | F(M) 3 |
|  | b) Work with other entities to develop regional habitat status and trends monitoring of high level indicators | FY08 (initial lead-in to FY09 workplan) | USFS, PNAMP, BoR, Washington Governor’s Forum | F(L) 1 |
| 5.4 Hatchery | a) Facilitate the completion of a regional M&E framework for hatchery evaluations. Complete M&E designs for two large scale hatchery questions (i.e., hatchery straying into wild populations, relative reproductive success). | FY08 | Ad Hoc Supplementation Work Group, ISRP/ISAB, StreamNet, CBFWA data management group | H 5 |
|  | b) Initiate a regional hatchery effectiveness analysis based on the final framework design | FY08 | Ad Hoc Supplementation Work Group, Hatchery managers, ISRP/ISAB, StreamNet, CBFWA data management group | F(H) 5 |
|  | c) Disseminate results of the analyses through a workshop; present hatchery effectiveness report to NPCC | FY08 | Ad Hoc Supplementation Work Group, Hatchery managers, NPCC | F(H) 1 |
| 5.5 Harvest | Document FY06/07 tasks | FY08 | Harvest managers (e.g. TAC, US v. OR, PST, CTC), ISRP/ISAB | H 1-3 |
|  | Develop alternative monitoring designs for steelhead harvest monitoring | FY08 | Harvest managers (e.g. TAC, US v. OR, PST, CTC), ISRP/ISAB | F(M) 5 |
| 5.6 Integration | a) Complete CSMEP’s Cost Integration Database Tool and user guide | FY08 | IDFG, WDFW, ODFW, NOAA, tribes | H 1 |
|  | b) Work with local management groups to employ the tool for evaluating costs of alternative integrated monitoring designs | FY08 | Recovery planning teams for the Middle Columbia, Upper Columbia and Snake | F(H) 3 |
|  | c) Develop statistical analysis for PIT-tagging of Snake River steelhead to assess ability of integrated tagging to answer multiple S&T and 4Hs questions | FY08 | Fish Passage Center, mid-Columbia steelhead recovery team, PNAMP, Hatchery Managers, TRTs, Hatchery Managers, CBFWA Data Management Group, Corps | F(H) 3 |
|  | Begin development of a simulation model (based on completed PIT tagging analyses for Chinook and steelhead) that can allow dynamic exploration of alternative tagging scenarios (numbers, locations) for addressing multiple S&T and 4Hs monitoring questions at varied levels of reliability | FY08 | AFEP, NOAA-Hydro, PUDs, Fish Passage Center, ISRP/ISAB | F(M) 5 |
|  | Identify new analyses/tools that can better assess/quantify cost and data gathering efficiencies of integrating monitoring across S&T and the 4Hs | FY08 | AFEP, NOAA-Hydro, PUDs, Fish Passage Center, ISRP/ISAB | F(L) links to 4.1 decisions 1 |
| 5.7 ISAB review | Present Snake River Pilot Study results in a report to ISAB and revise report to respond to comments | FY08 | ISAB/ISRP, MAG, PNAMP, Federal Caucus, technical groups | H 3 |
| 6. Multi-agency implementation of monitoring programs. |
| 6.1 Provide input to conceptual plan for M&E implementation across CRB | a) Consolidate and document CSMEP findings and recommendations on M&E required for decisions identified in Task 4.1, useful tools, and priority work to fill identified gaps in information or the existing suite of analytical tools. | FY08 |  | H 5 |
|  | b) Apply CSMEP recommendations within a regional M&E framework. | FY08 | Interact with programmatic/policy entities with responsibility for decisions in recovery assessment and 4 H's to fine tune M&E designs, costs (e.g. harvest group to work with TAC on implementation of monitoring) | F(H) 5 |
| 7. Multi-agency evaluation of results of new monitoring programs. |
| 7.1 Improve regional M&E within an adaptive management cycle | a) Incorporate results of pilot projects as they are made available and incorporate into CSMEP design ideas/products e.g., federal RME, WA-SFRB, others) | FY08 | NOAA-AA pilot projects, IMW, WA SRFB, others | F(M) 1 |
|  | b) Assess current viability analyses and data inputs to these analyses; recommend adaptive changes in M&E needed to better answer viability questions in different ESUs | FY08 (transition to more active analytical role in FY09) | NOAA, TRT groups, Remand RME, other groups keenly interested in M&E to support viability analyses (e.g. Oregon Plan, WA Governor’s Forum) | F(M) 5 |

H:\WORK\MBRS\2007_0918-19\Proposed_CSMEP_Tasks_For_FY08.doc

# Footnotes

H – support if only half funding ($500,000) (highest priority)

F(H) – support with full funding (high priority)

F(M) – support with full funding (medium priority)

F(L) – support with full funding (low priority)