February 12, 2009

| TO: | Brian Lipscomb |
| --- | --- |
| FROM: | Iverson and MacDonald |
| SUBJECT: | Preliminary CBFWA BiOp M&E Work Plan Extracted from Coordination Contract |

CBFWA staff has been working to extract the BiOp M&E deliverables from the approved budget in order for the MAG to focus on development of a work plan.  This breakout should address the initial concerns raised by Tony Grover and Greg Delwiche in response to receiving the CBFWA 2009 SOW and Budget.

Please find attached the following documents:

1) Our statement of work and budget as approved by our members (Page 2),

2) Our statement of work and budget, minus BiOp M&E tasks (Page 4),

3) A statement of work and budget, consistent with our approved SOW, for the BiOp M&E tasks previously contained in our coordination contract (Page 6),

4) A preliminary CBFWA work plan for the BiOp M&E tasks, and

5) A comparison of the prelimary work plan to BiOp M&E projects identified in BPA's start of year budget that have not yet been contracted.

We anticipate full discussion with the MAG regarding the development of the final BiOp M&E work plan and budget.

January full CBFWA Proposal

- $1,896,201 (does not include CBFWA Members’ time and travel for M&E activities related to BiOp RPAs)

- 7.9 FTE

High Level Deliverables for Coordination

- Foundation for Coordination (1.4 FTE)

  - Web services to support Program for information dissemination (0.4)

  - Web/meeting services to support CBFWA for information dissemination (0.5)

  - Tribal coordination and outreach (0.2)

  - CBFWA public relations and outreach (0.1)

  - Fish and Wildlife Manager administrative support (0)

  - IT Services to support CBFWA Members / Staff (0.2)

- Planning (2.2 FTE)

  - Update Subbasin Management Plans and Basinwide Management Plan (0.5)

  - Regional Monitoring and Evaluation Plan (0.55)

  - Regional Anadromous Fish Monitoring Program (0.45)

  - Participate in project review process with NPCC and BPA (0.4)

  - Develop process for defining wildlife operational losses and resident fish losses (0.3)

- Implementation (2.9 FTE)

  - Program Implementation Tracking (BOG) (0.2)

  - Programmatic issues (MAG and Members) (0.9)

  - Anadromous Fish Advisory Committee (0.3)

  - Lamprey Technical Workgroup (0.1)

  - Fish Passage Advisory Committee (0.0)

  - Resident Fish Advisory Committee (0.2)

  - Wildlife Advisory committee (0.2)

  - Fish Screen Oversight Committee (0.2)

  - Ad-hoc workgroups (0.8)

- Evaluation (1.4 FTE)

  - Project Effectiveness reviews (0.45)

  - Program Effectiveness tracking (0.95)

| FY 2009 CBFWA |
| --- |
| Columbia Basin Fish and Wildlife Foundation |
| Annual Implementation Work Plan |
| Grant #000020620, Project 8906201 |
| CBFWA Staff and Facilities |  |
| Salaries | $ 714,462 |
| Benefits | $ 324,294 |
| Staff Travel | $ 53,000 |
| Network IT | $ 25,000 |
| Copier Usage | $ 750 |
| Network | $ 20,000 |
| Postage | $ 466 |
| Printing | $ 10,000 |
| Supplies | $ 4,000 |
| Telephone/Conference Calls | $ 7,500 |
| Meeting Costs* | $ 23,500 |
| Total | $ 1,182,972 |
| Cost Pool Allocation - 29.36% | $ 347,321 |
| Total CBFWA Staff and Facilities | $ 1,530,293 |
| CBFWA Members |  |
| Members Salary, Benefits and Travel | $ 323,500 |
| Cost Pool Allocation - 12.8% | $ 41,408 |
| Total CBFWA Members | $ 364,908 |
| Total CBFWA Request | $ 1,895,201 |

Modified CBFWA Proposal

(removing BiOp M&E coordination)

- $1,638,391 (includes Members time and travel for identified tasks)

- 6.65 FTE

Deliverables for Coordination

- Foundation for Coordination (1.4 FTE)

  - Web services to support Program for information dissemination (0.4)

  - Web/meeting services to support CBFWA for information dissemination (0.5)

  - Tribal coordination and outreach (0.2)

  - CBFWA public relations and outreach (0.1)

  - Fish and Wildlife Manager administrative support (0)

  - IT Services to support CBFWA Members / Staff (0.2)

- Planning (1.45 FTE)

  - Update Subbasin Management Plans and Basinwide Management Plan (0.4)

  - Regional Monitoring and Evaluation Plan (0.45)

  - Regional Anadromous Fish Monitoring Program (0)

  - Participate in project review process with NPCC and BPA (0.3)

  - Develop process for defining wildlife operational losses and resident fish losses (0.3)

- Implementation (2.6 FTE)

  - Program Implementation Tracking (BOG) (0.2)

  - Programmatic issues (MAG and Members) (0.85)

  - Anadromous Fish Advisory Committee (0.15)

  - Lamprey Technical Workgroup (0.1)

  - Fish Passage Advisory Committee (0.0)

  - Resident Fish Advisory Committee (0.2)

  - Wildlife Advisory committee (0.2)

  - Fish Screen Oversight Committee (0.2)

  - Ad-hoc workgroups (0.7)

- Evaluation (1.2 FTE)

  - Project Effectiveness reviews (0.45)

  - Program Effectiveness tracking (0.75)

| FY 2009 CBFWA |
| --- |
| Columbia Basin Fish and Wildlife Foundation |
| AWP Less BiOp M&E Deliverables |
| Grant #000020620, Project 8906201 |
| CBFWA Staff and Facilities |  |
| Salaries | $ 588,364 |
| Benefits | $ 267,081 |
| Travel and Meeting Rooms | $ 53,000 |
| Meeting Rooms | $ 22,000 |
| Network IT | $ 20,000 |
| Copier Usage | $ 1,700 |
| Network | $ 12,500 |
| Postage | $ 530 |
| Printing | $ 7,000 |
| Supplies | $ 4,000 |
| Telephone/Conference Calls | $ 7,500 |
| Total | $ 983,675 |
| Cost Pool Allocation - 29.36% | $ 288,807 |
| Total CBFWA Staff and Facilities | $ 1,272,483 |
| CBFWA Members |  |
| Members Salary, Benefits and Travel | $ 323,500 |
| Cost Pool Allocation - 12.8% | $ 41,408 |
| Total CBFWA Members | $ 364,908 |
| Total CBFWA Request | $ 1,637,391 |

CBFWA Proposal for BiOp M&E tasks

- $257,810 (does not include Members time and travel for identified tasks)

- 1.25 FTE

Deliverables for M&E (as identified in Coordination SOW)

- Planning (0.75 FTE)

  - Update Subbasin Management Plans and Basinwide Management Plan (0.1)

  - Regional Monitoring and Evaluation Plan (0.1)

  - Regional Anadromous Fish Monitoring Program (0.45)

  - Participate in project review process with NPCC and BPA (0.1)

- Implementation (0.3 FTE)

  - Programmatic issues (MAG and Members) (0.05)

  - Anadromous Fish Advisory Committee (0.15)

  - Ad-hoc workgroups (0.1)

- Evaluation (0.2 FTE)

  - Program Effectiveness tracking (0.2)

| FY 2009 CBFWA |  |
| --- | --- |
| Columbia Basin Fish and Wildlife Foundation |  |
| BiOp M&E Proposal |  |
| April 1, 2009 - March 31, 2010 |  |
| CBFWA Staff and Facilities |  |  |
| Salaries | $ 130,779 |  |
| Benefits | $ 59,318 |  |
| Travel and Meeting Rooms | $ 9,200 |  |
| Total | $ 199,297 |  |
| Cost Pool Allocation - 29.36% | $ 58,514 |  |
| Total CBFWA Staff and Facilities | $ 257,810 |  |
| Preliminary CBFWA Members* | Unknown |
| Members Salary, Benefits and Travel | $ ????? |
| Cost Pool Allocation - 12.8% | $ ????? |
| Total CBFWA Members | $ ????? |
| Estimated CBFWA Request | $ ????? |

*CBFWA Members have not developed estimated budgets for time and travel necessary to participate in this work.  A budget estimate from past requirements for participation in the CSMEP project would range from $350,000 to $900,000.

Preliminary CBFWA BiOp M&E Work Plan

Develop and implement a coordinated regional fish monitoring strategy to support and integrate fish and wildlife manager M&E programs, the FCRPS BiOp, salmon/steelhead recovery plans, and the NPCC Fish and Wildlife Program:

  - Using CBFWA amendment framework, develop tasks for Regional Monitoring Strategy in support of the various initiatives

  - Cross check tasks with Agency Management Decision Survey (CSMEP 08)

  - Link/Cross-check tasks with BiOp RPAS (especially RPA 50 and 51)

  - Link/Cross-check tasks with BPA’s “unclear” projects

  - Work with NOAA and Action Agencies to adjust tasks as necessary

- Task 1 - Work with and support NOAA to finalize a regional anadromous fish data dictionary to be used by the fish managers

- Task 2. - Work with NOAA to complete the VSP monitoring guidance document for regional application

- Task 3 - Use the CSMEP strength and weakness assessments and initial work of Bruce Crawford to:

  - complete the inventory of basin-wide VSP monitoring programs for anadromous fish,

  - assess the adequacy of the monitoring based upon NOAA’s monitoring guidance, and

  - identify potential gaps in monitoring programs.

- Task 4 - Building upon the results of Tasks 1-3, work with the Action Agencies and local recovery entities to identify and implement a preferred strategy for anadromous fish VSP monitoring.

- Task 5 – Report results of annual VSP monitoring through the SOTR including an assessment of the quality of monitoring designs in terms of precision and accuracy.

- Task 6 - Build upon the CSMEP Snake Basin Pilot report and the CSMEP Inventory of Management Decisions to develop an integrated, “All H” monitoring program for 1 ESU.  This will require coordination with the Action Agencies, U.S. vs Oregon TAC, regional hatchery monitoring programs, local recovery entities, and appropriate land and water managers.

- Task 7 - Begin an annual process to assure the information necessary for run reconstructions for targeted populations is collected and stored in a regionally compatible and accessible format.  Report annually the status of the information through the SOTR including spatial structure and diversity metrics.

Comparison of Preliminary CBFWA BiOp M&E Work Plan

with projects identified in BPA FY2008-2010 Budget July 2008

| Potential Sponsor | BPA Project Number* | BPA Project Title | BPA09 Expense |
| --- | --- | --- | --- |
| Unclear | 200872700 | Regional Data Mgt Support and Coordination (i.e NED, etc) | $ 500,000 |
|  | Task 2 | Deliverable- Facilitate agreement by A&T on: 1) VSP monitoring guidance document, and 2) Protocols (guidance) for collecting and reporting data. |  |
| Unclear | 200872900 | Adult monitoring of as part of regional cost shared strategy for population status monitoring (assumes 50% cost share) | $ 1,500,000 |
| Unclear | 200874700 | Juvenile productivity monitoring with limited habitat condition monitoring (assumes 50% cost share with the region) | $ 5,000,000 |
|  | Task 3 | Deliverable- A&T agreement on: 1) Inventory basinwide VSP monitoring programs and assess adequacy, based on NOAA monitoring guidance and recommendations of AHSWG 2) Identify gaps in data collection, and 3) Prioritize populations for monitoring with Action Agencies. 4) Identify current IMWs |  |
| Unclear | 200873300 | Technical Support Contract for developing Regional Strategy for Status and Trend monitoring | $ 100,000 |
|  | Task 4 | Deliverable- Based upon NOAA VSP monitoring inventory and gap analysis: 1) Facilitate A&T, Action Agencies, and NPCC agreement on prioritized populations, 2) Implement a preferred strategy for VSP monitoring, and 3) Annually report through SOTR. |  |
| Unclear | 200873400 | Technical Support for annual population status reporting | $ 100,000 |
|  | Task 4 | Deliverable- Provide techical services to A&T to support reporting VSP data and ensure data for run reconstruction is gathered and reported through SOTR. |  |
| Unclear | 200873500 | Data compilation and assessments for adult and juvenile fish passage performance tracking | $ 150,000 |
| Unclear | 200873600 | Technical support for Review and Modification Recommendations for F&W Program Status and Trend projects | $ 100,000 |
| Unclear | 200873900 | Technical Support for Fish Population Status Monitoring Regional Strategy | $ 200,000 |
| Unclear | 200874000 | Fund additional marking of hatchery produced fish | $ 500,000 |
|  | Task 5 | Deliverable- 1) Report results of annual VSP monitoring including an assessment of the quality of monitoring designs. 3) Facilitate gathering information to report juvenile and adult passage through SOTR. 2) Assess adequacy of current VSP monitoring and recommend potential changes. |  |
| Unclear | 200873800 | Technical Support for Hydro Tagging and Marking Action Plan | $ 200,000 |
|  | Task 6 | Deliverable- Build from CSMEP Snake Basin Pilot report and the CSMEP Inventory of Management Decisions to develop an integrated monitoring program for 1 ESU. |  |
|  |  |  | $ 8,350,000 |

H:\WORK\MonitoringCommittee\2009_0224\ProposalmemoMAG.doc(sentbyTIverson021809)

# Text boxes

851 SW Sixth Avenue, Suite 300  |  Pacific First Building  |  Portland, OR 97204-1339  |  Phone: 503-229-0191 |  Fax: 503-229-0443

Coordinating and promoting effective protection and

restoration of fish, wildlife, and their

habitat in the

Columbia River Basin.

The Authority is comprised of the following tribes

and government agencies:

Burns Paiute Tribe

Coeur d’Alene Tribe

Confederated Salish and Kootenai Tribes

of the Flathead Reservation

Confederated Tribes

of the Colville Reservation

Confederated Tribes

of the Umatilla Indian Reservation

Confederated Tribes

of the Warm Springs Reservation

Confederated Tribes and Bands of the Yakama Nation

Idaho Department

of Fish and Game

Kootenai Tribe

of Idaho

Montana Fish, Wildlife & Parks

National Marine Fisheries Service

Nez Perce Tribe

Oregon Department

of Fish and Wildlife

Shoshone-Bannock Tribes of Fort Hall

Shoshone-Paiute Tribes of Duck Valley

U.S. Fish & Wildlife Service

Washington Department of Fish

and Wildlife

Coordinating Agencies

Columbia River

Inter-Tribal Fish Commission

Upper Columbia

United Tribes

Compact of the Upper Snake River Tribes