## Cost by Task
Timeline
| Comments | Full CBFWA Cost Estimate | BPA Proposed Funding Level | Priority (High, Medium, Low) for CBFWA involvement | Keep in Work Plan? (can funding be provided from another source?) | Other potential funding source? | 2010-01-01 | 2010-06-01 | 2011-01-01 | 2011-06-01 | 2012-01-01 | 2012-06-01 | 2013-01-01 | 2013-06-01 | 2014-01-01 | 2014-06-01
Policy Directive # 1: the Members direct CBFWA staff to facilitate technical and policy committees and workshops for Members to exchange perspectives and information related to policy, technical and scientific interests to support fish and wildlife management in the Columbia River Basin. |  |  |  | High | Yes
A - Members |  | 64176.5 | 64176.5
1.1.A.1. The Members will meet twice per year to: 1) provide overall policy directions to the Executive Director, the Members Advisory Group, and committees; 2) establish operating guidelines for each committee; 3) retain, assign, or recall issues to the appropriate committee as needed; and 4) review actions taken and evaluate implementation of policy directives. | Policy level briefings to each member and visits, Meeting facilitation, Support material management, face to face meetings |  |  | High | Yes |  | Approve workplan | Review actions taken Evaluate policy directives Affirm work plan Approve SOTR publication | Review actions taken Evaluate policy directives Approve annual workplan | Review actions taken Evaluate policy directives Affirm work plan Approve SOTR publication | Review actions taken Evaluate policy directives Approve annual workplan | Review actions taken Evaluate policy directives Affirm work plan Approve SOTR publication | Review actions taken Evaluate policy directives Approve annual workplan | Review actions taken Evaluate policy directives Affirm work plan Approve SOTR publication | Review actions taken Evaluate policy directives Approve annual workplan | Review actions taken Evaluate policy directives Affirm work plan Approve SOTR publication
B – Members Advisory Group (MAG) |  | 96264.75 | 83429.45
1.1.B.1. The MAG will meet ten times per year to implement the policy directives of the Members by discussing policy positions and recommendations from the committees and approving transmittal of consensus recommendations to decision makers; maintaining the active consensus model consistent with the current CBFWA charter, | Policy level briefings to each member, Meeting facilitation, Support material management, WebEx meetings |  |  | High | Yes. Reduce to 10 mtgs per year |  | 2010-01-01: Implement workplan Consider committee recommendations BiOp Implementation Program Plan& Implement; 2011-01-01: Implement workplan Consider committee recommendations BiOp Implementation Program Implementation BPA Rate Case initiation; 2012-01-01: Implement workplan Consider committee recommendations BiOp Evaluation Program Implementation; 2013-01-01: Implement workplan Consider committee recommendations BiOp Implementation Program Evaluation BPA Rate Case initiation; 2014-01-01: Implement workplan Consider committee recommendations BiOp Implementation Program Planning
C – Anadromous Fish Advisory Committee (AFAC) |  | 64176.5 | 57758.85
1.1.C.1. The AFAC will meet approximately ten times per year to consider specific assignments by the Members and MAG and to support a forum to coordinate anadromous fish projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The AFAC will review and comment on the following topics and provide recommendations for MAG consideration: | Meeting facilitation, Support material management, WebEx meetings |  | 10% reduction in BPA option results in fewer meetings and fewer products | High | Yes |  | 2010-01-01: ongoing
1.1.C.2. the continued development and implementation of the basinwide monitoring priorities , |  |  |  | High | Yes | Funding should be provided to integrate CBFWA priorities with other regional efforts | 2010-01-01: Monitoring framework discussions (Mainstem); 2010-06-01: Monitoring framework discussions cont'd
1.1.C.3. a basinwide tagging strategy , |  |  |  | High | Yes | Funding should be provided to integrate CBFWA priorities with other regional efforts | 2010-01-01: Basinwide tagging strategy recs
1.1.C.4. common templates and strategies for updating Subbasin Plans and creating Multi-year Action Plans (coordinate priority actions and reporting), |  |  |  | High |  | add to RFAC and WAC | 2010-01-01: SBP/MYAP Updates
1.1.C.5. reporting of hatchery and wild anadromous fish, |  |  |  | High | Yes |  | 2010-01-01: Recommendations for monitoring conversation
1.1.C.6. consistent proposal development and review in the Council's Categorical Review to verify consistency with Program measures (linkage of actions to objectives), |  |  |  | High | Yes |  | 2010-01-01: Mainstem Artificial Production; 2010-06-01: Geographic Reviews; 2011-01-01: Geographic Reviews
1.1.C.7. support the Lamprey Technical Work Group (LTWG) which will meet as necessary (approximately 5 times per year) to discuss issues specific to lamprey in the Columbia River Basin and provide recommendations for AFAC then MAG consideration, | Meeting facilitation, Support material management, WebEx meetings |  |  | High | Yes |  | 2010-01-01: ongoing
· technical recommendations for operations of the FCRPS that protect migrating lamprey, |  |  |  | Medium |  |  | 2010-01-01: ongoing
· organize and host a lamprey workshop to share current information on life history, abundance and distribution in the Columbia River Basin, |  |  |  | Medium |  | CRITFC/ USFWS/ CTUIR | 2011-06-01: host workshop; 2013-06-01: host workshop
· develop a literature review paper including information on risks and benefits of, and alternatives to, trans-locating adult lamprey, |  |  |  | Medium |  |  | 2010-01-01: review draft
· work with the US Army Corps of Engineers (COE) and other interested parties to develop passage standards for Pacific Lamprey which will include defining and selecting metrics, |  |  |  | Medium |  | CRITFC | 2010-01-01: rec priority metrics; 2010-06-01: develop standards for metrics
· support the US Fish and Wildlife Service (USFWS) Pacific Lamprey Conservation Initiative by providing a forum for communication and discussion. |  |  |  | Medium |  | USFWS | 2010-01-01: ongoing
1.1.C.8. anadromous fish reintroduction strategies into blocked areas, | Added by MAG on Oct 19 |  |  | High | Yes | OWEB, IPC, Others
1.1.C.9. interaction of introduced fish species with salmon and steelhead smolts, | Added by MAG on Oct 19 |  |  | Medium | Yes
D – Resident Fish Advisory Committee (RFAC) |  | 38505.9 | 34655.31
1.1.D.1. The RFAC will be approximately ten times per year to consider specific assignments by the Members and MAG and to support a unique forum to coordinate resident fish projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The RFAC will review and comment on the following topics and provide recommendations for MAG consideration: | Meeting facilitation, Support material management, WebEx meetings |  | 10% reduction in BPA option | High |  |  | 2010-01-01: Ongoing
1.1.D.2. comments on resident fish specific issues related to implementation of the Fish and Wildlife Program as they arise (i.e., Independent Scientific Advisory Board (ISAB) Report on non-native fish, Risk Assessment Templates for resident fish), |  |  |  | High |  |  | 2010-01-01: Ongoing ad-hoc
1.1.D.3. recommendations for Council or BPA processes to develop protocols to define and evaluate operational losses for resident fish caused by operation of the FCRPS, |  |  |  | High |  |  | 2010-01-01: Consultation on recommendations
1.1.D.4. develop criteria and review project proposals to facilitate implementation of resident fish loss assessments consistently across the Columbia River Basin, |  |  |  | High |  |  | 2010-01-01: Criteria development; 2010-06-01: Review proposals
1.1.D.5. consistent proposal development and review in the Council's Categorical Review to verify consistency with Program measures (linkage of actions to objectives). |  |  |  | High | Yes |  | 2010-01-01: Mainstem Artificial Production Blocked Area; 2010-06-01: Blocked Area Geographic Reviews; 2011-01-01: Geographic Reviews
1.1.D.6. common templates and strategies for updating Subbasin Plans and creating Multi-year Action Plans (coordinate priority actions and reporting), |  |  |  | High |  | add to RFAC and WAC | 2010-01-01: SBP/MYAP Updates
E – Wildlife Advisory Committee (WAC) |  | 38505.9 | 34655.31
1.1.E.1. The WAC will meet approximately ten times per year to consider specific assignments by the Members and MAG and to support a unique forum to coordinate wildlife projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The WAC will review and comment on the following topics and provide recommendations for MAG consideration: | Meeting facilitation, Support material management, WebEx meetings |  | 10% reduction in BPA option | High |  |  | 2010-01-01: Ongoing
1.1.E.2. development policy and technical recommendations to the Council's Wildlife Crediting Forum, |  |  |  | High | Yes | NPCC
1.1.E.3. collaboratively develop and agree on a template for wildlife area management plans to support Program objectives, |  |  |  | Medium |  |  | 2010-01-01: Ongoing
1.1.E.4. recommendations on a framework or guidelines for developing wildlife mitigation agreements between BPA and the fish and wildlife agencies and Tribes, |  |  |  | High |  |  | 2010-01-01: Draft guidelines; 2010-06-01: Recommendations
1.1.E.5. recommendations on a wildlife monitoring framework to assess and report the effectiveness of Program funded wildlife projects, |  |  |  | Medium |  |  | 2010-01-01: Draft framework; 2010-06-01: Recommendations
1.1.E.6. recommend a methodology to evaluate and define FCRPS operation losses for wildlife, |  |  |  | High |  |  | 2010-01-01: Recommendations
1.1.E.7. consistent proposal development and review in the Council's Categorical Review to verify consistency with Program measures (linkage of actions to objectives). |  |  |  | High | Yes |  | 2010-01-01: Blocked Area; 2010-06-01: Blocked Area Geographic Reviews; 2011-01-01: Geographic Reviews
1.1.E.8. common templates and strategies for updating Subbasin Plans and creating Multi-year Action Plans (coordinate priority actions and reporting), |  |  |  | High |  | add to RFAC and WAC | 2010-01-01: SBP/MYAP Updates
F – Fish Passage Advisory Committee (FPAC) |  | 12835.3 | 11551.77
1.1.F.1. The FPAC will provide policy direction for and administration of the Fish Passage Center and will provide policy recommendations for MAG consideration as necessary, |  |  | 10% reduction in BPA option | High |  |  | 2010-01-01: Ongoing
G – Fish Screening Oversight Committee (FSOC) |  | 25670.6 | 23103.54
1.1.G.1. The FSOC will meet quarterly to consider specific assignments by Members and MAG and to support a unique forum to discuss fish screening projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The FSOC will review and comment on the following topics and provide recommendations for MAG consideration: |  |  | 10% reduction in BPA option | High |  | NOAA/USFWS | 2010-01-01: Ongoing
1.1.G.2. organize and host the Bi-Annual Northwest Fish Screening and Passage Workshop, |  |  |  | Medium |  |  | 2011-06-01: workshop; 2013-06-01: workshop
1.1.G.3. support coordination and facilitation of Mitchell Act and Fisheries Restoration and Irrigation Mitigation Act (FRIMA) funding for fish screens in the Columbia River Basin, |  |  |  | Medium |  |  | 2010-01-01: ongoing
1.1.G.4. develop and evaluate fish screen criteria that are adequate for lamprey as well as juvenile salmonids, |  |  |  | Medium |  |  | 2010-01-01: ongoing
1.1.G.5. develop a review paper on the possible effects of invasive species on compliance of screens with criteria, |  |  |  | Medium |  |  | 2010-01-01: review draft; 2010-06-01: recommendations
H - CBFWA Staff will: |  | 385059 | 374148.995
1.2.H.1. maintain the CBFWA website (directory, calendar, databases, job list, etc.), | Administrative support |  |  | High |  |  | 2010-01-01: ongoing
1.2.H.2. maintain CBFWA committee web pages and data management to support all CBFWA activities, | Administrative support |  |  | High |  |  | 2010-01-01: ongoing
1.3.H.1. provide CBFWA meeting facilities and administrative support for all CBFWA policy and technical committee meetings, | Meeting logistics |  |  | High |  |  | 2010-01-01: ongoing
1.3.H.2. manage contracts to provide coordination support to fish and wildlife managers for participation in Fish and Wildlife Program activities through the Columbia Basin Fish and Wildlife Foundation (CBFWF). | CBFWF contracting support |  |  | High |  |  | 2010-01-01: ongoing
Policy Directive # 2: the Members direct CBFWA staff to monitor and report on activities of key regional forums where policies, programs, and actions that affect fish and wildlife are planned and implemented. |  | 314464.85 | 288794.25 | High
2.1.1. CBFWA staff will attend regional meetings and provide information updates to the CBFWA Members, | Attend 9 Council meetings, Attend monthly BOG meetings, Attend other ad-hoc meetings and workshops, |  |  | High |  |  | 2010-01-01: ongoing
2.1.2. CBFWA staff will perform analyses as requested to support the activities of the CBFWA MAG and technical committees, | Policy, budget, and technical analyses to support committees |  |  | High |  |  | 2010-01-01: ongoing
2.1.3. CBFA staff will provide information updates to the co-managers on other issues related to fish and wildlife activities occurring within the Columbia River Basin. | Track other issues in the Basin through publications, reports, and hear-say |  |  | High |  |  | 2010-01-01: ongoing
2.1.4. CBFWA staff will provide support for the 13 Tribes involvement in Columbia River Treaty discussions, |  |  | do not include in BPA option, consider alternative funding | High | No | BPA Power Operations | 2010-01-01: facilitate and support meetings and recommendations Phase 1 Report comments/feedback; 2010-06-01: facilitate and support meetings and recommendations Phase 2 guidance; 2011-01-01: facilitate and support meetings and recommendations Phase 2 Report comments/feedback; 2011-06-01: facilitate and support meetings and recommendations Phase 2 Report comments/feedback; 2012-01-01: facilitate and support meetings and recommendations Phase 2 Report comments/feedback
Policy Directive # 3: the Members direct CBFWA staff to maintain a “Status of the Resources” (SOTR) website and annually prepare a written report summarizing the current information provided on the website. | Professional staff and adminstrative staff time, printing costs, other costs | 372223.7 | 362224 | High
3.1.1. maintain the SOTR website, |  |  |  | High |  |  | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
3.2.1. publish the SOTR report annually, |  |  | do not print SOTR in BPA option | Medium | Don't print (-$10,000) | BPA | 2010-01-01: Prepare publication; 2011-01-01: Prepare publication; 2012-01-01: Prepare publication; 2013-01-01: Prepare publication; 2014-01-01: Prepare publication
3.2.2. facilitate CBFWA Members collaboration with Council, BPA, National Oceanic and Atmospheric Administration (NOAA) Fisheries, tribes and states to ensure the SOTR supports regional reporting requirements, |  |  |  | High |  |  | 2010-01-01: Ongoing collaboration
3.3.1. work with other entities [US Forest Service (USFS), Bureau of Land Management (BLM), Washington Department of Ecology (WDOE), CRITFC, Oregon Department of Fish and Wildlife (ODFW) to inform the WA State of the Salmon Report, OWEB, Biological Opinion (BiOp) and Accord reports],to coordinate reporting of habitat status and trend information at the relevant population scale will be reported in the SOTR, consistent with the needs of the collecting agencies, |  |  |  | High |  |  | 2010-01-01: Ongoing collaboration
3.4.1. work with data management entities to support transfer of data to support regional reporting requirements. |  |  |  | High |  |  | 2010-01-01: Data management discussion follows monitoring framework discussion; 2010-06-01: Engage in data management discussion
Total |  | 1411883 | 1334497.975
|  |  | 1681355 | < BPA proposed total budget
|  |  | 1340247.8 | < CBFWA staff target

## FTE by Task
|  |  | Functions provided through CBFWA contract with BPA* | [9 empty] | Functions supported through Indirect Costs attributed to CBWFA contract
| Comments | Total FTE | Policy Coordinator | Program Coordinator | Budget Coordinator | RFAC Coordinator | SOTR Coordinator | AFAC Coordinator | WAC Coordinator | RME Coordinator | IT/Web services | Adminstrative Support | IT/Web services | Adminstrative Support
Policy Directive # 1: the Members direct CBFWA staff to facilitate technical and policy committees and workshops for Members to exchange perspectives and information related to policy, technical and scientific interests to support fish and wildlife management in the Columbia River Basin. | [14 empty] | 7.15
A - Members
1.1.A.1. The Members will meet twice per year to: 1) provide overall policy directions to the Executive Director, the Members Advisory Group, and committees; 2) establish operating guidelines for each committee; 3) retain, assign, or recall issues to the appropriate committee as needed; and 4) review actions taken and evaluate implementation of policy directives. | Policy level briefings to each member and visits, Meeting facilitation, Support material management, face to face meetings | 0.5 | 0.2 | 0.1 | [7 empty] | 0.1 |  | 0.1
B – Members Advisory Group (MAG)
1.1.B.1. The MAG will meet ten times per year to implement the policy directives of the Members by discussing policy positions and recommendations from the committees and approving transmittal of consensus recommendations to decision makers; maintaining the active consensus model consistent with the current CBFWA charter, | Policy level briefings to each member, Meeting facilitation, Support material management, WebEx meetings | 0.75 | 0.2 | 0.2 | [7 empty] | 0.1 |  | 0.25
C – Anadromous Fish Advisory Committee (AFAC)
1.1.C.1. The AFAC will meet approximately ten times per year to consider specific assignments by the Members and MAG and to support a forum to coordinate anadromous fish projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The AFAC will review and comment on the following topics and provide recommendations for MAG consideration: | Meeting facilitation, Support material management, WebEx meetings | 0.45 | [5 empty] | 0.2 |  | 0.2 |  | 0.05
1.1.C.2. the continued development and implementation of the basinwide monitoring priorities ,
1.1.C.3. a basinwide tagging strategy ,
1.1.C.4. common templates and strategies for updating Subbasin Plans and creating Multi-year Action Plans (coordinate priority actions and reporting),
1.1.C.5. reporting of hatchery and wild anadromous fish,
1.1.C.6. consistent proposal development and review in the Council's Categorical Review to verify consistency with Program measures (linkage of actions to objectives),
1.1.C.7. support the Lamprey Technical Work Group (LTWG) which will meet as necessary (approximately 5 times per year) to discuss issues specific to lamprey in the Columbia River Basin and provide recommendations for AFAC then MAG consideration, | Meeting facilitation, Support material management, WebEx meetings | 0.25 | [5 empty] | 0.2 |  |  |  | 0.05
· technical recommendations for operations of the FCRPS that protect migrating lamprey,
· organize and host a lamprey workshop to share current information on life history, abundance and distribution in the Columbia River Basin,
· develop a literature review paper including information on risks and benefits of, and alternatives to, trans-locating adult lamprey,
· work with the US Army Corps of Engineers (COE) and other interested parties to develop passage standards for Pacific Lamprey which will include defining and selecting metrics,
· support the US Fish and Wildlife Service (USFWS) Pacific Lamprey Conservation Initiative by providing a forum for communication and discussion.
1.1.C.8. anadromous fish reintroduction strategies into blocked areas, | Added by MAG on Oct 19
1.1.C.9. interaction of introduced fish species with salmon and steelhead smolts, | Added by MAG on Oct 19
D – Resident Fish Advisory Committee (RFAC)
1.1.D.1. The RFAC will be approximately ten times per year to consider specific assignments by the Members and MAG and to support a unique forum to coordinate resident fish projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The RFAC will review and comment on the following topics and provide recommendations for MAG consideration: | Meeting facilitation, Support material management, WebEx meetings | 0.35 |  |  |  | 0.3 | [5 empty] | 0.05
1.1.D.2. comments on resident fish specific issues related to implementation of the Fish and Wildlife Program as they arise (i.e., Independent Scientific Advisory Board (ISAB) Report on non-native fish, Risk Assessment Templates for resident fish),
1.1.D.3. recommendations for Council or BPA processes to develop protocols to define and evaluate operational losses for resident fish caused by operation of the FCRPS,
1.1.D.4. develop criteria and review project proposals to facilitate implementation of resident fish loss assessments consistently across the Columbia River Basin,
1.1.D.5. consistent proposal development and review in the Council's Categorical Review to verify consistency with Program measures (linkage of actions to objectives).
1.1.D.6. common templates and strategies for updating Subbasin Plans and creating Multi-year Action Plans (coordinate priority actions and reporting),
E – Wildlife Advisory Committee (WAC)
1.1.E.1. The WAC will meet approximately ten times per year to consider specific assignments by the Members and MAG and to support a unique forum to coordinate wildlife projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The WAC will review and comment on the following topics and provide recommendations for MAG consideration: | Meeting facilitation, Support material management, WebEx meetings | 0.35 | [6 empty] | 0.3 |  |  | 0.05
1.1.E.2. development policy and technical recommendations to the Council's Wildlife Crediting Forum,
1.1.E.3. collaboratively develop and agree on a template for wildlife area management plans to support Program objectives,
1.1.E.4. recommendations on a framework or guidelines for developing wildlife mitigation agreements between BPA and the fish and wildlife agencies and Tribes,
1.1.E.5. recommendations on a wildlife monitoring framework to assess and report the effectiveness of Program funded wildlife projects,
1.1.E.6. recommend a methodology to evaluate and define FCRPS operation losses for wildlife,
1.1.E.7. consistent proposal development and review in the Council's Categorical Review to verify consistency with Program measures (linkage of actions to objectives).
1.1.E.8. common templates and strategies for updating Subbasin Plans and creating Multi-year Action Plans (coordinate priority actions and reporting),
F – Fish Passage Advisory Committee (FPAC)
1.1.F.1. The FPAC will provide policy direction for and administration of the Fish Passage Center and will provide policy recommendations for MAG consideration as necessary, |  | 0.1 | 0.05 |  |  |  |  | 0.05
G – Fish Screening Oversight Committee (FSOC)
1.1.G.1. The FSOC will meet quarterly to consider specific assignments by Members and MAG and to support a unique forum to discuss fish screening projects, programs and funding sources to ensure efficiency in implementing the Fish and Wildlife Program, The FSOC will review and comment on the following topics and provide recommendations for MAG consideration: |  | 0.1 | [5 empty] | 0.1
1.1.G.2. organize and host the Bi-Annual Northwest Fish Screening and Passage Workshop,
1.1.G.3. support coordination and facilitation of Mitchell Act and Fisheries Restoration and Irrigation Mitigation Act (FRIMA) funding for fish screens in the Columbia River Basin,
1.1.G.4. develop and evaluate fish screen criteria that are adequate for lamprey as well as juvenile salmonids,
1.1.G.5. develop a review paper on the possible effects of invasive species on compliance of screens with criteria,
H - CBFWA Staff will:
1.2.H.1. maintain the CBFWA website (directory, calendar, databases, job list, etc.), | Administrative support | 0.45 | [8 empty] | 0.05 | 0.2 | 0.1 | 0.1
1.2.H.2. maintain CBFWA committee web pages and data management to support all CBFWA activities, | Administrative support | 0.7 | [9 empty] | 0.3 | 0.1 | 0.3
1.3.H.1. provide CBFWA meeting facilities and administrative support for all CBFWA policy and technical committee meetings, | Meeting logistics | 1.55 | [8 empty] | 0.05 | 0.7 |  | 0.8
1.3.H.2. manage contracts to provide coordination support to fish and wildlife managers for participation in Fish and Wildlife Program activities through the Columbia Basin Fish and Wildlife Foundation (CBFWF). | CBFWF contracting support | 1.6 | [9 empty] | 0.3 |  | 1.3
Policy Directive # 2: the Members direct CBFWA staff to monitor and report on activities of key regional forums where policies, programs, and actions that affect fish and wildlife are planned and implemented. | [14 empty] | 1.85
2.1.1. CBFWA staff will attend regional meetings and provide information updates to the CBFWA Members, | Attend 9 Council meetings, Attend monthly BOG meetings, Attend other ad-hoc meetings and workshops, | 0.8 | 0.25 | 0.1 | 0.05 | 0.1 | 0.05 | 0.1 | 0.05 | 0.1
2.1.2. CBFWA staff will perform analyses as requested to support the activities of the CBFWA MAG and technical committees, | Policy, budget, and technical analyses to support committees | 0.55 |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.05 | 0.1
2.1.3. CBFA staff will provide information updates to the co-managers on other issues related to fish and wildlife activities occurring within the Columbia River Basin. | Track other issues in the Basin through publications, reports, and hear-say | 0.25 | 0.1 | 0.1 | [5 empty] | 0.05
2.1.4. CBFWA staff will provide support for the 13 Tribes involvement in Columbia River Treaty discussions, |  | 0.25 | 0.05 | 0.1 | [7 empty] | 0.1
Policy Directive # 3: the Members direct CBFWA staff to maintain a “Status of the Resources” (SOTR) website and annually prepare a written report summarizing the current information provided on the website. | Professional staff and adminstrative staff time, printing costs, other costs | [13 empty] | 2
3.1.1. maintain the SOTR website, |  | 1.2 | 0.1 | 0.1 |  |  | 0.2 | 0.25 |  | 0.05 | 0.4 |  |  | 0.1
3.2.1. publish the SOTR report annually, |  | 0.45 |  |  |  |  | 0.2 |  |  |  | 0.2 |  |  | 0.05
3.2.2. facilitate CBFWA Members collaboration with Council, BPA, National Oceanic and Atmospheric Administration (NOAA) Fisheries, tribes and states to ensure the SOTR supports regional reporting requirements, |  | 0.1 | 0.05 |  |  |  | 0.05
3.3.1. work with other entities [US Forest Service (USFS), Bureau of Land Management (BLM), Washington Department of Ecology (WDOE), CRITFC, Oregon Department of Fish and Wildlife (ODFW) to inform the WA State of the Salmon Report, OWEB, Biological Opinion (BiOp) and Accord reports],to coordinate reporting of habitat status and trend information at the relevant population scale will be reported in the SOTR, consistent with the needs of the collecting agencies, |  | 0.15 | [7 empty] | 0.1 | 0.05
3.4.1. work with data management entities to support transfer of data to support regional reporting requirements. |  | 0.1 |  | 0.05 | [6 empty] | 0.05
Total |  | 11 | 1 | 0.85 | 0.15 | 0.5 | 0.5 | 1 | 0.4 | 0.6 | 0.8 | 2 | 0.2 | 3

## 2010 Members Funding
Participation funding provided through the CBFWA project.
CBFWA Member | Annual Estimated Cost of All Program Related Coordination in FY09 | FY09 BPA Contribution Through CBFWA* | FY10 BPA Contribution Through CBFWA | % Requested from BPA
Burns Paiute Tribe | 40000 | 15000 | 15000 | 37.5%
Confederated Colville Tribes | 80000 | 15000 | 10000 | 12.5%
Coeur d' Alene Tribe | 135000 | $- | 0 | 0%
Confederated Salish and Kootenai Tribes | 18000 | 6000 | 4500 | 25%
Confederated Tribes of the Umatilla Indian Reservation | 60000 | 25000 | 20000 | 33.33%
Confederated Tribes of the Warm Springs Reservation | 60000 | 17000 | 10000 | 16.67%
Idaho Fish and Game | 107000 | 35000 | 35000 | 32.71%
Kootenai Tribe of Idaho | 90000 | $- | 0 | 0%
Montana Department of Fish, Wildlife, and Parks | 25000 | 10000 | 10400 | 41.6%
NOAA Fisheries | 30000 | $- | 0 | 0%
Nez Perce Tribe | 185000 | 60000 | 60000 | 32.43%
Oregon Department of Fish and Wildlife | 157000 | 37500 | 37500 | 23.89%
Shoshone Bannock Tribe | 75000 | 25000 | 25000 | 33.33%
Shoshone Paiute Tribe | 130000 | 15000 | 14000 | 10.77%
US Fish and Wildlife Service | 100000 | 6000 | 4000 | 4%
Washington Department of Fish and Wildlife | 120000 | 45000 | 45000 | 37.5%
Yakama Nation | 145000 | 12000 | 12000 | 8.276%
Total | 1557000 | 323500 | 302400 | 20.56%
Cost Pool (12.8%) |  | 41408 | 38707.2
Total Members |  | 364908 | 341107.2
*Does not include contract funding for Member participation in development of M&E Framework and Strategy.