| Bruce A. Measure Chair Montana |  | Dick Wallace Vice-Chair Washington |
| --- | --- | --- |
| Rhonda Whiting Montana W. Bill Booth Idaho James A. Yost Idaho |  | Tom Karier Washington Melinda S. Eden Oregon Joan M. Dukes Oregon |

February 25, 2010

MEMORANDUM

TO:	Council Members

FROM:	Staff

SUBJECT:	Update on RM&E/Artificial Production Category Review and BiOp Fast-track proposals review

RM&E/Artificial Production Categorical Review

At the February meeting, staff presented a schedule that would have the RM&E/Artificial Production categorical review beginning on April 2, 2010.  After consideration of several issues, Council and Bonneville staffs agree that an extension of the start date may be warranted to 1) allow the Taurus team time to program all essential components for the proposal form intake; 2) allow for public feedback on the Monitoring and Evaluation Review and Reporting document after the Council releases it for public comment; and 3) allow time for project proponents to test the new proposal system and provide feedback.  Council staff will have available at the Committee meeting, a detailed schedule reflecting a start date of between April 2, and June 1, 2010 for the categorical review.

Fast Track BiOp Projects

The ISRP completed its initial review of the 19 proposals on February 24th.  See http://www.nwcouncil.org/fw/budget/2010/rme.  Attachment 1 is a summary of the ISRP’s initial recommendations by project.  The recommendations represent a final review for a subset of projects, while others represent a preliminary review with a “response to ISRP requested”.

The schedule has been updated to reflect a public comment period (Attachment 2).  The major change to the schedule is the date that the Council makes recommendations to BPA, which will occur at the April meeting rather than the March meeting.

Attachment 1.  ISRP Initial Review of BiOp Fast Track Proposals (ISRP 2010-7)

The ISRP found that 9 proposals met scientific review criteria; 5 of these had qualifications that the ISRP recommended could be considered by the Council and addressed by the proponent and BPA during contracting. These 9 proposals are ready for immediate Council and BPA decisions. In response to the Council and BPA’s stated desire to implement the fast track action in 2010, the ISRP considered the option to specifically identify if a fast track work element is justified independently of other project actions. The ISRP found that 2 proposals justified the fast track component of their project but the complete project needed a response. These 2 proposals received an “in part/response requested” recommendation. The ISRP requested a response on the remaining 8 proposals.

| ID | Title | Proponent | Province | ISRP: Meets Criteria? |
| --- | --- | --- | --- | --- |
| 199305600 | Research to advance hatchery reform | NW Fisheries Science | Mainstem / Systemwide | Yes |
| 199703000 | Chinook Salmon Adult Abundance Monitoring | Nez Perce Tribe | Mountain Snake | Yes |
| 201003500 | Abundance, productivity and life history of Fifteenmile Creek Steelhead | ODFW |  | Yes |
| 201004200 | Tucannon Expanded PIT Tagging |  | Blue Mountain | Yes |
| 199801600 | Salmonid Productivity, Escapement, Trend, and Habitat Monitoring in the John Day River Subbasin | ODFW | Columbia Plateau | Yes (Qualified) |
| 201002600 | Chinook and Steelhead Genotyping for Genetic Stock Identification (GSI) at Lower Granite Dam | IDFG | Mainstem on the ground / Multiprovince | Yes (Qualified) |
| 201003100 | Snake River Chinook and Steelhead Parental Based Tagging | IDFG / NPT / SBT | Mainstem on the ground / Multiprovince | Yes (Qualified) |
| 201003400 | Upper Columbia Spring Chinook and Steelhead Juvenile and Adult Abundance, Productivity, and Spatial Structure Monitoring. | WDFW | Columbia Cascade | Yes (Qualified) |
| 201003800 | Lolo Creek Permanent Weir Construction | Nez Perce Tribe | Mountain Snake | Yes (Qualified) |
| 198909800 | Idaho Supplementation Studies | IDFG / NPT / SBT | Mountain Snake | In Part / Response requested |
| 199800702 | Grand Ronde Supplementation: Lostine River Operation and Maintenance and Monitoring and Evaluation | Nez Perce Tribe | Blue Mountain | In Part / Response requested |
| 199005500 | Idaho Steelhead Monitoring and Evaluation Studies | IDFG | Mountain Snake | Response requested |
| 199107300 | Idaho Natural Production Monitoring | IDFG | Mountain Snake | Response requested |
| 200301700 | Integrated Status and Effectiveness Monitoring Program (ISEMP): The design and evaluation of monitoring tools for salmon populations and habitat in the Interior Columbia River Basin. | NW Fisheries Science | Mainstem /Systemwide | Response requested |
| 201002800 | Implement a Rotating Panel Sampling Adult Steelhead in Small Tributaries of the Tucannon and Snake rivers | WDFW, NOAA | Columbia Plateau | Response requested |
| 201003000 | Estimate viable salmon population (VSP) parameters for Yakima steelhead major population group (MPG) | Yakama Nation, WDFW | Columbia Plateau | Response requested |
| 201003200 | Imnaha River Steelhead Status Monitoring (was 200205600) | Nez Perce Tribe | Blue Mountain | Response requested |
| 201003300 | Estimate the Relative Reproductive Success of Hatchery and Natural Origin Steelhead in the Methow River Basin | WDFW | Columbia Cascade | Response requested |
| 201003600 | Expansion of Washington’s Tag Recovery Program in the Lower Columbia Region to Improve Fisheries and Viable Salmonid Population Monitoring | WDFW | Lower Columbia | Response requested |

Attachment 2.  Fast-Track Project Schedule

| Date | Milestone | Note |
| --- | --- | --- |
| 14 December 2009 | Proposal Forms Ready | Done. On Council’s website; updated for RM&E |
| 25 January 2010 | Proposal Forms Due | Done. |
| 27 January | Proposals Sent to ISRP for Review | Done. |
| 24 February | ISRP Initial Report complete | Final recommendations on some projects; preliminary recommendations on others. Complete. |
| 24 February | Public Comment on ISRP Report begins |  |
| 24 February | Emails Requesting “response” to ISRP |  |
| 25 March | Public Comment Period ends | Council and staff consider comments and prepare recommendations |
| 25 March | Sponsor Responses Due back to ISRP | ISRP reviews responses and develops final report due April 16th |
| 1 April | Staff Recommendations to Council | On subset of projects that met scientific criteria from Feb 24 |
| 13 April | Committee Recommendations | On staff recommendations |
| 14 April | Council Recommendations | On committee recommendations |
| 15 April | Final ISRP Report Due | On “response requested” proposals |
| Late April/ May | Possible Special Council meeting or at regular May meeting | To approve final fast-track set |