Bonneville Power AdministrationAdministration

Fish and Wildlife Program FY99 Proposal Form

Section 1.  General administrative information

ANNUAL FISH MARKING-MISSING HATCHERY PROD’N GROUPS

| Bonneville project number, if an ongoing project | 8906500 |
| --- | --- |

Business name of agency, institution or organization requesting funding

U.S. Fish and Wildlife Service

| Business acronym (if appropriate) | USFWS |
| --- | --- |

Proposal contact person or principal investigator:

| Name | Walt Ambrogetti |
| --- | --- |
| Mailing Address | 9317 Highway 99, Suite I |
| City, ST Zip | Vancouver, Wa 98665 |
| Phone | 360/696/7605 |
| Fax | 360/696/7968 |
| Email address | Walt_Ambrogetti@mail.fws.gov |

Subcontractors. List one subcontractor per row; to add more rows, press Alt-Insert from within this table

Organization

Mailing Address

City, ST Zip

Contact Name

PSMFC

845 S.E. 82nd Dr. Suite100

Gladstone, Or 97027

Pam Kahut

Fish Passage Center

2501 SW First Ave Suite 230

Portland, Or. 97201

Michelle DeHart

CT of Umatilla IR

P.O. Box 638

Pendleton, 0r. 97801

Gary James

Yakama IN

P.O. Box 151

Toppenish, Wa 98948

Tom Scribner

Clatsop EDC

250 36th St.

Astoria, Or 97103

Jim Hill

WDFW

600 Capitol Way N.

Olympia, Wa 98501

Howard Fuss

ODFW

28655 Hwy 34

Corvallis, Or 97333

Mark Lewis

NPPC Program Measure Number(s) which this project addresses.

7.2D.1,  7.2D.3,  7.2D.4,  7.4I (Umatilla Production), 8.4c.2, 8.4D.1

NMFS Biological Opinion Number(s) which this project addresses.

Other planning document references.

If the project type is “Watershed” (see Section 2), reference any demonstrable support from affected  agencies, tribes, local watershed groups, and public and/or private landowners, and cite available documentation.    2.1.d.5

Subbasin.

Columbia River Basin and tributaries, from Wells WDFW Hatchery downstream.  Snake River Basin and tributaries, from Dworshak National Fish Hatchery downstream.

Short description.

The USFWS will mark various groups of fish for BPA funded projects using mobile fish marking trailers at federal and state hatcheries in the Columbia River basin. In order to meet objectives, a minimum of one marked group of fish for each production release is necessary for evaluation.  All fish released from the various facilities along with mark/unmarked ratios are reported to the Pacific States Marine Fisheries Commission (PSMFC).  All fish recovered in various fisheries or at the hatchery are sampled to recover coded-wire tags.  The various purposes of evaluation include: to estimate the survival of each release group, to estimate the contribution of each release group to ocean and in-river fisheries, to estimate straying rate of hatchery fish, to estimate smolt migration speed, to evaluate hatchery practices, and individual broodstocks.

The USFWS will continue rearing of spring chinook at the Little White Salmon/Willard National Fish Hatchery Complex for release into the Umatilla River as a joint project with the Confederated Tribe of the Umatilla Indian Reservation.

The USFWS will also conduct all the fish health exams necessary to meet fish disease requirements necessary for these fish to be planted in the Umatilla River.

Section 2.  Key words

Mark

Programmatic

Categories

Mark

Activities

Mark

Project Types

X

Anadromous fish

Construction

Watershed

Resident fish

O & M

Biodiversity/genetics

Wildlife

X

Production

Population dynamics

Oceans/estuaries

Research

Ecosystems

Climate

+

Monitoring/eval.

Flow/survival

Other

Resource mgmt

Fish disease

Planning/admin.

X

Supplementation

Enforcement

Wildlife habitat en-

Acquisitions

hancement/restoration

Other keywords.

Section 3.  Relationships to other Bonneville projects

Project #

Project title/description

Nature of relationship

8300600

Operation & Maint of BPA Fish Marking Trailers

8906500 was combined with this project in 1995

8401400

PSMFC/Fish Passage Center

Smolt Monitoring Program

sponsor

9101400

Umatilla Hatchery Satellite Project

sponsor

9506300

Yakima River Basin Evaluation

sponsor

Clatsop Economic Develop Council

sponsor

8906600

WDFW Missing Production Groups

Complementary Project

8906900

ODFW Missing Production Groups

Complementary Project

Section 4.  Objectives, tasks and schedules

Objectives and tasks

Obj 1,2,3

Objective

Task a,b,c

Task

1

Mark & Release at least one group of smolts from those Federal Hatcheries not currently doing so and mark the fish for the other projects within this contract.

a

Coordinate the marking with all appropriate entities, provide routine supervision of marking areas at each tagging site, and a quality-control plan

2

Recover and decode tags and estimate survival of tagged groups, and evaluate the results

a

Collect snouts from adult returns to hatcheries

3

Prepare an annual written report which will evaluate the survival and contribution of all representative groups of fish for all federal fish hatcheries in the Columbia River Basin.

a

Retrieve coded wire tag recoveries from PSMFC database.

4

Raise Spring chinook salmon at the Little White Salmon/Willard NFH Complex for the Umatilla Program

a

Begin rearing brood year 1998 spring chinook salmon

5

Conduct all fish Health exams necessary to meet the fish disease requirements necessary for these fish to be planted in the Umatilla River

a

Collect all samples and do required lab work and tests.

(See Section 7 for more Details on this table.)

Objective schedules and costs

Objective #

Start Date

mm/yyyy

End Date

mm/yyyy

Cost %

1

01/1999

12/1999

65%

2

01/1999

12/1999

2%

3

01/1999

12/1999

4%

4

01/1999

12/1999

22%

5

01/1999

12/1999

7%

Schedule constraints.

NA

Completion date.

Ongoing.

Section 5.  Budget

FY99 budget by line item

Item

Note

FY99

Personnel

$129,298

Fringe benefits

$50,282

Supplies, materials, non-expendable property

$69,405

Operations & maintenance

$54,932

Capital acquisitions or improvements (e.g. land, buildings, major equip.)

PIT tags

# of tags:25,500

$73,950

Travel

$21,593

Indirect costs

$102,535

Subcontracts

Other

TOTAL

$501,995

Outyear costs

Outyear costs

FY2000

FY01

FY02

FY03

Total budget

$552,195

$607,414

$668,155

734,970

O&M as % of total

11%

11%

11%

11%

Section 6.  Abstract

Over 26.3 million juvenile salmonids have been marked by USFWS for evaluation in the Columbia River basin as a result of this project  The various purposes of evaluation include: to estimate the survival of each release group, to estimate the contribution of each release group to ocean and in-river fisheries, to estimate straying rate of hatchery fish, to estimate smolt migration speed, to evaluate hatchery practices, and individual broodstocks.

Under this 1999 proposal the USFWS will continue to mark fish for evaluation studies and also continue to rear spring chinook salmon for release for the Umatilla Fisheries Program. The USFWS will also conduct all the fish health exams necessary to meet fish disease requirements for these fish to be planted in the Umatilla River.

Section 7.  Project description

a.	Technical and/or scientific background.

PREVIOUS WORK HISTORY:

In 1989 the USFWS received a BPA contract, “Annual Fish Marking -Missing Hatchery Production Groups” (8906500),  to begin annually fish marking/coded-wire tagging production releases of anadromous salmonids at federal hatcheries which were not currently being marked.  This project was combined with the ongoing project “Operation and Maintenance of BPA Fish Marking Trailer” (8300600).  The (830060) number was dropped after the combining of the projects in 1995. The “Operation and Maintenance of BPA Fish Marking Trailer” Project began in 1983. Under 8300600, the USFWS received  funding for 12 years to mark fish for several BPA funded projects such as the Yakima Reprograming study, Youngs Bay- Clatsop County Salmon Rearing Program,  Fish Passage Center study, and several other Tribal , State, and Federal Programs.  During that time period, fish marking assistance or equipment was not available to many groups needing to mark fish.

Starting in 1996, the U.S. Fish & Wildlife Service (Service) Little White Salmon/Willard National Fish Hatchery Complex began raising upriver bright fall chinook salmon for the Umatilla Fisheries Program.  This program expanded in 1997 to include the rearing of spring chinook salmon.  The spring chinook program will continue in 1998 and beyond, however, the upriver bright fall chinook program will be transferred to the the Oregon Department of Fish and Wildlife (ODFW) Bonneville Hatchery after 1998.  Both of these programs were originally completed by ODFW, but a reduction in Mitchell Act funding at the Bonneville facility caused ODFW to change their production priorities and the Umatilla fish program was deleted.  The U.S. Fish & Wildlife Service agreed to take over this program for the tribe and the ongoing Bonneville Power Administration funding for this project was shifted to the Service.  This project was added to our existing Missing Group Contract in 1996. The 1998 fund request for the Little White Salmon/Willard National Fish Hatchery Complex has been adjusted to reflect reduced production due to the transfer of the upriver bright fall chinook program back to ODFW.

PROPOSED WORK IN 1999

The “1999 Annual Fish Marking-Missing Hatchery Production Groups Proposal” is for the USFWS to continue marking fish for ongoing evaluation studies to evaluate survival, contribution and hatchery goals.  The USFWS will continue rearing of spring chinook salmon at the Little White Salmon National Fish Hatchery Complex for release into the Umatilla River as a joint project with the Confederated Tribes of the Umatilla Indian Reservation.

The USFWS will also conduct all the fish health examinations necessary to meet fish disease requirements for these fish to be released in the Umatilla River.

The information collected through well established standard procedures for coded-wire tagging of juvenile salmonids will provide a long term database on hatchery fish survival, ocean catch distribution and contribution rates, and Columbia River harvest and return rates.  This information is critical for reviewing and auditing performance of artificial propagation (e.g. Integrated Hatchery Operations Team audits), identifying potential interactions such as straying with critical stocks (e.g. Section 7 consultations), managing harvest in the Columbia River basin and in ocean fisheries under the Pacific Fishery Management Council and Pacific Salmon Commission, and for assessing whether fish health, genetics, environmental trends, or other factors have altered the overall performance of artificially propagated stocks over time.

This project complements other marking programs including the Pacific Salmon Commission indicator stock marking, and Mitchell Act, Corps of Engineers, and U.S. Fish and Wildlife Service stock assessment activities.  The data collected is accessible to a wide variety of users through the PSMFC database.

The project addresses a number of goals and objectives of the 1994 Columbia River Basin Fish and Wildlife Program including development and demonstration of improved husbandry practices and fish health at hatcheries (7.2D.1, 7.2D.3, 7.2D.4), marking salmon from hatcheries with high stray rates (8.4C.2), and developing expanded marking programs required for ocean and inriver fisheries where Columbia River weak stocks are caught (8.4D.1).  The fish reared for release in the Umatilla River address production objectives under 7.4I.

Reports and Papers:

“Annual Coded Wire Tag Program:Missing Production Groups” Annual Reports 1989,1990,1991,1992,1993,1994,1995,1996,1997.

“Operation and Maintenance of BPA Fish Marking Trailer” Annual Reports, 1984,1985,1986,1987,1988,1989,1990,1991,1992,1993,1994,1995.

Project Presentations were given at the 1992 and 1997 BPA Projects Review Meetings.

Smolt monitoring and adult production reports provide the mechanism for feedback to managers concerning future decisions.

b.	Proposal objectives.

SCHEDULE

Coordinate, plan, and supervise. 	All Year.

Mark yearling fish for release in spring.	By September 1, 1999.

Mark underyearling fish.		At least 30 days prior to release.

Bio-sample and recover snouts of marked fish.	At time of spawning.

Recover coded-wire tags and decode.	By January 1, 2000.

Read scales for age analysis.	By January 1, 2000.

Input all bio-data into database.	By January 1, 2000

Analyze all bio-data on representative groups spawned.	By January 1, 2000

Prepare written annual marking and budget report.	By January 1, 2000.

Provide written annual analysis report.	By March 1, 2000.

Rear Umatilla fish.		All Year

Conduct fish health exams on Umatilla fish.	All Year

| Activity | Schedule |
| --- | --- |
| Activity 1 | Coded-wire tag 50k coho salmon at Eagle Creek NFH in January 1999 to be released in 1999. |
| Activity 2 | Coded-wire tag 50k spring chinook salmon at Little White Salmon NFH in March 1999 to be released in 1999. |
| Activity 3 | PIT tag 1.5k steelhead at Dworshak NFH in February 1999 to be released in 1999. |
| Activity 4 | PIT tag 7.5k spring chinook salmon at Leavenworth NFH in March 1999 to be released in 1999. |
| Activity 5 | PIT tag 6.0k summer chinook salmon at Wells SFH in May 1999 to be released in 1999. |
| Activity 6 | PIT tag 3.0k upriver bright chinook salmon at Priest Rapids SFH in May 1999 to be released in 1999. |
| Activity 7 | PIT tag 7.5k spring chinook salmon at Winthrop NFH in January 1999 to be released in 1999. |
| Activity 8 | Coded-wire tag 100k spring chinook salmon at Carson NFH in May 1999 to be released in 2000. |
| Activity 9 | Coded-wire tag 50k coho salmon at Willard NFH in August 1999 to be released in 2000. |
| Activity 10 | Coded-wire tag 120k spring chinook salmon at Entiat NFH in May 1999 to be released in 2000. |
| Activity 11 | Coded-wire tag 200k spring chinook salmon at Entiat NFH in May 1999 to be released in 1999. |
| Activity 12 | Coded-wire tag 50k coho salmon at Eagle Creek NFH in July 1999 to be released in 2000. |
| Activity 13 | Coded-wire tag 50k coho salmon at Eagle Creek NFH (CEDC) in July 1999 to be released in 2000. |
| Activity 14 | Coded-wire tag and ventral clip 20k spring chinook salmon at Carson NFH Umatilla) in May 1999 to be released in 2000. |
| Activity 15 | Coded-wire tag and ventral clip 40k spring chinook salmon at Little White Salmon NFH (Umatilla) in May 1999 to be released in 2000. |

| Activity 16 | Fin clip LV, 600k upriver bright chinook salmon at Little White Salmon NFH in March 1999) to be released in 1999. |
| --- | --- |
| Activity 17 | Fin clip, RV, 600k upriver bright chinook salmon at Little White Salmon NFH in March 1999 to be released in 1999. |
| Activity 18 | Bio-sample returning adults at various hatcheries associated with BPA Missing Production Groups. |
| Activity 19 | Prepare annual marking and budget report associated with BPA Missing Production Groups. |
| Activity 20 | Prepare annual analysis report associated with BPA Missing Production Groups, and other U.S. Fish and Wildlife Service hatchery programs in the Columbia River. |
| Activity 21 | Raise fish for Umatilla Project. |
| Activity 22 | Complete all fish health work on fish for Umatilla Project. |

c.	Rationale and significance to Regional Programs.

This Missing Hatchery Production Groups Project is a multi-agency project with joint cooperation between ODFW, WDFW, and the USFWS.  The coordination and regulation of the region wide tagging and tag recovery effort is handled through  PSMFC.  This cooperative project allows all the Tribes and agencies in the Columbia River basin to have a comprehensive and long term information on survival and contribution of individual hatchery production groups in the basin. Region wide consistency  in the tagging programs, data collection and data sharing are important tools that support a variety of critical management activities in the basin.

d.	Project history

“1999 Annual Fish Marking-Missing Hatchery Production Groups Proposal”

Project Number #8906500

Over 26.3 million juvenile salmonids have been marked by the USFWS in the past as a result of this contract for evaluation in the Columbia River basin. The Service proposes to mark 1,955,000 fish in 1999.  The various purposes of evaluation include: to estimate the survival of each release group, to estimate the contribution of each release group to ocean and in-river fisheries, to estimate straying rate of hatchery fish, to estimate smolt migration speed, to evaluate hatchery practices, and individual broodstocks.

Historic Obligations*

1990   $170,614*

1991   $271,410*

1992   $294,786*

1993   $406,790*

1994   $360,855*

1995   $502,700*

1996   $205,965

1997   $362,913

1998   $407,942

*Totals shown for historic funding are for both project 8300600 and 890065 combined.  Funding has fluctuated over the years due to variations in the fish marking programs.

1999 Objectives and Tasks

Objective 1:	Tag and release at least one group of smolts from those Federal and anadromous fish hatcheries not currently doing so in the Columbia River Basin.

Task 1.1	Coordinate the marking with all appropriate entities, provide routine supervision of marking areas at each tagging site, and provide a quality-control plan.

Task 1.2	Apply coded wire tags, PIT tag, and remove the adipose or other designated fins of smolts in species, numbers, and locations annually approved by Bonneville Power Administration (BPA) and listed in Table 1.  All procedures shall conform to those set forth in “Procedures for Coded Wire Tagging of Pacific Salmonids, 1987,” or most recent edition (Pacific States Marine Fisheries Commission).

Task 1.3	Report the number and species marked and released each year at each location in the annual report.

Objective 2:	Recover and decode tags and estimate survival of tagged groups, and evaluate the results.

Task 2.1	Collect snouts from adult returns to hatcheries.

Task 2.2	Recover tags from snouts in Task 2.1 and decode tags.

Task 2.3	Read scales.

Task 2.4	Input data into database.

Task 2.5	Using the above data and the data provided from fish recovered in the commercial fisheries, estimate survival and 95 percent confidence limits therein for each tagged group.  When two or more tagged groups are released from a site in a given year, test the null hypothesis that survival was not significantly different at the 95 percent confidence level.

Task 2.6	Analyze the results and recommend improvements in hatchery practices in the annual report.

Objective 3:	Prepare an annual written report which will evaluate the survival and contribution of all representative groups of fish for all federal fish hatcheries in the Columbia River Basin.

Task 3.1	Retrieve coded wire tag recoveries from PSMFC database.

Task 3.2	Analyze contribution and survival data for each representative group of fish.

Task 3.3	Prepare an annual report in summarized and narrative format for each representative group of production fish released at each of the following 14 hatcheries:

Willard-Coho Salmon

Entiat-Spring Chinook Salmon

Eagle Creek-Coho Salmon

Little White-Spring Chinook Salmon, URB Fall Chinook Salmon

Winthrop-Spring Chinook Salmon

Carson-Spring Chinook Salmon

Kooskia-Spring Chinook Salmon

Spring Creek-Fall Chinook Salmon

Warm Springs-Spring Chinook Salmon

Leavenworth-Spring Chinook and Steelhead Trout

Dworshak-Spring Chinook Salmon and Steelhead Trout

Wells-Summer Chinook Salmon

Priest Rapids-URB Fall Chinook Salmon

Route Butte-Spring Chinook Salmon

Objective 4:		The U.S. Fish and Wildlife Service Little White Salmon/Willard National Fish Hatchery Complex will raise upriver bright fall chinook and spring chinook salmon for the Umatilla Fisheries Program.

Task 4.1		Begin rearing brood year 1998 spring chinook (SCS) salmon.

Objective 5:		The U.S. Fish and Wildlife Service Lower Columbia River Fish Health Center at Underwood, Washington will conduct all fish health exams necessary to meet the fish disease requirements necessary for these fish to be planted in the Umatilla River.

Task 5.1		Collect all samples and do required lab work and tests.  Monthly health exams and one or two diagnostic exams on the Umatilla fish will be conducted consisting of parasite, bacterial and viral exams for pathogens of importance to salmonids including an Enzyme Linked Immunosorbent Assay (ELISA) used to initially segregate fish as to high, low or negative Bacterial Kidney Disease levels.  This will be followed by a first exam for virus on the fry.

e.	Methods.

The Missing Production Groups Report primarily addresses the problem of assessing releases of fish from production facilities.  The release information is collected with the USFWS Columbia River (information) System-CRiS.  Information prior to the Columbia River basin wide implementation of Cris, and from USFWS hatcheries in Idaho, is obtained from the Interagency StreamNet database (formerly the Coordinated Information System).

Recovery information is obtained from the PSMFC Regional Mark Information Center coded-wire tag database.  Tag lists are created for each release year, and reports are generated using the PSMFC TSI format.  These reports are downloaded in ASCII format.  A series of dBASE V programs transforms these ASCII files into a single dbf file.

A stock Assessment Reference Document is prepared for each hatchery, brood year, and species that had coded-wire tags.  Because many fish were released without representative coded-wire tags before the Missing Production Groups program began, a single Production Expansion Factor (PEF) - the total number of fish released divided by the total number of tagged fish released) is calculated for each hatchery, brood year, and species.  This PEF is used to expand recovery information for unmarked fish released, and to determine a general picture of the overall contribution and survival rates for each facility.

Total survival and contribution by fishery graphs are prepared with a combination of dBASE programs and spreadsheets. A brief description of the estimated survival and contribution for each species raised and released at national fish hatcheries is calculated.  Graphs for each hatchery and species are prepared, and summaries of release and recovery information are also included in the Annual  Reports.

f.	Facilities and equipment.

The USFWS uses mobile fish marking trailers which were purchased by BPA to mark the fish at hatcheries on the Columbia River and its tributaries.  The most modern fish marking machines and techniques are used to mark the fish, the same as used by the ODFW and WDFW.

g.	References.

Section 8.  Relationships to other projects

The “Annual Fish Marking-Missing Hatchery Production Groups” project has the following sponsors or non-financial supporters:  PSMFC,  Fish Passage Center, Yakima Indian Nation, Confederated Tribes of the Umatilla Indian Reservation, WDFW, ODFW, Clatsop Economic Development Council, NMFS and the  Army COE.  The BPA COTR is  Tom Morse.

In addition to marking the Missing Production Groups at the USFWS Hatcheries in the Columbia Basin the USFWS will also mark fish for PSMFC/Fish Passage Center (Project # 8401400 Smolt Monitoring Program-multiple agencies). In support of this project, fish will be PIT tagged at Dworshak, Leavenworth, Wells, Priest Rapids, and Winthrop hatcheries.

Fish will be marked for the Confederated Tribes of Umatilla Indian Reservation (Project #9101400 Umatilla Hatchery Satellite Program).  Starting in 1996 the USFWS began rearing and marking upriver bright fall chinook and spring chinook salmon in support of this project.  The USFWS also conducts all fish health exams necessary to meet fish disease monitoring requirements necessary for these fish to be transferred to the Umatilla River.

Section 9.  Key personnel

PERSONNEL FOR THE LOWER COLUMBIA RIVER FISHERIES PROGRAM OFFICE (1/23/98)

AMBROGETTI, WALTER J.

CURRENT TITLE:	Deputy Project Leader

Supervisory Fishery Management Biologist

Lower Columbia River Fisheries Program Office

B.S.	Fish and Wildlife Management, Oregon State University, 1968

Mr. Ambrogetti joined the USFWS in 1970 and has worked in the field of fish marking for the last 25 years.

OLHAUSEN, STEVEN K.

CURRENT TITLE:	Fishery Management Biologist

Lower Columbia River Fisheries Program Office

B.S.	Fish and Wildlife Management, Oregon State University, 1973

Mr. Olhausen joined the USFWS in 1975 and has worked in the field of fish marking for the last 14 years.

WILLS, DAVID A.

CURRENT TITLE:	Fishery Management Biologist

Lower Columbia River Fisheries Program Office

B.S.	Wildlife Management, Humboldt State University, 1976

B.S.	Fisheries Biology, Humboldt State University, 1978

Post Graduate studies: Humboldt State University and Uppsalla University, Sweden, 1982-1985.

Mr. Wills joined the USFWS in 1987.  He has six years PIT tagging experience and is the current PIT Tag Steering Committee Chairperson.

WALCH, KEN

CURRENT TITLE:	Fishery Management Biologist

Lower Columbia River Fisheries Program Office

B.S.	Wildlife Management, University of Montana, 1964

Mr. Walch joined the USFWS in 1983 and has worked in the field of fish marking for 15 years.

MAGNESON, DAN

CURRENT TITLE:	Fishery Management Biologist

Lower Columbia River Fisheries Program Office

A.S.	Wildlife Management, North Dakota State University, 1982

B.S.	Fisheries and Wildlife Biology, Iowa State University, 1984

Mr. Magneson joined the USFWS in 1992 and has worked in the field of fish marking for 4 years.

FULLER, CHUCK

CURRENT TITLE:	Biological Fisheries Technician

Lower Columbia River Fisheries Program Office

Mr. Fuller joined the USFWS in 1981 and has worked in the field of fish marking for the last 5 years.

KEMPER, PAT

CURRENT TITLE:	Biological Fisheries Technician

Lower Columbia River Fisheries Program Office

Mr. Kemper joined the USFWS in 1991 and has worked in the field of fish marking for the last 7 years.

MINOR, CAROLYN

CURRENT TITLE:	Fisheries Program Assistant

Mrs. Minor joined the USFWS in 1983 and has worked in an administrative capacity for the agency on fish marking for the last 15 years.

PASTOR, STEPHEN

CURRENT TITLE:	Fishery Management Biologist

Columbia River Fisheries Program Office

B.S.	Biology, Pennsylvania State University, 1972

Mr. Pastor joined the USFWS in 1974 and has worked in the field of fish marking/hatchery data base for the last 12 years.

PERSONNEL FOR THE LITTLE WHITE SALMON/WILLARD NFH COMPLEX (1/23/98)

PAPPAS, MICHAEL

CURRENT TITLE:	Fish Culturist 5

B.S.	Biology, Central Missouri State University, 1975

Mr. Pappas joined the USFWS in 1983 and has worked in hatchery production since that time.

PERSONNEL FOR THE LOWER COLUMBIA RIVER FISH HEALTH CENTER (1/23/98)

GUTENBERGER, SUSAN K.

CURRENT TITLE:	Supervisory Microbiologist/Project Leader

Lower Columbia River Fish Health Center

Ph.D.	Microbiology, Oregon State University, 1993

M.S.	Veterinary Science, University of Idaho, 1983

B.S.	Microbiology and Zoology, University of Idaho, 1976

Dr. Gutenberger joined the USFWS in 1997 as the project leader at the Lower Columbia River Fish Health Center and has worked in the field of fish health from 1987 until the present time.

KERR, THERESA A.

CURRENT TITLE:	Biological Science Technician, (Micro)

Lower Columbia River Fish Health Center

Undergraduate work	Biology, Columbia Gorge Community College

Ms. Kerr has worked in the field of fish health, USFWS, from 1985 until the present time.

LEIGHTON, JACKIE A.

CURRENT TITLE:	Fishery Program Assistant

Lower Columbia River Fish Health Center

Ms. Leighton has worked for the Federal Government from 1987 until the present time, and in an administrative capacity for agencies relating to fish health and fishery research since 1994.

LUJAN, KENNETH M.

CURRENT TITLE:	Fishery Biologist

Lower Columbia River Fish Health Center

M.S.	Life Science, New Mexico Highlands University, 1996

B.S.	Biology, New Mexico Highlands University, 1993

Mr. Lujan has worked in the field of fish health, USFWS, from 1996, until the present time.

PELTON, ERIC H.

CURRENT TITLE:	Fishery Biologist

Lower Columbia River Fish Health Center

Post graduate work 	Limnology, University of Utah

B.S.			Zoology and Limnology, Weber State University, 1967

Mr. Pelton, a certified fish pathologist, began as a hatchery biologist and has worked in the field of fish health for the USFWS from 1977 until the present time.

PETERS SWIHART, MARY H.

CURRENT TITLE:	Microbiologist

Lower Columbia River Fish Health Center

M.S.	Biochemistry, Purdue University, 1989

M.S.	Exercise Physiology, Purdue University, 1985

B.S.	Psychology / Chemistry, Hope College, 1983

Ms. Peters Swihart has worked in the field of fish health, USFWS, from 1994, until the present time, and in fish culture and fisheries extension, USGS, for two years.

FTE’S FOR THIS PROJECT

Objective 1 - Marking

M.D.

Ambrogetti		GS-12		10

Olhausen		GS-11		32

Wills			GS-11		18

Walch			GS-11		30

Magneson		GS-09		38

Fuller			GS-07		59

Kemper		GS-07		59

Minor			GS-07		14

TOTAL	260

Objective 2 - Bio-sampling

M.D.

Olhausen		GS-11		2

Walch			GS-11		5

Wills			GS-11		4

Olson			GS-11		5

Fuller			GS-07		10

Kemper		GS-07		10	`

TOTAL	36

Objective 3 - Annual Report

M.D.

Olhausen		GS-11		18

Pastor			GS-11		34

TOTAL	52

Objective 4-Fish Rearing

Pappas		 WG-05	260

TOTAL	260

Objective 5- Fish Health

MD

Gutenberger		GS-12		5

Kerr			GS-07		25

Leighton		GS-06		5

Lujan			GS-09		5

Pelton			GS-11		5

Peters Swihart	GS-11		20

Temporary Help	GS-07		30

TOTAL	95

Section 10.  Information/technology transfer

Reports and Papers:

“Annual Coded Wire Tag Program:Missing Production Groups” Annual Reports 1989,1990,1991,1992,1993,1994,1995,1996,1997.

“Operation and Maintenance of BPA Fish Marking Trailer” Annual Reports, 1984,1985,1986,1987,1988,1989,1990,1991,1992,1993,1994,1995.

Project Presentations were given at the 1992 and 1997 BPA Projects Review Meetings.

Smolt monitoring and adult production reports provide the mechanism for feedback to managers concerning future decisions.