Project ID:	(198805307)

Title:		(Hood River Production Program: Powerdale, Parkdale, Oak Springs O&M)

# Section 9 of 10. Project description

a. Abstract

The goal of HRPP is to restore summer and winter steelhead trout populations and re-establish spring chinook using supplementation techniques in the Hood River subbasin in accordance with the Hood River Production Master Plan ( July, 1991) and the Hood River Fisheries Project EIS (BPA, 1996).  This project addresses the majority of the hatchery components of the Hood River Production Program (HRPP).  Overall, project objectives include a level of production that will eventually achieve an adult return to the mouth of Hood River of 8,000 summer steelhead (1,200 wild and 6,800 hatchery), 5,000 winter steelhead (1,200 wild and 3,800 hatchery), and 1,700 hatchery spring chinook. To achieve that level of hatchery adult returns, it will require rearing 150,000 summer steelhead, 85,000 winter steelhead and 250,000 spring chinook smolts with a smolt to adult survival rate of 4.5% for steelhead and 0.68% for spring chinook. The Northwest Power Planning Council (NPPC), in their approval of the HRPP, asked that managers phase-in hatchery production to allow for evaluation of potential impacts.  The interim objectives are to achieve an adult return of 1,800 summer steelhead, 2,250 winter steelhead and 850 spring chinook. The current (interim) hatchery program production goals are to annually release 40,000 summer steelhead, 60,000 winter steelhead and 125,000 spring chinook smolts.  The “phase in” management approach also meant that not more than 25 percent of the returning adult steelhead from one run year could be collected and used for hatchery broodstock.  The project does not have a specified completion date because of the uncertainties associated with the “phased-in implementation”, the depressed status of the steelhead stocks, and the variety of habitat factors affecting fish population recovery.

Supplementation of steelhead utilizes hatchery reared smolts derived from wild stocks of the respective races. Re-introduction of spring chinook will be achieved through use of Deschutes stock, which are taken from an adjacent subbasin and are likely to be best suited to habitat conditions found in the Hood River subbasin. The techniques of supplementation will allow increased spawner escapement and distribution of adults, which should result in increased numbers of naturally produced juveniles to emigrate from the system.  Ongoing and planned habitat restoration activities will result in improved egg to smolt survival.  Cooperation with other entities has resulted in improved upstream and downstream fish passage. Some of the stock recovery / restoration measures implemented in this project to date include: restricting passage of out-of-basin and excess hatchery adults upstream of Powerdale Dam (Rm 4), use of indigenous Hood River steelhead broodstock, matrix spawning, acclimation and volitional releases.

The ultimate measure of project success will be the achievement of the adult return objectives as previously discussed and as found in the umbrella Hood River / Fifteenmile umbrella document. The ODFW and CTWS M&E  projects (8805303 and 8805303) on Hood River have gathered five years of baseline information that will be used to evaluate project implementation).

b. Technical and/or scientific background

The Hood River subbasin is home to four species of anadromous salmonids: Chinook salmon, Coho salmon, steelhead, and sea run cutthroat trout.  Indigenous spring chinook salmon were extirpated during the late 1960's.  The naturally spawning spring chinook currently present in the subbasin are the progeny of Deschutes stock released into the subbasin beginning in 1993.  The historical Hood subbasin hatchery steelhead program utilized out-of-basin stocks for many years.  Recently the indigenous stocks of summer and winter steelhead have been determined by ODFW to be at a moderate to high risk of extinction and NMFS has designated these steelhead stocks as threatened under the ESA.

The HRPP is a fish supplementation project in the Lower Columbia River ESU funded by BPA and jointly implemented by CTWSRO and ODFW.  The primary goals of the HRPP are to (1) re-establish naturally sustaining runs of spring chinook salmon in Hood River,  (2) re-build naturally sustaining runs of summer and winter steelhead in Hood River, (3) maintain genetic characteristics of the various Hood River populations, and (4) contribute to tribal and non-tribal fisheries, ocean fisheries, and the Northwest Power Planning Councils (NPPC) goal of doubling salmon runs in the Columbia Basin (OToole, P. 1991a).

The NPPC, in accepting the HRPP Master Plan, recommended adopting a three-phased approach for the program, which included the collection of baseline information, project implementation (including facilities construction), and follow-up monitoring and evaluation (NPPC, 1992).  Comprehensive collection of data began in the Hood River subbasin in 1991, including information on the life history and production of anadromous salmonid stocks and habitat availability and status (CTWS and ODFW 1997).  In 1996, the HRPP Environmental Impact Statement was completed cooperatively by BPA, CTWSRO, and ODFW.  A record of decision was completed on October 10, 1996 by BPA administrator Randy Hardy, which supports the NPPC goals.

In Section 7 of the 1994 version of the Columbia River Basin Fish and Wildlife Program, the NPPC recommended that implementation of production and habitat activities be fully coordinated (NPPC, 1994). The Tribes, in Volume II of the Spirit of the Salmon Plan, support the NPPC in the need for a combination supplementation and habitat restoration project. Restoration of the anadromous fish populations in the Hood River subbasin will need to incorporate a combination of improved natural fish production and supplementation with cultured fish. Improved natural production could occur through improvements in the screening of irrigation diversions, habitat restoration and passage restoration (CRITFC, 1996).

Implementation of HRPP has included a major switch in the hatchery steelhead broodstocks used for Hood River releases, from out of basin stocks (Big Creek and Skamania stocks) to the Hood River indigenous stocks.  Collection of wild Hood River stock winter steelhead began in 1992 with a volunteer angler brood collection program.  The following year wild Hood River winter steelhead were selected from throughout the entire run at the Powerdale fish ladder and were subsequently matrix spawned to maximize potential genetic diversity.  Out-of basin origin hatchery winter steelhead have not been passed upstream from Powerdale Dam (river mile 4) since 1993, in order to protect the genetic integrity of the wild Hood River population.  In addition ODFW has implemented the Oregon Wild Fish Management Policy, which states that Hood River stock hatchery winter steelhead can comprise no more than 50% of the total spawner population passed upstream from Powerdale Dam.  Hood River wild summer steelhead were first collected at the Powerdale Trap for broodstock during the 1997-98 run.  Hatchery origin (Skamania stock) summer steelhead are now prevented from migrating upstream beyond Powerdale Dam.  The first release of Hood River stock summer steelhead smolts occurred in 1999.  Winter steelhead smolts released into the Hood River subbasin have been acclimated since 1996. Summer steelhead release information is presented in Table 1.  Winter steelhead release information is summarized in Table 2.  All future releases of winter and summer steelhead are scheduled for volitional release from subbasin acclimation facilities in order to increase smolt to adult survival and minimize potential adverse impacts associated with competition with wild resident and anadromous fish.  ODFW implemented a mandatory wild steelhead release angling regulation within the subbasin beginning in 1992 to maximize protection of the depressed wild stocks during the subbasin sport fishery.  In addition the subbasin upstream from Powerdale Dam (river mile 4.0) is closed to all salmon and steelhead angling.

Deschutes stock spring chinook were first released into the Hood River subbasin in 1993. Table 3 presents spring chinook smolt releases since 1993.   In 1997 the spring chinook broodstock for the HRPP were collected from adults returning to the Powerdale Trap.  However, because of low adult returns to Hood River, broodstock has been taken at the Pelton Trap on the Deschutes River in three other years.  Eggs are incubated at Round Butte Hatchery.   Fingerling chinook are started in the hatchery circulars and later transferred into raceways where they remain until late fall.  The pre-smolts are moved to the modified Pelton Ladder rearing cells where they remain until mid-March.  Smolts are then trucked to acclimation sites in the Hood River subbasin.  During the cell-rearing period, juvenile mortality from BKD has been as high as 7 percent.  Fungus and tail rot is another common problem with these fish.  With mild winter temperatures during the last two years, smolts have exceeded the target size of 8 fish per pound and averaged 5-6 fish per pound.  As a consequence the 1999 and 2000 return to the Powerdale Trap of  “mini-jacks” has been 183 and 719 (not final count) fish, respectively.  During the same two years adult returns have been 85 and 67 (not final count) adults.  Because of these technical problems associated with smolt quality at Round Butte Hatchery, smolt to adult returns have been well below the HRPP objective of 0.68 percent.

Table 1.  Hatchery summer steelhead smolt releases in the Hood River subbasin, 1990 – 2000 by brood yeara.

____________________________________________________________________________________________________________________

Broodstock,        Fin clipb

Hatchery,        or coded     Survival     Date(s)                  Number

Brood year     wire tag     rate (%)     released     Fish/lb     released            Release location

____________________________________________________________________________________________________________________

1989           Ad              --        04/04/90        5.3        4,876       Hood River

1989           Ad              --        04/11/90        6.5       10,660       Hood River

1989           Ad              --        04/04-05/90     5.3       25,422       West Fork Hood River

1989           Ad              --        04/03/90        5.4        5,940       West Fork Hood River

1989           Ad              --        04/03-09/90     5.5       20,306       West Fork Hood River

1989           Ad              --        04/06/90        5.7       14,591       West Fork Hood River

1990           Ad              --        04/29/91        5.4        7,020       Hood River

1990           Ad              --        04/30/91        5.5       14,743       Hood River

1990           Ad              --        04/24/91        5.8        7,013       Hood River

1990           Ad              --        04/22/91        5.2       12,787       West Fork Hood River

1990           Ad              --        04/23/91        5.3        6,943       West Fork Hood River

1990           Ad              --        04/24/91        5.5        6,869       West Fork Hood River

1990           Ad              --        04/23/91        5.6        6,776       West Fork Hood River

1990           Ad              --        04/23/91        5.8       14,981       West Fork Hood River

1991           Ad              --        04/08/92        4.8        5,880       Hood River

1991           Ad              --        04/07/92        5.2       12,870       Hood River

1991           Ad              --        04/06/92        5.4       13,365       Hood River

1991           Ad              --        04/08/92        5.5        6,958       Hood River

1991           Ad              --        04/07/92        4.7       15,082       West Fork Hood River

1991           Ad              --        04/07/92        5.2       15,023       West Fork Hood River

1991           Ad              --        04/06/92        5.4       13,750       West Fork Hood River

1991           Ad              --        04/08/92        5.5       17,045       West Fork Hood River

1992           Ad              --        04/07-08/93     6.0       33,570       West Fork Hood River

1992           Ad              --        05/04/93        6.3       17,955       West Fork Hood River

1992           Ad              --        05/05/93        6.5       19,403       West Fork Hood River

Foster,c (cont.)

Oak Springs,

1993           Ad              --        03/29-31/94     4.6       71,760       West Fork Hood River

1993           Ad              --        03/29/94        4.8        5,880       West Fork Hood River

1993           Ad              --        03/30-31/94     5.2       12,402       West Fork Hood River

1994           Ad              --        04/11/95        4.6       13,600       West Fork Hood River

1994           Ad              --        04/10-11/95     5.3       46,232       West Fork Hood River

1994           Ad              --        04/12/95        5.5       16,498       West Fork Hood River

1995           Ad              --        04/01-11/96     5.2       48,346       West Fork Hood River

1995           Ad              --        04/03/96        5.5       15,017       West Fork Hood River

1995           Ad              --        04/11-12/96     5.9        5,015       West Fork Hood River

1996           Ad              --        04/09/97        5.0       12,745       West Fork Hood River

1996           Ad              --        04/10/97        5.0        5,250       West Fork Hood River

1996           Ad              --        04/10/97        5.1       14,890       West Fork Hood River

1996           Ad              --        04/10/97        5.5       14,850       West Fork Hood River

1996           Ad              --        04/15/97        5.2        9,360       West Fork Hood River

1996           Ad              --        04/16/97        5.0        2,044       West Fork Hood River

1996           Ad              --        04/16/97        5.3        1,854       West Fork Hood River

1997           Ad              --        04/08/98        4.9       12,250       West Fork Hood River

1997           Ad              --        04/08/98        5.4       29,024       West Fork Hood River

1997           Ad              --        04/08/98        5.7       15,518       West Fork Hood River

1997           Ad              --        04/09/98        5.8        8,118       West Fork Hood River

1998           Ad              --     04/07-08/99        6.0       32,697       Below Powerdale Dam (@ RM 4.5)

1998           Ad              --        04/08/99        6.8       17,000       Below Powerdale Dam (@ RM 4.5)

1998           Ad              --     04/08-09/99        5.6       12,521       Below Powerdale Dam (@ RM 4.5)

1999           Ad              --     04/12-14/00        6.1       49,284       Below Powerdale Dam (@ RM 4.5)

Table 1.  (Continued) Hatchery summer steelhead smolt releases in the Hood River subbasin, by brood yeara.

____________________________________________________________________________________________________________________

Broodstock,        Fin clipb

hatchery,        or coded     Survival     Date(s)                  Number

brood year     wire tag     rate (%)     released     Fish/lb     released            Release location

____________________________________________________________________________________________________________________

Hood River,

Oak Springs,

1998           LM              --        04/15/99        5.5       15,616       West Fork Hood River

1998           LM              --        05/10/99        6.6        3,897       Near mouth of Hood River

1999           LM 30%, RM 70%  --        04/13/00        6.2       15,620       West Fork Hood River

1999           LM 30%, RM 70%  --        04/27/00        5.1       13,541       West Fork Hood River

1999           LM 30%, RM 70%  --        05/09/00        6.2        4,738       near mouth of Hood River

____________________________________________________________________________________________________________________

a	Production releases prior to the 1987 brood are in Oregon Department of Fish and Wildlife and Confederated Tribes of the Warms Springs Reservation of Oregon (1990).

b	Ad = Adipose; LM = Left Maxillary.

c	The Foster stock was developed from the Skamania stock of summer steelhead.

Table 2.  Hatchery winter steelhead smolt releases in the Hood River subbasin, 1993 – 2000, by brood yeara.

____________________________________________________________________________________________________________________

Broodstock,       Fin clipb

hatchery,       or coded      Survival     Date(s)                  Number

brood year    wire tag      rate (%)     released     Fish/lb     released            Release location

___________________________________________________________________________________________________________________

Hood River,

Oak Springs,

1992      Ad-LP                --        04/06/93        5.8       15,225       Middle Fork Hood River

1992      Ad-LP                --        04/06/93        6.0       15,420       East Fork Hood River

1992      Ad-LP                --        04/06/93        5.6       18,340       East Fork Hood River

1993      Ad-LM                --        04/12-13/94     4.5        7,423       East Fork Hood River

1993      Ad-LV;07-05-36       --        04/12-13/94     4.5        6,863       East Fork Hood River

1993      Ad-LV;07-05-37       --        04/12-13/94     4.5        6,189       East Fork Hood River

1993      Ad-LM                --        04/12/94        5.4        2,414       East Fork Hood River

1993      Ad-LV;07-05-38       --        04/12/94        5.4        6,445       East Fork Hood River

1993      Ad-LV;07-05-39       --        04/12/94        5.4        6,531       East Fork Hood River

1993      Ad-LP                --        06/28/94        5.8        2,169       East Fork Hood River

1994      Ad-LV;07-08-63       --        04/19-20/95     5.1       10,534       East Fork Hood River

1994      Ad-LV;07-09-16       --        04/19-20/95     5.1       10,367       East Fork Hood River

1994      Ad-LV;07-09-17       --        04/19/95        5.4        3,426       East Fork Hood River

1994      Ad-LV;07-09-17       --        04/19/95        5.8        7,707       East Fork Hood River

1994      Ad-LV;07-09-18       --        04/19/95        5.4        3,331       East Fork Hood River

1994      Ad-LV;07-09-18       --        04/19/95        5.8        7,495       East Fork Hood River

1995      Ad-LV-RM;07-11-31    --        04/02/96        5.5        5,621       East Fork Hood River

1995      Ad-LV-RM;07-11-31    --        04/01/96        5.7       11,649       East Fork Hood River

1995      Ad-LV-RM;07-11-31    --        04/04/96        5.8        3,508       East Fork Hood River

1995      Ad-LV-RM;07-11-32    --        04/22-24/96     5.0       19,913       East Fork Hood River

1995      Ad-RM                --        04/22-24/96     5.0        3,793       East Fork Hood River

1995      Ad-RM                --        04/02/96        5.5          115       East Fork Hood River

Hood River

Oak Springs,

1995      Ad-RM                --        04/01/96        5.7          238       East Fork Hood River

1995      Ad-RM                --        04/04/96        5.8           72       East Fork Hood River

1995      Ad-LV-RM;07-11-31    --        04/04/96        5.5          749       Hood River (RM 0.5)

1995      Ad-LV-RM;07-11-31    --        04/04/96        5.7        1,553       Hood River (RM 0.5)

1995      Ad-LV-RM;07-11-31    --        04/04/96        5.8          468       Hood River (RM 0.5)

1995      Ad-LV-RM;07-11-32    --        04/22/96        5.0        2,655       Hood River (RM 0.5)

1995      Ad-RM                --        04/04/96        5.0          505       Hood River (RM 0.5)

1995      Ad-RM                --        04/04/96        5.5           15       Hood River (RM 0.5)

1995      Ad-RM                --        04/04/96        5.7           32       Hood River (RM 0.5)

1995      Ad-RM                --        04/04/96        5.8           10       Hood River (RM 0.5)

1996      Ad-LM                --        04/11/97        5.8       16,791       East Fork Hood River

1996      Ad-LM                --        04/15/97        5.6       10,920       East Fork Hood River

1996      Ad-LM                --        05/05/97        8.3       32,126       East Fork Hood River

1997      Ad-RM                --        04/14/98        5.2       29,510       East Fork Hood River

1997      Ad-RM                --        04/28/98        7.5       31,707       East Fork Hood River

1997      Ad-RM                --        06/04/98        9.0          918       East Fork Hood River

1998      Ad-RV                --        04/15/99        5.6       12,430       East Fork Hood River

1998      Ad-RV                --        05/05/99        5.8       10,572       East Fork Hood River

1998      Ad-RV                --        04/14/99        5.6        9,857       Middle Fork Hood River

1998      Ad-RV                --        05/05/99        6.0        9,816       Middle Fork Hood River

1998      Ad-RV                --        04/08/99        5.6        1,792       Below Powerdale Dam (@ RM 4.5)

1998      Ad-RV                --        05/25/99        8.1        2,314       Near mouth of Hood River

1999      Ad-LV (09-29-23)     --        04/17/00        7.3       13,852       East Fork Hood River

1999      Ad-LV (09-29-24)     --        05/01/00        7.8       15,694       East Fork Hood River

1999      Ad-LV (09-29-23,24)  --        05/16/00       10.3        1,590       near mouth of Hood River

1999      Ad-LV (09-29-23)     --        04/17/00        7.3       15,279       Middle Fork Hood River

1999      Ad-LV (09-29-24)     --        05/01/00        7.7       15,578       Middle Fork Hood River

1999      Ad-LV (09-29-23/24)  --        05/19/00       11.3        1,162       near mouth of Hood River

____________________________________________________________________________________________________________________

Table 2.  (Continued) Hatchery winter steelhead smolt releases in the Hood River subbasin, 1993 – 2000, by brood yeara.

a	Production releases prior to the 1987 brood are in Oregon Department of Fish and Wildlife and Confederated Tribes of the Warm Springs Reservation of Oregon (1990).

b	Ad = Adipose; LV = Left Ventral; RV = Right Ventral; LP = Left Pectoral; LM = Left Maxillary; RM = Right Maxillary.

c	The 1991 brood are progeny of wild x Big Creek stock hatchery crosses.

Table 3.  Hood River Subbasin Spring Chinook Salmon hatchery releases, 1991 – 2000, by brood year.

__________________________________________________________________________________________________________________

Life history stage,

broodstock,        Fin clip

hatchery,        or coded          Survival     Date(s)                  Number

brood year     wire tag          rate (%)     released     Fish/lb     releaseda        Release location

____________________________________________________________________________________________________________________

Smolt,

Deschutes,

Bonneville,

1991           Ad;07-33-35          --        04/01/93       11.2       11,760       West Fork Hood River

1991           Ad;07-33-35          --        04/01/93       11.3       34,685       West Fork Hood River

1992d          --                   --        --               --           --       --

Round Butte,

1991           Ad;07-50-22 R2       --        04/08-09/93     6.7       28,760       West Fork Hood River

1992d          --                   --        --               --           --       --

1993           Ad;07-05-49          --        04/04-05/95    13.1       13,111       West Fork Hood River

1993           Ad;07-05-49          --        04/03-04/95    13.2       13,211       West Fork Hood River

1993           Ad;07-05-49          --        04/03/95       13.7       12,865       West Fork Hood River

1993           Ad;07-05-49          --        04/04/95       13.8       13,175       West Fork Hood River

1993           No mark              --        04/04-05/95    13.1       29,455       West Fork Hood River

1993           No mark              --        04/03-04/95    13.2       29,682       West Fork Hood River

1993           No mark              --        04/03/95       13.7       28,905       West Fork Hood River

1993           No mark              --        04/04/95       13.8       29,600       West Fork Hood River

1994           Ad-RV;07-11-30       --        04/22-23/96     9.5       40,348       West Fork Hood River

1994           Ad-RV;07-11-30       --        04/10/96       10.0       25,776       West Fork Hood River

1994           Ad-RV;07-11-30       --        04/08/96       10.1       23,354       West Fork Hood River

1994           Ad-RV;07-11-30       --        04/09/96       10.3       23,893       West Fork Hood River

1994e          Ad;07-09-38          --        04/22-23/96     9.5        3,509       West Fork Hood River

1994e          Ad;07-09-38          --        04/10/96       10.0        2,241       West Fork Hood River

1994e          Ad;07-09-38          --        04/08/96       10.1        2,031       West Fork Hood River

1994e          Ad;07-09-38          --        04/09/96       10.3        2,078       West Fork Hood River

1995           Ad-LV;09-17-47       --        04/07/97        7.9       33,469       West Fork Hood River

1995           Ad-LV;09-17-47       --        04/08/97        8.2       11,928       West Fork Hood River

1995           Ad-LV;09-18-06       --        04/16/97        8.3       22,315       West Fork Hood River

1995           Ad-LV;09-18-06       --        04/17/97        8.2       10,138       West Fork Hood River

1995           Ad-LV;09-18-06       --        04/17/97        8.6       22,869       West Fork Hood River

1996           Ad-RV;09-22-26       --        04/09/98        9.8       62,049       West Fork Hood River

1996           Ad-RV;09-22-27       --        04/22/98        9.7       53,658       West Fork Hood River

1996           Ad-RV;09-22-27       --        04/22/98        9.7        8,053       West Fork Hood River

Smolt

Deschutes,

Round Butte,

1997           Ad-LV;09-25-55       --        04/08/99        7.5       35,163       West Fork Hood River

1997           Ad-LV;09-25-56       --        04/20/99        6.7       36,485       West Fork Hood River

1997           Ad-RM;09-25-57       --        04/12/99        6.4       30,164       Middle Fork Hood River

1997           Ad-RM;09-25-57       --        05/05/99        5.9          214       Near mouth of Hood River

1997           Ad-LV;09-25-55/56    --        05/06-11/99     8.3       19,322       Near mouth of Hood River

Table 3. (Continued)  Hood River Subbasin Spring Chinook Salmon hatchery releases, 1991 – 2000, by brood year.

__________________________________________________________________________________________________________________

Life history stage,

broodstock,        Fin clip

hatchery,        or coded          Survival     Date(s)                  Number

brood year     wire tag          rate (%)     released     Fish/lb     releaseda        Release location

____________________________________________________________________________________________________________________

_

Smolt

Deschutes,

Round Butte,

1998           Ad-LM;09-28-55       --        04/10/00        7.6       30,277       West Fork Hood River

1998 	  Ad-LM;09-28-55       --        04/10/00        8.3       17,420       West Fork Hood River

1998           Ad-LM;09-28-56       --        04/24/00        6.4       28,222       West Fork Hood River

1998           Ad-LM;09-28-56       --        04/24/00        6.3       16,189       West Fork Hood River

1998           Ad-RV;09-28-57       --        04/10/00        6.7       15,293       Middle Fork Hood River

1998           Ad-RV;09-28-57       --        04/25/99        5.7       15,136       Middle ForkHood River

- Ad-LV;09-17-04,      --        03-20-00       14.9        4,126       Middle Fork Hood River

07-11-23: 07-11-24

1998           Ad-RV;09-28-57       --        05/15/00        5.7           91       Near mouth of Hood River

_	   1998           Ad-LM;09-28-55/56    --        05/08/00        7.0        4,822       Near mouth of Hood River

1998           Ad-LM;09-28-55/56    --        05/10/00        7.5        5,835       Near mouth of Hood River

_ __________________________________________________________________________________________________________________

a Estimates for the 1994 – 1997 brood releases were adjusted for mortality at downstream migrant screw traps.

b No hatchery spring chinook salmon were released from the 1992 brood.

c This coded wire tag group was to have been released in its entirety in the Deschutes River, but seals broke around the rotary screens, used to    prevent movement among the cells in the Pelton Ladder, allowing a small percentage of this tag group to mix with fish destined for release in the Hood River.

This proposal includes engineering design funds for expansion of Parkdale Fish Facility to allow spring chinook rearing capability.   With this colder water station, the Parkdale Fish Facility should be able to control growth and achieve the desired size at release and also minimize disease problems. This year, a release of a small experimental group of spring chinook (1999 brood) at this facility met the desired smolt size criteria.

To date, other related HRPP projects have completed and assimilated subbasin biological and physical habitat surveys showing that the available Hood River subbasin anadromous habitat is likely underseeded and also has identified areas in need of habitat restoration. The project has planned and undertaken some stream habitat restoration projects.  One project identified in the approved Hood River Master Plan called for the screening of a major irrigation diversion (129 cfs) on the East Fork Hood River.  The East Fork Irrigation District screened this diversion in 1997. Other habitat projects are being proposed by CTWS for FY 2001.  These projects include replacing the existing Farmers Irrigation District fish screen, improving adult and juvenile fish passage at the East Fork Irrigation District Neal Creek diversion, restoring fish passage in Evans Creek blocked by irrigation diversion structures, and improving fish habitat in Baldwin Creek.

c. Rationale and significance to Regional Programs

The NPPC, under the Columbia River Basin Fish and Wildlife Program, has approved a number of projects in the state of Oregon, Washington and Idaho that are similar to HRPP.  Several of these projects have been successfully implemented, including combinations of supplementation and habitat projects within the Umatilla and Yakima subbasins, involving state and tribal entities (CBFWA, 1997).

The O&M for this supplementation project is designed to implement restoration of depressed summer and winter steelhead stocks in the Hood River subbasin through the use of native Hood River stock smolt releases.  The project also is designed to re-establish a self-sustaining spring Chinook salmon population using a stock that is best adapted to the Hood River habitat conditions.  It is believed that supplementation is the best alternative for restoring the extremely depressed steelhead stocks.  Use of hatchery stocks in the subbasin should help to jump-start the remnant, naturally reproducing, populations and take advantage of the subbasins underseeded habitat.

The HRPP is consistent with several subsections of Section 7.0 of the NPPCs Fish and Wildlife Program.  Specifically, the project is consistent with sections 7.0A, 7.4L.1, and 7.4L.2, with a combination of supplementation (HRPP, ongoing projects) and habitat restoration activities, with the ultimate goal of significantly increasing natural fish production and survival.  This goal will be achieved through a number of activities within the subbasin that will complement supplementation efforts. These activities include: cooperative habitat restoration measures with private and public land managers and irrigation districts; watershed restoration activities coordinated through the Hood River Watershed Council; and improvements in adult fish passage, juvenile fish protection (i.e. screening), water quality and quantity to be achieved by working cooperatively with individuals, PacifiCorp and local agencies. We believe these habitat improvements will increase the likelihood that the HRPP supplementation activities will be successful in achieving project goals.

The complementary HRPP M&E projects are assessing the affects of supplementation.

d. Relationships to other projects

The HRPP is composed of six separate contracts designed to increase production of wild summer and winter steelhead and to re-establish spring chinook within the Hood River subbasin.  The six separate contracts, approved by the NPPC and funded by BPA, primarily provide funding for four broad categories of activities.  These include implementation (O&M), and monitoring and evaluation studies and habitat restoration.  Funding for the engineering component of the HRPP provided for the design and construction of facilities at Powerdale Dam, Parkdale, and Oak Springs Hatchery that were needed to implement the HRPP. Implementation funding provides for broodstock collection, holding, fish transport, spawning, rearing, marking, and tagging.  Funding for monitoring and evaluation studies provides for the evaluation of the HRPP and any interaction the hatchery program may be having on wild fish populations. And finally, the Hood River Habitat Project is important in assisting species recovery by identifying and restoring fish habitat where opportunities exist in the Hood River subbasin.

There are a number of other, non-BPA funded programs in the subbasin that have direct positive impacts on the success of the HRPP.  For example, the East Fork Irrigation District  (EFID) implemented new fish screening on their 130 cfs diversion from the East Fork Hood River.  In the process of installing this new fish screen EFID constructed concrete sediment retention ponds.  EFID has allowed HRPP to utilize one of these ponds for winter steelhead smolt acclimation.  EFID is working with HRPP personnel to determine the most efficient type of fish screen to install at their second major diversion.  The Middle Fork Irrigation District (MFID) provided a temporary adult holding facility adjacent to the Parkdale site.  In addition MFID cooperated in the construction of the Parkdale facility, including the water supply tap into their powerhouse tailrace.  MFID, in cooperation with the US Forest Service, installed an upstream migrant fish trap at the base of Clear Branch Dam (Middle Fork Hood River).  The Farmers Irrigation District (FID) implemented instream habitat restoration on Green Point Creek, a major West Fork tributary.  FID has been actively upgrading district fish screens and implementing water conservation measures.  The Mount Hood National Forest has had an active stream habitat restoration program throughout the subbasin.  Their work has included the placement of instream structures and large wood in each of the main Hood River tributaries with a goal of restoring instream habitat diversity.  Long View Fibre, Inc. has provided sites for smolt acclimation on the West Fork Hood River. The Hood River Watershed Group has completed a Hood River subbasin assessment and is taking an active role in activities that will improve the overall condition of the Hood River watershed and streams.  They provided their unqualified endorsement of a proposal that will allow the placement of salmon and steelhead carcasses in the Hood River streams to enhance primary stream productivity.  PacifiCorp has provided the land needed for development of the Powerdale Fish Facility. They are currently undergoing FERC re-licensing of Powerdale Hydroelectric Project which should result in major improvements to downstream migrant screening, instream minimum flows, overall water quality and development of a SOP for Powerdale Dam.  Earlier they made needed improvements to the adult fish ladder.

e. Project history (for ongoing projects)

Implementation of the O&M portion of the HRPP has resulted in some significant resource achievements, including a major switch in the hatchery steelhead broodstock used for Hood River releases, from out of basin stocks (Big Creek and Skamania stocks) to the Hood River indigenous stocks.  In 1993 wild Hood River winter steelhead were selected from throughout the entire run at the Powerdale fish ladder and were subsequently matrix spawned to maximize potential genetic diversity.  Out-of basin origin winter steelhead have not been passed upstream from Powerdale Dam since 1993, in order to protect the genetic integrity of the wild Hood River population (CTWS, 1997).  In addition ODFW has implemented the Oregon Wild Fish Management Policy, which specifies that Hood River stock hatchery winter steelhead can comprise no more than 50% of the total spawner population.  Hood River wild summer steelhead were first collected for broodstock during the 1997-98 run.  Hatchery origin (Skamania stock) summer steelhead are prevented from migrating upstream beyond Powerdale Dam.   Winter steelhead smolts released into the Hood River subbasin have been acclimated since 1996 (Jennings, 1996).  ODFW implemented a mandatory wild steelhead release angling regulation within the subbasin beginning in 1992 to maximize protection of the depressed wild stocks during the subbasin sport fishery.

The HRPP project includes several physical facilities that have been constructed.  HRPP project implementation included the construction of the Powerdale Dam Fish Facility, which is a state of the art fish trapping and sorting facility.  This facility allows project personnel to efficiently trap, sort, pass and/or transport all the adult salmonids arriving at Powerdale Dam.  The project also includes the Parkdale Fish Facility. This facility provides adult broodstock holding and spawning facilities as well as juvenile acclimation ponds.  The project also includes new egg incubation, early rearing, and smolt rearing facilities at Oak Springs Fish Hatchery. Other important physical facilities associated with the HRPP project include three fish rearing cells in the PGE Pelton Fish Ladder, steelhead acclimation ponds on the East and West forks Hood River (provided at no charge by the East Fork Irrigation District, and temporary fish acclimation ponds located on Longview Fibre Company property on the West Fork Hood River).

To date, the project has completed and assimilated subbasin biological and physical habitat surveys showing that the available Hood River subbasin anadromous habitat is likely underseeded and also has identified areas in need of habitat restoration. The project has planned and undertaken some stream habitat restoration projects.  One project identified in the approved Hood River Master Plan called for the screening of a major irrigation diversion (130 cfs) on the East Fork Hood River.  The East Fork Irrigation District screened this diversion in 1997.

The HRPP has released approximately 125,000 spring chinook salmon smolts and 40,000 to 60,000 Hood River stock winter steelhead smolts into the subbasin annually since 1993.  These releases have been acclimated prior to liberation since 1996.

The ongoing HRPP M&E project provides the data feedback needed to modify project actions when appropriate or necessary.  For example: to restore the depressed wild steelhead populations, management actions have been implemented to maximize the protection of the wild component of the two steelhead stocks by implementation of wild release angling regulations. Blockage of access of out of basin stray steelhead and excess Hood River hatchery stock from the subbasin upstream of Powerdale Dam should insure protection of genetic integrity of the wild population. Further, 1: 1 or matrix spawning (not to exceed 2 X 2) of Hood River broodstock selected from throughout the run has been implemented to maintain natural genetic variability. Results from trapping winter steelhead outmigrants have shown a significant in-river survival advantage for acclimated and volitionally released hatchery smolts. This technique should result in better smolt to adult survival and minimize interaction with wild anadromous and resident juveniles.

FY 98 was the first year of the HRPP Powerdale, Parkdale, and Oak Springs O&M budget and consisted of a total of $277,000.  FY99 O&M costs amounted to $467,567.  Funding for earlier fiscal years was spent entirely on capital construction of HRPP facilities.

f. Proposal objectives, tasks and methods

Objectives:

(1).  Achieve an interim adult return of 1800 hatchery summer steelhead to the mouth of Hood River (see umbrella for the Hood River Master Plan run size objectives).

2).  Achieve an interim adult return of 2250 hatchery winter steelhead to the mouth of Hood River (see umbrella for the Hood River Master Plan run size objectives).

3).  Achieve an interim adult return of 850 hatchery spring chinook to the mouth of Hood River

(see umbrella for the Hood River Master Plan run size objectives).

4).  Maintain the genetic integrity of the steelhead and chinook stocks.

5).	Expand Parkdale Fish Facility to accommodate the spring chinook smolt production for the subbasin.

Tasks:

(1). A.	Collect 40 Hood River wild summer steelhead broodstock at Powerdale Dam.  Transfer broodstock to the Parkdale Fish Facility.

(1). B.	Hold and spawn 40 wild summer steelhead.

(1). C.	Transfer summer steelhead eggs to Oak Springs Fish Hatchery.  Incubate, rear and mark 40,000 summer steelhead smolts.

(1). D.	Produce summer steelhead smolts that average 18 cm with a condition factor of 1.00 or less.

(1). E.	Transport summer steelhead smolts to Hood River acclimation facilities.

(1). F.	Monitor and evaluate the operation and maintenance of each fish facility.

(2). A.	Collect 70 Hood River winter steelhead broodstock (50% wild and 50% hatchery) at the Powerdale Fish Facility.

(2). B.	Hold and spawn 70 winter steelhead.

(2). C.	Transfer winter steelhead eggs to Oak Springs Fish Hatchery.

(2). D.	Produce summer steelhead smolts that average 18 cm with a condition factor of 1.00 or less.

(2). E.	Transfer winter steelhead smolts to Hood River acclimation sites.

(3). A.	Collect 110 spring Chinook salmon broodstock at the Powerdale Fish Facility or Round Butte Fish Hatchery.

(3). B.	Hold and spawn 110 spring Chinook salmon.

(3). C.	Transfer eyed eggs to Round Butte Fish Hatchery.

(3). D.	Acclimate spring chinook smolts received from Round Butte Fish Hatchery / Pelton Fish Ladder.

Tasks: (Continued)

(4). 	A.	Revise the HRPP NEPA document to cover the proposed Parkdale Facility expansion.

(4).	B.	Complete the appraisal and purchase of adjacent land needed for the facility expansion.

(4).	C.	Complete facility expansion planning, and preliminary and final design.

(4).	D.	Drill test wells to assess subsurface water availability.

(4).	E.	Complete topographic mapping of the facility expansion site.

Methods:

Steelhead broodstock collection

Summer and winter steelhead adults are collected for HRPP broodstock at the Powerdale Fish Facility.  Fish are selected randomly from throughout the entire run to minimize the opportunities for truncating the run timing of the hatchery progeny.  The frequency of collection is based on the anticipated run size for a specific year.  Only wild summer steelhead are collected for broodstock, while both wild and hatchery Hood River stock winter steelhead are collected.  Each fish has scales collected and individually numbered tags applied at the time it is processed at Powerdale.  If a wild fish is determined to be of hatchery origin, based on the scale analysis, that fish is rejected for use in the hatchery supplementation program because of the uncertainty of its origin.

Spring Chinook salmon broodstock collection

Spring chinook salmon broodstock are also collected randomly at the Powerdale Fish Facility.  However, if the projected run is expected to be below spawner escapement objectives, all or a major portion of the returning jacks and adults may be passed upstream from the dam to spawn naturally.  If the adult return to Hood River is expected to be low the broodstock may be collected from Deschutes River stock at Round Butte and/or Warm Springs fish hatcheries.

Steelhead broodstock holding and spawning

Winter and summer steelhead broodstock are held in brood ponds at the Parkdale Fish Facility.  The fish are held on cold spring or river water until they sexually mature.  The fish receive regular prophylactic antiseptic treatments to prevent fungal infection and pre-spawning mortality.  Fish are live spawned in 1:1 (male: female) family groups, or pairings that do not exceed a 2 X 2 matrix.  There is a conscious attempt made to have at least one Hood River wild steelhead parent in each winter steelhead family group.  All summer steelhead broodstock are wild fish.  Individual family groups of eggs are held separately until viral samples have been analyzed for the IHN virus.  Eggs from parents with a high incidence of IHN virus may be culled from the hatchery production.

Spring Chinook salmon holding and spawning

Spring chinook broodstock are held in the brood ponds at the Parkdale Fish Facility until they sexually mature. The fish receive regular prophylactic antiseptic treatments to prevent fungal infection and pre-spawning mortality.  Fish are killed prior to spawning.  Spawning occurs in 1:1 (male: female) family groups. Individual family groups of eggs are held separately until viral samples have been analyzed for the BKD virus.  Eggs from parents with a high incidence of BKD virus are culled from the hatchery production.

Steelhead egg incubation and rearing

Summer and winter steelhead eggs are transferred as green or eyed eggs to Oak Springs Fish Hatchery.  The earliest egg takes are incubated on chilled water in order to slow development until later egg takes are completed.  The chilling allows hatchery operators to rear fish are that are generally a similar size.  Once the eggs have hatched the fry are moved to the normal hatchery water supply, which is a constant 54oF.  This constant temperature spring water aids in the production of smolts in one year.  The juveniles are marked with distinctive fin marks that enable managers to differentiate adults from individual brood years.  It is the objective to have the smolts at 6 to 8 per pound with a condition factor of 1.00 or less at release.

Spring Chinook salmon incubating and rearing

Spring chinook eggs are incubated on chilled water to achieve similar size for the juveniles.  The fingerling are reared in traditional starter ponds and concrete raceways until late fall when the fish are transferred to the Pelton Ladder rearing cells.  Prior to their transfer to the ladder rearing cells the juveniles are marked and tagged with coded-wire tags.  The objective is to produce spring chinook smolts that average 15 fish per pound at release.

Future Hood River subbasin hatchery spring chinook smolt production is proposed to occur at an expanded Parkdale Fish Facility site.  This potentially could potentially be ready to begin egg incubation with the 2002 brood year egg collection.  This facility would produce up to 250,000 spring chinook smolts at 15 to 20 per pound.  A portion of the production would be volitionally released from the Parkdale Facility into the Middle Fork Hood River, while the remainder would be transferred to acclimation sites on the West Fork Hood River.  All smolts produced at the expanded Parkdale Facility would be differentially marked and tagged with coded wire tags.

Transfer steelhead smolts to Hood River acclimation sites

Summer and winter steelhead are transferred from Oak Springs Fish Hatchery in a conventional fish tanker truck.  The water temperature en route is tempered to approximate the temperature at the acclimation site.  Fish are released directly into the individual acclimation ponds.  The fish are held in the acclimation ponds for a week to ten days before volitional release begins.  Fish that do not volitionally migrate are collected and transported to the mouth of Hood River for release.  Human disturbance to acclimating fish is minimized and artificial hiding/escape cover is present in the ponds in an attempt to mimic a natural environment.

Transfer spring Chinook salmon smolts to Hood River acclimation sites

Spring chinook smolts are transferred from Round Butte Fish Hatchery in a conventional fish tanker truck.  The water temperature en route is tempered to approximate the temperature at the acclimation site.  Fish are released directly into the individual acclimation ponds.  The fish are held in the acclimation ponds for a week to ten days before volitional release begins. .  Human disturbance to acclimating fish is minimized and artificial hiding/escape cover is present in the ponds in an attempt to mimic a natural environment.

Maintain facility equipment and structures

Facility equipment is routinely checked and serviced per manufacturer recommendations.  Facility buildings, ponds and other structures are monitored and needed maintenance is preformed before any major problem develops.  Facility grounds are maintained in a neat appearance, which makes worker access easy, while reducing potential hazards such as fire.

g. Facilities and equipment

The Powerdale Fish Facility is a new facility that includes a fish trapping and sorting ponds, a mechanical fish lift, truck loading equipment, and fish recovery and bypass structures. The facility is a continuous trapping operation at Powerdale Dam (RM 4).  This facility gives project personnel the opportunity to enumerate and gather specific biological data from each adult salmonid reaching the dam. The facility is comprised of two buildings.  One building houses the fish sorting, loading, and water pumping equipment, including electronic controls.  The second building provides restroom facilities, as well as equipment storage, and space for the primary air compressor used to operate key trap components.  A small utility building is also present on site to house the air compressor used to clean the facility water intake structure.  This facility also includes a perimeter security fence and a one mile long single lane access road. The facility is directly connected to the Powerdale Dam fish ladder and uses gravity water flow from the upper fish ladder to supply the fish trap.  Operation of the fish trap and the processing of fish also utilize large water pumps that supply the fish lift, staging and fish anesthetic tanks, as well as the fish distribution delivery tubes. Several large electrically powered compressed air systems are utilized to operate air actuated water valves associated with the fish lift (i.e. elevator). The major equipment necessary to operate the facility was acquired during FY 97 and FY 98.  A one ton flat bed truck with detachable snowplow and a portable 500-gallon fish tank is also important facility equipment.

The Parkdale Facility, completed in FY98, includes two adult holding ponds, two acclimation ponds, a fish trap/weir, spawning, incubation and cold storage building, office and two bedroom bunkhouse building, shop and garage, and two single family residences. Most of the equipment necessary to operate the facility was purchased in FY 99. Major capital expenditures include a tractor, snow blower, tools, office and bunkhouse furnishings and appliances (computer and communication equipment). The facility has three water sources (i.e. spring, well and river).  Water delivery involves an elaborate gravity and pump water distribution system.

The proposed expansion of the Parkdale Fish Facility could ultimately produce all the spring chinook smolt production for the subbasin.  This expansion would include six concrete raceway ponds; a storage/ garage/ auxiliary generator building; a residence and garage; two wells; pollution abatement pond; small bridge; and water distribution and drainage system.

The Oak Springs Hatchery expansion associated with the HRPP was completed in 1999 and includes incubation trays with isolation capabilities with sufficient capacity to accommodate up to 250,000 steelhead eggs and a water chiller.  Early rearing troughs and circular ponds are included to handle the Hood River steelhead production.  The facility also includes equipment necessary to adequately treat the effluent from the isolation/incubation and early rearing equipment. A new water supply has been developed to provide the water needed for the four new raceway rearing ponds used in the final rearing of Hood River steelhead smolts.  Most of the equipment needed to operate this hatchery addition was provided as part of the facility construction. One additional capital construction expenses scheduled for completion during FY 2000 is the completion of a carport at the residence developed for the Warm Springs Tribal Trainee.  This will complete the housing needs of the additional FTE as a result of HRPP steelhead rearing project.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| CRIFC. 1996. WY-KAN-USH-MI WA-KISH-WIT. The Columbia River Anadromous Fish Restoration Plan of the Nez Perce, Umatilla, Warm Springs, and Yakama Tribes. Portland, Oregon. | N |
| CTWS and ODFW, cooperators. 1996. Annual progress report. Hood River and Pelton Ladder evaluation studies. Annual Progress Report of the CTWS and ODFW (Projects 88-053-03 and 88-053-04) to Bonneville Power Administration (BPA), Portland, Oregon. | N |
| CTWS and ODFW, cooperators. January 1998. Annual progress report. Hood River and Pelton Ladder evaluation studies. Annual Progress Report of the CTWS and ODFW (Projects 88-053-03 and 88-053-04) to BPA, Portland, Oregon. | N |
| DOE and BPA (U.S. Department of Energy and Bonneville Power Administration). March 1996. Hood river fisheries project. Draft Environmental Impact Statement (DOE/EIS-0241). Bonneville Power Administration, Portland, Oregon. | N |
| DOE and BPA (U.S. Department of Energy and Bonneville Power Administration). July 1996. Hood River fisheries project. Final Environmental Impact Statement (DOE/EIS-0241). Bonneville Power Administration, Portland, Oregon. | N |
| Lambert M.B., J. McCanna, and Mick Jennings, CTWSRO. December 1998. Annual progress report 1997 (Project 1988-053-03; Contract DE-B179-89BP00631) of the CTWSRO to BPA, Portland, Oregon. | N |
| Lambert M.B., J. McCanna, and Mick Jennings, CTWSRO. December 1999. Annual progress report 1998 (Projects 1988-053-03 and 1998-021; Contract DE-B179-89BP00631 and 98BI-08334)) of the CTWSRO to BPA, Portland, Oregon. | N |
| NEOH Project (Northeast Oregon Hatchery Project). 1991. Hood River Master Plan. Draft monitoring and evaluation plan produced for NPPC’s Monitoring and Evaluation Group review. CTWS, Warm Springs, Oregon. | N |
| Northwest Power Planning Council (NPPC). 1987. Columbia River basin fish and wildlife program. Portland, Oregon. | N |
| ODFW and CTWS. September, 1990. Hood River Subbasin Salmon and Steelhead Production Plan. | N |
| Olsen, E.A., R.A. French, and J.A. Newton. 1994. Hood River and pelton ladder evaluation studies. Annual Progress Report of CTWS and ODFW (Projects 88-053-03 and 88-053-04) to BPA, Portland, Oregon. | N |
| Olsen, E.A. and R.A. French, ODFW. December 1998. Annual progress report 1997 (Project 1989-053-04; Contract DE-B179-89BP00632) of the ODFW to BPA, Portland, Oregon. | N |
| Olsen, E.A. and R.A. French, ODFW. September 1999. Annual progress report 1998 (Project 1989-053-04; Contract DE-B179-89BP00632) of the ODFW to BPA, Portland, Oregon. | N |
| OToole, P., and ODFW. 1991a. Hood River production master plan. Final report of the CTWS and the ODFW (Project 88-053-03, Contract DE-BI79-89BP00631) to BPA, Portland, Oregon. | N |
| OToole, P., and ODFW. 1991a. Hood River production master plan (Appendices). Final report of the CTWS and the ODFW (Project 88-053-03, Contract DE-BI79-89BP00631) to BPA, Portland, Oregon. | N |

# Section 10 of 10. Key personnel

MICK JENNINGS

3430 W 10th Street

The Dalles, OR 97058

EDUCATION

B.S. in Fisheries Science 1965

Dept. of Fisheries and Wildlife

Oregon State University, Corvallis, OR

PROFESSIONAL EXPERIENCE

CONFEDERATED TRIBES OF THE WARM SPRINGS RESERVATION OF OREGON

The Dalles, Oregon. March 1995 to present.  Salaried-40+hrs/week.

Job Title: Program Coordinator, Hood River Production Program

Duties: This position oversees the Tribal portion of the Hood River Production Program (HRPP), a Bonneville Power Administration funded program to restore anadromous fish runs in Hood River. Duties include oversight of project administration, engineering, construction, monitoring and evaluation of Hood River research, habitat evaluation and fish culture. This position coordinates all aspects of the HRPP with the Oregon Department of Fish and Wildlife, updates Tribal Fish and Wildlife Committee, Tribal Council, Northwest Power Planning Council and others on progress of HRPP.  This position budgets and administers a $500,000 monitoring and evaluation contract of Hood River research and supervises a staff of five full-time and three seasonal employees in an office in The Dalles, Oregon.

OREGON DEPARTMENT OF FISH AND WILDLIFE

Portland, Oregon.  April 1990 to February 1995.  Salaried 40+hrs/week.

Job Title: Steelhead Program Leader

Duties: This position directs, guides and assists the regions in the Department to implement a Statewide Steelhead Management program. Major duties consist of providing programmatic direction by coordinating the implementation of the policies, objectives and guidelines contained in the Statewide Steelhead Plan; preparing quarterly program progress reports, annual Steelhead Report, and other special reports and news releases; preparing and monitoring biennial budget; directing the research necessary to implement the Steelhead Plan; directing staff involved in collection and analysis of fisheries data; coordination of projects affecting steelhead resources; and providing guidance to Department personnel responsible for implementing the Steelhead Plan on state-of-the-art steelhead management techniques.

OREGON DEPARTMENT OF FISH AND WILDLIFE

Roseburg-Grants Pass, Oregon

Job Title: District Fish Biologist, June 1982 to March 1990.  Salaried-40+hrs/week.

Assistant District Fish Biologist, November 1966 to May 1982.  40hrs/week

Duties: Management biologist responsible developing, planning, supervising, analyzing and completing various fish management programs in the district. Approximately 60 percent of activities involved habitat protection and restoration.  A considerable amount of the habitat restoration activities involved adult and juvenile fish passage issues. Improvements to artificial fish passage barriers that I assisted in design and personally worked on included Little Butte Dam, Fielder Dam, Waters Creek Dam, Savage Rapids Dam, Kane Creek culvert, and Wimer Dam. I was continually evaluating fish passage at the approximately 100 small dams in the Rogue Basin. Also, a major part of my duties was spent supervising the fish screens program in the upper Rogue where over 150 rotary screens were in operation. Coordinated stream habitat restoration projects with the five USFS ranger districts that I worked with were routinely reviewed and evaluated for fishery resource benefits.

PUBLICATIONS/JOB COMPLETIONS

Steelhead Plan, Oregon Department of Fish and Wildlife, Wade M., et al. 1995. This is a comprehensive plan for production and management of Oregons anadromous steelhead. I was the primary person responsible for its development and completion, including setting up and overseeing technical and public advisory committees, incorporating comments and developing support of co-managers and the public, and finally adoption by the Fish and Wildlife Commission. This process took about 18 months.

Jennings, M., Hooton, B., Jacobs S., Kostow, K., McPherson, B., Nickelson T., Smith, A., Weeks, H.  1995. Biennial report on the status of wild fish in Oregon. Oregon Department of Fish and Wildlife.  Portland, Oregon. 217 p.

Jennings, M. D., M. Lambert. Acclimating salmonids in the wilds near Hood River, Oregon.  January 1996.  Proceedings of the 47th annual Fish Culture Conference. Victoria, British Columbia, V8V 1X4, Canada. Pages 38-44.

Jennings, M., Lambert, M. B., OToole, P.  1995.  Hood River and Pelton Ladder evaluation studies.  Annual Progress Report (Project 89-053-03) of the Confederated Tribes of the Warm Springs Reservation of Oregon. In cooperation with Oregon Department of Fish and Wildlife.  Report B, pages 173-285 to Bonneville Power Administration, Portland. Oregon.

Jennings, M., Lambert, M.B., McCanna J. 1996. Hood River and Pelton Ladder evaluation studies. Annual Progress Report (Project 89-053-03) of the Confederated Tribes of the Warm Springs Reservation of Oregon.  In cooperation with Oregon Department of Fish and Wildlife.  Report B, pages 163-257 to Bonneville Power Administration, Portland, Oregon.

JIM NEWTON

3701 West 13th Street

The Dalles, Oregon 97058

EDUCATION

B.S. in Wildlife Management 1970

Dept. of Fisheries and Wildlife

Oregon State University, Corvallis, OR.

PROFESSIONAL EXPERIENCE

OREGON DEPARTMENT OF FISH AND WILDLIFE

The Dalles, Oregon, May 1981 to present.  Salaried monthly - 40+ hours/week.

Job Title: District Fish Biologist, Mid-Columbia District.

Duties: This position is responsible for all fishery management activities within the 5,000 square mile Mid-Columbia Fish District.  Specific duties include the overseeing of that portion of the Hood River Production Project dealing with the Powerdale Fish Facility operation and maintenance, project coordination with the CTWS and managers of the Round Butte and Oak Springs fish hatcheries.  These duties include oversight for the Powerdale Fish Facility operation and maintenance, fish trapping, broodstock collection and transportation.  This position budgets and administers a $150,000 operation and maintenance contract for the Powerdale Fish Facility and supervises four full time and three seasonal positions in the Mid-Columbia District Office.

OREGON DEPARTMENT OF FISH AND WILDLIFE

Portland, Oregon.  September 1979 to May 1981.  Salaried monthly - 40+ hours/week.

Job Title: Habitat Conservation Division Staff Biologist.

Duties: This position coordinated the review and comments on State Clearinghouse notices of proposed federally funded projects throughout the state.  The review and comments on proposed oil, gas, and geothermal energy exploration projects was also coordinated with department field biologists.  This position worked with Portland and appropriate field staff to review and comment on county land use plans being developed and amended land use planning meetings throughout the state to insure that the states fish and wildlife resources were adequately addressed and protected.

OREGON DEPARTMENT OF FISH AND WILDLIFE

The Dalles, Oregon.  September 1971 to September 1979.  Salaried monthly - 40+ hours/week.  Job Title: Assistant District Fish Biologist.

Duties: This position assisted the district fish biologist with all phases of fishery management within the Mid-Columbia Fish District.  Specific duties included: working with research personnel conducting fishery research on the lower Deschutes River; stream habitat restoration planning and implementation; environmental investigations (i.e. Corps, DSL, Forest Practices, etc); angler use and harvest sampling programs; fish population inventory; and regular and special report preparation.

PUBLICATIONS/JOB COMPLETIONS

Mid-Columbia Fish District Annual Report - 1996, ODFW (unpublished).  This is a concise reporting of all fishery management activities occurring within the Mid-Columbia Fish District during calendar year 1996.  I was the person responsible for the preparation and completion of this report and distribution within the ODFW.  This is an ongoing process that has been greatly facilitated by the preparation of detailed monthly reports.  This report provides a concise summary of much of the districts institutional knowledge.  83 p.

Lower Deschutes River Resident Trout Population Inventory Report, ODFW.  Newton, James and Leslie Nelson, 1997.  This is a report on annual Deschutes River redband trout population inventory in two representative reaches of the lower Deschutes River.  I was the person responsible for the initiation and completion of the field inventory, data analysis, and report preparation and completion.  This project was completed in cooperation with the CTWS.  32 p.

Annual Progress Report - Lower Deschutes River, Oregon, Fish Population Studies (federal aide report for Sport Fish Restoration funding).  Newton, James and Steven Pribyl, 1996.  This is a comprehensive summary of lower Deschutes River anadromous fish studies, including harvest and population and spawner escapement estimates.  I am the person responsible for the annual inventory program and completion of annual data analysis and progress report completion.  This is an ongoing program that provides important biological data that is used as a valuable tool for fish management strategies.  37 p.

Lower Deschutes River Management Plan and Environmental Impact Statement.  BLM, et al.  1993.  This is a comprehensive plan for recreational use of the lower 100 miles of the Deschutes River.  The plan also contains specific management goals and objectives for natural resource management.  I was one of the people comprising the technical team that drafted much of the plan dealing with natural resource management within the river corridor.  I provided much of the technical support for the fish and wildlife resources covered by this plan.  Development of the plan included considerable coordination with other state, federal, and local government agencies, as well as the CTWS, and various river user groups.  This plan took more than four years to complete.  160 p.

RANDALL J. ROBART

85001 Oak Springs Road

Maupin, Oregon 97037

EDUCATION

A.S. Fisheries Technology 1977

Mt. Hood Community College

Gresham, Oregon

PROFESSIONAL EXPERIENCE

OREGON DEPARTMENT OF FISH AND WILDLIFE

Oak Springs Fish Hatchery, Maupin Oregon. February 1987 to present.  Salaried 40+ hrs/week

Job Title: Fish and Wildlife Manager 2

Duties: This position manages all aspects of Oak Springs Fish Hatchery, including: fish propagation, facility maintenance, staff development, planning, and  monitoring and evaluation.  This position is responsible for rearing three stocks of catchable and fingerling-sized rainbow trout, one stock of hatchery summer steelhead, one stock of wild summer steelhead, and two stocks of wild winter steelhead, as well as maintaining two hatchery rainbow brood stocks.  This position closely coordinates fish culture activities with four ODFW administrative regions, ODFW headquarters staff, seven other ODFW hatcheries, and seven ODFW fish districts.  This position also closely coordinates with HRPP personnel in all aspects of the Hood River stock summer and winter steelhead production.

OREGON DEPARTMENT OF FISH AND WILDLIFE

Round Butte Fish Hatchery, Madras, Oregon.  October 1984 to February 1987. Salaried 40+ hrs/week

Job Title: Fish and Wildlife Manager 1

Duties: This position managed all aspects of fish culture at Round Butte Fish Hatchery, including: fish propagation,  facility maintenance, staff development, planning, and  monitoring and evaluation.  This position is responsible for rearing one stock of hatchery summer steelhead and one stock of hatchery spring chinook.  Facility management included the operation of an adult trapping facility located at the Pelton Regulation Dam on the Deschutes River.  This position closely coordinates fish culture activities with one ODFW administrative region,  ODFW headquarters staff, one  ODFW fish district, Portland General Electric Company staff, and CTWSRO.

EXPERTISE

Described above

PUBLICATIONS / JOB COMPLETIONS

There are no relevant publications.  Job completions are adequately described above.

JAMES W. GIDLEY

HC 66 Box 528

Cascade Locks, Oregon 97014

EDUCATION

A.S. in Fisheries Technology

Mt. Hood Community College

Gresham, Oregon

PROFESSIONAL EXPERIENCE

OREGON DEPARTMENT OF FISH AND WILDLIFE

Cascade Locks, Oregon.  April 1982 to present.  Salaried 40 hrs/wk

Job Title: Assistant Hatchery Manager

Duties: This position assists with the planning and supervision of hatchery operations, including: adult broodstock collection, spawning, incubation, rearing, and liberation of smolts.  This position is responsible for maintaining daily, monthly and annual facility reports, as well as maintaining hatchery equipment and grounds.

OREGON DEPARTMENT OF FISH AND WILDLIFE

Nehalem, Oregon. April 1979 to April 1982.  Salaried 40 hrs/wk

Job Title: Fish and Wildlife Technician 1

Duties: This position assisted with the collection of adult broodstock, which was sorted by lot, species, sex, and maturity. This position assisted with all phases of the fish culture program, equipment and grounds maintenance, and record keeping.

OREGON DEPARTMENT OF FISH AND WILDLIFE

Butte Falls, Oregon. August 1976 to April 1979. Salaried 40 hrs/wk

Job Title: Fish and Wildlife Technician

Duties: This position assisted with various fish culture activities, including fish feeding, collection of mortalities, and record keeping.  The position also assisted with the collection of adult broodstock at remote sites, fish spawning, and the transfer of eggs.  This position also was responsible for driving and maintaining the fish liberation truck.