Project ID:	199801900

Title:		Wind River Watershed Restoration

Section 9 of 10. Project description

a. Abstract

Recognizing that wild adult steelhead returning to the Wind River had dipped to perilously low levels and that watershed conditions needed improvement, a concerned group of biologists from several agencies first met in 1992 to coordinate efforts towards restoring fish runs by compiling historical information, monitoring and evaluating biological conditions, and restoring habitat.  Since that time, a strong coalition of cooperators has been assembled and maintained to provide and apply their diverse expertise to actions within the watershed.  These actions have included obtaining funding for and enacting the following: forming and coordinating a watershed council and technical advisory committee, conducting a variety of watershed assessments using several different methods, identifying and prioritizing habitat restoration projects, completing cooperative restoration projects, conducting pre- and post monitoring and evaluation, and encouraging community and school involvement.  This blend of research, monitoring, evaluation, on-the-ground restoration, and education-outreach activities has proven to be highly effective and has resulted in many accomplishments.  Our proposed actions for FY 2001 build upon these accomplishments and address key measures and recovery issues identified by the Columbia Basin Fish and Wildlife Authority and by the federal listing of Lower Columbia River wild steelhead, while continuing the cooperative process and framework established in the past.  Restoration activities proposed for FY 2001 will target areas identified as highest priority by a 1999 limiting factors analysis for the watershed, by U.S. Forest Service's Wind River Watershed Analysis (1996a, to be updated and expanded by Dec 2000), and by our ongoing EDT modeling effort (targeted for completion by Dec 2000).  The ultimate goal of the Wind River Watershed Project is to restore habitat conditions that will facilitate recovery of wild steelhead populations to numbers assuring their persistence and allowing for healthy expression of genetic diversity and life history.

b. Technical and/or scientific background

On March 13, 1998 Wind River steelhead were listed as ‘threatened’ under the Endangered Species Act.  Most populations of salmonids that historically occupied the Wind River watershed are considered depressed (WDF et al. 1993).  According to a report by the American Fisheries Society, the Wind River winter steelhead stock is at a high risk for extinction, the summer steelhead stock is at a moderate risk for extinction, and the sea-run cutthroat may be extirpated from the subbasin (Nehlsen et al. 1991, Rawding 2000). Historically, Shipherd Falls (located 2.3 miles upstream from the mouth of the Wind River) was a natural barrier to all anadromous fish except steelhead, which were numerous above this barrier.  Bryant (1949) estimated summer steelhead run size was 3,250 with an escapement of 2,500 spawners.  The current number of wild summer steelhead spawning in the Wind River subbasin has been reduced to under 200 adults in recent years (Rawding 1997b, Rawding 2000).  In addition, a fall race of chinook that dominated the lower reach of the Wind River is depressed and composed of a substantial number of stray hatchery fish (WDF et al. 1993, Rawding 2000).

Anadromous fish losses have been attributed to the construction of migration barriers, timber harvest, and rural development of the upper watershed (WDW et al. 1990).  Activities in the upper watershed have severely impacted riparian areas and stream channels in several key steelhead subbasins evidenced by maximum water temperatures exceeding 75 degrees F, increased peak flows, and increased sedimentation (USFS 1996a).  There is also concern of the ecological and genetic risks posed by the anadromous hatchery programs (NMFS 1996b).  Carson National Fish Hatchery was constructed in 1938 to mitigate for the construction of Bonneville Dam and currently produces 1.8 million spring chinook smolts.  A fish ladder at Shipherd Falls, which is at river mile 2, was constructed to allow salmon access to the hatchery at river mile 18.  Between 20,000 and 100,000 hatchery steelhead smolts were released annually in the basin between 1960 and 1997.  Hatchery steelhead plants were terminated after 1997 due to concerns about ecological and genetic risks.

The Wind River Technical Advisory Committee (TAC) was formed in 1994 in response to the decline of steelhead within the Wind River subbasin.  The team currently includes technical specialists from the UCD, USFS, USFWS, WDFW, USGS, Washington State University Cooperative Extension, Longview Fibre Corp., Washington Dept. of Natural Resources (WDNR), and the Yakama Nation (YN).  Based on USFS’s (1996a) watershed analysis and USFS’s (1993) Trout Creek watershed assessment, the TAC and agency staff secured funding and completed a number of restoration projects.  Restoration efforts have resulted in the design and implementation of bio-technical methods to improve steelhead habitat by stabilizing stream banks, improving channel complexity, reconnecting flood plains, rebuilding riparian areas, and decommissioning roads.  High priority fish passage problems at Hemlock Dam identified by Orsborn et al. (1987) were addressed in 1996 by increasing adult attraction flow at the ladder entrance and eliminating false attraction flow from the Wind River Nursery.  Remaining concerns with fish passage and water quality at this facility are currently being assessed for feasibility and restoration potential with BPA FY1998 funding.

This proposal incorporates both public and private lands recognizing that “limiting restoration to public lands would be biologically futile and wasteful of public funds” (NPPC 1994).  The ISG (1996) and most other regional planning bodies recommend a watershed approach.  In an effort to address habitat concerns across all land ownerships, the UCD and TAC developed a watershed council in the subbasin with funding through USFWS and BPA (FY1998 funding).  This group of stakeholders, known as the Wind River Watershed Council (WRWC), was formed in 1997 and was modeled after other successful councils, such as the Grande Ronde Model Watershed Program.  Membership includes representatives from small private businesses, private timber companies, government agencies, landowners, recreational users, conservation groups, schools, and others.  The WRWC, with technical assistance from the TAC, ranks proposed restoration, monitoring & research projects.

The Columbia Basin Fish and Wildlife Program (NPPC 1994) stated that salmonid restoration should be linked to identification of key uncertainties and variables that limit populations.  We have proposed to link the steelhead’s productivity and life history diversity to address this issue. The information will: 1) directly and immediately help the planning efforts of the Wind River Watershed Council, and 2) fill gaps in implementation of measures of the Fish and Wildlife Program that have received little attention to date.  The Wind River represents an important but relatively overlooked type of watershed in the Columbia Basin: subbasins above Bonneville Dam but with steelhead stocks of coastal lineage.  Our results can be incorporated to help rebuild other coastal stocks, such as those in small tributaries between Bonneville Dam and the Hood River.  Results may also be useful for planned efforts to reintroduce anadromous fish into the White Salmon River above Condit Dam.

The WRWC, TAC, and agency staffs have endorsed our holistic, community-based watershed approach to restore steelhead and their habitat.  Our proposed projects are consistent with the plans and priorities of stakeholders, along with state, federal, and tribal agencies.  We propose to preserve and protect the remaining run of steelhead by rehabilitating watershed health, water quality, channel morphology, and stream habitat; by monitoring populations and production of steelhead; and by increasing our knowledge of the problems and needs of the watershed.  Successful restoration projects require public involvement, and we have established a public education and involvement process through the formation of a local watershed council.  The decline of steelhead returning to the Wind River, the potential reasons for this decline, and the recovery of steelhead in this watershed exemplify a spectrum of problems and activities that the Fish and Wildlife Program (FWP) was designed to address.

c. Rationale and significance to Regional Programs

The FWP (Section 7.6C) and the ISG (1996) have recommended a holistic, watershed approach to identify key physical and biological limitations for the recovery of salmon and steelhead stocks.  The activities we have proposed for the Wind River watershed meet the FWP goals to encourage interagency cooperation along with public participation.  We have proposed an on-the-ground, multi-faceted, and broad-scaled restoration project.  We have proposed activities that will provide specific information to the Wind River TAC for their efforts to restore steelhead to the subbasin, and will provide managers with the data needed to make informed decisions about additional efforts to restore the Wind River ecosystem.  By involving the community in watershed planning and in on-the-ground restoration activities, we hope to foster a healthy stewardship that will last for generations.

The proposed project is multi-faceted and our objectives attend to every one of the eight “Fish and Wildlife Needs” identified in the Wind River Subbasin Summary (Rawding 2000).  The needs that our objectives are particularly strong in addressing are: “Determine abundance, distribution, survival by life-stage, and status of fish...” (see our Objective 2); “Determine genetic and life history types of native fish...” (see our Objective 2, although there is not an explicit genetic component, but certainly a life history component); “Assess effect of natural escapement of hatchery spring chinook and brook trout on natural production of steelhead” (see our Objective 2); “Determine if high infestations of the ciliated protozoan Hydropolaria lwoffi (formerly Epistylis lwoffi) lowers survival of juvenile steelhead...” (see our Objective 2); “Determine the effectiveness of habitat restoration projects...” (see our Objective 2); “Implement restoration actions identified in the watershed assessments...” (see our Objective 4, and indirectly Objective 2 because it constitutes a valuable assessment that will be used to help prioritize restoration projects); and “Continue watershed coordination and local stewardship programs...” (see our Objectives 1 and 5).

Measure 7.6C of the FWP recognizes the value of the collaborative efforts of the Wind River TAC operating within a local watershed.  Measure 7.6C also stresses the importance of landowner and community participation in restoration activities.  This is being addressed through the WRWC, through which all stakeholders, including public and private entities, work on activities in concert.  Restoration activities address Measure 7.7 of the FWP.  Because of the concern for health of steelhead in the lower Columbia, the need for the type of data sought, and the location of the Wind River (above Bonneville Dam but within the lower Columbia River system), we believe that funding of the proposed projects will yield highly valuable results.

Life history diversity may be an important factor in the persistence of steelhead in the Wind River subbasin.  These investigations address measures 2.2A, 5.9A, 7.1, 7.1C, and 7.8B of the FWP.  Protection of wild steelhead and their habitat is the goal of the Endangered Species Act (NMFS 1996b).  Protection of wild steelhead and their habitat is also the goal of the Wild Salmonid Policy of WDFW (1997), the tribal restoration plan (Wy-Kan-Ush-Mi Wa-Kish -Wit, Nez Perce Tribe, et al. 1996), and the Northwest Forest Plan (USFS and BLM 1994).  The Wind River summer steelhead has received the highest priority for restoration under the State of Washington’s (1998) steelhead recovery plan (LCSCI).  Full funding of this proposal would be a timely way of addressing concerns about declining status of steelhead in the lower Columbia River basin.

d. Relationships to other projects

Our efforts in the Wind River watershed have been recognized by other salmon recovery programs, and our generated data have proved valuable to ongoing and proposed projects.  The Washington State legislature recently enacted regional strategies for addressing habitat concerns for listed salmonid species.  The Lower Columbia Fish Recovery Board (LCFRB) was established to prioritize actions put forth in the State of Washington’s (1998) LCSCI.  The Wind River TAC, which is coordinated under our current BPA funding, served as a local planning team to compile known limiting factors in the Wind River watershed that was used by the LCFRB to rank proposed projects in Evolutionary Significant Unit 4 (ESU 4).  The TAC has and will continue to coordinate with the WRWC to provide the LCFRB updated prioritized lists of Wind River projects to be ranked with other ESU 4 projects for various state and federal funding sources.    These funds would likely be limited to on-the-ground restoration actions, and would serve as cost-share to our proposed BPA-funding for the Wind River Watershed Restoration Project.  A prioritized list of Wind River projects was recently provided to CBFWA by the Wind River TAC and was incorporated in the Wind River Subbasin Summary (Rawding 2000).

The data we have on habitat conditions and on multiple life history stages of steelhead (parr, smolt, adult holding, adult spawning) is growing and qualifies as a valuable regional database.  Personnel working on the BPA-funded project “Bull Trout Population Assessment in the Columbia River Gorge, WA” (Project no. 9095) have used the water temperature and habitat data from the Wind project to help with their assessment of potential bull trout sites.  Our extensive database on stream temperatures has been requested for and used by USDA Forest Service (USFS, baseline monitoring and cumulative effects modeling), Washington Department of Ecology (WDOE, for 303d listing determinations), and Washington Department of Fish and Wildlife (WDFW, for development of a riparian shading model).

This project is a collaborative effort between UCD, WDFW, USFS, USGS, and YN.  Key personnel within these groups have an established working relationship with the WRWC and its TAC.  The results have been highly available and directly used by the wide representation of other agencies (USFWS, WDNR) and private stakeholders in the WRWC and its TAC in their efforts to restore the health of the Wind River watershed.  Many of the ongoing and planned future restoration projects of these groups rely on continued gathering of this data.

e. Project history (for ongoing projects)

The Wind River Watershed Restoration Project has been funded by BPA since FY1998.  Funding began midway through FY1998 under Project Number 9154.  Funding requested and received in the last three fiscal years has been: FY1998, requested $891K, received $350K; FY1999, requested $669K, received $350K; FY2000, requested $1,386K, received $554K.  Each of the four cooperating agencies (UCD, USFS, USGS, and WDFW) receiving BPA funding in FY1998 submitted their first annual report in December 1999 (Connolly 1999) covering FY1998 activities.  The annual report for FY1999 is due in December 2000.  Major results achieved to date are summarized by category below.  Note that all figures and tables referenced occur at the end of the Project History section.

Coordination:  The Wind River Watershed Council (WRWC) was developed in 1997 and meetings continue to be held monthly.  Meetings of the Wind River Watershed Council and its Technical Advisory Committee were held to address restoration planning, monitoring planning, and project prioritization.  The WRWC  & TAC have provided oversight and direction for the project.  The WRWC is comprised of a wide range of stakeholder representatives.  Accomplishments include the development of a mission and goals statement, identification and prioritization of over 40 potential restoration projects –mostly on private lands, selection and completion of the top two as demonstration projects, with two more underway having secured additional grant funding from the SRFB.  Meetings have provided a clearinghouse for local input to the projects and knowledge and also serve as a forum to ensure coordination of all watershed restoration activities.  The meetings have had substantial indirect benefits serving as a forum for sharing viewpoints, technical exchange of information, building trust and community involvement. Watershed Council members have enjoyed getting out and doing hands-on restoration activities such as tree-planting and garbage cleanup at project sites.

Monitoring:  Index stream reaches have been surveyed for density and biomass of juvenile steelhead under BPA funds since 1998.  These estimates have been compared to past estimates that are available (Table 1), such as those from 1984 (Crawford et al. 1985), 1985-88 (USFS, unpublished data), 1996 (Connolly 1997), 1997 (Connolly et al. 1997), 1998 (Connolly 1999), and 1999 (Connolly, unpublished data).  Wide annual variation has been observed, particularly with age-0 steelhead.  Observed densities of age-0 steelhead have served to validate redd surveys and substituted for lack of redd surveys in some areas for a more complete picture of where steelhead spawn.  One trend that has emerged from our analysis to date is that the population and biomass of age-1 and older juvenile steelhead in Trout Creek during 1996-1999 are always much lower or similar, but never much higher, than those during 1984-1988 (Figure 1).  We are actively collecting and analyzing data to help understand the role of habitat conditions and fish population dynamics to these findings.  Information from these index sites will serve as baseline data for assessing change to the system as a result of our restoration efforts.  Fish population surveys have also served to determine distributions of native resident fish species (rainbow trout, shorthead sculpin, mountain whitefish) and to locate primary areas for production of exotic species (brook trout, hatchery-origin spring chinook salmon).

Annual smolt production from the Wind River subbasin has been estimated since 1995, with estimates varying between 7,000-24,000 for the entire subbasin (Figure 2, Rawding 1999).  Under BPA funding (and with in-kind funds from WDFW, USFS, and USFWS), three smolt traps were fished in 1997 and four smolt traps were fished in 1998-2000.  Smolt traps have been sited to gain estimates for Trout Creek, Panther Creek, upper Wind River (from just below Trapper Creek), and the entire Wind River subbasin.

Multiple methods have been used to gain estimates of adult steelhead returning to the Wind River subbasin since 1984.  Redd surveys have been annually conducted throughout the Wind River watershed and over 20 miles have been annually snorkel surveyed to monitor returning adults.  Adult traps at Hemlock Dam and Shipherd Falls have been modified for efficiency and monitored with BPA funding.  Adult return numbers have been low (under 200) for the last decade, and returns to the Trout Creek watershed have been precipitously low (Figure 3).  These low returns continue to be of great concern.

A large network of continuous temperature recorders -approximately 40 units total, placed by UCD, USFS and USGS, have been deployed throughout the Wind River watershed.  Multiple daily readings track the seasonal changes and extremes in the streams.  Three tributaries of the Wind River (Bear, Eightmile, and Trout creeks) have been identified as exceeding temperature standards by the WA Dept. of Ecology (WDOE).  Temperature data gathered have been shared with WDOE for their TMDL study and the data have also been incorporated into the Subbasin Summary, the USDA Forest Service’s current effort to update the 1996 Wind River Watershed Analysis (expected completion in Dec 2000), and an EDT analysis, contributing to identifying and prioritizing stream reaches in need of restoration.

We have conducted physical stream surveys to assess sediment within the Wind River basin for two years (1998-1999).  A completion report detailing methods, results and conclusions was completed for each of these years.  Sediment samples were collected from nine subbasins on an annual basis.  Approximately 200 samples were collected and processed for about 10$/ sample.  Major results demonstrated that there is a positive relationship between instream fine sediment and percent of roaded area in the watershed (Figure 4).  However, fine sediment is not manifested in areas of large-scale deep-seated failures.  Overall, the data supports that fine sediment has not reached threshold proportions in the Wind River study area.

We have contracted USGS-Water Resources Division to maintain and operate a stream-flow gauge at Trout Creek for two years at a cost of approximately $9,400 per year.  Stream discharge data has proven to be very useful.  Stream stage has been used as a primary tool for physical and biological monitoring (e.g. smolt movemeent).  A rudimentary rating curve for Trout Creek was established; however, a complete curve for Trout Creek may require several years of data collection to include a range of discharges.  Collection of stream discharge data was successful and relatively effective.

There are however, several aspects to the gauge site location and project design that are less than ideal for meeting the stated objecives.  Several complications arise due to the location of the gauge.  Lack of electrical power requires the use of an auxillary battery source.  Reliance on a single power source increases the risk of power failure.  Data was lost during a during the 1996 field season as a result of power failure.  Real-time data transmission is currently unavailable.  Gauge data is available only following a field visit and manual download of data.  This can result in lengthy delays in obtaining flow data spanning up to 2-3 months when the location can only be reached by snowmobile.  Consequently, this system is ineffective at providing prompt flow data to support operational management decisions such as smolt trap modification or instream flow adjustments.  There are no exiting phone lines to transmit signals; therefore satellite or cellular phone would be required for remote, real-time transmission.  The existing gauge location does not lend itself to effectively monitoring Trout Creek instream flow requirements.  Because the existing gauge is located upstream of the water withdrawal at Hemlock Lake (RM 2.0), it is not possible to use the gauge data to track the instream flows below the diversion.  To best monitor the effect of water withdrawls at Hemlock Lake, there should be a gauge and/or a rating curve developed below the dam and above the dam.  Channel bottom mobility is another complicating factor at the existing gauge location.  The gravel/cobble size substrate is relatively easy to move.  Consequently, channel bottom elevation fluctuates, which could result in an unreliable rating curve or the need to continuously modify the rating curve.

We propose to continue theTrout Creek gauge operation becasue this data is critical to stream resotatrion planning and monitoring.  Development of a real-time data transfer system via satelite or cellular phone transmission should be considered for the future operation of the Trout Creek gauge.  The location of the future Trout Creek gaging station should be at a site that is stable over time and suitable for developing a dependable rating curve.

Baseline water quality data has been gathered from 10 stations filling data gaps primarily on private land areas of the watershed.  Four quarterly rounds were completed and one flush-flow round.  Parameters tested include dissolved oxygen, nitrogen, phosphorus, fecal and total coliform, turbidity, pH & conductivity.  Preliminary results indicate that overall the water in the Wind River is fairly clean, low in nutrients, and within standards on other parameters.  Data gathered have been incorporated into current efforts of completing an EDT analysis and updating the USFS (1996a) Wind River Watershed Analysis.

Assessment:  Our assessment of the Wind River has been evolving for the past three years in a synergistic manner: (1998-2000).  The findings of our assessment are included in our Wind River Restoration Project annual report (Connolly 1999), and incorporated into several recent or on-going assessments of the Wind River watershed: WRIA 29 Limiting Factors Analysis (WCC 1999), Wind River Watershed Analysis (USFS 1996a, update in prep.), and the Wind River Subbasin Summary (Rawding 2000).  We have been successful at conducting a subbasin-level evaluation and producing a prioritized list of restoration projects (Table 2).  We are currently working on inputs for the Ecosystem Diagnostics and Treatment (EDT) model, which will be completed in December 2000.  We will continue to use adaptive management techniques to revisit and revise past assessments in light of new data and to apply new knowledge for identification and re-ranking of project proposals.

Restoration:  Since the inception of this project, two demonstration projects on private lands have been completed: Martha Creek riparian reforestation and the Stabler Cut-Bank project on the middle reach of the Wind River (2000 linear feet of stream bank were stabilized through installation of 16 fish habitat and erosion control structures, placement of erosion matting, and riparian plantings over a period of two years).  Two additional projects, Sand Hill Slide reforestation and Hot Springs Trail restoration are underway.  Mapping & coordination is underway for another riparian reforestation project, Price Properties, on the middle reach of the Wind, with implementation planned for February-March 2001.  Photo-documentation stations have been installed at each site and current stream profiles will be made for comparison to pre-construction shots to monitor the recovery of the Stabler reach (UCD, lead)

This restoration program has included a full array of treatments covering upland and instream sites.  Major instream restoration projects have been completed in Trout Creek, Panther Creek, and Middle and Upper Wind watersheds.  Our efforts have made significant progress in restoring hydraulic processes and rehabilitation of critical habitat.  BPA has contributed to our restoration efforts from 1998-2000.  During this period of time, approximately 12 miles of road have been decommissioned or stabilized, 300 riparian acres have been planted, and 2,000 pieces of large woody debris have been place back in six river miles of stream by the USDA Forest Service.  Agreements have also been drafted for an evaluation of fish passage and development of restoration at Hemlock Dam.  Table 3 provides a list of recently completed restoration projects in the Wind River subbasin, and Rawding (2000) provides a complete watershed restoration summary for projects occurring within the Wind River.

Post-project monitoring indicates that we are meeting our short-term objectives.  Bank stability has been increased to 80 percent in Trout Creek, channel width-to-depth ratios have meet expected marks, and increase in LWD is above targeted numbers.  Long-term restoration objectives of reducing stream temperature and increasing stream shade will not be achieved for several decades.

Major types of restoration projects include the following:

- Channel Work - Place key pieces of LWD to achieve the range of natural variability for the Wind River watershed (75-120 pieces/mile). (USFS, UCD)

- Road Decommissioning – Restore drainage pattern by removing drainpipes, obliterating road surface and pulling back sloughing.

- Riparian Restoration - Plant and thin riparian forest to increase stream shade; provide future LWD and channel stability.

A report on Hemlock Dam Assessement and Restoration was recently completed under a subcontract (WSU 1999).  The objective of this study was to assess fish passage at Trout Creek’s Hemlock Dam and prescribe options for restoring fish passage.  The assessment relied on existing field data, along with modeling techniques, and literature review to evaluate passage.  The assessment noted that Trout Creek was historically very important to production of wild steelhead in the Wind River.  Restoration conservation scientists and engineers have been actively working on watershed restoration in Trout Creek for nearly two decades.  Hemlock Dam is identified as a factor for decline of wild steelhead trout in the Wind River.  This evaluation identified several key concerns that are direct source of mortality and/or impediments to safe and efficient fish passage of migrants including; ineffective flow conditions, outdated ladder design, and fishway and trap operation.  An array of the options for restoring fish passage were proposed which involve partial removal of the dam, replacing the fish ladder, replacing the fish screen, redesigning the fish channel and full removal of the dam.  A detailed work plan and activity schedule identified a timeline and resources needed to implement each prospective restoration option.  A benefit -cost analysis measured the value of expected fish returns against the implementation and operating cost of three options.  The economic assessment clearly identified full dam removal as the most cost-effective measure in the long term.  The full dam removal option addresses all of the fish passage concerns assessed in this study.  BPA contributed $28,037 to the $65,000 study.

Education:  A Stevenson High School stream monitoring program was established on the Wind River, and technical assistance was provided by UCD and USFS staff.  Stevenson High students and fish biologists from Russia received hands-on experience with smolt trapping in May of 1998.  A USFS biologist participated in the Stevenson High School mentor program by assisting a student with their senior project.  Students in the Columbia River Studies and Advanced Biology classes compiled reports into a website outlining the history, flora and fauna, water quality & their own monitoring results on the Wind River and presented their findings to the WRWC.  This website was accessible and on display at the Columbia River Conference IV (2000) as part of our interactive, cooperative display showcasing restoration & salmon related activities on the Wind River.

Technical support was also provided to the Wind River Middle School’s Junior Environmental Trouble Shooters (JETS) and Outdoor Education program.  Students compiled reports on photo monitoring of restoration projects and made detailed measurements of stabilized and eroding stream bank areas, identified Large Woody Debris, and tallied mortality in riparian plantings. They then presented their findings to the WRWC in excel and power-point formats.  The Outdoor Education program then partnered with and mentored a 5th grade class to adopt-a stream (see below).

UCD personnel organized several agencies to assist a 5th grade class from Carson Elementary to adopt a local stream and conduct 5 field trips over 5 months.  Classroom presentations, lessons and fieldwork included: macroinvertebrate surveys, noxious weed removal, native tree planting, water quality testing, interpretive sign design and placement.  Students raised salmon in the classroom, courtesy of US Fish & Wildlife Service and grants obtained by their teacher.  They also shared their knowledge with younger classes at the elementary school by writing and performing a salmon life-cycle play and song. They also presented these to the Wind River Watershed Council.

USDA Forest Service wrote (1999) and implemented (2000) a new curriculum: “Trout Creek Aquatic Ecosystems” with a local 4th grade class.  The USFS also gave classroom presentations on Trout Creek to the Columbia River Studies Class at Stevenson High School.

UCD co-hosted two Project Learning Tree workshops for teachers in 1999, emphasizing local resources and opportunities to get involved with restoration activities. The link with the 5th grade class was one result.

A timber stand management workshop with Wind River landowner attendance was conducted in cooperation with WSU Cooperative Extension.

Technical assistance has been provided to an average of three landowners per year to create plans incorporating water resource mitigation measures for a landscaping projects and other activities on the lower Wind River.

An interagency poster-display titled: “Repaying old debts, Wind River Watershed Restoration” was created for the Columbia River Conference IV depicting the history of the Wind River Watershed and current restoration, education and monitoring efforts, including the Wind River Watershed Council.  The display won rave reviews and will be exhibited again at the Skamania County fair, and other upcoming events, community and Technical.

A Power-point presentation: “Wind River Restoration activities and data available” covering the same historical and background material and incorporating all data generated and available as assessments or reports was created and presented at the CBFWA meeting to begin creation of sub-basin summaries for the ISRP.  This presentation was also given to the Lower Columbia Fish Recovery Board for inclusion in their decision-making toolbox.

Several professional presentations were made in 1999 and 2000.  These were given to the BC Ministry of the Environment’s Provincial Interagency Executive Committee, Trout Unlimited, and at the Western Division and North Pacific Chapter of the American Fisheries Society.

Figure 1.  Abundance and biomass estimates of juvenile steelhead (age-1 and older) in tributaries of and mainstem reaches of Trout Creek, Wind River subbasin.  Estimates from 1984 are from Crawford et al. (1985), estimates from 1986-88 are from US Forest Service (unpublished data), estimates from, 1996 (Connolly 1997), 1997 (Connolly et al. 1997), 1998 (Connolly 1999), and 1999 (Connolly, unpublished data).  See Table 1 for stream names indicated by four-letter code above.

Figure 2.  Estimated steelhead smolts emigrating from Wind River as determined from screw-trapping efforts.  The 1999 estimate is preliminary.

Figure 3.  Estimated adult escapement of adult steelhead to Trout Creek watershed from redd surveys and adult trapping at Hemlock Dam.

Figure 4. - Relationship between land management activity and fine substrate particle sizes (<1.69 mm) measured in nine subwatersheds in the Wind River watershed, Skamania County, Washington.

Table 1.  Abundance and density of juvenile steelhead in stream reaches within the Wind River subbasin.  Estimates from 1984 are from Crawford et al. (1985), estimates from 1986-88 are from US Forest Service (unpublished data), estimates from, 1996 (Connolly 1997), 1997 (Connolly et al. 1997), 1998 (Connolly 1999), and 1999 (Connolly, unpublished data).  See Table 1 for stream names indicated by four-letter code above.

Table 1.  Continued.

Table 2.  List and timeline of ongoing and completed restoration projects in the Wind River subbasin.

| Project Name | Implementation Status (complete/ ongoing) | Survey / Design | NEPA Planning | Contract Award | Implement | Monitng | Cost Estm |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Restoration |  |  |  |  |  |  |  |
| Middle Reach Rehab | Ongoing | 1997 | 1998 | 1998 | 2000 | 2002 | $60,000 |
| 6200 Rd. Decom | Ongoing | 1999-2000 | 2000 | 2000 | 2000 | 2002 | $65,000 |
| Limbo / Hdwaters Rd Decom | Ongoing | 1997-2000 | 2000 | 2000 | 2001 | 2002 | $65,000 |
| Dry Creek Channel Rehab | Ongoing | 1998-2000 | 1998 | 2000 | 2001 | 1998-2003 | $94,000 |
| Rd Decom - Wind | Ongoing | 2001 | 2001 | 2001 | 2001 | 2003 | $45,000 |
| Hemlock Dam Fish Passage | Ongoing | 1999-2000 | 2001- 2002 | 2003 | 2003-2005 | 2000- 2005 | $1,800,000 |
| Mine Reach Rehab. | Ongoing | 1996-2000 | 1998 | 1999 | 1999-2000 | 1998-2002 | $105,000 |
| Riparian Gaurdians | Ongoing | 1999-2000 | 1999 | NA | 2000-2001 | 2000-2001 | $40,000 |
| Upper Trout Creek V | Ongoing | 2001 | 2001 | 2001 | 2002-2005 | 2000-2008 | $333,000 |
| Dry Creek Rd. Obliteration | Completed | 1998 | 1998 | 1999 | 1999 | 1999-2001 | $78,000 |
| Stabler Cutbank Restoration | Completed | 1998 | 1998 | 1998 | 1998-1999 | 1999-2005 | $75,000 |
| Martha Creek Riparian Reforestation | Completed | 1998 | 1998 | na | 1998 | 1999-2004 | $10,000 |
| Monitoring and Evaluation |  |  |  |  |  |  | Cost/Yr |
| Redd Surveys -Wind Basin | Ongoing | 1998 |  |  |  | 2000-2005 | $20,000 |
| Smolt Trap - Wind Basin | Ongoing | 1998 |  |  |  | 2000-2005 | $12,500 |
| Adult Snorkle - Wind | Ongoing | 1998 |  |  |  | 2000-2005 | $4,000 |
| Sediment Surveys - Wind | Ongoing | 1998 |  |  |  | 2000-2005 | $15,500 |
| Water Qual (macro inverts) - Wind | Ongoing | 1998 |  |  |  | 2000-2005 | $5,000 |
| Water Quant - Wind Gauge | Ongoing | 1998 |  |  |  | 2000-2005 | $10,000 |
| Hemlock Dam - Adult Trap | Ongoing | 1998 |  |  |  | 2000-2005 | $7,000 |
| Level II Physical Stream Surveys | Ongoing | 1998 |  |  |  | 2000-2005 | $50,000 |
| Juv. Biomass/ Relative Density | Ongoing | 1998 |  |  |  | 2000-2005 | $200,000 |
| Baseline Water Qual on Pvt land | Ongoing | 1998 |  |  |  | 1999-2004 | $20,000 |
| Water Temp Monitoring | Ongoing | 1998 |  |  |  | 1998-2004 | $10,000 |
| Analysis |  |  |  |  |  |  |  |
| Wind River - first iteration | Completed |  |  |  | 1996 |  | $75,000 |
| Wind River - second iteration | Ongoing |  |  |  | 2000 |  | $8,000 |
| Ecosystem Diagnostic Treatment | Ongoing |  |  |  | 2000 |  | $10,000 |

Table 2.  Continued.

| Environmental Education |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Columbia River (Field) Studies | Ongoing | 1998 |  |  | 2000-2005 |  | $2,000 |
| Stevenson HS - Water Quality Monitoring | Ongoing | 1998 |  |  | 2000-2005 |  | $2,000 |
| Interpretive Signing | Ongoing | 2001 | 2001 | 2001 | 2001-2002 |  | $25,000 |
| Snorkel Surveys/Habitat Monitoring | Ongoing | 1998 |  |  | 2000-2005 |  | $1,500 |
| Trout Creek Aquatic Curriculum | Ongoing | 1998 |  |  | 2000-2005 |  | $4,000 |
| Carson Elem - Water Quality Monitoring | Ongoing | 1998 |  |  | 2000-2005 |  | $1,000 |
| Interpretive Signing O/M | Ongoing | 2001 |  |  | 2000-2005 |  | $1,000 |
| Snorkel Surveys/Habitat Monitoring | Ongoing | 1998 |  |  | 2000-2005 |  | $1,000 |
| 4H - Fish Stewardship Project | Ongoing | 2000 |  |  | 2000-2005 |  | $2,500 |
| Technical Assistance to Landowners | Ongoing | 1998- 2000 |  |  | 2000-2005 |  | $3,000 |
| Public Informaiton / community awareness | Ongoing | 1998-2000 |  |  | 2000-2005 |  | $4,000 |
| Wind River Middle School - outdoor ed | Ongoing | 1998-2000 |  |  | 2000-2005 |  | $3,000 |
| Coordination |  |  |  |  |  |  |  |
| Watershed Council - Wind | Ongoing | 1998 - 1999 |  |  | 2000-2005 |  | $20,000 |
| Technical Advisory Committee | Ongoing | 1998 |  |  | 1998-2005 |  | $10,000 |

Table 3.  Watershed restoration summary for BPA-funded projects completed within the Wind River subbasin, WA.

| Award Year | Location 5th field | Project Title | Activity Type | Miles Done | Total Funded | Plan Cost | Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1998 | Trout | Trout Creek Old Growth | Channel Resto | 0.8 | 119,800 | 23,800 | 96,000 |
| 1998 | Trout | Martha Ck Reforestation | Riparian | .76 | 5,000 | 1,000 | 4,000 |
| 1998 | Dry | Rd 65202-3 | Road Decom | 4.4 | 109,000 | 21,800 | 87,200 |
| 1999 | Mid Wind | Stabler Reach | Channel Work | 0.1 | 35,000 | 6,000 | 29,000 |
| 1998 | Mid Wind | Riparian Resto | Riparian | 1.0 | 26,000 | 5,000 | 2,100 |
| 1999 | Panther | Bank Stabilization | Channel Work | .1 | 10,000 | 3,000 | 9,000 |
| 2000* | Panther | 6200 | Road Decom | 4.4 |  |  |  |
| 1999 | UpWind | Mine Reach | Channel | 2.0 |  |  |  |
| 1999 | Up Wind | Mine Reach | Riparian | 2.0 | 136,000 | 22,800 | 113,200 |
| 2000* | Mid Wind | Mid Reach Channel | Channel Work | 2.0 | 25,000 | 5,000 | 20,000 |

* In-progress.

f. Proposal objectives, tasks and methods

Objectives

OBJ-1.  (Coordination) Coordinate watershed stakeholders in order to guide the implementation of watershed restoration actions that are consistent with stakeholder objectives. [UCD, USFS, USGS, WDFW]

OBJ-2.  (Monitoring) Monitor physical habitat conditions and natural production of juvenile, smolt, and adult steelhead in the Wind River subbasin.  [USGS, WDFW, USFS, UCD]

OBJ-3.  (Assessment) Use a science based framework to assess the condition of the watershed to determine what factors prevent stakeholder objectives from being met and to prioritize actions that result in meeting those objectives. [USGS, WDFW, USFS, UCD]

OBJ-4.  (Restoration) Restore stream habitats and watershed processes that will support self-sustaining populations of steelhead. [USFS, UCD, USGS]

OBJ-5.  (Education) Promote watershed stewardship among students, the community, private landowners, and local governments. [UCD, USFS, WDFW]

Tasks and Methods by Objective

OBJ-1

Task 1-a.  Facilitate 12 monthly meetings of the Wind River Watershed Council.  (Coordinated by UCD; participation by USFS, USGS.  Participation by WDFW and other agencies are in-kind) [FY 01-05]

Methods:  Coordination of the various interest groups will follow our established planning methodology.  The watershed council is modeled after similar, local councils, including the White Salmon Watershed Management Committee and the Grande Ronde Model Watershed Program.  The group will generally follow guidelines prescribed for in the “Management of Non-Point Source Pollution” handbook (Puget Sound Water Quality Authority, 1989).  The stakeholders that are represented on the WRWC include land owners, government agencies, businesses, recreation interests, conservation groups, the timber industry, tribes, and others.  Monthly meetings of the WRWC are conducted to provide project identification, evaluation, final project prioritization, review current activities, share information, and investigate funding opportunities.

Task 1-b.  Facilitate 12 monthly meetings of the Wind River Technical Advisory Committee  (Coordinated by UCD; participation by USFS, USGS.  Participation by WDFW and other agencies are in-kind [FY 01-05]

Methods:  The Technical Advisory Committee (TAC) and the Wind River Watershed Council (WRWC) work collectively to solicit projects and to prioritize proposed actions for funding.  The TAC is an interdisciplinary, multi-agency group composed of managers and researchers in fish and wildlife biology, silviculture, hydrology, civil engineering, and environmental education.  Public and private entities (including small private landowners) seeking funding to conduct restoration projects in the basin are strongly encouraged to submit proposals to the WRWC to be put through this prioritization process. Our project review process has been recently refined as a result of the continued support received from BPA.  Project development begins with review of proposals by the TAC for technical merit.  Proposals then go through review by the WRWC for socioeconomic and other considerations.  To ensure that available funds target the most important projects, proposed projects are put through a basin-wide prioritization process.  After prioritization, projects are considered ready to submit to various funding sources, primarily state and federal agencies, which allocate money for anadromous fish habitat restoration, including BPA.

TAC members also devise strategies to meet the objectives outlined by the WRWC.  The group will prescribe Best Management Practices and devise appropriate assessment methods to identify restoration opportunities.  Monthly meetings of the TAC will be held to conduct assessment, review on-going actions, and plan activities.

OBJ-2

Task 2-a.  Conduct sampling and derive population estimates for juvenile steelhead and other salmonids in a major tributary watershed.  (USGS) [FY 01-05]

Methods:  As currently being conducted in FY 00, we propose to produce annual estimates of population density and biomass of juvenile steelhead, other salmonids (resident rainbow trout, brook trout, spring chinook) for the portion of watershed accessible to anadromous salmonids and directly above an existing smolt trap (see Task 2-c) watershed.  The watersheds of primary interest, based on steelhead production areas, on USFS’s (1996a) watershed analysis, and on Rawding’s (2000) subbasin summary are: Upper Wind River, Trout Creek, and Panther Creek.  We plan to survey one of these watersheds each year on a rotating basis.  We are currently surveying Upper Wind River (with FY 00 BPA funding).  In FY 01, we propose to survey Trout Creek watershed.  We are actively pursuing additional funds (i.e., matching funds) to allow survey of two of the three major watersheds simultaneously to analyze for differences between watersheds while accounting for annual variability.

To obtain estimates of fish density and biomass, we will first conduct intensive habitat surveys of sampling sites during summer low-flow conditions.  Soon after these habitat surveys, fish surveys will be conducted either by snorkeling (for stream sizes greater than or equal to third order) or by electrofishing (for stream sizes less than or equal to third order).  When we conduct snorkel surveys, we will largely follow the methodology of Hankin and Reeves (1988), which utilizes a stratified systematic surveying technique to sample and derive an estimate of fish population.  We will calibrate our snorkel estimates by the ratio method following guidelines of Dolloff et al. (1993).  For small stream reaches that cannot be snorkeled, we will electrofish a systematic sample of habitat units within strata of habitat types (e.g., pools, glides, riffles, or finer gradations to achieve desired precision in estimates).  When electrofishing is used, habitat units chosen for sampling will be blocked off with nets to insure no movement into or out of the unit during sampling.  A backpack electrofisher will be used to conduct two or more passes under the removal-depletion methodology (Zippin 1956, Bohlin et al. 1982, White et al. 1982).  The field guides of Connolly (1996) will be used to insure that a pre-determined level of precision for the population estimate is achieved (generally, coefficient of variation no greater than 25%) within each sampling unit for each salmonid species (expected: steelhead/rainbow trout, brook trout) and age group (expected: 2-3 groups).  These methods have been chosen to minimize the number of units sampled by electrofishing and in the number of electrofishing passes conducted, which lessen the chance that individual fish will be exposed to potentially harmful effects of electroshocking

In order to track movements, growth, and survival of juvenile steelhead, we will PIT tag selected groups of age-1 or older juvenile steelhead that we capture during our stream surveys and during smolt trapping (see Task 2-c).  We will search for tagged fish in downstream smolt traps, in subsequent within year and annual surveys, and in the adult fish traps at Shipherd Falls and Hemlock Dam.  These PIT tags will also be detectable at Bonneville Dam at the smolt and adult stage.  As we are currently doing, all data will be entered in the PITAGIS database.

In addition to surveys for salmonids, our surveys will allow qualitative estimates of abundance and distribution of important nonsalmonid fish (sculpin, mountain whitefish) and other aquatic biota (crayfish, salamanders, frogs).  Our past efforts have revealed some definitive patterns of distribution (Connolly 1999), and new data will help us understand the role of barriers, exotic species introductions, and interactions among species.

Previous work by Connolly (1997) has revealed that many juvenile steelhead are infested with the ciliated protozoan Heteropolaria lwoffi (formerly Epistylis lwoffi).  In-kind contributions from USFWS’s Lower Columbia Fish Health Lab (Susan Gutenberger, Project Leader) will continue to allow us to map the distribution and to potentially understand the severity, variability, and causes of this infestation.  This activity addresses a specific data need identified in the Wind River Subbasin Summary (Rawding 2000).

Task 2-b.  Relate density and biomass of juvenile summer steelhead to stream habitat conditions and geomorphological contexts.  (USGS) [FY 01-05]

Methods:  To relate density and biomass of juvenile summer steelhead to stream habitat conditions and to geomorphological contexts, we will relate the data collected from habitat surveys to our estimates of fish populations and densities (such as done by Connolly and Hall 1999).  Data to be obtained from habitat surveys will include stream gradient, amount of large woody debris, pool and other habitat type frequencies, fish cover, stream substrate, channel and habitat unit morphology, hillslope condition and vegetation, riparian condition and vegetation, and affecting anthropogenic and natural disturbances.  We will maintain our current network of 30 continuous recording loggers for water temperature.  UCD maintains another 10 loggers as part of their water quality monitoring (see Task 2-g).  These loggers will allow us to track seasonal and diel variations and extremes in water temperature.  We will relate stream habitat and geomorphic characteristics to fish condition factors and age structure, which will help us define the limits and potential capacity of the Wind River system to rear juvenile steelhead.

Our multi-year database on stream habitat and fish population surveys will be used to assess cumulative effects of ongoing and future restoration efforts, unplanned natural disturbances (floods, droughts), and egg-to-parr survival.

We will relate densities of juvenile steelhead to densities of spring chinook juveniles and to brook trout, both of which are introduced species to the Wind River above Shipherd Falls.  Tracking annual variability in these density relationships and assessing habitat use and availability will allow us to determine the degree of negative interactions among these species.

Task 2-c.  Conduct sampling at smolt traps and use data to derive an estimate for the annual steelhead smolt production in the subbasin.  (WDFW) [FY 01-05]

Methods:  We will develop annual estimates of smolt production from the Wind River subbasin.  Trap sites will be located at established sites to estimate total basin production (mouth of Wind River) and production from key watersheds (Trout Creek, Panther Creek, and Upper Wind River).  Rotary screw traps will be fished from March 15 to June 15, which coincides with Wind River smolt migration (Rawding 1999).  Traps will be checked daily and fish will be enumerated.  After fish are anesthetized, we will obtain fork lengths and weights from all fish and scale samples will be obtained from up to 10 fish daily.  Ages from these fish will be used in conjunction with fork-length frequencies to determine age composition for the smolt outmigration.  Smolt estimates will be determined by the trap efficiency method of releasing marked fish upstream of each trap (Thedinga et al. 1994).  All fish will be tattooed and marks will be rotated weekly to determine changes in trap efficiency.  Trap efficiency will be determined by Bailey’s (1951) modification of the Petersen estimator.  Short-term survival and mark retention will be measured and used to adjust trap efficiency (Murphy et al. 1996).  Confidence intervals will be determined using a bootstrap method (Efron and Tibshirani 1986).  In addition, smolts will be coded-wire tagged or PIT tagged.  This will enable us to determine an independent smolt estimate using a back calculation from trapped adults (Seiler et al. 1997).

Similar to Task 2-b, our multi-year database on annual smolt production will be used to assess the cumulative effects of restoration efforts, unplanned natural disturbances (floods, droughts), and parr-to-smolt survival.

Task 2-d.  Conduct sampling and use data from redd surveys, snorkel surveys, and adult trappings to derive an estimate for the annual steelhead adult production in the subbasin. (WDFW) [FY 01-05]

Methods:  We propose to assess the annual adult steelhead returns to the Wind River subbasin.  Currently, expanded redd surveys are used to develop adult escapement estimates based on assumptions on differences in winter and summer steelhead distribution and differences in hatchery and wild spawning time.  Knudsen (1997) rated these methods as fair to poor for determining escapement estimates.  Therefore, we propose to reinstall an adult trap in the Shipherd Falls fish ladder to improve the accuracy of adult escapement estimates.  We propose to operate the adult trap year round.  Adult steelhead will be floy tagged and released upstream.  Since summer steelhead can successfully jump the falls, snorkel surveys and the Trout Creek trap will be used to determine the ratio of tagged to untagged fish.  Adult run size will be estimated using Bailey’s (1951) modification to the Peterson estimator.  Floy tag loss will be estimated by use of double marking.  In addition to receiving a floy tag, a small hole will be placed in the caudal fin with a paper punch.  As fish are recaptured upstream at the Trout Creek trap floy tag loss will be estimated.  The caudal fin tissue obtained from the secondary mark will be archived for future genetic analysis (DNA).

Task 2-e.  Conduct physical stream habitat surveys in 6 new reaches to assess stream conditions and changes over time at selected sites throughout the subbasin.  For FY 02, this task becomes: Conduct physical stream habitat surveys to assess stream conditions and changes over time at selected sites throughout the subbasin. (USFS) [Initiated in FY 01, to M&E for replicating in FY 02-05]

Methods:  We propose to conduct physical stream surveys following Hankin and Reeves (1988) methodology in a manner consistent with the USFS (1997, version 9.7) Pacific Northwest Region’s Stream Inventory Handbook.  The field inventory will quantify key stream habitat components and indicators of aquatic health including: 1) large woody debris, 2) stream habitat units following Platts (1974), 3) substrate composition following Wolman (1954), 4) channel geometry following Leopold (1994), and 5) riparian vegetation classification.  This extensive stream channel, riparian vegetation, and aquatic habitat condition inventory will focus on private lands and supplement USFS surveys conducted on federal land.

Task 2-f.  Operate and maintain real-time flow gauges at Trout Creek and Shipherd Falls.  (USFS) [FY 01-05]

Methods:  We propose to contract the USGS to maintain and operate two pre-existing gauging stations located on Trout Creek and Wind River.  Continuous flow and temperature data will be collected for twelve months by the gauge along with a minimum of six regularly scheduled discharge measurements per year by personnel, which is necessary to develop a hydrologic rating curve as described in the USGS Quality Assurance Plan.  Data will be downloaded monthly and made available for public use.

Task 2-g.  Monitor water quality at established stations and use these data to determine if water quality is a limiting factor.  (UCD) [FY 01-05]

Methods:  Water quality monitoring will be conducted at 10 stations located primarily on private lands.  These stations will augment existing stations on National Forest land.  Monitoring will consist of an initial assessment in the first year, consisting of four quarterly sampling rounds and two flush-flow sampling rounds.  One flush flow and one base flow sampling round will occur each year for the next four years to monitor change over time.  Parameters to be sampled include pH, turbidity, dissolved oxygen, conductivity, continuous temperature, nitrate and nitrite nitrogen, phosphorous, and total and fecal coliform bacteria.  Water quality monitoring program will be devised according to DOE QA/QC plan criteria.  UCD will maintain a current network of 10 continuous recording loggers for water temperature.  USGS maintains another 30 loggers as part of their effort to link fish distribution and abundance to habitat characteristics (see Task 2-c).  These efforts address an identified data gap in USFS’s (1996a) Wind River Watershed Analysis and Rawding’s (2000) Wind River Subbasin Summary.

Task 2-h.  Monitor suspended sediments and amount of fines in redds of 6 new reaches to determine if these characteristics are limiting factors.  For FY02, this task becomes: Monitor suspended sediments and amount of fines in redds to determine if these characteristics are limiting factors.  (USFS) [Initiated in FY 01, to M&E for replicating in FY 02-05]

Methods:  We will estimate gravel composition within six index spawning reaches using methods described by McNeil and Ahnell (1960) and the protocol incorporated in the Yakima River Resource Management Plan.  This standardized process will extract substrate samples using a McNeil core sampler in locations that represent spawning habitat.  Comparative samples taken from within expired redds will serve to evaluate micro-environmental change resulting from spawning activity.  Samples will be processed and sieved using standards described by the U.S. Conservation Service (1982).  Analysis will focus on the relative abundance of fine-textured materials (< 8 mm.), which will be used to estimate the potential egg-to-fry survival as described by Young (1991).  Site selection will be based on several factors including known spawning locations, land management activity, landform characteristics, and channel stability indicators.

OBJ-3

Task 3-a.  Update assessment data, revise list of needed projects, and prioritize the list based on value and likely success of desired outcomes.  (USGS, WDFW, USFS, UCD) [FY 01-05]

Methods:  Data from fish assessments and physical habitat surveys (OBJ-2) will be combined with existing data to help assess the health of the Wind River subbasin.  Substantial information on habitat conditions is available in the USFS’s (1996a, 2000 update in prep.) Wind River Watershed Analysis.  In addition, we will use results of our Ecosystem Diagnosis and Treatment (EDT) modeling efforts (initiated in FY2000 and expected to be completed by December 2000).  As described in Mobrand et al. (1995), Mobrand and Lestelle (1997), and Lestelle et al. (1996), the EDT will allow us to link environmental factors with population biology by using life-history diversity, capacity, and productivity information to provide more certainty in the analysis and outcomes of proposed restoration activities to help rebuild the Wind River summer steelhead population.

OBJ-4

Task 4-a.  Decommission 5 miles of road annually within sub-watersheds as prioritized in the Wind River Watershed Analysis.  (USFS) [FY 01-05]

Methods:  Road obliteration will be accomplished in accordance with the USFS’s (1996b) Forest Service Technology and Development manual.  Five miles of road will be decommissioned in FY2001.  Work will be conducted in accordance with the State of Washington Hydraulic Permit Approval.  Erosion control prescriptions will follow best management practices using native or non-invasive grass seed and shrubs along with natural filter netting.  Culvert will be removed and sites will be fitted with erosion control mat, grass seed and shrubs.  Road surfaces will be scarified and seeded with non-invasive or native grass seed and native trees and shrubs.  Photo points and vegetative growth/survival plots will be established to monitor rehabilitation.  Road decommissioning projects are expected to reduce risk of mass failure/landslides, reduce road related sediment sources, restore natural water routing, and reduce surface run-off.

Task 4-b.  Place key pieces of LWD to achieve the range of natural variability for the Wind River watershed (75-120 pieces/mile). (USFS, UCD) [FY 01-05]

Methods:  In-stream LWD will be increased in 2.25 river miles to within the range of natural variability (75--120 LWD pieces/mile) as documented in the USFS’s (1996a) Wind River Watershed Analysis.  Pieces of LWD will be placed within the bankfull channel to supplement LWD levels until riparian stands are old enough to contribute wood into the channel.  This supplementation is expected to store sediment, dissipate water velocity, and restore habitat complexity.  This restoration activity will incorporate methods developed by Rosgen (1994) and Leopold (1994).  Placement of wood will be within reaches of stream that do not pose a significant threat to bridges, roads or structures.  For effectiveness monitoring, LWD will be photographed, tagged and mapped.  All work proposed under this objective will be preceded by an environmental analysis.  All work will be conducted in accordance to the standards of US Army Corps of Engineers, State of Washington permitting process, and other appropriate requirements.

Task 4-c.  Plant and thin riparian forest to increase stream shade, provide future LWD and channel stability.  (USFS, UCD) [FY 01-05]

Methods:  We propose to: 1) thin 45 acres of overstocked, homogeneous stands of hardwoods and Douglas-fir to release native conifers such as cedar, hemlock and grand fir, and 2) under-plant 45 acres of stands with native conifers.  Environmental analysis will follow EPA and NEPA standards.  Plant survival and growth plots will be established and monitored for four years after treatment.  A solar path finder will be used to evaluate the percentage of stream shaded during the months of June, July, August, and September.  Riparian rehabilitation will accelerate growth rates and diversify stream-side vegetation, which increases potential LWD, bank stability, and stream shade.  Restoration of riparian areas will contribute to plant and animal species diversity and support a self-sustaining aquatic ecosystem.

Task 4-d.  Evaluate Hemlock Dam and conduct NEPA process [FY 01-02].  For FY 03, this task becomes: Modify Hemlock Dam.  For FY 04-05, this task becomes:  Hemlock Dam post-modification.  [FY 01-05]

Methods:  This task will complete the prerequisite planning phase of Hemlock Dam restoration [FY 01-02].  This item will complete phase II of IV for this proposal (see below for full description).  Documentation of methods will be in accordance with the National Environmental Policy Act (1974) planning regulations.  Elements of the planning process will include the following:

- Public scooping – a minimum of five meetings and two news releases

- Alternative refinement – develop a full range of alternatives

- Effects Analysis – full disclose the long and short term, direct and indirect effects of the proposed action.

- Draft Environmental Impact Statement – publish document for public review

- Response to public comments- produce written reply to public comments

- Final Environmental Impact Statement – publish document

- Record of Decision – publish document

We will complete necessary ground surveys for survey and manage species that are required by law.  Lastly we will conduct preliminary cultural resources surveys and develop a data recovery plan in accordance with state Historic American Engineers Report (HAER).

Our proposed action is to remove Hemlock Dam and reconstruct a free-flowing channel in place of the reservoir and rehabilitate the riparian area.  The proposed actions are consistent with the recommendations produced in the independent evaluation of restoration options (WSU 1999).

The complete project is composed of five phases including the following:

Phase I:  Project feasibility (1998-1999). Conduct a fish passage assessment and design restoration options

Phase II: NEPA planning (2000-2001). Complete alternative development, public scooping, survey and manage field surveys and cultural resources Data Recovery Plan and HAER level documentation.  Present Hemlock Dam environmental education, and produce informational brochure.

Phase III: NEPA planning (2002-2003). Complete effects analysis, permitting process (HPA), consultation, Draft EIS, final EIS and Record of Decision (ROD), prepare contract

Phase IV (2003-2004).  Project implementation (pending outcome of NEPA) including

    - Reconstruct channel - excavate 71,000 CY and recontour 200 CY of sediment

    - Place LWD – 10- 20 pieces

    - Remove and dispose 440 CY of dam material

    - Remove 2,507 SF of ladder material

    - Revegetate 15,004 SY of lake area

Phase V: Project monitoring (1995 – 2006 and beyond)

      - Maintain baseline water quality monitoring station

      - Enumerate adult and juvenile steelhead populations

      - Measure channel geometry and substrate conditions

      - Gauge stream flow

Dam removal will result in many benefits to salmonids and their habitat.  Dam restoration will provide for safe and efficient fish passage as a result of the following action:  removing known sources of impingement, eliminating excessive vertical drop, providing appropriate flows to guide fish downstream, eliminating confounding and erratic flows that inhibit migration, providing necessary low velocity resting water, and providing necessary water velocities to attract fish upstream.  Riparian conditions will improve with the development of streamside vegetation.  Channels will return to a properly functioning condition as barriers are removed.  Sediment and large wood transport will restore organic material, nutrients, and structural complexity to the aquatic ecosystem.  Instream conditions will improve with the recovery of riparian stands, of in-stream habitat, and of water quality in upper Trout Creek watershed.

OBJ-5

Task 5-a.  Support Stevenson High School stream monitoring program, Wind River Middle School’s environmental education program, and develop and support a Carson Elementary School Adopt-A-Stream program.  (UCD, USFS, WDFW) [FY 01-05]

Methods:  The Stevenson High School and Wind River Middle School programs are based generally on the Streamwalk (EPA) and Project Green models.  The programs consist of classroom study, water quality, project monitoring, and assessment of land-use impacts.  UCD Staff will assist teachers with curriculum development, give classroom presentations and assist students with water quality & project monitoring in the field.   The Carson Elementary School program will be based on the Adopt-A-Stream format and will involve water quality monitoring, macro-invertebrate surveys, and classroom salmon rearing in partnership with US Fish & Wildlife Service and other local EE groups (in kind).  A Teacher workshop focusing on local resources & opportunities for student involvement in restoration activities (Project Learning Tree) will also be included.

Students will present results of their projects at a Watershed Council meeting to inform and educate the community.

Task 5-b.  Distribute informational brochures, submit articles to local paper, and conduct community volunteer events to inform public about watershed issues, activities, and opportunities for involvement.  (UCD, USFS) [FY 01-05]

Methods:  Participation in established community events to raise public awareness of watershed issues and restoration efforts on the Wind River, and inform them of opportunities to get involved.  Possible volunteer events include tree plantings, river clean-ups, fish education days, and fish viewing events. Tree planting events will utilize conifers from UCD Tree Sales Program and will target degraded private riparian areas.  River clean-ups will follow the WA Water Weeks and White Salmon Trash Rodeo models.  Fish viewing events will be conducted to let people see fish in their natural environment.  Fish Education Days will utilize agency personnel and build on established local models.  Schools, environmental groups, service organizations, and the general public will be targeted for participation.

Task 5-c.  Provide technical assistance to landowners and agency personnel developing water resource mitigation measures for projects on private lands.  (UCD) [FY 01-05]

Methods:  Technical assistance will be provided at the request of landowners or the county for proposed projects that may affect watershed resources.  Staff will primarily provide information on technical measures for lessening or mitigating impacts to water resources.  Staff may also facilitate the implementation of these measures via lining up trained labor, supplying materials, providing on-site supervision, or assisting with grant applications, etc.

g. Facilities and equipment

The UCD’s offices in White Salmon (WA), WDFW’s office at North Bonneville, USFS’s Wind River Work Center near Stabler (WA), and USGS’s Columbia River Research Laboratory near Cook (WA) have existing office facilities and much of the equipment needed to conduct the proposed project.  In combination with the personnel that will be hired and the equipment that will be purchased with the requested funds, these offices offer veteran professionals and modern office equipment (computers with latest software and internet connections, copiers, FAX machines, phones), vehicles appropriate for highways and field work, and a large array of sampling equipment (late-model backpack electrofishers, LB2 laser levels, flow meters, snorkeling gear, GPS units, analytical balances, sediment processing shaker, McNeil core sampler, pH meters, temperature data loggers) to ensure that the highest quality professional research can be conducted.

Special or higher-cost equipment to be purchased with project funds, by task, include: Task 2-a, Marsh-McBirney flow meter ($3,525); Task 2-c, smolt trap ($13,000); Task 2-f, fixed-site stream flow and temperature data recorder ($2,000); Task 4-a, erosion control matting (6 rolls at $300/roll=$1,800); Task 4-e, rooted seedling stock for 15 acres ($424/acre=$6,360).

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Bailey, N.T.J. 1951. On estimating the size of mobile populations from recapture data. Biometrika 38:293-306. | N |
| Bohlin, T. 1982. The validity of the removal method for small populations -- consequences for electrofishing practice. Institute of Freshwater Research Drottningholm Report 60:15-18. | N |
| BPA (Bonnevile Power Administration). 1997. Watershed Management Program EIS. Portland, OR. | N |
| Bryant, F.G. 1949. A survey of the Columbia River and its tributaries with special reference to its fishery resources. Part 2. U.S. Fish and Wildlife Service. Spec. Sci. Rep. No. 62. | N |
| Cederholm, C.D., D.B. Houston, D.L. Cole, and W.J. Scarlett. 1989. Fate of coho salmon (Oncorhynchus kisutch) carcasses in spawning streams. Canadian Journal of Fisheries and Aquatic Sciences 46:1347-1355. | N |
| Connolly, P.J. 1996. Resident cutthroat trout in the central Coast Range of Oregon: logging effects, habitat associations, and sampling protocols. Doctoral dissertation. Oregon State University, Corvallis. | N |
| Connolly, P.J. 1997. Status of juvenile steelhead rearing in Trout and Panther creeks of the Wind River Basin. Prepared for: Washington Trout, Duvall, WA. | N |
| Connolly, P.J. 1999. Editor. Wind River watershed project. 1998 Annual Report. Project number 9801900, Prepared for: Bonneville Power Administration, Portland, Oregon. http://www.bpa.gov | N |
| Connolly, P.J., and J.D. Hall. 1999. Biomass of coastal cutthroat trout in unlogged and previously clear-cut basins in the central Coast Range of Oregon. Transactions of the American Fisheries Society. 128:890-899. | N |
| Connolly, P.J., R.P. Hanten, and J.H. Petersen. 1997. Juvenile steelhead in Trout and Panther creeks of the Wind River basin sampled in August-September 1997. U.S.G.S.,Biological Resources Department, Columbia River Research Laboratory, Cook, WA. | N |
| Crawford, B.A., R. Pettit, and R. Claflin. 1985. Study of juvenile steelhead densities and biomass in the Wind and E.F. Lewis rivers. Washington Department of Game, Olympia. | N |
| Dolloff, C.A., D.G. Hankin, and G.H. Reeves. 1993. Basinwide estimates of habitat and fish populations in streams. General Technical Report SE-83. Asheville, North Carolina: U.S.F.S., Southeastern Forest Experiment Station. 25 p. | N |
| Efron, B., and R. Tibshirani. 1986. Bootstrap methods for standard errors, confidence intervals, and other measures of statistical accuracy. Statistical Science 1:54-77. | N |
| Hankin, D.G., and G.H. Reeves. 1988. Estimating total fish abundance and total habitat area in small streams based on visual estimation methods. Canadian Journal of Fisheries and Aquatic Sciences 45:834-844. | N |
| ISG (Independent Science Group). 1996. Return to the river: Restoration of salmonid fishes in the Columbia River ecosystem. No. 96-6. Northwest Power Planning Council, Portland, OR. | N |
| Knudsen, E.E. 1997. Managing Pacific salmon escapements: the gaps between theory and reality. U.S. Geological Survey, Biological Resources Division. Proceedings from the Sustainable Fisheries Conference. In press. Anchorage, AK. | N |
| Leopold, L. B. 1994. A view of the river. Harvard Univ. Press, Cambridge, MA. | N |
| Lestelle, L.C., L.E. Mobrand, J.A. Lichatowich, and T.S. Vogel. 1996. Applied ecosystem analysis--a primer, EDT: the ecosystem diagnosis and treatment method. Project No. 9404600. Prepared for: Bonneville Power Administration, Portland, OR. | N |
| McNeil, W.J., and W.H. Ahnell. 1960. Measurement of gravel composition of salmon stream beds. University of Washington, Fish Res. Inst., Circ. 120. Seattle. 7 p. | N |
| Mobrand, L., and 10 coauthors. 1995. Grande Ronde model watershed ecosystem diagnosis and treatment. Final Report, Project number 94-030, Bonneville Power Administration, Portland, OR. | N |
| Mobrand, L., and L. Lestelle. 1997. Application of the ecosystem diagnosis and treatment method to the Grande Ronde model watershed project. Final Report. Project No. 94AM33243. Prepared for: Bonneville Power Administration, Portland, OR. | N |
| Murphy, M.L., J.F. Thedinga, and J.J. Pella. 1996. Bootstrap confidence intervals for trap efficiency estimates of migrating fish. National Marine Fisheries Service, Juneau, AK. | N |
| Nehlsen, W., J.E. Williams, and J.A. Lichatowich. 1991. Pacific salmon at the crossroads: stocks at risk from California, Oregon, Idaho, and Washington. Fisheries 16:4-21. | N |
| Nez Perce Tribe et al. 1996. Wy-Kan-Ush-Mi Wa-Kish-Wit, Spirit of the Salmon. Lapwai, ID. | N |
| NMFS (National Marine Fisheries Service). 1996a. Coastal salmon conservation: working guidance for comprehensive salmon restoration initiatives on the Pacific coast. National Marine Fisheries Service, Seattle, WA. | N |
| NMFS (National Marine Fisheries Service). 1996b. Factors for decline: a supplement to the notice of determination for west coast steelhead under the Endangered Species Act. Environmental and Technical Services, Portland, OR. | N |
| NPPC (Northwest Power Planning Council). 1994. The Columbia basin fish and wildlife program. No. 94-55. Portland, OR. | N |
| Orsborn, J. et al. 1987. A preliminary analysis of alternatives for improving fish passage at Trout Creek Dam (preliminary design report). Prepared for: U.S.F.S., Wind River Ranger District. By: Fisheries Engineering Class, WA State Univ., Pullman. | N |
| Plafkin, J.L. and four co-authors. 1989. Rapid bioassessment for use in streams and rivers: benthic macroinvertebrates and fish. U.S. Environmental Protection Agency, EPA/444/4-89-001, Washington D.C. | N |
| Platts, W.S. 1974. Geomorphic and aquatic conditions influencing salmonids and stream classification with application to ecosystem classification. U.S. Department of Agriculture, SEAM (Surface Environment and Mining) Program, Billings, MT. | N |
| Puget Sound Water Quality Authority. 1989. Management of non-point source pollution. Seattle, WA. | N |
| Rawding, D.J. 1997a. Wind River smolt monitoring program. Washington Department of Fish and Wildlife, Vancouver, WA. | N |
| Rawding, D.J. 1997b. Stock status update for steelhead in the lower Columbia River , Washington. Washington Department of Fish and Wildlife, Olympia, WA. | N |
| Rawding, D.J. 1999. Wind River steelhead smolt and parr production monitoring. Pages D1-D28 in P.J. Connolly, editor. Wind River watershed project. Volume I, Project number 9801900, Prepared for: Bonneville Power Administration, Portland, Oregon. | N |
| Rawding, D.J. 2000. Wind River subbasin summary. 30 June 2000 Draft. Prepared for: NW Power Planning Council, Portland, OR. http://www.cbfwf.org/files/province/subsum.htm. | N |
| Rosgen, D.L. 1994. A classification of natural rivers. Elsevier Science, B.V. Amsterdam. Catena 22:169-199. | N |
| Seiler, D., and five co-authors. 1997. Wild salmon production and survival evaluation. Annual Report No. RAD97-03. Washington Department of Fish and Wildlife, Olympia. | N |
| Slaney, P.A., C.J. Perrin, and B.R. Ward. 1986. Nutrient concentration as a limitation to steelhead smolt production in the Keogh river. Proceedings of the annual conference of Western Association Fish and Wildlife Agencies 66:146-157. | N |
| State of Washington. 1998. Lower Columbia steelhead conservation initiative. Draft. Olympia. | N |
| Thedinga, J.F., S.W. Johnson, K V. Koski, J.M. Lorenz, and M.L. Murphy. 1994. Determination of salmonid smolt yield with rotary screw traps in the Situk River, Alaska, to predict effects of glacial flooding. N. Am. J. Fish. Mgmt. 14:837-851. | N |
| UCD (Underwood Conservation Department). 1998. Wind River restoration project: missions and goals. Underwood, WA. 1p. | N |
| USFS (USDA Forest Service). 1993. 1992 basin assessment. Wind River Ranger District. Draft report. Carson, WA. | N |
| USFS (USDA Forest Service). 1996a. Wind River basin watershed analysis. Wind River Ranger District, Carson, Washington. | N |
| USFS (USDA Forest Service). 1996b. Guide for road closure and obliteration. U.S. Government Printing Office, Washington, D.C. | N |
| USFS (USDA Forest Service). 1997. Stream inventory handbook. Version 9.7. Pacific Northwest Region, Portland, OR. | N |
| USFS (USDA Forest Service) and BLM (Bureau of Land Management). 1994. Record of Decision for amendments to Forest Service and Bureau of Land Management planning documents within the range of the northern spotted owl... April 13, 1994. | N |
| U.S. Soil Conservation Service. 1982. Soil Survey Handbook. U.S. Government Printing Office, Washington, D.C. | N |
| WCC (Washington Conservation Commission). 1999. Salmon and steelhead limiting factors analysis, WRIA 29. Olympia, WA. http://www.conserver.org/salmon/LFInquiry.php3?id=29. | N |
| WDF (Washington Department of Fisheries), Washington Department of Wildlife, and Western Washington Treaty of Indian Tribes. 1993. 1992 Washington State salmon and steelhead stock inventory. Olympia. | N |
| WDFW (Washington Department of Fish and Wildlife). 1997. Wild Salmonid Policy. Olympia, WA. | N |
| WDW (Washington Department of Wildlife), Confederated Tribes and Bands, and Washington Department of Fisheries. 1990. Wind River subbasin salmon and steelhead production plan. Columbia Basin System Planning, NPPC, Portland, OR. | N |
| White, G.C., D.R. Anderson, K.P. Burnham, and D.L. Otis. 1982. Capture-recapture and removal methods for sampling closed populations. No. LA-8787-NERP, UC-11. Los Alamos National Laboratory, Los Alamos, NM. | N |
| Young, M.K., W.A., and T.A. Wesche. 1991. Selection of measures of substrate composition to estimate survival to emergence of salmonids and to detect changes in substrate. North American Journal of Fisheries Management 11:339-346. | N |
| Wolman, M.G. 1954. A method of sampling coarse river-bed material. Transactions American Geophysical Union 35(6):951-956. | N |
| Zippin, C. 1956. An evaluation of the removal method of estimating animal populations. Biometrics 12:163-189. | N |

# Section 10 of 10. Key personnel

Name			Employer	Title				Hours to be funded

Thomas Brian Bair 	USFS		Project Fishery Biologist		   688

Duties:  Habitat surveys and restoration, watershed health assessment.

Lee C. Carlson	YN		USFS/Tribal Liaison Biologist	0 (all in-kind)

Duties:  Monitoring of spawning bed sediment

Patrick J. Connolly	USGS		Research Fishery Biologist		2,080

Duties:  Monitoring of steelhead parr populations, watershed health assessment.

Tim R. Cummings	USFWS	Fishery Management Biologist	0 (all in-kind)

Duties:  Smolt monitoring

Susan James		UCD		Watershed Coordinator		2,080

Duties:  Coordination of the Wind River Watershed Council and Technical Advisory Committee, community education and outreach.

James H. Petersen	USGS		Research Fishery Biologist		    40

Duties:  Watershed health assessment, project administration

Daniel J. Rawding	WDFW	Fish Biologist				  640

Duties:  Monitoring of smolt and adult populations, watershed health assessment.

Steve Stampfli		UCD		Manager				  520

Duties:  Project management, community education activities.

Ken Wieman		USFS		Fisheries Program Manager		 1,048

Duties:  Habitat surveys and restoration, watershed health assessment, monitoring of spawning bed sediment.

Resume for:  Thomas Brian Bair

Experience

1992-Present	Project Fishery Biologist, USDA Forest Service, Wind River Ranger District, Carson, WA.

Current Responsibilities: Analyze, plan, design, coordinate and implement instream and riparian restoration projects on the South Zone of the Gifford Pinchot National Forest.

1991-1992	Assistant District Fishery Biologist, Wind River Ranger District, Carson, WA.

1990-1991	Fishery Technician, Flathead National Forest, Kalispell, MT.

1989-1990	Assistant Packer/Fishing Guide, Yellowstone Mountain Guides, Belgrade, MT.

1986-1988	Forest Technician,  North Fork Land Corporation, Big Sky, MT.

Education:		School					Degree and Date Received

Montana State University		B.S. Biology, 1990

Expertise:  My expertise and focus for the last five years has been on stream channel and riparian restoration.  I have been responsible for the analysis, planning, design, partner coordination, budget, contract writing/administration, implementation and monitoring on the South Zone of the Gifford Pinchot National Forest.  During the past five years, I have completed and am currently working on large-scale watershed restoration projects totaling $1.26 million dollars. I have designed and implemented the following types of restoration projects: road obliteration, riparian rehabilitation (planting and thinning), land slide rehabilitation, and channel/flood plain restoration.

Publications and Reports (five most relevant)

Bair, T.B.  1992.  Wind River Ranger District 1992 Anadromous Fish Basin Assessment.  USDA, Forest Service, Gifford Pinchot National Forest.

Bair, T.B.  1993.  Little Soda Springs Restoration Completion Report.  USDA Forest Service, Gifford Pinchot National Forest, Wind River Ranger District.

Bair, T.B.  1994.  Trout Creek Channel Restoration Analysis/Plan. USDA, Forest Service, Gifford Pinchot National Forest, Wind River Ranger District.

USDA, Forest Service.  1995.  Wind River Watershed Analysis.  Gifford Pinchot National Forest, Wind River Ranger District.  T.B. Bair, principal investigator/author of fisheries, stream channel, and riparian vegetation analysis.

Bair, T.B.  1996.  Trout Creek Restoration Monitoring/Completion Report.  USDA, Forest Service, Gifford Pinchot National Forest, Wind River Ranger District.

Resume for:  Lee C. Carlson

Experience

1991-Present	USFS/Tribal Liaison Biologist, Fishery Resource Management Program, Confederated Tribes and Bands, Yakama Nation, Toppenish, WA.

Current responsibilities: Tribal Fisheries program liaison to Gifford Pinchot, Wenatchee, and Okanogan National Forests (YN Ceded Area).

1979-1991	Fishery Biologist, Assistant Fishery Director, Resource Manager; Pyramid Lake Paiute Tribe, Nixon, NV.

1973-1977	U.S. Army

Education:

School						Degree and Date Received

Colorado State University, Fort Collins, CO	B.S.  Biology, 1973

Colorado State University, Fort Collins, CO	2nd B.S.  Fisheries Biology, 1978

Expertise: My primary areas of expertise include salmonid and catastomid culture and habitat protection.  I have conducted water quality monitoring studies in a lake environment, creel census, and lotic fish population sampling.  I have advocated for tribal treaty rights since 1979 and have become versed in the NEPA and FACA processes, especially through participation in the Eastern Washington Cascades, Yakima, and Southwest Washington Provincial Advisory Committees.

Resume for:  Patrick J. Connolly

Experience

1997-Present	Research Fishery Biologist, US Geological Survey, Biological Resources Division, Columbia River Research Laboratory, Cook, WA.

Current responsibilities:  Principle Investigator on research project to monitor juvenile steelhead populations, determine life history aspects, and limiting factors to production in the Wind River watershed (WA).

1994-1997	Consultant to Wind River Restoration Team, WA.

1990-1996	Research Assistant, Oregon State University, Corvallis.

1988-1991	Fish Biologist--Subbasin Planner, Oregon Dept. Fish & Wildlife, Corvallis.

1987-1988	Fish Biologist--Research, Oregon Dept. Fish & Wildlife, Columbia River Research, Clackamas, OR.

1985-1987	Fish Biologist, Beak Consultants Inc., Portland, OR.

1984-1985	Fishery Biologist, U.S. Fish and Wildlife Service, National Fisheries Research Center, Columbia River Field Station, Cook, WA.

1983	Fish Habitat Surveyor, Idaho Transportation Dept., Coeur d’Alene, ID.

Education:

School						    Degree and Date Received

Oregon State University, Corvallis		    Ph.D.  Fisheries Science, 1996

University of Idaho, Moscow			    M.S.   Zoology, 1983

Centre College of Kentucky, Danville		    B.S.    Biology, 1977

Expertise:  The primary areas of my expertise include stream fish ecology and population dynamics.  I have contributed to numerous studies involving anadromous and resident salmonids as well as non-salmonids of the Pacific Northwest.

Publications and Reports (five most relevant)

Connolly, P.J.  1999.  Juvenile steelhead and rearing conditions.  Pages E1-E20 in P.J. Connolly, editor.  Wind River watershed project. Volume I, Project number 9801900, Prepared for: Bonneville Power Administration, Portland, Oregon.

Connolly, P.J., and J.D. Hall.  1999.  Biomass of coastal cutthroat trout in unlogged and previously clear-cut basins in the central Coast Range of Oregon.  Transactions of the American Fisheries Society.  128:890-899.

Connolly, P.J.  1997.  Status of juvenile steelhead rearing in Trout and Panther creeks of the Wind River Basin.  Prepared for:  Washington Trout, Duvall, WA.

Connolly, P.J.  1997.  Influence of stream characteristics and age-class interactions on populations of coastal cutthroat trout.  Pages 173-174 in J.D. Hall, P.A. Bisson, and R.E. Gresswell, editors.  Sea-run cutthroat trout: biology, management, and future conservation.  Oregon Chapter, American Fisheries Society, Corvallis.

Connolly, P.J.  1996.  Resident cutthroat trout in the central Coast Range of Oregon:  logging effects, habitat associations, and sampling protocols.  Doctoral thesis, Oregon State University, Corvallis.

Resume for:  Timothy R. Cummings

Experience

1989-Present	Fishery Management Biologist, U.S. Fish and Wildlife Service, Columbia River Fisheries Program Office, Vancouver, WA.

Current responsibilities: Service representative on Wind River Restoration Team and ESA review for Bull Trout.

1988-1989	Fishery Biologist, U.S. Fish and Wildlife Service, Fort Collins, Colorado.

1987-1988	Computer Aide, TGS Technology on contract to the U.S. Fish and Wildlife Service, Fort Collins, Colorado.

Education:

School					Degree and Date Received

Michigan State Univ., East Lansing	B.S.  Fish and Wildlife Biology, 1983

Colorado State Univ., Fort Collins	M.S.  Fish and Wildlife Biology, 1987

Expertise: My primary areas of expertise include stream fish ecology and habitat restoration.  I have conducted numerous studies on resident and anadromous species.  I have done extensive investigations on the habitat requirements of stream fish species in large and small riverine systems.  In addition, I am well versed in the application of the Endangered Species Act and development of critical habitat designation.

Publications and Reports (five most relevant)

Cummings, T.R.  1996.  Wind River Steelhead Smolt Inventory.  US Fish and Wildlife Service, Vancouver, WA.

Cummings, T.R.  1995.  Wind River Steelhead Smolt Inventory.  US Fish and Wildlife Service, Vancouver, WA.

Cummings, T.R. 1994.  Wind River Fishery Stewardship.  Annual Progress Report.  US Fish and Wildlife Service, Vancouver, WA.

Cummings, T.R.  1992.  Swan Falls Instream Flow Study.  US Fish and Wildlife Service, Vancouver, WA.

Cummings, T.R.  1987.  Brook trout competition with greenback cutthroat trout in Hidden Valley Creek, Colorado.  M.S. Thesis, Colorado State University, Fort Collins.

Resume for: Susan K. Gutenberger

Experience

1996 - Present	Supervisory Microbiologist/ Project Leader, U.S. Fish & Wildlife Service, Lower Columbia River Fish Health Center, Underwood, WA.

Current responsibilities:  Supervise personnel, operations, and studies of a fish health diagnostic laboratory serving seven hatcheries and the Abernathy Fish Technology Center.  Direct field and lab operations for wild fish health surveys in Washington and Oregon.

1993 - 1996	Post-doctoral position and private consultant, Oregon Cooperative Fisheries Research Unit, Oregon State University, Corvallis, OR.

1987 - 1993	Research Assistant, Oregon State University, Corvallis, OR.

1985 - 1986	Research Biologist-technician, Oregon Regional Primate Center, Aloha, OR.

1983 - 1985	Fishery Biologist, U.S. Fish and Wildlife Service, National Fisheries Research  Center, Columbia River field Station, Cook, WA.

1976 - 1983	Research Biologist-Technician, Dept. Veterinary Science, University of Idaho,  Moscow.

Education

School							Degree and Date Received

Oregon State University, Corvallis		Ph.D.  Microbiology, 1993

University of Idaho, Moscow			M.S.    Veterinary Science, 1983

University of Idaho, Moscow			B.S.     Microbiology, Zoology, 1976

Expertise: Research and diagnostics of fish disease in hatchery and wild fish.  Work includes studies on infectious pathology, physiology, immunology, and pharmacology as well as involvement in day-to-day operations of hatcheries and the fisheries of the Columbia Basin.

Publications and Reports (five most relevant)

Gutenberger, S.K., and K. Lujan.  1999 and 2000.  Accomplishment reports, 1998 and 1999, National Wild Fish Health Survey, Lower Columbia River Fish Health Center.  Prepared for:  U.S. Fish and Wildlife Service, Washington office.

Bowker, J., S.K. Gutenberger, M. Peters Swihart, D. Erdahl, and D.Dysart.  1999.  A clinical field trial to evaluate the efficacy of 10 and 14 d administration of oxytetracycline medicated feed to control mortality caused by cold water disease in young coho salmon.  Submitted to FDA for drug approval process.

Gutenberger, S.K., E. Pelton, M. Peters Swihart, K. Lujan, and T. Kerr.  1998.  Annual Report for the Lower Columbia River Fish Health Center.  Prepared for U.S. Fish and Wildlife Service Regional Office and field stations.

Gutenberger, S.K., J.R. Duimstra, J.S. Rohovec, and J.L. Fryer.  1997.  Intracellular Survival of Renibacterium salmoninarum in trout mononuclear phagocytes.  Dis. Aquat. Org.  28:93-106.

Schreck, C.B., and S.K. Gutenberger.  1996.  Effects of balloon tags on physiological indices and swimming performance of chinook salmon juveniles.  Consultation project for private company.

Resume for:  Susan James

Experience

1999-Present	Watershed Coord., Underwood Conservation District, White Salmon, WA.

Current responsibilities:  Coordinate and facilitate meetings of the Wind River Watershed Council and its Technical Advisory Committee.  Coordinate and implement water quality restoration projects.  Conduct water quality monitoring.  Coordinate and implement educational programs in the community and schools.

1998-Present	Project Learning Tree workshop facilitator, Oregon Forestry Education

1997-1999	Park Ranger, Bonneville Lock & Dam, US Army Corps of Engineers

1997		Interpretive Naturalist, Wind River Canopy Crane Research Facility

1996-1997	(seasonal) Amphibian Surveys, Resources NW Inc., Portland, OR

1993-1997	Substitute Teacher, Stevenson-Carson School District

1996		Crew Leader, Scientific Technician II, Spotted Owl Surveys, WDNR

1995-1996	Watershed Analysis Writer & Editor, USDA Forest Service

1995	Wildlife Tech. Assistant. Crew Leader, Spotted Owl Surveys, USDA Forest Service, Mt Adams Ranger District.

1994	Wildlife Tech. Crew Leader, Spotted Owl Surveys, USDA Forest Service, Wind River Ranger District.

1992-1993	Technician I, Spotted Owl Surveys, Beak Consultants Inc. Kirkland, WA

1988-1991	Wildlife / Forestry Technician/ Firefighter (summer seasonal), USDA Forest Service, Mt. St. Helens National Volcanic Monument.

Education:

School							Degree and Date Received:

Washington State University				Master in Teaching	1993

The Evergreen State College				BA 			1991

Certification							Endorsement Areas:

Washington State Teaching Certificate		Biology, Grades 4-12

Elementary Education

Expertise:  My expertise includes working with a variety of ages and abilities of people to promote understanding of scientific principles.  As a teacher, naturalist and park ranger, I have honed my skills working with children, adults, teachers and community members and act as a bridge to facilitate communication and better relations between them and agency personnel.  I also have extensive technical experience conducting scientific surveys in the field, and compiling the data for analysis.  During the past year I have developed skills in the areas of grant writing, water quality monitoring, and design and implementation of on the ground watershed-restoration activities.

Publications and Reports

USDA Forest Service.  1994.  Spotted owl survey summaries.  Unpublished report. Wind River Ranger District, Stabler, WA.

USDA Forest Service Editors.  1996.  Wind River watershed analysis.  Wind River Ranger District, Stabler, WA.  [S. James was a writer and editor].

Resume for:  James H. Petersen

Experience

1995-Present	Research Fishery Biologist, U.S. Geological Survey, Biological Resources Division, Columbia River Research Laboratory, Cook, WA.

Current responsibilities: Project leader on research project to determine survival of summer steelhead over their first winter in the Wind River Basin (WA).  Co-leader on various mainstem Columbia and Snake River projects concerning juvenile salmon passage, predation, and reservoir drawdown.

1994	Acting Director, Columbia River Research Laboratory, USGS, Cook, WA.

1988-93	Research Fishery Biologist, Columbia River Research Laboratory, U.S. Fish and Wildlife Service.

1984-88	Associate Research Curator, Section of Fishes, Natural History Museum of Los Angeles County, Los Angeles, CA.

1983-84	Environmental Scientist, Section of Fishes, Natural History Museum of Los Angeles County.

1977-83	Graduate Teaching Assistant, University of Oregon, Eugene, OR.

Education:

School						Degree and Date Received

University of Oregon, Eugene			Ph.D., Marine Ecology, 1983

University of Queensland, Australia		Rotary Fellowship, 1976

Boise State University, Boise			B.S., Biology, 1975

Expertise:  The primary areas of my expertise include predator-prey dynamics, population dynamics, and application of various modeling techniques to fisheries.

Publications and Reports (five most relevant)

Petersen, J.H.  1994.  The importance of spatial pattern in estimating predation on juvenile salmonids in the Columbia River.  Trans. Am. Fish. Soc.  123:924-930.

Petersen, J.H. and D.M. Gadomski.  1994.  Light-mediated predation by northern squawfish on juvenile salmon.  J. Fish Biol.  45: 227-242.

Petersen, J H., D.M. Gadomski, and T.P. Poe.  1994.  Differential predation by northern squawfish on live and dead juvenile salmonids in the Bonneville Dam tailrace (Columbia River).  Can. J. Fish. Aquat. Sci.  51:1197-1204.

Ward, D.L., J.H. Petersen, and J.J. Loch.  1995.  Index of predation on juvenile salmonids by northern squawfish in the lower and middle Columbia River and in the lower Snake River.  Trans. Am. Fish. Soc.  124:321-334.

Houck, A., B. Kaufman, and J. Petersen.  1995.  Smallmouth bass in the Horseshoe Bend Reach of the San Joaquin River:  Limiting factors and bioenergetic modeling.  Report prepared for Southern California Edison Company, Rosemead, California.

Resume for:  Daniel J. Rawding

Experience

1995-Present	Fish Biologist, Washington Department of Fish and Wildlife, Southwest Region, Vancouver, WA.

Current Responsibilities: As the agency’s steelhead and sea-run cutthroat stock assessment and harvest specialist I am currently responsible for development of  adult and juvenile population estimates from the mouth of the Columbia to the Klickitat River, development and implementation of recovery plans for all Lower Columbia River tributaries and reintroduction plans for the Cowlitz and White Salmon rivers, and development and implementation of mainstem and tributary harvest regulations.

1994	District Fish Biologist, Washington Department of Fish and Wildlife, Region 5, Vancouver, WA.

1989-1993	Fish Biologist, Washington Department of Fish and Wildlife, Steelhead Program, Olympia, WA.

1986-1988	Fish Biologist, U.S. Army Corps of Engineers, Cascade Locks, OR.

1983-1986	Fish Biologist, Washington Department of Fish and Wildlife, Steelhead Program, Forks, WA.

1982-1984	Fishing Guide, Royal Coachman Lodge, Dillingham AK.

1984	Fisheries Technician, Washington Department of Natural Resources, Fish Program, Forks, WA.

1981	Fisheries Technician, U.S. Forest Service, Tongass National Forest, Sitka, AK.

Education:	School						Degree and Date Received

University of Washington, Seattle		B.S.  Fishery Science, 1982

Expertise:  The primary area of my expertise is steelhead and sea-run cutthroat trout biology and management including population dynamics, life history, stream ecology, stock assessment, and harvest management.

Publications and Reports (five most relevant)

Rawding, D.J.  1997.  Stock status update for steelhead in the lower Columbia River, Washington.  Washington Department of Fish and Wildlife.  Olympia, WA.

Hale, D.A., and D.J. Rawding.  1997.  Columbia River Fish Management Plan -- Winter steelhead,  all species review .  Washington Department of Fish and Wildlife.  Olympia, WA.

Rawding, D.J.  1997.  Wind River smolt monitoring report.  Washington Department of Fish and Wildlife, Southwest Washington Region, Vancouver, WA.

Hale, D.A., and D.J. Rawding.  1997.  Annual anadromous gamefish report.  Washington Department of Fish and Wildlife.  Vancouver, WA.

Rawding, D.J., and D.A. Hale.  1996.  Annual anadromous gamefish report. Washington Department of Fish and Wildlife.  Vancouver, WA.

Resume for:  Steve Stampfli

Experience

1988-Present	Manager, Underwood Conservation District, White Salmon, WA.

Current responsibilities:  Guide functions of the district including office management, technical assistance to private landowners and governments on natural resource topics, grant writing and administration, and managing on-ground projects.

1984-1987	Environmental Coordinator, Wharf Resources Inc. Annie Creek Mine, Lead, SD.

1981-1984	Director, South Dakota Department of Water and Natural Resources – Exploration and Mining Program, Pierre.

1980-1981	Mine Reclamation Specialist, South Dakota Department of Water and Natural Resources, Pierre.

Education:

School					Degree Received

Duke University, Durham, NC		Masters of Environmental Management

Colorado College, Colorado Springs	B.A., Biology

Expertise:  Prime topics of expertise include watershed management methodology, disturbed land restoration, environmental monitoring and coordination of various governments and private interests.

Publications and Reports (five most relevant)

Stampfli, S.  1994a.  White Salmon River watershed: basin land-use investigation report.  Underwood Conservation District, White Salmon, WA.

Stampfli, S.  1994b.  White Salmon River watershed: basin water quality investigation report.  Underwood Conservation District, White Salmon, WA.

Stampfli, S.  1992.  Restoration of steep slopes adjacent to roadways in south central Washington.  Underwood Conservation District, White Salmon, WA.

Stampfli, S.  1989.  Water quality survey of Underwood Conservation District, Skamania and Klickitat Counties, WA.  Underwood Conservation District, White Salmon, WA.

Ring, C., S. Stampfli, and B. Parish.  1986.  Broad-winged hawk nesting in the Black Hills of South Dakota.  South Dakota Bird Notes.  Volume 6, Rapid City, SD.

Resume for:  Kenneth Wieman

Experience

1993-Present	Fisheries Program Manager, USDA Forest Service, Wind River Ranger District, Carson, WA.

Current Responsibilities:  Represent Forest Service serving on the Wind River Restoration Team.  South zone fisheries program manager responsible for developing fisheries stream restoration activities.  Project leader on restoration project to evaluate and improve fish passage at Hemlock Dam.  Conduct watershed analysis and environmental documentation for proposed forest management and land development activities.

1990-1993	Assistant district fisheries biologist, USDA Forest Service, Wind River Ranger District, Carson, WA.

1989-1990	Wildlife Biologist USDA Forest Service, Mount Saint Helens National Volcanic Monument, Amboy, WA.

1987-1990	Biological Technician USDA Forest Service, Mount Saint Helens National Volcanic Monument, Amboy, WA.

1986-1987	Student Conservation Association volunteer, Ridgefield National Wildlife Refuge, Ridgefield, WA.

Expertise:  My primary areas of expertise and interest are in stream ecology, habitat evaluation and steam restoration.  I have designed and implemented a number of stream monitoring and evaluation activities.  I have gained considerable fish program management experience including contracting, budgeting supervision and interagency coordination.

Education:

School 		Degree and Date Received

University of Wisconsin-Madison,	B.S.  Biological Aspects of Conservation, 1986

B.S.  Physical Geography, 1986

Publications and Reports (five most relevant)

Wieman, K.  1997.  Restoration of adult fish passage at Hemlock Dam - completion report.  USDA Forest Service, Wind River District, Carson, WA.

Wieman, K, and N. Adams.  (in preparation).  An evaluation of Hemlock Dam smolt passage.  USDA Forest Service, Wind River District, Carson, WA.

Roper, B.B., D. Konnoff, D. Heller, and K. Wieman.  1998.  Durability of Pacific Northwest instream structures following floods.  North American Journal of Fisheries Management 18:686-693.

Conklin, C., and K. Wieman.  1990.  A paired watershed assessment of Canyon Creek and Siouxon Creek.  Report prepared for the Siouxon environmental impact statement. USDA Forest Service, Wind River District, Carson, WA.

Wieman, K.  1987.  The biological response of aquatic macro-invertebrates to Reed’s canary grass management at Ridgefield National Wildlife Refuge.