# Bonneville Power Administration

# FY 2001 High Priority Project Proposal Review

# PART 2 of 2. Narrative

Title:	Evaluate live capture selective harvesting methods for commercial fisheries on the Columbia River.

# Section 3. Project description

a. Abstract

Healthy populations of hatchery spring chinook are expected to return to the Columbia River in spring 2001, intermingled with listed stocks that need protection. In its current form, the commercial gill net fleet will not be able to harvest the hatchery fish because the fishing methods they use are generally lethal and would impose an unacceptably high impact on the wild fish. We are proposing to evaluate live capture selective harvesting methods for commercial fisheries on the Columbia River to provide a fishery where tooth nets and trap nets, live capture gears, are used to harvest marked hatchery chinook while unmarked wild fish can be released to continue their migration. Our experiments will address the catch efficiency of the gears in comparison to conventional gill nets, and will evaluate the survival of released fish. This proposal addresses two criteria for high priority projects: it has measurable, quantitative biological objectives and will result in clear benefits to salmon survival, and it has immediate, measurable benefits to ESA-listed spring chinook. The six considerations identified all apply to this proposal.  This project warrants expedited consideration because we have a time-limited opportunity to test the gears for protecting ESA-listed stocks.  Live capture selective harvesting is recognized by the National Marine Fisheries Service, Washington Department of Fish and Wildlife, Oregon Department of Fish and Wildlife, and Fisheries and Oceans Canada as directly increasing the survival of anadromous fish in the presence of commercial fishing.

b. Justification as high priority

In the Columbia River basin, several stocks of spring, summer and fall chinook are listed as threatened or endangered under the Endangered Species Act. These chinook return to the Columbia River intermingled with healthy stocks of spring chinook and coho returning to hatcheries and lower river spawning sites. The recovery plan for Columbia River chinook includes sport and commercial harvest, so those listed stocks are vulnerable to fisheries targeting the healthy stocks they are mixed with. The remaining commercial salmon harvest on the Columbia River is done by gill net fleets that are managed using time, area, and gear restrictions to minimize catch of listed fish since there is little opportunity to release fish live and unharmed. To protect increasingly numerous weak stocks, the fisheries have been drastically reduced to the point that large quantities of hatchery fish are ending up as surpluses at the hatcheries or on the spawning grounds rather than in the fisheries they were produced to support.

In 2001, we expect the largest runs of spring chinook on record to return to the Columbia River, and a large portion of the lower river hatchery spring chinook will be marked. This provides the potential to distinguish between hatchery and wild fish during harvest operations. In spite of this high return, WDFW and ODFW are unable to increase the harvest on hatchery fish to appropriate levels because of the concurrent increase in impacts to listed fish. There is therefore a clear need to adjust our salmon harvest strategies to meet the biological realities of the Columbia River fisheries. One could argue that the harvest strategy that would provide the maximum benefit to fish and wildlife is no harvest at all. However, this management strategy is not acceptable to WDFW or ODFW and is not condoned by any legitimate management plan for the Columbia River. Rather, there is a renewed commitment to providing sustainable commercial fisheries and we must meet the challenge of implementing these while still protecting weak salmon stocks.

We are proposing to introduce and test tooth nets and a floating trap for live capture selective harvesting of spring chinook in 2001. Tooth nets look similar to a gill net with a small mesh size (3.5” compared to 6-8” in a conventional net) made from multifilament web.  Both gears are fished in the same method and locations, but the similarities stop there.  Unlike a gill net which captures an adult salmon around the head or body, the mesh size of the tooth net prevents adult fish from entering the net that far.  Instead, the fish is caught by the maxillary or teeth and can be released live. Because these gears allow fishers to sort their catch before the fish are dead, they can select which fish are harvested and which are released. Proper implementation of these fishing methods can reduce the impacts on listed fish while still permitting, and hopefully increasing, commercial harvest of healthy stocks of spring chinook and coho. Testing these gears requires a substantial amount of fishing time before full implementation. In 2001, we have an excellent opportunity to test the gears on spring chinook (because they should be abundant) and to allow some harvest with the gears. If we delay our tests, then we will also forego fishing opportunity. We have excellent support from our agencies and commercial fishers to test these gears now as they are well aware of the fishing opportunity they continually forfeit to allow weak stocks to pass upstream.

Live capture selective harvesting is fully recognized by the Canadian Department of Fisheries and Oceans as a legitimate strategy to protect coho. They implemented some measures in 1995, and have not tolerated harvest of coho in any sector since 1998. The potential benefits of live capture selective harvesting are also recognized by NMFS in the updated “All-H Paper” titled “Conservation of Columbia Basin Fish, Draft, Basin-Wide Salmon Recovery Strategy", by the CBFWA in the Fish and Wildlife Program, by WDFW in its Wild Salmonid Policy and by ODFW.

We expect to begin work on this project in March 2001, when spring chinook begin to return to the Columbia River. This evaluation of tooth nets will require comprehensive review and permitting under the Endangered Species Act. ODFW and WDFW are already working with NMFS to obtain the necessary permits. Because of the necessity for protecting listed stocks, we are aware of the importance of coordinating these studies with NMFS.

The success of this study requires considerable participation from local fishing communities. We have already begun discussions with fishers, processors, and commercial fishing organizations and will share our ideas with them even before the project is approved. To date, we have received a favorable response. Awarding fishing contracts, choosing final sites, and preparing gear are long processes that will not be completed if we wait until the final decisions on awarding contracts are made. However, we recognize that these early preparations will be done at the expense of WDFW and ODFW.

c. Rationale and relationship to criteria for high priority projects adopted in the 2000 Fish and Wildlife Program

The objectives of this proposal include measuring the impacts of capture and release from the new gears on the survival of released fish, and will compare this to the survival of fish caught in conventional gill nets. Tests of these gears in other places and for other species show a clear improvement in immediate survival and condition of fish compared to the conventional gill nets. We expect this to result in improved long-term survival and therefore faster recovery of listed or weak stocks and species. Successful completion of all of our objectives will allow us to estimate the actual benefits to ESA listed stocks when live capture selective harvesting is implemented.

Our proposal therefore addresses two criteria for high priority projects; it has measurable, quantitative biological objectives and will result in clear benefits to species survival, and it has immediate, measurable benefits to ESA-listed species. Our project is a collaboration between WDFW and ODFW and has the support of the commercial fishing industry (Northwest Gillnetters Association). WDFW and ODFW are making substantial cash and in-kind contributions to the project.

This proposal is recommended by several action plans. Our objectives address the measures for developing selective fisheries called for in Section 8.2 “Adopt Exploitation Rates and Regimes”, Section 8.3A “Live-catch Technology and Known-stock Fisheries” and Section 8.3B “Selective Harvest Technologies” of the 1994 Fish and Wildlife Program.

In March 1995, the NMFS produced the "Proposed Recovery Plan for Snake River Salmon" which called for the protection of listed species through development of alternative harvest methods in Section 3.4. Specifically, Section 3.4.a recommends the implementation of fishing practices that allow for selective harvest of surplus hatchery production.

Selective fisheries are supported in the 2000 NMFS draft Biological Opinion. Section 9.6.3, “Overview of Harvest Measures” speaks extensively about the development of selective fishing. In particular, Objective 1 of our proposal will directly address action items outlined in Section 9.6.3.2.1 to “estimate incidental mortalities in selective fisheries”. The overall goal of our project, to develop commercial selective fishing on the lower Columbia River is reflected in all four of our objectives and addresses action items described in Section 9.6.3.2.2 “Measures to develop or expand the use of selective fishing methods and gear”.

The federal caucus in their update of the All-H Paper titled “Conservation of Columbia Basin Fish, Draft, Basin-Wide Salmon Recovery Strategy” supports live capture selective harvesting. In section 3.3, “Harvest Actions”, one of the Federal Caucus's recommendations for harvest is to "expand, develop and/or apply alternative, more selective fishery techniques to reduce impacts on listed fish and provide alternative harvest opportunities". Additionally, the Caucus recommends “fishery managers develop a menu of options that includes alternative fishing gear deployment and testing the feasibility and effectiveness of various options”.

In its September 1999 “Extinction is not an option – Statewide Strategy to Recover Salmon”, the Washington State Joint Natural Resources Cabinet recognizes selective fishing as an important component of harvest in Section IV, Core Elements: “Incentives and opportunities for selective commercial fisheries will be implemented in several areas throughout the state; as funding is available, effectiveness of new approaches will be evaluated through increased bycatch monitoring”.

Clearly, developing commercial live capture fisheries is a high priority in these science-based regional fish management goals and programs. Finally, our objectives all require data collection critical for understanding the economic viability of live capture selective harvesting and its effect on non-target species and stocks. Without the data that will be collected in this proposal, we cannot implement a fishery that it truly science based.

d. Relationships to other projects

Over the past several years, Fisheries and Oceans Canada has invested a large amount of money and effort into developing commercial selective fisheries, particularly in the area of gear development. Many of these gears are potentially useful for Washington and Oregon commercial fisheries, and merit extensive testing here. The Canadians have also evaluated other fish friendly fishing and handling techniques such as shorter drifts and the use of recovery boxes before release. The main gap in Canada’s selective fishing effort has been a proper evaluation of the post-release survival of the captured fish.

In 2000, WDFW began evaluating the tooth net as a selective fishing gear in Puget Sound and Willapa Bay. Geraldine Vander Haegen, one of the principle investigators for this study, is leading those projects. Pilot studies on the Columbia River were directed by Patrick Frazier, also a principle investigator on this project, and showed that the tooth net is promising from the point of catching fish and that a comprehensive evaluation is worthwhile. This proposal draws on the experience in all of these projects, and ODFW and WDFW believe the tooth net holds promise for selective live release commercial fisheries on the lower Columbia River. We build on the Canadian experience, the ongoing WDFW study, and recent ODFW test fisheries by specifically evaluating the effect of mesh sizes and soak times on the post-release survival of spring chinook captured in the lower Columbia River. Our results will guide the implementation of selective fishing on the Columbia River. The principle investigators will ensure coordination with other live capture research in the United States and Canada.

We submitted this proposal as an Innovative Project, and request that if that project is approved for funding, or if this project can’t be approved in time to target spring chinook, that this proposal be considered for work on coho that could begin in July to August, 2001. In this case, Objective 1 would have to be modified to accommodate a site that is suitable for returning coho, but Objective 2, 3 and 4 would remain as they are. The same fish management problems plague our commercial coho fisheries as the chinook fisheries. Information learned by testing the gear on chinook will be relevant to, but not a replacement for, tests with coho as the target species. Our highest priority is for spring chinook because of their high economic value, the expected high returns in 2001, and our commitment to recovering upriver chinook populations. We will be glad to work with you to modify the proposal for coho if that becomes an option.

Two other projects related to live capture selective harvesting were submitted as Innovative Projects. While the funding status of those projects is unclear, WDFW and ODFW are committed to cooperative efforts in developing these fisheries. We will coordinate with, and assist those projects in any way we can.

e. Proposal objectives, tasks and methods

The goal of this project is to gather information that would support or refute a decision to implement selective fishing for spring chinook on the Columbia River using a tooth net or trap net. This project is designed to provide information on catch rates, gear handling and survival rates of the released fish. Each piece of information about the tooth net is in comparison to a conventional gill net so that the scientific basis for changing to a different gear is clear. Throughout the project, WDFW will post ongoing work and results on our selective fishing website. At the end of the study, we will publish the results in a scientific journal so they are easily accessible to other scientists and fishers.

The objectives of the project address the measures for developing selective fisheries called for in Section 8.2 “Adopt Exploitation Rates and Regimes”, Section 8.3A “Live-catch Technology and Known-stock Fisheries” and Section 8.3B “Selective Harvest Technologies” of the 1994 Fish and Wildlife Program.

Objectives

Objective 1:	Compare impacts of capture and release from a conventional gill net to capture and release from a tooth net on the long-term survival of adult spring chinook.

Hypothesis 1a:	The percentage of spring chinook counted at Bonneville Dam that pass The Dalles Dam is not significantly different for fish captured with tooth net, with the convention gill net, or trapped in the Bonneville Dam fish ladder.

Hypothesis 1b:	Catch rate of spring chinook or bycatch species will not be significantly different for the tooth net compared to the conventional gill net.

Assumptions:	1.	The use of anesthetic at the dam trap will not significantly affect the post-release survival of spring chinook.

- Tag loss will be equal among the three groups.

- Misidentification or missed tags at the counting windows will be equal among the three groups.

- Changes in migration patterns will be equally affected by each capture method, such that tag recovery patterns will not be biased by the capture method.

- Survival rates between Bonneville and The Dalles dams represent long-term survival rates.

Scope: 	Post-release survival will be evaluated on the mainstem Columbia River in spring, 2001. Marked spring chinook will be tracked from Bonneville Dam through The Dalles Dam and as much of their remaining migration route as possible. This project will not include an evaluation of fecundity in relation to capture and release. Data collection for this objective will occur from March 2001 to June 2001, and reporting will be complete by December 2001.

Approach:	A mark-recapture experiment will be used to compare the post release survival of spring chinook caught in the tooth net to spring chinook caught in gill nets and to controls caught in a trap at Bonneville Dam.

Tasks and Methods

Task 1.1:	Capture, describe, tag and release adult spring chinook in the mainstem Columbia River. Describe bycatch.

Task 1.2	Capture, tag, and release adult spring chinook using the trap in the Washington shore fish ladder at Bonneville Dam.

Task 1.3	Count adult spring chinook with tags passing Bonneville and The Dalles dams.

Task 1.4	Recover tags on spawning grounds, at hatcheries and in fisheries.

Task 1.5	Summarize and analyze dam counts of tagged fish, tag recoveries in subsequent fisheries and escapement areas.

Detailed Methods:

Adult spring chinook returning to the Columbia River will be captured within 5 miles downstream of Bonneville Dam from March through May 2001. Two local fishers will be contracted to fish a net that has 75 fathoms of conventional gill net (7”-8” mesh size) shackled to 75 fathoms of tooth net (3.5” mesh) for about 30 days each. The fishers will provide boats, and we will supply the nets and other associated gear. Two project employees will be on board during each fishing trip to characterize the catch, tag and recover fish. The project employees will work with the fishers to select appropriate fishing times and locations. Before we begin collecting data, all observers and fishers will be trained in fish handling and data collection.

Each set will be timed from the moment the last cork of the net is put in the water to the time the first cork is removed. The exact location (using GPS), the air and water temperatures and times will be noted for each set. As the net is brought in, each fish will be removed carefully from the net and placed quickly into a holding tank, and kept separate by net type where they were captured. The species, length, sex, and condition at capture and at release, based on a 5-tiered system developed in Canada will be noted. A fish will be ranked condition 1 if it is lively and not bleeding, condition 2 if it is lively but bleeding, condition 3 if it is lethargic but not bleeding, condition 4 if it is lethargic and bleeding, and condition 5 if it shows no visible signs of life. Fish that are in condition 1 or 2 at capture will be tagged and released overboard immediately. Fish in conditions 3 through 5 will be held in the holding tank or in recovery boxes designed to facilitate recovery until they either recover to condition 1 or 2 or they die. The time for recovery, and the condition at release will be noted for each fish. Marks and other visible injuries will also be noted for each fish. All dead fish will be donated to local food banks.

Each marked spring chinook will be tagged with a numbered tag that is also color-coded to the gear type it was caught in. The tag number will provide individual information about each fish. Early indications from ODFW statisticians suggest that a minimum of 1000 fish must be tagged from each gear to compare the overall survival, and considerably more fish will have to be tagged to estimate differences in survival by condition at capture. These estimates are based on the expected rate of tag recoveries, and we will continue to work with ODFW and WDFW statisticians to determine the optimal sample size. Indications from the pilot studies suggest that we will be able to capture at least 1000 fish per gear type.

Task 1.1 will provide only a comparison between the two gear types, but will not indicate the survival compared to a fish that was not captured at all. Bonneville Dam has a trap where adults migrating upstream are regularly captured. We will tag some of these fish with a third colored tag to serve as controls for the fish captured in the nets. This way, we can compare the survival of fish from each net type to a baseline survival of spring chinook passing through Bonneville Dam. The standard procedures for trapping spring chinook will be followed, and this includes anesthetizing the fish using clove oil. Each fish will be measured, the sex, marks, visible injuries and other characteristics noted, and then tagged. Fish will be captured and tagged at the trap two to three times weekly during the same time the nets are fished. As noted in task 1.1, we must tag at least 1000 fish from the trap. We will continue to work with our agency statisticians to refine the sample size.

At Bonneville and The Dalles dams, WDFW staff count the number of fish passing by counting windows 24 hours per day. The counters are also able to count the number of fish tagged with a particular type of tag that pass by the window. We have obtained a commitment from this program to count the tags from our study fish. Most of the subsequent tag recovery on spawning grounds, in fisheries, and at hatcheries will rely on existing tag recovery and fish survey programs. Project employees will principally be involved in notifying regional programs where tags may be recovered and tracking tag recoveries from these programs.

Our experiment will provide an estimate of the number of fish passing through Bonneville and the Dalles dams from each capture type. A comparison of the ratios of fish detected at Bonneville Dam to the fish detected at The Dalles Dam will indicate differences in survival between the gear types. Additional recoveries at hatcheries, in fisheries, on spawning grounds and in upstream dams will provide more detailed information about the characteristics at capture that may influence survival. We will work with ODFW and WDFW statisticians to evaluate statistical differences in survival.

Objectives

Objective 2:	Estimate the effects of soak time on catch rate and short-term survival of adult spring chinook captured and released from a conventional gill net and from a tooth net. Describe bycatch.

Hypothesis 2A: The soak time does not affect the short-term survival of adult spring chinook captured and released from a conventional gill net or from a tooth net

Hypothesis 2B: The condition at capture does not affect the short-term survival of adult spring chinook captured and released from a conventional gill net or from a tooth net.

Hypothesis 2C: The catch per unit effort for target and bycatch species is not significantly different between sets with soak times of 10, 20 and 30 minutes.

Hypothesis 2D: The immediate mortality rates of target or bycatch species are not significantly different for tooth net compared to conventional gill net.

Assumptions:	Mortality of all groups is affected equally by handling procedures and the particular net pen the fish are held in.

Scope: 	The effect of soak time on short-term survival and catch rate will be evaluated on the mainstem Columbia River in spring, 2001. “Short-term” refers to 72 hours. Data collection will occur in April and May 2001. Reporting will be complete by December 2001.

Approach:	Spring chinook caught in the tooth net and spring chinook caught in gill nets fished for specific soak times will be held in net pens to evaluate short-term survival. Catch efficiencies will be compared for each soak time. These results will be used to justify constraints placed on commercial fishers to ensure that immediate mortality is minimized during a selective fishery.

Tasks and Methods

Task 2.1	Using 10, 20, or 30 minute soak times, capture, describe, and tag adult spring chinook. Hold the tagged adults in net pens.

Task 2.2:	Summarize results and compare catch efficiency and condition at capture and release by soak time.

Detailed Methods:

In April and May 2001, we will contract two local fishers for about 16 days each to fish nets made from one shackle of conventional gill net and one shackle of tooth net (3.5” mesh) near Skamokawa Washington during April and May. The fishers will provide boats, and we will supply the nets and other associated gear. Two project employees will be on board each fishing trip to characterize the catch, and to tag and recover fish. The project employees will work with the fishers to select appropriate fishing times and locations. Soak times of 10, 20 and 30 minutes will be randomly assigned, but stratified by fisher and week. These soak times will be strictly adhered to.

As in Objective 1, each fish brought on board will be measured, the sex, condition at capture, visible injuries and other characteristics noted. Fish will be handled as in Objective 1, except none will be released. Rather, the fish will be transported in live tanks to net pens near the mouth of Deep River, WA for holding. Each fish will have a numbered tag designating the gear it was caught in, and other individual characteristics. All the fish caught on a given day will be placed into a single net pen, and observed for 3 days. During that time, all dead fish will be removed and the tag numbers noted. Live fish will be released after 3 days. Different tags will be used than in Objective 1 to ensure that there is no confusion between the parts of the study. We will work with WDFW and ODFW statisticians to determine the number of replicates required to properly evaluate each factor.

For each soak time, we will look for significant differences in the condition at capture (which includes immediate mortality) and the catch efficiency using analysis of variance. Additionally, bycatch will be described for each soak time.

Objectives

Objective 3:	Compare the catch efficiency and condition at capture of adult spring chinook salmon caught in tooth nets with mesh sizes from 3-1/2” to 5” and describe bycatch.

Hypothesis 3A:	The difference in catch rates of fish caught in the tooth nets with different mesh sizes will not be more than 5%.

Hypothesis 3B:	The mesh size of the tooth nets will not affect the condition of adult spring chinook at capture.

Assumptions:	If the condition at capture (which includes immediate mortality) is not significantly different between mesh sizes, then the long-term mortality will also be the same.

Scope:	About 20 fishers will participate in the fishery. The fishery will occur on the mainstem Columbia River in areas selected by the fishers. Each fisher will fish for about 10 days and will have to meet strict guidelines for impacts on unmarked chinook.  The fishery will occur between March and May 2001.  Reporting will be complete by December 2001.

Approach:	We will enlist the participation of local fishers to fish gears that are one panel of 3-1/2” mesh tooth net, and one panel of tooth net with the mesh size of their choice within set guidelines (not to exceed 5"). The fishers will keep marked hatchery fish they catch as compensation, but all live unmarked fish will be released. The fishery will be conducted in a competitive manner, with an observer on board.

Tasks and Methods

Task 3.1:	Select fishers to participate in experimental gear permit fishery.

Task 3.2	Fish gears and characterize catch.

Task 3.3	Summarize and analyze data and compare catch and immediate mortality rates by gear type.

Detailed methods:

About 10 fishers from each state will be able to participate in this experimental fishery.  The manner of selecting the fishers will depend in part on the interest we receive from solicitation letters that will be sent in December 2000 to all fishers holding valid licenses for the Columbia River. The selection process will be worked out with ODFW and WDFW fish managers with input from local fisher’s groups (e.g. Salmon for All, Northwest Gillnettter’s Association, and Columbia River Fisher’s Protection Union). Each fisher will have to provide all fishing gear, recovery boxes and pumps, except for a 75 fathom shackle of 3.5” tooth net that will be provided by the project. This material is not locally available and must be ordered several months in advance. The fisher will have to provide another 75 fathom shackle of tooth net with the mesh size of their choice within the specified guidelines.

During April and May, each fisher will be able to fish for about 10 days on a rotating basis. By using a rotating schedule, we can ensure that we have adequate project personnel to place one observer on board during every fishing trip. No trips will occur without observers to monitor the catch. The specific sites fished will be selected in cooperation with project personnel, and will be on the mainstem Columbia River downstream of St. Helens, Oregon. The soak time will be limited to 20 minutes, and the ends of the nets will be switched each set to ensure that both mesh types are fished evenly.

Like every other fishery, this one will have some impact on listed fish. We have begun to work with NMFS and state fish managers to design the fishery with a set impact that would be equally distributed among the fishers. Once the individual impact is reached (for example, a specific number of dead unmarked chinook), the fisher will not be able to continue fishing. Thus, there is considerable incentive for careful fish handling.

As each fish is brought on board, the observer will note which gear it was caught in, the condition at capture and the mark status. All fish will be measured, and unmarked fish either released directly overboard if they are in condition 1 or 2, or allowed to recover until they either die or recover to condition 1 or 2 and can be released. If the fisher is near the limit of his/her impact on unmarked spring chinook, he/she will not be permitted to continue fishing while unmarked fish are being held in the recovery box, to ensure that he/she does not exceed their allowable impact. The observers will work with the fishers to recover fish and to modify or develop fishing and handling methods to improve the condition at capture of unmarked fish.

Fishers will retain marked spring chinook for sale – there will be no restrictions on where they sell fish, or for how much they can sell them. Rather, we will encourage them to develop markets that will realize the full value of a high quality product. To that end, we will also try to schedule the fishing days that will be most beneficial to them from a marketing perspective.

All dead fish will be sampled for coded-wire tags.

With the assistance of ODFW and WDFW statisticians, we will compare the catch efficiency of each alternative gear to the 3.5” mesh size. We will also evaluate the effect of the gears on the condition at capture. The intent of this analysis will be to provide fishers with catch efficiency data that might allow them a choice of mesh sizes provided the condition at capture is acceptable.

Objectives

Objective 4:	Examine the feasibility of using a floating trap net to capture spring chinook in the lower Columbia River.

Scope: A single floating trap will be fished on the mainstem Columbia River to evaluate its potential for live capture of spring chinook. Fishing will occur in April and May 2001, and reporting will be complete by December 2001.

Approach: Fred Hawkshaw, a fisher from BC, developed a floating, drifting trap that was quite successful for catching pink salmon. WDFW purchased a similar trap to evaluate its potential for catching coho on the Naselle River, WA. In this part of the study, we will fish WDFW’s floating trap on the mainstem Columbia River to evaluate its potential as a live capture gear for spring chinook.

Tasks and Methods

Task 4.1	Modify and fish the floating trap, characterize the catch.

Task 4.2	Summarize catch data by species to determine total catch and catch per hour statistics.

Detailed methods:

While working with fishers on the Naselle River and consulting with Fred Hawkshaw, some modifications to the trap were identified that will likely increase its catch efficiency. WDFW will contract with a qualified net manufacturer or fisher to modify the trap before we begin fishing. Because of its size, two boats are required to operate the trap cooperatively; therefore, two local fishers will be contracted to fish the trap in the mainstem Columbia River. An observer will be on board during all trips to characterize the catch (the same data will be collected as in the tooth net studies). Because the fish do not directly contact the net, the condition of fish caught in the trap tends to be excellent, and very low impacts on unmarked fish are expected. Depending on the catch rate and agreements reached with NMFS and state fish managers, fishers may be allowed to sell marked hatchery fish as compensation for fishing.

The catch data will be summarized by species to evaluate catch rates and to compare them to catch rates of the tooth and gill nets fished in this project. The success of this trial will indicate the potential for this trap for catching spring chinook.

f. Facilities and equipment

Vehicles and work areas for field staff will be provided as necessary at existing facilities owned or operated by WDFW or ODFW. ODFW will provide a boat for fishery monitoring purposes and transportation of fish to net pens. The principle investigators have adequate office space, computers and other office equipment at their current locations to meet the needs of this project.  We are requesting two portable computers that the field staff can use to update data each day, and later, for data analysis.  We feel that prompt data entry is critical to keep us and other interested parties up to date with the project’s progress. Both computers will be equipped such that the databases can be e-mailed daily to the principle investigators.

This project budgets a significant amount of money to nets and net pens. These are critical components of the project and are unavailable through either agency.

g. References

None

# Section 4. Key personnel

###### Geraldine Vander Haegen - Principle Investigator, 1/3 FTE

Fish and Wildlife Biologist 4

Washington Department of Fish and Wildlife, Fish Program, Science Division

600 Capitol Way North, Olympia, WA, 98501-1091

Tel: (360) 902-2793		Fax: (360) 902-2943		Email: vandegev@dfw.wa.gov

Duties:	Coordinate activities, review data quality, obtain permits, manage budgets, analyze data consult with statisticians, and prepare reports. Oversee web site maintenance.

Education: 	B.Sc., McGill University, Quebec, 1989

M.Sc., McGill University, Quebec, 1991

Current Employer:		Washington Department of Fish and Wildlife (1994-present)

Current Responsibilities:	WDFW lead for evaluation and development of commercial selective fisheries, evaluation of electronic tag detection, development and evaluation of the automated mass marking machine. Also evaluate methods for improving post-release survival of hatchery fish.

Previous Employers:

Maine Atlantic Sea Run Salmon Commission 1993, 1994

Maine Department of Inland Fish and Wildlife, 1993

Fisheries and Oceans Canada, Science Branch, 1991-1993

Expertise and Experience: I have coordinated and completed several fisheries related research projects with WDFW since 1994. These include an examination of homing by hatchery fish, production and evaluation of triploid salmonids, and evaluating natural rearing techniques for hatcheries. Since 1998, I have been involved in the development of commercial live capture selective fisheries, and am the project lead for evaluating these gears in Washington. I obtained funding for, and implemented selective fishing evaluations in Puget Sound and Willapa Bay in 2000. I also have experience handling and tagging fish, doing statistical analysis, and in report writing and presentation.

Publications:

Vander Haegen, G.E., J.T. Tipping, S. Hammer. 1998. Consumption of juvenile salmonids by adult steelhead in the Cowlitz River, Washington. California Fish and Game. 84/1 (1998),

Cornel, G.E. (later Vander Haegen, G.E.) & F.G. Whoriskey. 1994. The effects of rainbow trout (Oncorhynchus mykiss) cage culture on the water quality, zooplankton, benthos and sediments of Lac du Passage, Quebec. Aquaculture 109(2):101-118.

Patrick A. Frazier- Principle Investigator, 1/3 FTE

Natural Resource Specialist 4

Oregon Department of Fish and Wildlife, Fish Division,

Interjurisdictional Fishery Management Program

17330 SE Evelyn Street, Clackamas, OR, 97015

Tel: (503) 657-2000 ext.253 Fax: (503) 657-2095 Email: patrick.a.frazier@state.or.us

Duties:	Coordinate activities, review data quality, obtain permits, manage budgets, analyze data consult with statisticians, and prepare reports.

Education: B.Sc., Oregon State University, 1981

Current Employer: Oregon Department of Fish and Wildlife, 1982

Current Responsibilities: Program leader for Columbia River Management Program.  The Columbia River Management Program is responsible for updating stock status of Columbia River fish runs, proposing Columbia River sport and commercial fishing seasons through the Columbia River Compact process, representing ODFW on the U.S. v. Oregon Technical Advisory Committee (TAC), and sampling and monitoring all sport and commercial fisheries operating in the Columbia River below McNary Dam.

Expertise and Experience: I have worked in the Columbia River Management Program for 12 years and have considerable experience in managing and sampling sport and commercial fisheries. I have developed a good working relationship with commercial fishers, and have worked with them to develop fishery proposals. I have considerable knowledge about commercial fishing methods. As a program leader, I am responsible for obtaining funding and overseeing implementation of several different studies. I also have experience in performing statistical analyses, preparing reports, and making public presentations.