Project ID:	199104600

Title:		Spokane Tribal (Galbraith Springs) Hatchery Operation & Maintenance

# Section 9 of 10. Project description

a. Abstract

The Spokane Tribal Hatchery project is a key component of a comprehensive program to restore and enhance the fishery in Lake Roosevelt.  The hatchery is operated in conjunction with the Sherman Creek Hatchery, Lake Roosevelt Rainbow Trout Net Pen Rearing and Kokanee Net Pen Rearing Projects to produce kokanee salmon (Oncorhynchus nerka) and rainbow trout (Oncorhynchus mykiss) for release into Lake Roosevelt.  The Lake Roosevelt Fisheries Evaluation Program (Formerly known as Lake Roosevelt Monitoring, Evaluation, Modeling and Data Collection Program) evaluates performance of hatchery production, its effects on Lake Roosevelt biota and facilitates management implications for operating the hatchery and net pen projects.  Initial stocking from 1988 to 1994 focused on kokanee fry releases.  However, monitoring and evaluation data indicated kokanee released as yearlings performed significantly better than fry release specific to survival and adult returns.  In 1995, initial evaluation results and recent established biological objectives resulted in a shift to stocking kokanee yearlings.  The new and current annual target release goal is 1 million kokanee yearlings, 300,000 kokanee fingerlings and 550,000 rainbow trout yearlings for the project area.  In 1999, the combined total fish released by the Lake Roosevelt hatcheries and net pen rearing operations included 808,505 kokanee yearlings, 201,948 kokanee fingerlings, 78,421 rainbow trout fingerlings and 670,601 rainbow trout yearlings.  Since 1988, the principle sport fishery has shifted from walleye (Stizostedion vitreum) to rainbow trout and kokanee, kokanee runs have been established and restored in Lake Roosevelt tributaries and the angler use, harvest rates for kokanee and rainbow trout and the economic value of the fishery have increased substantially.  The current Spokane Tribal Hatchery annual production goal to meet target release goals includes 500,000 kokanee yearlings, 1.3 million kokanee fingerlings and 550,000 rainbow trout fingerlings.  The intention of this project is to continue providing a readily accessible sport fishery as partial mitigation for hydropower–caused fish losses caused by the construction of Grand Coulee Dam.  This project is funded by the Bonneville Power Administration under directives by the Northwest Power Planning Councils Columbia River Basin Fish & Wildlife Program, Resident Fish Substitution Measures from 1987 to 1995.

b. Technical and/or scientific background

Description of Project Area

#### Lake Roosevelt is a mainstem Columbia River impoundment formed by Grand Coulee Dam in 1941.  The reservoir, located in Northeast Washington, inundates 33,490 hectares at a full pool elevation of 393 m above sea level.  Lake Roosevelt has a maximum width of 3.4 km, and maximum depth of 122 m (Stober et al. 1981).  The Spokane Tribal Hatchery is located near the south/eastern region of Lake Roosevelt at Metamooteles Springs (formerly known as Galbraith Springs), which effluent flows into Chamokane Creek, a tributary near the Spokane arm of the reservoir.  The map below illustrates the project area including sites of associated Lake Roosevelt restoration and enhancement projects in the captioned boxes.

Lake Roosevelt Fisheries Scientific Background History

In 1939, construction of Grand Coulee Dam completely blocked and subsequently extinguished anadromous fish runs in the Upper Columbia River.  Prior to this, the Columbia, Spokane and San Poil rivers in the region now occupied by Lake Roosevelt produced large numbers of salmon, steelhead and resident rainbow, cutthroat and bull trout, whitefish and land-locked sockeye or kokanee salmon (Gilbert and Everman 1985; Gangmark and Fulton 1949; Bryant and Parkhurst 1950; Earnest et al. 1966; Fulton and Laird 1967-unpublished; reviewed by Stober et al. 1977, Beckman et al. 1985, Scholz et al. 1986, and Peone et al. 1989).

From the 1940’s to the late 1960’s fishery surveys indicated a prominent population of kokanee salmon were abundant in Lake Roosevelt.  Large numbers of kokanee were reportedly harvested in the forebay of Lake Roosevelt and high gill net and purse seine catches were made in the forebay in 1966 and 1967 by Bureau of Commercial Fisheries personnel (Snyder 1967, reviewed by Stober et al. and Scholz et al. 1986).  There were additional reports of large numbers of kokanee that emigrated through Grand Coulee Dam during this time period.  Interviews of local residents as well as National Park Service and Bureau of Reclamation personnel indicated that there was a salvage fishery for the “tens of thousands to hundreds of thousands” of disabled kokanee in the tailrace of Grand Coulee Dam (Cash 1985).  These observations indicate that ecological conditions after 1939 to the late 1960’s were favorable for successful reproduction and survival of kokanee.

Kokanee abundance declined precipitously, commencing in 1968, after the reservoir was drawn down for the construction of a third powerhouse at Grand Coulee Dam.  The drawdown was thought to negatively effect kokanee in at least two ways; first, through increased entrainment through the dams because of a higher flushing rate; second, by reducing access to tributaries and shoreline areas for spawning (Scholz et al. 1986).  Since completion of the third powerhouse, the magnitude and duration of reservoir level fluctuations has been altered (U.S. Geological Survey reports for water years 1960-1984; reviewed by Scholz 1986).   Analysis of the increased annual drawdown over time, specifically 1941 to 1976, indicated the kokanee decline after 1968 was because reservoir elevations reduced egg and fry survival rates (Stober 1977).

Stober et al. (1977) evaluated the historical drawdown patterns of Lake Roosevelt in relation to spawning and incubation timing of kokanee and concluded that the decline in kokanee during the 1960’s and 1970’s could be explained by the impact of the annual drawdown regime on kokanee reproductive success (Scholz et al. 1985). Since 1968, the reservoir has been operated to produce more power, follow flood control rule curves and meet ESA requirements (1990’s), thus causing lower water elevations and reduced water retention times from winter through spring.  Since kokanee spawn in late fall when water levels are high, maintenance of reservoir levels in winter and spring are critical importance to the normal development of eggs and the early life history stages.  Given these current reservoir operations, any type of natural production to support a sustainable kokanee salmon or fishery would be impossible (Scholz et al. 1986, Peone et al. 1989).

Comparison of zooplankton standing crops in Lake Roosevelt to those of other good kokanee producing lakes indicates zooplankton densities in Lake Roosevelt are greater than, or comparable to, other kokanee lakes (Jagielo 1984, Beckman et al. 1985, Peone et al. 1989, Griffith and Scholz 1990).  Taking into account that kokanee are primarily planktivorous feeders and analyzing the high productivity of zooplankton (e.g., Daphnia sp.), Beckman et al. (1985) estimated the forage base in Lake Roosevelt could support 16 million fingerlings and 5.9 million adult kokanee (Scholz et al. 1986, Peone et al. 1989).

Nigro et al. (1983) determined that 27,200 m of suitable natural spawning habitat was available for kokanee in Lake Roosevelt and tributaries, and calculated that 181,000 adult fish or 5.4 fish/hectare could be produced by natural spawning if the habitat was fully utilized.  Thus, the ability of naturally spawned kokanee to populate the reservoir was far less than the number that could be produced given the food availability in the reservoir.  The primary (phytoplankton) and secondary (zooplankton) biological productivity of the reservoir can support 5.9 million adults, whereas the maximum number that can be produced, if all natural spawning habitat is used, is 0.18 million adults (Scholz et al. 1986, Peone et al. 1989).   The amount of spawning habitat and fluctuating reservoir levels also effect the ability for Lake Roosevelt to sustain an adequate population of rainbow trout as noted by Stober et al. (1977) and Scholz et al (1986).  However, these factors less severely impact the reproductive success of walleye due to a spawning and incubation cycle that compliments reservoir operations (Stober et al. 1977, Beckman et al. 1985 and Scholz et al. 1986).

Development of Lake Roosevelt Fisheries Restoration and Enhancement Projects

In 1986, the Spokane Indian Tribe, Colville Confederated Tribes and Washington Department of Fish in Wildlife (formerly know as Washington Department of Game) proposed the following steps to the Northwest Power Planning Council to restore and enhance the Lake Roosevelt fishery as partial mitigation for hydropower-caused fish losses resulting from the Construction of Grand Coulee Dam:  (1) maintain existing walleye stocks via natural reproduction and strict harvest management controls; (2) enhance kokanee populations via large-scale hatchery stocking and restoring natural production of kokanee in tributaries, and; (3) enhance natural spawning populations of rainbow trout by improving spawning and rearing habitat and passage into tributary streams (Scholz et al. 1986).  The approach to accomplish these objectives included construction of two Lake Roosevelt kokanee salmon hatcheries, improvement of selected tributaries to enhance natural production of rainbow trout and a monitoring program designed to evaluate the effectiveness of the above measures.

As a result, the Northwest Power Planning Council included two kokanee hatcheries, a rainbow habitat improvement project and a program for monitoring and evaluating these Lake Roosevelt fishery restoration measures in its 1987 Columbia River Basin Fish and Wildlife Program.  The measure for the hatcheries included one constructed in 1991 at Galbraith Springs on the Spokane Indian Reservation operated by the Spokane Tribe of Indians (Spokane Tribal Hatchery), and one constructed in 1992 at Sherman Creek (a northern tributary in Lake Roosevelt) operated by the Washington Department of Fish and Wildlife.  Operation of the two hatcheries compliments each other.  Kokanee and rainbow trout eggs are incubated at the Spokane Tribal Hatchery.  Resulting kokanee and rainbow fry are reared to age 0+ and/or 1+ size at the Spokane Tribal Hatchery before: (a) release into Lake Roosevelt following the spring drawdown period, or; (b) transfer to net pen rearing operations and/or the Sherman Creek Hatchery.  Kokanee and rainbow fingerlings/yearlings are reared at these sites and also released into Lake Roosevelt after the spring drawdown period.

In the 1980’s, volunteers from Lake Roosevelt initiated a successful rainbow trout net pen rearing project.  Fingerlings raised by state and federal hatcheries were transferred to net pens in the fall and the volunteers reared the fish to the following spring before release.  Creel surveys performed by Peone et al. (1989) estimated 65,515 rainbow trout were harvested from January to December 1989.  In comparison, Harper et al. (1981) estimated anglers harvested 1,517 rainbow trout from April 15, 1981 to September 15, 1981.  This large increase in harvest was attributed to the net pen rearing program (Peone et al. 1989).  Fishery surveys in 1986 and 1987 conducted by the Upper Columbia United Tribes Fisheries Center indicated net pen reared trout grew in length at rates ranging from 22 to 36 mm/month and anglers caught most of the fish within 14 months after release (Peone et al. 1989).   Prompted by excellent harvest returns and growth rates of net pen reared rainbow trout, as well as insufficient space at state and federal hatcheries, additional space was incorporated in the design of the kokanee hatcheries to rear rainbow trout for the Lake Roosevelt net pen program.  In 1994, the Northwest Power Planning Council implemented the net pen rearing operation in its Fish and Wildlife Program.

From 1988 to 1991, the Lake Roosevelt Monitoring Program began by conducting a baseline evaluation of the fishery before hatchery production.  From 1991 to 1994, the program was conducted to evaluate the effectiveness of the hatcheries and propose management directives.  During the first 4 years (1991 to 1995) of hatchery stocking, the emphasis was for production and release of kokanee fry/fingerlings (age 0+).  However, coded wire tag data and a study to chemically imprint and assess smoltification of hatchery produced kokanee indicated that kokanee released as residualized smolts (e.g. yearlings/age 1+) performed more favorable than the kokanee released as fry/fingerlings (age 0+) (Scholz et al. 1993, Tilson et al. 1994 and 1995).  Additionally, entrainment losses and predation are thought to be a greater factor for kokanee released as fry as opposed to residualized smolts (Tilson et al. 1994 and 1995).  As a result, the hatcheries have shifted from kokanee fry to residualized smolts/yearling releases.   The Lake Roosevelt Monitoring Program is currently conducted to develop a model to predict biological responses to reservoir operation, evaluate the effects of releasing hatchery origin kokanee salmon and rainbow trout on the fishery and evaluate success of various stocking strategies to increase fish harvest while maximizing the return of spawning kokanee to egg collection facilities.

In 1994, the Chief Joseph Kokanee Enhancement Project was implemented into the Council’s Fish and Wildlife Program to evaluate the status of naturally producing kokanee in Lake Roosevelt, determine if there is a stock native to the system, evaluate the use of natural stocks for hatchery production with respect to conservation and/or recovery measures and determine the level of entrainment of fish through Grand Coulee Dam.   While taking into account the necessity of maintaining the genetic integrity of existing stocks, the Chief Joseph Kokanee Enhancement Project and Lake Roosevelt Fisheries Evaluation Project are investigating management implications that may be incorporated into the hatcheries program.   These projects are collecting and analyzing genetic samples from existing Lake Roosevelt kokanee stocks while also performing coded wire tagging studies to differentiate hatchery stocks and analyze their effectiveness (e.g. survival, harvest benefit, return to spawning sites).  Currently, stocks from Lake Whatcom, Kootenay Lake and Lake Roosevelt are used while fishery managers are investigating the most appropriate stock and possible conservation or recovery measures to be taken.   Additionally, the hatchery programs completed Hatchery Planning and Genetic Management Plans in 2001 to address stock selection.  These plans can be found as appendices in the Inter-Mountain Lake Roosevelt Subbasin Summary report (draft form Aug. 2000).

In 1995, the Northwest Power Planning implemented specific biological objectives for mitigating fish losses in the blocked area above Grand Coulee Dam.  The objectives include numerical targets for total adult populations of kokanee, rainbow trout and walleye and goals for harvest and escapement.  The goals and objectives were based upon the theoretical number of fish that could be supported by the primary and secondary productivity of the reservoir (Jagielo 1984, Beckman et al. 1985, reviewed by Scholz et al. 1986), the first 4 years of hatchery production and new data from the Lake Roosevelt Monitoring Program (Peone et al. 1989, Griffith and Scholz 1990 & 1991 and Underwood and Shields 1995).  Included in the objectives is an annual release target goal of 1 million yearling (age 1+ residualized smolts) kokanee and 500,000 age rainbow trout yearlings for Lake Roosevelt.  In order to accomplish this goal, a net pen rearing project for kokanee similar to the rainbow trout net pen program was implemented in 2000 for annually rearing 500,000 kokanee for release into Lake Roosevelt.

At the present time, the hatcheries in conjunction with the net pen programs are operated in accordance to meet these biological objectives in the year 2001.   In terms of enhancing, restoring and conserving natural/native stocks of Lake Roosevelt kokanee (aside from the program objectives noted above), the Spokane Tribe in conjunction with the Lake Roosevelt fishery managers are seeking funding of a feasibility study for the use of spawning channels and streamside incubation, rearing and release of kokanee in tributaries where runs have been restored and where existing stocks are naturally producing.  This technique is used in British Columbia where natural producing kokanee are supplemented with artificial production.

c. Rationale and significance to Regional Programs

Northwest Power Planning Council’s Columbia River Basin Fish & Wildlife Program

The Spokane Tribal Hatchery -- (Galbraith Springs) -- was originally amended under the resident fish substitution section of the Northwest Power Planning Council's 1987 Columbia Basin Fish and Wildlife Program [Sections 903(1)(g)(C)].  The significance of establishing this project to further goals of the Fish and Wildlife Program is exhibited in the Council’s 1987 Five-Year Action Plan where in section 1403(7)(7.3) states that the BPA shall:  "Fund design, construction, operation and maintenance of kokanee salmon hatcheries at Galbraith Springs and at Sherman Creek, starting in Fiscal Year 1988."  (Emphasis added.)  Additional language for the operation and maintenance of this project is included in the resident fish substitution section [10(8)(b)(2)] of the Council’s 1994 Fish and Wildlife Plan (as amended in 1995).

Provincial Review Inter-Mountain Subbasin Planning Process

The fundamental goal of this project adheres to the Council’s Resident Fish Substitution Policies and specifically to Biological Objectives Measures to mitigate for hydropower related fish losses in the blocked area above Chief Joseph/Grand Coulee Dams (see NPPC citations above).   Further more, since this project is in a blocked area where anadromous fish will probably never return and existing populations of naturally producing fish (including native species replica) are limited by reservoir operations (e.g. normal and ESA/Bi-Op mandated salmon flow measures, flood control) this project is identified as a “high priority” to meet the Council’s Fish and Wildlife Program measure’s for Lake Roosevelt as well as the fishery management objectives outlined in the Inter-Mountain Lake Roosevelt Subbasin Summary.  As noted in the summary, fishery management objectives and limiting factors for the Lake Roosevelt fisheries resource necessitates this project in conjunction with the Sherman Creek Hatchery and the Lake Roosevelt Net Pen Rearing (Kokanee and Rainbow Trout) Projects.

All-H Process and Artificial Production Review

This project submitted daft Hatchery and Genetic Management Plans, one each for kokanee salmon and rainbow trout production, as part of the Inter-Mountain Provincial Review Process/Lake Roosevelt Subbasin Summary.  The plans are in draft form due to the incompletion of approved performance standards and indicators addressing risks and benefits of artificial production.  However, an ad-hoc committee is currently reviewing recent ISRP comments and is expected to finalize the performance standards and indicators in 2000.  Once these are established, this project will address them in its plans and incorporate them into the Lake Roosevelt Subbasin Summary.

In terms of hatchery reform measures pursuant to the All-H and Artificial Production Review processes’, final approved reform measures that are applicable to this program will be addressed and implemented as required.  Funding for performing a feasibility study of enhancing natural producing Lake Roosevelt kokanee populations is currently being sought through the All-H process.   An initial aspect of enhancing natural producing and possibly native populations of Lake Roosevelt kokanee includes the use of spawning channels and streamside incubation, early rearing and release.  This is a proven technique used in British Columbia.

d. Relationships to other projects

Collaborative Agencies

The Spokane Tribal Hatchery project is a result of collaborative efforts, dating from 1985 to the present time, between the Bonneville Power Administration, Spokane Tribe of Indians, Colville Confederated Tribes, Upper Columbia United Tribes Fisheries Research Center, Eastern Washington University Biology Department, Washington Department of Fish & Wildlife, National Park Service, Lake Roosevelt Fisheries Development Association and the Lake Roosevelt Forum.

Related Northwest Power Planning Council’s Projects

The Lake Roosevelt fisheries restoration and enhancement program consists of a series of Northwest Power Planning Council Fish & Wildlife projects that work collaboratively to achieve common management objectives established in the Council’s Fish & Wildlife Program and the Provincial Planning Process/Inter-Mountain Subbasin Summary.

These projects and their association include the following:  (a) Spokane Tribal Hatchery, Sherman Creek Hatchery, and Lake Roosevelt Rainbow Trout and Kokanee Net Pen Rearing Programs - operate in conjunction with each other to annually produce 1 million kokanee yearlings, 300,000 kokanee fingerlings and 550,000 rainbow trout yearlings for release into the project area; (b) Lake Roosevelt Fisheries Evaluation Program (Formerly known as Monitoring/Data Collection Program) - serves as a monitoring and evaluation mechanism for the hatcheries and net pen projects; (c) Lake Roosevelt Rainbow Trout Habitat and Passage Improvement and Evaluation Project - promotes natural production of Lake Roosevelt rainbow trout by improving passage for migrating adults and instream habitat for fry and fingerling rearing in selected tributaries; (d) Chief Joseph Kokanee Enhancement Project - monitors entrainment of fish through Grand Coulee Dam, evaluates measures to ensure self-sustaining natural/native populations of kokanee in Lake Roosevelt and is responsible for determining the feasibility of using these fish in the kokanee hatcheries program; (e) Phalon Lake Wild Rainbow Trout Program – evaluates local redband and/or native stock use for the Lake Roosevelt fishery program; (f) Ford Hatchery Improvements – capital improvements to allow production of kokanee for Banks Lake, (g) Banks Lake Monitoring and Evaluation Program – baseline fisheries study and evaluation of hatchery kokanee stocking and; (f) Resident Fish Stock Status Above Chief Joseph and Grand Coulee Dams - compiles resident fish data useful to fisheries management for waters in the project area, identifies data gaps and collects appropriate data to fill those gaps.

Information Coordination and Program Direction Process

The restoration and enhancement program directives, per project, are facilitated through the Lake Roosevelt Fisheries Coordination Team (also/previously known as the Hatcheries Coordination Team).  This team is comprised of applicable fishery agency personnel from the Spokane Tribe of Indians, Colville Confederated Tribes and Washington Department of Fish & Wildlife who have expertise in fishery management and extensive knowledge of regional goals and objectives.  These group of managers meet quarterly, or as needed, to coordinate their programs and exchange information.

Public and Local Government Agencies Information Sharing Process

Information from these projects is channeled to the public and local government agencies through the Lake Roosevelt Forum.  The Lake Roosevelt Forum consists of management agencies, public and private groups that have concerns relating to the environmental and economic integrity of Lake Roosevelt.  The forum facilitates quarterly and annual meetings between the public, federal, state and tribal agencies to present current data and exchange information about the program through an open panel and discussion process.

Additional Support and Peer Review

Throughout the duration of these projects, the Department of Biology from Eastern Washington University Department has supported all of the above Lake Roosevelt fisheries restoration efforts.  Currently, professionals from University aid the hatcheries in collection of mature Lake Roosevelt kokanee for spawning and analyze the kokanee coded wire tag returns. Additionally, Dr. Allan T. Scholz and Dr. Ross Black, Icthyology and Limnology professors at Eastern, peer review applicable portions of this program in collaboration with the Lake Roosevelt Fisheries Evaluation Project.  Comments and recommendations by the University are facilitated through the Lake Roosevelt Fisheries Coordination Team via the Lake Roosevelt Fisheries Evaluation project.

e. Project history (for ongoing projects)

Project History, Implementation & Cost

After implementation of the Pacific Northwest Electric Power Planning and Conservation Act in 1980, Scholz et al. (1986) on behalf of the Spokane Tribe of Indians, Colville Confederated Tribes and Washington Department of Fish & Wildlife, investigated the feasibility of restoring and enhancing the Lake Roosevelt fisheries to partially mitigate hydropower caused fish losses resulting from the construction of Grand Coulee Dam.  The investigation included extensive review of existing literature as well as a fishery and limnological survey study of Lake Roosevelt and its tributaries.  The investigation resulted in the formulation of fisheries restoration and enhancement measures (Scholz et al. 1986) for Lake Roosevelt centered around artificial propagation of kokanee salmon (Peone et al. 1989).  In 1986, the Spokane Tribe of Indians submitted an application for amendment to the Northwest Power Planning Council (NPPC) for implementation into its 1987 Columbia River Basin Fish and Wildlife Program (FWP).  The application was approved by NPPC and amended into the Resident Fish Substitution Section of the FWP. In section 903 measure (g)(1)(c), the NPPC directed the BPA to “fund the design, construction, operation and maintenance of two kokanee salmon hatcheries: one at Galbraith Springs (Spokane Tribal Hatchery) and one at Sherman Creek.  The Sherman Creek Hatchery will be used as an imprinting site and egg collection facility to provide a source of kokanee fry for: i)stocking into Banks Lake and ii) transferring to Galbraith Springs (Spokane Tribal) Hatchery for rearing to fingerling size before planting into Lake Roosevelt.  Decisions on hatchery production, stocking and outplanting locations will be coordinated by a three member committee consisting of one representative each appointed by the Confederated Tribes of the Colville Reservation, the Spokane Tribe of Indians, and the Washington Department of Game” (NPPC 1987).  Additionally, the NPPC continued this language in their 1993 Phase IV Amendments [Section 9.4A(1)(d)] and 1994 FWP [Section 10.8B(5)].

In 1988, a three-member committee identified in the project measure was formed and designated as the Lake Roosevelt Hatcheries Coordination Team (this group is now structured as the Lake Roosevelt Fisheries Coordination Team).  On June 7, 1990, the Spokane Tribe of Indians and the Bonneville Power Administration entered into a 25-year agreement for funding the design, construction, operation and maintenance of the Spokane Tribal Hatchery.  Construction of the Spokane Tribal Hatchery began in 1990, was completed in April of 1991 and the facility officially dedicated on June 7, 1991.

In terms of cost, this program in conjunction with Sherman Creek Hatchery and Lake Roosevelt net pen projects, are responsible for a thriving economic base surrounding the sport fishery established through its efforts.  In 1985, six years before these projects began stocking fish, a U.S. Fish and Wildlife survey estimated the economic value of the Lake Roosevelt fishery at $2.8 million (Beckman et al. 1985).  More recent surveys estimate an annual range from $5.3 to $12.8 million, owing in large part to these projects (Peone et al. 1989, Griffith and Scholz 1991, Thatcher et al. 1993).   In 1998, the economic value of the Lake Roosevelt fishery was estimated at $8.0 million (Underwood et al. 1998).  In contrast, it costs the Bonneville Power Administration approximately $700,000 annually to operate the hatcheries and net pens.  The beneficial return to the surrounding area directly owing to these projects is unquestionable.

Project Results Summary:

The table below lists the number of fish the Spokane Tribal Hatchery has produced for stocking into the project area.   The data is separated by the number actually stocked by the Spokane Tribal Hatchery and the number transferred to Sherman Creek Hatchery and Lake Roosevelt net pens for rearing and acclimation before release into Lake Roosevelt.  Rainbow trout fingerlings transferred to the Sherman Creek Hatchery, which is done in the summertime period, are later transferred to Lake Roosevelt net pens in the fall.  This frees up rearing space at the Spokane Tribal Hatchery for rearing 500,000 kokanee fingerlings for transfer to Lake Roosevelt net pens in the fall and carry over 500,000 fingerlings for release as yearlings/post-smoltification the following year.

| Number fish stocked into project area by Spokane Tribal Hatchery, 1991 to 1999. |
| --- |
| Year | Kokanee Fingerlings | Kokanee Yearlings |
| 1991 | 1,674,577 | 0 |
| 1992 | 819,220 | 71,256 |
| 1993 | 1,024,293 | 21,190 |
| 1994 | 540,220 | 29,111 |
| 1995 | 515,425 | 59,825 |
| 1996 | 0 | 54,194 |
| 1997 | 381,513 | 40,808 |
| 1998 | 823,844 | 84,066 |
| 1999 | 201,948 | 149,922 |
| Number fish transferred to Sherman Creek Hatchery for stocking into the project area, 1991 to 1999. |
| Year | Kokanee Fingerlings | Kokanee Yearlings | Rainbow Trout Fingerlings |
| 1991 | 0 | 0 | 0 |
| 1992 | 1,099,000 | 68,552 | 0 |
| 1993 | 635,267 | 72,508 | 0 |
| 1994 | 1,087,161 | 90,881 | 60,534 |
| 1995 | 0 | 210,634 | 120,325 |
| 1996 | 0 | 224,562 | 146,380 |
| 1997 | 0 | 220,191 | 150,801 |
| 1998 | 349,832 | 294,532 | 0 |
| 1999 | 0 | 372,534 | 294,042 |
| Number fish transferred to Lake Roosevelt Net Pens for stocking into the project area, 1991 to 1998. |
| Year | Kokanee Fingerlings | Rainbow Trout Fingerlings |
| 1991 | 33,510 | 326,461 |
| 1992 | 0 | 424,395 |
| 1993 | 40,305 | 446,798 |
| 1994 | 0 | 288,046 |
| 1995 | 164,328 | 288,739 |
| 1996 | 50,899 | 430,473 |
| 1997 | 261,092 | 403,382 |
| 1998 | 294,186 | 311,594 |
| 1999 | 201,200 | 350,784 |

For the most part, this project has followed through with fish production as called for in the annual operating plans.  However, during the first seven years the hatchery water supply limited the carrying capacity.  In 1998, a new production well was constructed and an existing well was rehabilitated which has allowed the hatchery to produce 100% of the fish as outlined in the 1998 operating plan.  Also, in order for this program to achieve its target goals, it is reliant on the Sherman Creek Hatchery and Lake Roosevelt net pen projects (existing rainbow and recently implemented kokanee net pens).

Monitoring, Project Reports and Technical Papers

Monitoring and evaluation is of necessity.  The hatchery programs effect on the Lake Roosevelt fishery, as well as management implications, are under constant review by the Lake Roosevelt Fisheries Evaluation Program.  Results of the evaluation program continue to indicate the impact of the hatchery and net pen programs have been beneficial to restoring and enhancing the Lake Roosevelt fishery while not negatively impacting wild (natural & native) stocks within the lake.  Results for the past 9 years of monitoring and evaluation can be found in the annual reports:  Peone et al. 1989; Griffith and Scholz 1990; Thatcher et al.  1991 & 1992; Scholz et al. 1992; Tilson and Scholz 1991 through 1998; Underwood et al. 1993 through 1995; Cichosz et al. 1996, and; Underwood et al. 1997 through 1999(in print).  Technical reports summarizing the Spokane Tribal Hatchery fish production and accomplishments on a monthly and annual basis are submitted to the Bonneville Power Administration (Peone 1994 through 1999-in print).  These reports are submitted to the BPA for hard copying and distribution.  Electronic filling of the reports in the BPA Library/Fish & Wildlife web page will begin in 2000.

Adaptive Management Implications

Lake Roosevelt fishery investigations performed 1986 to present have determined artificial production is necessary to restore kokanee salmon and rainbow trout populations.  The primary implication associated with the survival of fish in Lake Roosevelt, including natural producing populations and hatchery stocked fish, is reservoir operations and its effect on the limited suitable spawning habitat, (Peone et al. 1989; Griffith and Scholz 1990; Thatcher et al.  1991 & 1992; Scholz et al. 1992; Tilson and Scholz 1991 through 1998; Underwood et al. 1993 through 1995; Cichosz et al. 1996, and; Underwood et al. 1997 through 1999 - in print).  Management strategies have changed since the beginning of this program to off set adverse reservoir operations.  For example, releases of kokanee salmon fry/fingerlings (age 0+) has changed to yearlings/post-smolt releases to reduce entrainment and predation.  This has increased higher survival and adult return of hatchery produced kokanee.  In terms of enhancing natural producing populations of kokanee in Lake Roosevelt, contingent upon funding, a feasibility study on the use of spawning channels and streamside incubation may begin in 2001.   Funding for this project is currently being sought through the Federal All-H process.

In terms of adaptive management concerning prudent hatchery practices, this project regularly implements prudent and sound fish culturing techniques and strategies.  For example, a direct oxygen injection system was constructed to compensate unfavorable water conditions (temp. and volume) that was limiting hatchery carrying capacity.  Incidentally, this hatchery was the first one actually be designed and constructed by the Bonneville Power Administration using the previously BPA partial-funded Cabinet Gorge Hatchery as a model.  Additionally, in 2000 this project will be investigating water development measures to increase water supply to the hatchery.  This may include the addition of a new well or re-use system.  Recent technological advances in re-use systems are impressive.  Any changes in hatchery design or operation will be evaluated in consideration of hatchery reform measures applicable from the artificial production review process.

f. Proposal objectives, tasks and methods

Project Goal, Objectives and Tasks

The goal of this project is to aid in the restoration and enhancement of the Lake Roosevelt fisheries.  In consideration of this and the Council’s Fish Resident Fish Substitution measures and policies (including artificial production review and reform), the hatchery program is dedicated to assure its effects on Lake Roosevelt ecological conditions and fish populations are compatible with native species recovery guidelines.  The objective of this project is to produce kokanee salmon and rainbow trout to continue providing a readily accessible sport fishery in Lake Roosevelt.

This project submits an annual operating plan to the Bonneville Power Administration that details the objectives to assure that guidelines are prudent to normal fish hatchery practices.  The annual operating plans include directives by the Lake Roosevelt Fisheries Coordination Team.  Listed in the section below are the objectives and tasks to be employed by this project to meet its FY 2000 production goals.

OBJECTIVE 1.  EGG COLLECTION, SPAWNING AND INCUBATION OF 1.2 MILLION KOKANEE EGGS AND 625,000 RAINBOW TROUT TO MEET 2001 APG.

Task 1.1  Brood stock capture and holding at Little Falls Dam and Hawk Creek:	Kokanee brood stock capture and holding at Little Falls Dam (LFD) will depend on the return size.  A fish trap with a holding/rearing raceways, constructed in 1998 below the tailrace of LFD, will be used for collecting adult kokanee for spawning.  Natural produced kokanee will be separated from hatchery fish, distinguished by missing adipose fins, for spawning   Kokanee will also be collected from Hawk Creek during their fall spawning migration.  A temporary fish weir and collection box will be installed in the creek to collect kokanee spawners migrating upstream.  A seasonal worker will be employed to maintain and keep the trap secure.  Mature fish will be spawned on site and the eggs will be transferred to the STH.  This project will be coordinated with the National Park Service and WDF&W.

Task 1.2  Kokanee egg collection from Sherman Creek:  Collection of kokanee spawners from Sherman Creek will be coordinated by the WDF&W.  Kokanee will be spawned on site and the water hardened eggs will be transferred to the STH.

Task 1.3 Egg allotments:  As a safeguard of the success of collecting eggs from fish returning to Lake Roosevelt Kokanee, a request for 1.2 million kokanee eggs will be requested from the Washington Department of fish and Wildlife and British Columbia Ministry of Fisheries.  In addition, 625,000 rainbow trout eggs will also be requested from WDF&W as a normal procedure for meeting our production goal for the net pen program.

Task 1.4  Infectious hematopoietic necrosis (IHN), infectious pancreatic necrosis (IPN) and viral hemorrhagic septicemia (VHS) virus sampling of Lake Roosevelt Kokanee:  Mature female kokanee captured in Lake Roosevelt will be tested for presence of IHN, IPN and VHS viruses.  Samples of ovarian fluid, spleen and kidney tissue will be collected from approximately 60 ripe females.  In collecting samples, an incision will be made from the anal fin to the isthmus and a separate syringe used to extract ovarian fluid from egg skeins.  Whole spleen and kidney tissue will be collected and kept on separate vials.  Samples will be chilled on ice and delivered to the WDFW pathology laboratory in Olympia, WA., where they will be analyzed by WDFW personnel.  Collection and delivery of samples will be coordinated with WDFW pathologist, Steve Roberts.  If any samples are tested positive, then Lake Roosevelt eggs will either be restricted from entering the hatchery facilities or incubated in isolation buckets.  If all samples are tested negative, WDFW will notarize a Fish Health Certificate.

Task 1.5  Egg enumeration and incubator loading:  Fertilized eggs will be disinfected before entering the Spokane Tribal Hatchery as a precaution in case Lake Roosevelt kokanee contain disease.   Eggs in each chest cooler will be bathed in a 100 part per liter Argentine solution (Piper et al. 1987) for approximately 15 minutes and then rinsed with clean water.  The Von Bayer method will be used for enumeration of eggs.  This method is efficient and considered the least stressful technique of enumerating eggs (Piper et al. 1982).  Vertical flow incubators (Heath Trays) and cylindrical upwelling incubators (upwellors) will be used for egg incubation.  Loading rate for the verticle flow incubators will be 12,000 eggs per verticle flow tray (7 trays in each stack) while upwelling incubator loading rates will be 67,000 rainbow eggs per unit and 100,000 kokanee eggs per unit.  Total anticipated incubator use will be 2 verticle flow incubator stacks and 16 upwelling incubators.

OBJECTIVE 2.  FRY AND FINGERLING REARING METHODS TO MEET 2001 APG.

Task 2.1  Incubation and hatching kokanee and rainbow trout:  Water will be drawn from the production well for incubating and hatching kokanee and rainbow eggs.  The water temperature from this source remains steady at 10(C during this time of year.  In respect to this, approximately 31 days or 558 centigrade temperature units (CTU’s) are expected for hatching the kokanee and rainbow eggs (Piper et al. 1982).  The number of days to egg eye-up, hatch and fry emergence, as well as daily water temperature will be recorded.  At 90% swim-up, kokanee fry will be released from the upwelling incubators by simply removing the lids and letting the fry swim out into the raceways.  At about the same life stage, rainbow fry will be released by removing the lids and pouring the fry into the raceways.  Mortality rates will be recorded throughout the incubation period and swim-up stage.

Task 2.2  Feeding and production of kokanee and rainbow trout:  Feed training of kokanee and rainbow trout will begin at the 90% swim-up stage.  The following feeding projections are based on a relatively constant temperature of 10(C.  Feeding rates and amount will change with varying water temperatures and will actually be calculated on a daily amount basis determined from monthly growth rates recorded from the Spokane Tribal Hatchery, 1991 to 1998.  Bio-diet starter (moist) will be used for feed training kokanee fry, while silver cup starter (dry) will be used for feed training rainbow fry.  For feed training, both species of fry will be fed 3 to 4% body weight 8 times per day.  Bio-diet grower and silver cup dry trout feed will be used for production feeding.  A frequency of five feedings per day will be performed during production.

OBJECTIVE 3.  IDENTIFICATION OF 2001 DISTRIBUTION DATES AND LOCATIONS FOR OUTPLANTING/TRANSFERRING KOKANEE AND RAINBOW TROUT.

Task 3.1  Transfer of 255,000 kokanee yearlings to the Sherman Creek Hatchery:  Approximately 255,000 kokanee averaging 10 fish per pound will be transferred to the Sherman Creek Hatchery in April 2001.  At a loading rate of 1,500 pounds per haul, approximately 17 trips will be required.

Task 3.2  Outplanting 85,000 kokanee yearlings into the Spokane Arm of Lake Roosevelt:  Approximately 80,000 kokanee yearlings averaging 8 fish per pound will be outplanted into the Spokane Arm of Lake Roosevelt in June 2001.  The main outplanting sites will be the Blue Creek and Owl Creek (known as “A-Frame”) tributaries.  Approximately 8 trips will be required to outplant these fish.

Task 3.3  Outplanting 300,000 kokanee fingerlings into Banks Lake:  Approximately 300,000 Kokanee fingerlings averaging 200 fish per pound will be outplanted into Banks Lake in June 2001.  At a loading rate of 500 fish per haul, 3 trips will be required to plant these fish.  Planting will be coordinated with the WDF&W.

Task 3.4  Transfer 500,000 kokanee fingerlings to Lake Roosevelt net pen rearing operations:  Lake Roosevelt net pens will receive 80,000 kokanee fingerlings by October 1, 2001.  The fish are expected to be 50 per pound in size and will require 20 trips to each site.  Kokanee transferred to the pens will be marked with coded wire tags and adipose fin clips prior to transfer.

Task 3.5  Hold 500,000 kokanee fingerlings for planting in 2002:  Approximately 500,000 kokanee fingerlings will be held over at the STH for outplanting in 2002.  A planting schedule for these fish will be developed during the 2001 LRHCT meetings.

Task 3.6  Transfer of 30,000 rainbow trout to the Kettle Falls summer net pen rearing program:  Approximately 30,000 rainbow fingerlings averaging 45 fish per pound will be transferred to the Kettle Falls net pen rearing operation in July 2001.  Transfer of these fish will require 2 trips.

Task 3.8  Transfer 150,000 rainbow trout to Sherman Creek Hatchery:  Approximately 150,000 rainbow fingerlings averaging 45 fish per pound will be transferred to the SCH in July 2001.  At total of 4 trips will be required to transfer these fish.  The SCH will hold these fish for later transfer to fall net pen rearing operations at Kettle Falls and Hall Creek.  The STH will assist in the later transfer to the pens.

Task 3.9  Transfer of 360,000 rainbow trout to fall FDR net pen rearing operations:  Approximately 360,000 rainbow fingerlings averaging 25 fish per pound will be transferred to Lake Roosevelt Net Pen rearing sites at Keller Ferry, Seven Bays, Two Rivers and Hunters from September 15 to November 1, 2001.  Each site will have 4 net pens (16 total) and will receive approximately 16,500 fish each.  A total of 15 trips will be required to transfer these fish.  Transfer dates will be coordinated with the Lake Roosevelt Development Association Net Pen Coordinator.

OBJECTIVE 4.  DETERMINE THE REARING VOLUME, WATER QUANTITY AND QUALITY NECESSARY TO MEET THE 2001 APG.

Task 4.1  Raceway loading for fry, fingerling and adult rearing:  A maximum volume of 24,320 cubic feet (ft3), or 40 raceways, rearing volume will be used to produce the 2000 APG.  Fish will be loaded in raceways relative to a density index of 0.5 (or less) and spread out as they increase in size.

Task 4.2  Regulation of water inflow during incubation:  Upwelling incubators containing un-eyed eggs will be supplied with 5-8 gallons per minute (gpm) per incubator until eye-up and then increased to 12-15 gpm until swim-up.  Vertical flow incubators containing un-eyed eggs will be supplied with 5 gpm per incubator until eye-up and increased to 8 gpm until swim-up.  The maximum water inflow needed should be 450 gpm (1.01 cfs) during incubation.

Task 4.3  Water inflow regulation during fry, fingerling and adult rearing: Water inflow required during fry, fingerling and adult rearing will be calculated using a flow index of 1.5 associated with projected lengths and weights in the following formula:

I =       W      			where:	I = total inflow

L x 1.5				W = projected weight

L = projected length

This formula, as well as size estimates, will be entered into a computer program as needed for determining water volume needed.

Task 4.4  Monitoring water quality during fry and fingerling rearing:  Daily temperatures ((C) will be recorded and used in determining feeding amounts and raceway loading rates.  Dissolved oxygen (DO) is expected to be near 100% saturation level (10 to 12 mg/l) while nitrogen (N2) levels should remain below 100% saturation level.  Packed column aerators in the head box should produce acceptable D.O. and N2 levels.  However, D.O. will be measured with a YSI meter and N2 levels will be measure periodically with a WEISS saturometer.  Other parameters monitored by the hatchery manager will include pH, conductivity, ammonia, nitrate and nitrite salinity and total settleable solids concentration in the hatchery effluent.  At least two broad spectrum analysis of water quality will be contracted to an EPA certified laboratory.

Task 4.5  Raceway hygiene:  Raceways will be sanitized and disinfected with 600 parts per million solution of Hyamine 3500 before initial incubator loading and transfer of fry to raceways.  Daily raceway sanitization of fecal matter will be performed when production feeding begins.  All waste water will be drained to the settling pond.

Task 4.6  Routine cleaning of spring pond waters:  The spring ponds will be routinely cleaned as needed using a vacuum/trash boat.  The cleaning will help keep algal and macrophyte densities at a low level to assure a clean water source flowing into the hatchery.

OBJECTIVE 5.  ADIPOSE CLIP KOKANEE SALMON BEFORE RELEASE INTO LAKE ROOSEVELT.

Task 5.1  Kokanee fin clipping:  Seasonal workers will clip all (approximately 960,000) adipose fins on kokanee fry and fingerlings prior to release into Lake Roosevelt.   Up to 3 fin clippers and 1 experienced supervisor will be employed for approximately 6 months to perform this task.  Fish will be sedated in a mix of salt and anesthetic, weighed for enumeration and adipose fins clipped using surgical type scissors.  Appropriate data for monitoring and evaluation will be collected.  Fin clipping will compliment coded wire tagging administered by the Lake Roosevelt Monitoring Program and facilitated by the Spokane Tribal Hatchery crew.

OBJECTIVE 6.  MAINTENANCE OF HATCHERY BUILDING AND GROUNDS, VISITATION IMPROVEMENTS AND CULTURAL PRESERVATION.

Task 6.1  Routine hatchery maintenance:  Routine maintenance of the hatchery building and grounds will be performed by hatchery personnel.  This includes painting, net and screen mending, lawn mowing, vehicle maintenance and building cleaning.

Task 6.2  Visitation improvements:	Additional visitation area will be improved for public use.  This will include adding educational and informative displays such as our fish mitigation efforts, fish hatchery management and natural resource preservation.

Task 6.3  Cultural Preservation:  A display illustrating the cultural significance of the Metamooteles Springs area will be put up near the visitors center and cultural sensitive sites identified during pre-hatchery construction archeological surveys.  If possible, we plan on working with the Spokane Tribal Cultural Department to build pit house and camas oven replicas near the cultural sensitive sites.

g. Facilities and equipment

The Spokane Tribal Hatchery, which is actually the first fish hatchery designed and constructed by the BPA, is a state of the art facility with modern fish production equipment.  The hatchery consists of 44 indoor/outdoor raceways with 26,752 cubic feet of rearing space, utilizes ground and surface water, incubates using self fabricated upwelling units, employs sophisticated oxygenation system and uses modern fish handling and transportation equipment.  The hatchery has a laboratory consisting of microscopes (phase contrast and dissecting), analytical balances, fish necropsy tools, centrifuge and microbiology equipment.  The grounds surrounding the hatchery include a visitor’s center, picnic and cultural interpretive center (under development).

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Beckman, L.G., J.F. Novotny, W.R. Persons, and T.T. Terrell. 1985. Assessment of the fisheries and limnology in Lake F.D. Roosevelt 1980-1983. U.S. Bureau of Reclamation. Contact No. WPRS-0-07-10-x0216; FWS-14-06-009-904, May 1985. 168 pp. | No |
| Bryant, F.G. and Z.E. Parkhurst. 1950. Survey of the Columbia River and its tributaries. Part IV. U.S. Fish and Wildl. Serv. Sci. Rep. Fish. No. 37. 99-108 p. | No |
| Cichosz, T.A., J.P. Shields, K.D. Underwood, A.T. Scholz, and M.B. Tilson. Lake Roosevelt Fisheries and Limnological Research, Annual Report 1996. Bonneville Power Administration. Portland, OR. Project No. 94-043 331 pp. plus Appendices. | No |
| Earnest, D.E., M.E. Spence, R.W. Kiser and W.D. Brunson. 1966. A survey of the fish populations, zooplankton, bottom fauna, and some physical characteristics of Roosevelt Lake. Rep. to Wash. Dept. of Game. 46 p. | No |
| Fulton, L.A. and M.C. Laird. No date. A cursory survey of tributaries to Roosevelt Lake with reference to spawning potential for salmon, 1965-66. Rough draft if unpublished mimeo report NOAA, Nat. Marine Fish. Serv., Seattle, WA. 100 pp. | No |
| Gangmark, H.A. and L.A. Fulton. 1949. Preliminary surveys of Roosevelt Lake in relation to game fishes. U.S. Fish and Wildl. Service Spec. Sci. Rep. Fish. No. 5. 29 p. | No |
| Jagielo, T. 1984. A comparison of nutrient loading. Phytoplankton standing crop, and trophic state in two morphologically and hydraulically different reservoirs. M.S. Thesis Univ. of Wash., Seattle, WA 99 p. | No |
| Nigro, A.A., T.T. Terrell and L.G. Beckman. 1981. Assessment of the limnology and fisheries in lake F.D. Roosevelt. Annual Rep. 1981. USFWS. 97 p. | No |
| NPPC. 1987. Columbia River Basin Fish and Wildlife Program—Amended February 11, 1987. Northwest Power Planning Council, Portland, OR. 246 pp.+ Appendices. | No |
| Peone, J. 1997. Colville Confederated Tribes Fish and Wildlife Department, Letter to Mr. Bernard Shanks, WDFW., May 21, 1997. | No |
| Peone, T. and D. Ford. 1997. Spokane Tribal Hatchery, January 1997 to December 1997, Annual Report. Bonneville Power Administration. Portland, OR. Project No. 91-46. Contract DE-MS79-90BP92906. 18 pp. plus Appendices. | No |
| Peone, T.L., A.T. Scholz, J.R. Griffith, S. Graves, and M.G. Thatcher. 1990. Lake Roosevelt Monitoring Program, August 1988 to December 1989, Annual Report. U.S. Department of Energy, Bonneville Power Administration. Project No. 88-63, Contract DE-817 | No |
| Piper, R.G., I.B. McElwain, L.O. Orme, J.P. McCracen, L.G. Fowler and J.R. Leonard. 1982. Fish Hatchery Management. U.S. Department of Interior, Fish and Wildlife Service, Washington, D.C. 517 pp. | No |
| Scholz, A.T., J. Uehara, J. Hisata and J. Marco. 1986. Feasibility report on restoration and enhancement of Lake Roosevelt Fisheries. Northwest Power Planning Council. Applications for Amendments Vol. 3:1375-1489. | No |
| Scholz, A.T., R.J. White, V.A. Koehler and S.A. Horton. 1992. Measurement of thyroxin concentration as an indicator of the critical period for imprinting in kokanee salmon (Oncorhynchus nerka). Annual Report 1991. BPA. Portland, OR. Proj. No. 88-63 | No |
| Scholz, A.T., R.J. White. M.B. Tilson and S.A. Horton. 1993. Artificial imprinting of Lake Roosevelt kokanee salmon (Oncorhynchus nerka) with synthetic chemicals. Annual Report 1993. BPA Proj. No. 88-63 | No |
| Stober, Q.J. 1977. Fishery resource study of Rufus Woods Reservoir. In: Erickson, A.W., Q.J. Stober, J.J. Brueggeman and R.L. Knight: An assessment of the impact on fish and wildlife resources from construction of a third powerhouse at Grand Coulee Dam | No |
| Stober, Q.J., R.W. Tyler, C.E. Petrosky, T.J. Carlson, C. Gaudet and R.E. Nakatoni. 1977. Survey of fisheries resources in the forebay of FDR Reservoir, 19765-1977. Fisheries research institute, Univ. of WA. Final Rep. to USBR Contr. No.14-06-100-9001 | No |
| Stober, Q.J., R.W. Tyler, E.F. Cowman, J. Wilcock and S. Quinnell. 1979. Irrigation drawdown and kokanee salmon egg to fry survival in Banks Lake. Univ. of Wash. College of Fisheries. Fish. Res. Inst. 73 p. | No |
| Stober, Q.J., and R.W. Tyler. 1982. Rules curves for irrigating drawdown and kokanee salmon. (Oncorhynchus nerka) egg to fry survival. Fisheries Res. 1: 195-218 p. | No |
| Thatcher, M.G., J.R. Griffith, A.C. McDowell, and A.T. Scholz. (In press submitted 1993). Lake Roosevelt Fisheries Monitoring Program, Annual Report 1992. Bonneville Power Administration. Portland, OR. Project No. 88-63. 237 pp. plus appendices. | No |
| Thatcher, M.G., J.R. Griffith, A.C. McDowell, and A.T. Scholz. (In press submitted 1993). Lake Roosevelt Fisheries Monitoring Program, Annual Report 1991. Bonneville Power Administration. Portland, OR. Project No. 88-63. 237 pp. plus appendices. | No |
| Tilson, M.B., A.T. Scholz, R.J. White and J. Galloway. 1994. Thyroid Induced Chemical Imprinting in Early Life Stages and Assessment of Smoltification on Kokanee Salmon. Annual Report 1994. BPA. Project No. 88-63. | No |
| Underwood, K.D. and J.P. Shields. 1996. Lake Roosevelt Fisheries Monitoring Program, Annual Report 1993. Bonneville Power Administration. Portland, OR. Project No. 88-63. | No |
| Underwood, K.D. and J.P. Shields and M.B. Tilson. 1997. Lake Roosevelt Fisheries Monitoring Program, 1995 Annual Report in K.D. Underwood and J.P Shields. Lake Roosevelt fisheries research, 1995 annual report. Bonneville Power Administration. | No |
| Voeller, A.C. 1996. Measurements of Lake Roosevelt Biota in Relations to Reservoir Operations. Annual Report 1993. Bonneville Power Administration. Portland, OR. Project No. 94-43. 109 pp. | No |

# Section 10 of 10. Key personnel

###### RESUME

TIM L. PEONE,  HATCHERY MANAGER

EDUCATION

Eastern Washington University; Cheney, WA; 1988.

**Bachelor of Science in Biology (3.0 GPA).

EMPLOYMENT EXPERIENCE

07/90 - Present

Spokane Tribal Hatchery, Ford, Washington.

Hatchery Manager.  Duties include management of daily fish culturing of 3 million kokanee salmon and 500,000 rainbow trout.  Budget and contract writing.

10/88 - 07/90

Upper Columbia United Tribes Fisheries Center, Department of Biology, Eastern Washington

University, Cheney, Washington.

Fisheries Biologist.  Duties include the collection and spawning of kokanee at Little Falls Dam, culturing of kokanee eggs in incubates at Galbraith Springs, and field training and release of kokanee fry.

06/88 - 12/88

Upper Columbia United Tribes Fisheries Center, Department of Biology, Eastern Washington

University, Cheney, Washington.

Fisheries Biologist.  Duties include developing the monitoring programs research proposal and contract, coordination from the collection and analysis of creel survey fisheries, zooplankton and water quality samples, supervising field and laboratory personnel, and responsible for reporting BPA by monthly progress and annual reports.

Wtr 1988

Idaho Department of Fish and Game; Cabinet Gorge Kokanee Salmon Hatchery; Clark Fork, Idaho.

Hatchery Internship.  Duties include selection and spawning of brood stock, spawning of kokanee eggs, culturing and fungal treatment of eggs, and quantification of fertilized eggs.  Extensive overview of the hatchery design and year round hatchery operations discussed.

Wtr/Spr 1987

Washington Department of Wildlife Rainbow Trout Hatchery; Spokane, Washington.

Hatchery Internship.  Duties included spawning, culturing and fungal treatment of rainbow trout eggs, food training and fish grading or rainbow trout fry and release of juvenile rainbow fingerlings.

MEMBERSHIP ON REGIONAL COMMITTEES

Columbia Basin Fish and Wildlife Authority (CBFWA), Resident Fish Committee Member, 1989.

UCUT representative participating in review and evaluating resident fish program measures, identify impacts on resident fish caused by hydro-power development, and assisting CBFWA in prioritizing resident fish research protection and mitigation needs.

PUBLICATIONS AND TECHNICAL REPORTS

1994-97	        Peone, T.  Annual Reports of the Spokane Tribal Hatchery.  Prepared for Bonneville

Power Administration, Division of Fish & Wildlife (Contract No.: DE-MS79-90BP92906; Project No.: 91-046).

1995	Peone, T.  Kokanee Captive Brood Investigations at the Spokane Tribal Hatchery.  Prepared for 	1995 International Kokanee Workshop.

1990	Peone, T., A.T. Scholz, J.R. Griffith, M. Thatcher, D. Brown, L. Hill, and C. Abrahamson.  Lake Roosevelt Monitoring Program: July 1988-December 1989.  Annual Report.  Upper Columbia United Tribes Fisheries Center.  Submitted  Bonneville Power Administration (Project No. 88-63).

1989	Peone, T., A.T. Scholz and J. Griffith.  Kokanee Salmon investigation as at Grand Coulee Reservoir (Lake Roosevelt).  In: Proceedings of the symposium on Native American Fisheries, Western Regional Conference, American Fisheries Society. 24 p.

1989	Scholz, A.T. and T. Peone.  Assessment of rainbow trout net pen program in Lake Roosevelt, WA.  Submitted N. Amer. J. Fish. Mgmt.

Project Duties:   Manages and supervises fish hatchery and staff, applying knowledge of management and fish culturing techniques.  Determines, administers, and executes policies relating to administration, standards of hatchery operation, and maintenance of facilities.  Modifies and/or changes working conditions and use of equipment to increase efficiency.  Budget and contract writing.  Confers with Biologists and other fishery personnel obtain data concerning fish habits; food and environmental requirements; and techniques for collecting, fertilizing, incubating spawn, and treatment of spawn and fry.  Participates in various committees, teams and forums that pertain the management and coordination of this resource.

Other Key Personnel:

Fish Culturist II, Assist. Mngr. - Delbert Brown

Fish Culturist II - James Andrews

Office Manager/Assist. Fish Culturist I - Darla Ford

Part-time Seasonal Fish Culturist I - Jayne Abrahamson

Resumes will be provided upon request for the aforementioned employees.