Project ID:	199506325

Title:	Yakima/Klickitat Fisheries Project Monitoring And Evaluation

# Section 9 of 10. Project description

a. Abstract

The YKFP is an effort to increase natural production and harvest opportunity of salmon and steelhead in the Yakima and Klickitat Subbasins using supplementation and habitat improvements. The project includes all stocks historically present in both basins. Currently, stock-specific plans are at widely differing levels of development: Yakima coho and fall chinook programs are in feasibility stages, while Yakima steelhead and all Klickitat programs involve only habitat/life history inventory, passage improvements and stock-status monitoring. The most complete program is the upper Yakima spring chinook supplementation program (Busack et al. 1997).

We will monitor each program in terms of natural production, harvest, genetics and ecological interactions. Studies of defined statistical power in these areas will guide project adaptive management and provide critical information for regional enhancement efforts. Expected outcomes include evaluations of:

·	Impacts on natural production of targeted stocks;

·	Ecological impacts on nontarget stocks;

·	Identification of factors determining success or failure for each program.

·	Relative survival between different experimental groups of hatchery fish and between hatchery fish and wild conspecifics.

Project success is defined as a significant increase in natural production with limited adverse impacts on non-target stocks.  Natural production is monitored in terms of natural origin recruits and its components (adult reproductive performance and survival from egg to fry, fry to smolt, and smolt to adult). Genetic impacts will be monitored in terms of domestication and within- and between-population variability. Ecological impacts on nontarget stocks will be monitored by comparing abundance, size structure, geographic distribution and interaction indices before and after supplementation.  Impacts of nontarget species on project fish will be assessed by indices of predation, competition, prey abundance, mutualism and disease.

b. Technical and/or scientific background

The Yakima Subbasin is located in south central Washington The city of Yakima is the largest and centrally located in the subbasin. The subbasin includes most of Yakima and Kittitas counties as well as small portions of Benton and Klickitat counties. The Yakima Nation Reservation is located in the southwest corner of the subbasin just south of the city of Yakima.  The Yakima River drains an area of 15,900 square km (6,155 square miles) contains about 3058 km (or about 1,900 river miles) of perennial streams. Originating near the crest of the Cascade Range above Keechelus Lake, the Yakima River flows 344 km (214 miles) southeastward to its confluence with the Columbia (RM 335.2).

Prior to 1850, spring chinook, as well as other stocks of anadromous fish, were much more abundant in the Yakima Subbasin than they are now.  Before the ocean and lower Columbia exploitation of salmon and steelhead in the late l9th century and early 20th century, and before the valley was developed, the Yakima supported large runs of spring, summer and fall chinook, summer steelhead, coho and sockeye.  Sockeye and summer chinook are now extinct in the subbasin.  Currently, due to efforts of the YKFP the number of naturally produced coho is increasing in the subbasin.  Historic spring chinook runs to the Yakima may range from a high of approximately 250,000 fish (Smoker 1956) to 202,500 (Mullan 1983).  Historic adult fall and summer chinook production in the Yakima Subbasin may have ranged from 250,000 (Smoker 1956) to 202,500 (Mullan 1983).  Estimates of historic steelhead run range from 100,000 fish (Smoker 1956) to 81,000 (Mullan 1983).  Estimation of the historic magnitude of the sockeye run is difficult, as the run was eliminated before counting stations were established.  However, Mullan (1986) presented statistics from which we estimated the historic sockeye run size to be between 103,000 – 211,100 adult sockeye salmon.

Presently, adult salmon and steelhead returns to the Yakima River are approximately two orders of magnitude lower than estimated historic returns.   The five-year average (1996-2000) number of steelhead, spring chinook, fall chinook, and coho to the Yakima River is 1,059, 6,146, 1,551, and 3,374 fish respectively.

Meaningful restoration of salmon and steelhead runs in the Columbia Basin ultimately requires a return to “normative” conditions throughout the basin (Williams et al., 1996), or at least to a much more normative state.  Because of the enormous societal obstacles and economic costs that constrain it, such an effort will take decades to implement and additional decades to take effect. Therefore interim measures, such as supplementation, are required to maintain fish runs for the foreseeable future.

The YKFP is in the process of planning and implementing habitat restoration and preservation projects that are prioritized through the Ecosystem, Diagnosis and Treatment Model (EDT).  A preliminary limiting factors analysis for Yakima Subbasin salmon and steelhead has been summarized in the Yakima Subbasin Summary, and will be refined by an ongoing EDT analysis.  EDT analysis has already identified high priority reaches and tributaries for preservation and restoration.  A number of restoration projects have recently been initiated based on this prioritization.  Ultimately the YKFP will comprise a series of complimentary habitat restoration and supplementation/reintroduction projects targeting all species historically present in the subbasin.

Supplementation is a cornerstone of efforts to rebuild salmon and steelhead runs throughout the Columbia Basin (RASP 1992; NPPC 1994; CRITFC 1995; ISAB, 1998).  In the Yakima Subbasin, supplementation seems particularly promising because it has been shown theoretically (Busack and Knudsen, in press) that populations of low productivity (viz., subjected to high levels of density-independent mortality) are optimal candidates for supplementation, as are populations subject to high levels of predation (Peterman 1987; McIntyre et al., 1988).  Such conditions characterize salmon and steelhead populations in the Yakima Subbasin (Dunnigan and Lamebull 2000; McMichael et al. 1998; Fast et al. 1991, Anonymous 1990). There are, however, concerns that supplementation might fail because of the following factors: poor smolt-adult survival (Miller et al. 1990; Steward and Bjornn 1990), poor reproductive success (Fleming and Gross 1992; Chilcote et al. 1986), adverse genetic change (Busack and Currens 1995; Reisenbichler 1997; Waples et al. 1990; Hindar et al. 1991; Waples 1991), adverse ecological impacts on target and nontarget species (Shoals and Hillock 1979; Collis et al. 1995; Shively et al. 1996; Hillman and Mullan 1989; Peery and Bjornn 1996; Nickelson et al. 1986; Hillman 1989; Reeves et al. 1987; Mullan et al. 1992; Swain and Riddell 1990; Tabor et al. 1993; Ward et al. 1995; Wood 1987) and diminished primary and secondary productivity attributable to the removal of salmon carcasses from streams (Johnston and Ringler 1979;  Michael 1995; Bilby et al. 1996; Levy 1997).

Table 1 summarizes the scope of ongoing and future YKFP monitoring activities, as well as current monitoring readiness and the significance of findings to date (summarized in Section e).  A comprehensive monitoring plan addressing all of the preceding considerations has been developed for upper Yakima spring chinook (Busack et al. 1997).  Stock-specific monitoring plans based on the spring chinook template will be developed for all other stocks, and plans for Yakima coho and fall chinook are in progress.  Because it was the first, the Yakima spring chinook plan is self-sufficient and exhaustive in scope.  Funding limitations may preclude explicit evaluation of every potential issue for other Yakima stocks.  Monitoring plans for other stocks will entail extrapolation from spring chinook findings.  Where appropriate, facility sharing (e.g., smolt and adult counting facilities) and an emphasis on performance, and risk monitoring will occur.

The YKFP monitoring program is a descendant of a number of earlier projects.  The general elements of a monitoring plan were first outlined in the YKFP’s 1993 Project Status Report (BPA 1993).  These ideas were transformed into specific measures in the Yakima Fisheries Project Spring Chinook Supplementation Monitoring Plan (Busack et al. 1997). The completion of Planning Status Reports for Yakima coho and fall chinook (YN, unpublished documents) represents initial steps in the development of comprehensive monitoring plans for these stocks.  Other efforts that have contributed to the evolution of the monitoring program include: the Yakima Spring Chinook Enhancement Study (Fast et al. 1991); genetic stock identification and genetic risk issues (Busack 1990; Busack et al. 1991; Busack and Currens 1995; Currens and Busack 1995; Kapuscinski and Miller 1993); power analysis for OCT/SNT comparisons (Hoffmann et al. 1994); semi-natural rearing treatment development (Maynard 1995); baseline hatchery/wild interaction studies (Pearsons et al. 1993 and 1996); Chandler smolt trap passage studies (Neeley 1992; Sanford and Ruehle 1996; Neeley 2001); reproductive success (Berejikian et al. 1997); spring chinook natural production objectives/strategies (Watson 1993); Yakima flow/survival studies (Yakama Nation, unpublished data); and project-specific marking methods (Schroder and Knudsen 1996).

| Table 1. Potential scope of YKFP Monitoring Effort. The first letter (I or i) in each cell indicates how much information has been acquired in the area, and the second (M or m) indicates the readiness level of monitoring procedures. Regarding information, a capital “I” indicates monitoring has been occurring for some time and significant findings have been obtained. A lower-case “i” indicates newly-initiated monitoring activities, and/or activities which have yet to generate significant findings. Regarding monitoring readiness, a capital “M” indicates ongoing monitoring activity or one for which facilities and procedures are in hand to begin monitoring immediately. A lower-case “m” indicates a complete monitoring procedure can be described at the conceptual level, but cannot currently be implemented because certain key elements (e.g., facilities) are missing. A minus sign (-) indicates either a total lack of information or monitoring readiness, respectively, depending on whether it occurs in the first or second position. |
| --- |
|  | Yakima Spring Chinook | Yakima Fall Chinook | Yakima Coho (naturalized) | Yakima Steelhead |
| Natural Production | Smolts per spawner | IM | im | iM | IM |
|  | Smolt/adult survival | IM | Im | -M | IM |
|  | Relative hatch/wild survival | -M | -m | -M | -m |
|  | Optimal Spawning Distribution | IM | im | -m | IM |
|  | Relative Hatch/Wild Spawning Behavior | -M | -m | -m | -m |
|  | Relative Hatch/Wild progeny per parent | -M | -m | -m | -m |
|  | Hatchery rearing regime defined | IM | im | im | -- |
|  | Impact of environmental factors | im | im | -m | im |
| Harvest | In basin | IM | iM | iM | IM |
|  | Out of basin | -m | im | iM | im |
| Genetics | Extinction Risk | im | im | -m | im |
|  | Within population variability | IM | IM | iM | IM |
|  | Between population variability | IM | IM | -m | IM |
|  | Domestication | -m | -m | -m | -m |
| Ecological Interactions (re. hatchery fish) | Interactions with nontarget taxa | IM | Im | IM | Im |
|  | Interactions with strong interactors | IM | Im | Im | Im |

c. Rationale and significance to Regional Programs

From its inception, monitoring has been a critical element of the YKFP.  The Yakima/Klickitat Fisheries Project was identified in the 1982 Columbia River Basin Fish and Wildlife Program (Measure 704(i)(3) and 904(e)(1).  A draft Master Plan was presented to the Northwest Power Planning Council in 1987 and the Preliminary Design Report was completed in 1990. In both cases the NPPC instructed the managers (YN and WDFW) to carry out planning functions that addressed uncertainties in regard to the efficacy of supplementation in the areas of meeting production objectives and limiting adverse ecological and genetic impacts.  At the same time, the Council underscored the importance of adaptive management in project implementation. The 1994 FWP again reiterated the importance to proceed with the YKFP because of the added production and learning potential the project would provide.  In 1997, a comprehensive conceptual monitoring plan for the Yakima spring chinook portion of the project was developed (Busack et al.  1997), which addresses most of the objectives and tasks for all YKFP target stocks.  The YKFP is unique in having been designed to rigorously test the efficacy of supplementation. Given the current dire situation of many salmon and steelhead stocks, and the heavy reliance on artificial propagation as a recovery tool, YKFP monitoring results will have great Region-wide significance.  Consequently, the project is developing a website and other tools for rapid and efficient dispersal of project results.

Another unique aspect of the YKFP is the fact that EDT analysis is being used to design and improve enhancement programs for all species and stocks.  Particular emphasis is placed on reconstructing the structure and function of the historic ecosystem (the “Template”).  The Template represents the definition of normative habitat conditions for the Yakima Subbasin.  Project scientists are in the process of prioritizing portions of the subbasin of greatest preservation value and restoration potential.  The EDT model will also be used to identify reach-specific habitat actions with the greatest potential to compliment supplementation.

As stated in the Yakima Subbasin Summary, the fundamental need for the Yakima Subbasin is to restore normative structure and function to aquatic and terrestrial habitat to the greatest degree practicable.  This overall need includes the following seven components: 1) Restore/preserve floodplain connectivity, 2) Restore normative flows, 3) Restore access to historical production areas to all life stages of resident and anadromous salmonids, 4) Restore normative water quality to basin streams, 5) Restore and preserve riparian communities and normative watershed function, 6) Restore normative ecological interactions among target species and aquatic communities in all portions of the basin, and 7) Protect and restore native fish and wildlife populations by increasing or maintaining productivity.

The YKFP will implement enhancement and restoration activities addressing issues in components 1-5 that are identified by the EDT process.  The YKFP has implemented monitoring and evaluation programs to evaluate ecological interactions and productivity described in components 6 and 7.  Specifically, component 6 (ecological interactions) entails monitoring in the following areas:

1) Predation on juvenile salmonids and exacerbating conditions, e.g. high temperatures, non-normative flows, introduction of exotic species and instream structures (dams and bypass outfalls) that increase the vulnerability of juveniles.

2) Possible constraints on fish and wildlife production attributable to limited availability or accessibility of habitat and/or food.

3) Impaired production of fish and wildlife attributable to the scarcity or elimination of mutualists and/or keystone species.

4) Possible constraints on fish and wildlife production associated with pathogens.

Component 7 identifies the need to increase productivity of native fish and wildlife populations, and therefore implies monitoring the abundance and survival rates of targeted populations.  The restoration of normative habitat conditions will substantially improve the productive capacity of the Yakima Subbasin, but will likely take many years to accomplish.   Therefore there is an interim need for artificial production to increase the productivity of existing fish populations.  Artificial production is also essential to restore extirpated species to the Yakima Subbasin.

d. Relationships to other projects

This project, “Yakima/Klickitat Monitoring and Evaluation”, and the following four projects comprise the entirety of the YKFP:  “YKFP Management, Data and Habitat”, Project 198812025, “YKFP Operations and Maintenance” Project 199701325, “YKFP Design and Construction”, Project 198811525 and “WDF&W Policy/Technical involvement and planning in YKFP”, Project 199506425.

Except for one element, this project completely covers YKFP monitoring activities.  The exception, smolt physiology monitoring, is provided by Dr. Walt Dickhoff and colleagues under Fish and Wildlife Program (FWP) project 9200200, “Physiological Assessment of Wild and Hatchery Juvenile Salmonids”.

FWP habitat improvement projects (both YKFP and others) in the Yakima Subbasin relate to this project, as they will influence the quality of the aquatic environment.  Project 199705100, “Yakima River Side Channel Survey” and “Yakima River Side Channel Restoration”, are intended to correct one of the most serious environmental problems in the upper Yakima: the lack of fry rearing habitat provided by side channels.  A series of riparian and instream flow enhancement projects targeting streams in or bordering the Yakama Nation Reservation – and therefore primarily benefiting steelhead – include project 199803400: “Re-establish Safe Access into Tributaries of the Yakima Subbasin”, project 199803300 “Restore Upper Toppenish Creek Watershed”, project 199705300 “Toppenish /Simcoe instream flow restoration and assessment”, project 199901300 “Ahtanum Creek Watershed Assessment”, and project 199603501 “Satus Creek Watershed Restoration”.  Projects, (“Upper Yakima Tributary Irrigation Improvement”) and 5510900 (“Teanaway River Instream Flow Restoration”) both attempt to restore adult and juvenile passage to upper Yakima tributaries dewatered or blocked by irrigation diversions.  The Teanaway project is especially important because an acclimation site will be located on the North Fork of the Teanaway River.  Finally, projects 9105700 and 9200900 provide funds for the WDFW Yakima screen shop and the Yakima Project Office of the Bureau of Reclamation (BOR) to build and maintain screens on irrigation diversions and to maintain fisheries monitoring and enhancement facilities (fish ladders, the Chandler and Roza smolt traps, the Roza adult trap, etc.) owned by the BOR.

e. Project history (for ongoing projects)

YKFP M&E is now a consolidation of nine earlier YKFP monitoring projects. The old project numbers and titles are listed below. All objectives and tasks in the current YKFP M&E Project are covered in the summary below. For the sake of clarity, we have included the current objective and task number along with the previous project number and title. The project history and accomplishments are summarized for each of the current objectives and tasks.

Project 9506300, “Yakima/Klickitat Monitoring and Evaluation Program”, 1995 – 1998. The implementation phase of this project basically began in 1997. Consequently most of the many papers and reports it will generate have yet to be completed or published. This project has, however, already led to significant developments in the following areas: Chandler Juvenile Monitoring Facility (current Objective 1 task f). Species-specific passage estimators have been developed and are being refined. Procedures to estimate confidence intervals around passage estimates from 1983 to present have also been developed. This facility is the only site available in the Yakima Subbasin to estimate natural smolt production. An essential element of monitoring fisheries enhancement in the Yakima is the detection of significant changes in natural smolt production. Therefore this monitoring task must be considered a long-term activity. Indirect predation (current Objective 4 task c). Survival from Prosser to McNary Dam for the years 1998-2000 has been indexed, and logistic regressions between survival and four independent variables were calculated. These variables were temperature, flow, turbidity, and smolt abundance, measured both immediately below Prosser Dam and McNary Dam. Findings to date include the following points. Determinants of survival are year and species specific. Fall chinook benefit from the density of co-mingled smolts. The survival of yearling smolts increases with the abundanceof co-mingled smolts during years of high flow, but decreases with abundance of co-mingled smolts during years of low flow. Columbia River parameters are more important in determining survival from Prosser Dam to McNary Dam during years of high flow in the Yakima River. These findings have implications for supplementation programs that produce large numbers of smolts, in that, during certain years, there may be a threshold release number above which the survival of all smolts may increase because of a “predator swamping” effect. Yakima spring chinook monitoring plan. Although production of the Yakima Fisheries Project Spring Chinook Supplementation Monitoring Plan (DOE/BP-64878-1), completed in 1997, is central to the monitoring and evaluation program of the YKFP, no specific objective and task numbers were assigned to it. This plan is still the template for monitoring and evaluation activities for the YKFP, and may be used for other supplementation projects in the region. Facility QC monitoring: Although monitoring the impact of Roza adult broodstock collection and monitoring facility on upper Yakima spring chinook is critical, no objective and task numbers were assigned to this activity. The adult broodstock collection and monitoring facility at Roza Dam was shown to have no adverse effects on passage timing or spawning distribution of wild Yakima spring chinook. Development of procedures to estimate wild/hatchery smolt survival from recaptures of smolts PIT-tagged and released at Roza Dam (current Objective 1 task e). Field studies conducted in the spring of 1998 indicated that it is not feasible to estimate smolt passage at the juvenile collection facility at Roza Dam. Currently the facility is used to collect, mark and release hatchery and wild spring chinook smolts, in order to estimate relative survival to Prosser and McNary dams. Knowledge of relative hatchery/wild survival rate from Roza Dam to McNary Dam is important because studies have shown (Steward and Bjornn 1990) that much of the difference between hatchery and wild survival is attributable to differential mortality occurring shortly after release. Hatchery smolt survival from Roza Dam to McNary Dam was 72 and 62% of the wild rate in 1999 and 2000 respectively. In previous studies (Fast et al. 1991) we found that relative smolt survival to Prosser Dam between marked groups of hatchery fish was significantly correlated to smolt-to-adult survival for the same groups. Coho/chinook predation studies. The project was concerned about the potential for significant predation by hatchery coho smolts on juvenile fall and spring chinook. Accordingly, we conducted field studies of coho predation on fall chinook in 1997 and 1998, and of coho predation on spring chinook in 1998 and 1999. The results of these studies were as follows. Fall Chinook Studies: During 1997 and 1998, 8,226 hatchery coho smolts were collected in the mid-lower Yakima River and irrigation facilities and only 13 contained salmonids in their stomach. Spring Chinook Studies: During 1998, 1,097 hatchery coho salmon were collected in the upper Yakima River and only two salmonids were found in the stomach of one coho salmon. Similarly, the 1999 study found that none of the 963 hatchery coho examined had consumed juvenile chinook. No further work is anticipated under this task during this contract period. Prey abundance seeding index (current Objective 4 task d). The feasibility of using a measure of prey availability (spring chinook parr stomach fullness) as an index of carrying capacity and as a strong biotic interaction is currently being tested. An index of prey availability was calculated by dividing the observed dry weight of stomach contents by the maximum estimated weight for a particular length of fish. Average stomach fullness for wild spring chinook during the day was 13% (2000), 12% (1999) and 9% (1998). Wild and hatchery salmon readily ate freeze-dried krill that was introduced, which suggested that fish would have eaten more food if it were available. Microhabitat use seeding index (current Objective 1 task c). Microhabitats of spring chinook salmon were identified by snorkelers and then subsequently measured. Total depths that spring chinook salmon occupied during 2000 were slightly higher than in 1999 and 1998, but focal depths, surface velocities, and focal velocities were all similar to those measured in 1999. Avian predation index (current Objective 4 task a). A bird predation index was calculated annually between 1998 and 2000. Bird predation on salmon was strongly associated with low stream discharge and dams. Gulls and common mergansers had the greatest predatory impact on juvenile salmonids and have the potential to limit natural production during years of average or low flows. Baseline incidence of residual and precocial spring chinook (current Objective 1task p). Abundance of residualized spring chinook salmon and precocially mature spring chinook salmon was assessed by snorkeling annually between 1998-2000. Abundance of hatchery residuals was highest directly below the Clark Flats and Jack Creek acclimation sites. Mortality of hatchery residuals appeared to be quite high with few being seen during spawning. The abundance of wild precocials was similar to counts in 1998 but the precocials were distributed over a much greater number of redds. Space and food competition index (current Objective 4 task d). Competition for food with wild spring chinook salmon was indexed by multiplying a per capita competition index by a population consumption index. Spring chinook salmon had the highest per capita competition index of the taxa that were examined, but mountain whitefish were the strongest population competitor because of their large abundance and food consumption. An index of space competition was calculated by multiplying a spatial overlap index by an index of competitor abundance. The index was highest for spring chinook salmon (intra-specific competition) between 1994 and 2000 with the exception of 1996. Correlations between spring chinook salmon condition and abundance of mountain whitefish and spring chinook suggest that competition is having detectable population level effects.

Project 9506406, “Monitoring Supplementation Response Variables”, 1995-1998. This project produced six technical reports and papers and led to significant developments in the following areas: Supplementation population dynamics modeling (current Objective 1 task a). Produced four models expressing natural production under supplementation as a function of release size, productivity of supplemented population, form of natural production function and variability of natural production. The models will, with refinements, be used to assess progress toward goal of increasing natural production and identify pre-conditions of success. Comparison of hatchery spring chinook survival by treatment. By 1998, the project had produced multi-year power analysis of OCT/SNT survival comparison. Release numbers to test OCT/SNT differences in smolt/adult survival with specified power (effect size = 50%) are based on this analysis. Results in terms of smolt survival rates to McNary Dam, for outmigrations for 1999 and 2000 (brood years 1997 and 1998), were as follows: For neither brood year was there a significant treatment effect, nor were there significant treatment by site interactions. There were significant site effects for both years. Specific survival values for brood year 1997 were mean OCT survival 52.1%, mean SNT survival 53.1%, pooled over treatments, survival for the Clark Flats acclimation site was 53.7%, and survival from the Easton acclimation site was 51.5%. Specific survival values for the 1998 brood year were, OCT 35.2%, SNT 35.0% . Survival rates pooled over treatment groups were 31.3%, 36.0%, and 38.4% at the Easton, Jack Creek, and Clark Flat acclimation sites respectively. Over both brood years, survival at the Clark Flat site was significantly higher than the Easton acclimation site. Undue significance should not be placed on the fact smolt survival rates have not differed by treatment. The definitive test will consist of the significance of differences in smolt-to-adult survival and reproductive success. Genetic modeling: broodstock impacts (current Objective 3 task c). Modeled genetic effects of broodstock collection and usage rules. Preliminary results include the suggestion that a wild-only broodstock policy has little beneficial impact during the initial phase of supplementation. Genetic modeling: DNA pedigreeing (current Objective 3 task a). Developed "pedigree" computer model for investigation of monitoring power using DNA markers (e.g., monitoring abundance of progeny of DNA-sampled hatchery and wild spawners on scales ranging from tens of fish in artificial spawning channels to all upper Yakima spring chinook). Reproductive success baseline work (current Objective 1 task o). Recorded detailed behavioral observations on wild spawning spring chinook (first ethological description of these behaviors on Columbia River spring chinook) and characterized detailed reproductive traits of wild Yakima spring chinook. Genetic baseline development (current Objective 3 task a). Developed DNA microsatellite profiles of Yakima spring chinook populations. Spring chinook marking (current Objective 1 task d). The YKFP developed a non-destructive mark consisting of a combination of VI-jet tags and/or coded wire tags (CWT) implanted at multiple body locations. For the 1997 and 1998 brood years (1999 and 2000 smolts), all hatchery spring chinook were adipose clipped and marked with CWTs implanted in various body locations, and for the 1999 brood year were also VI-jet marked in the adipose eyelid. Fish marked in this way can be non-lethally sampled as returning adults and identified to rearing treatment (OCT/SNT), raceway and acclimation site. In addition approximately 40,000 fish were PIT tagged in all years, using 400 KHz PIT tags for 1999 smolts and 134 KHz PIT tags thereafter. We PIT tagged these fish to estimate smolt survival to McNary Dam and PIT tag retention from smolt to adult. Smolt-to-adult PIT tag retention rates are currently unknown, but are vital to regional attempts to estimate smolt-to-adult survival. Hatchery spring chinook treatment specification. Juvenile survival studies indicated positive impacts from rearing treatments that included the following elements: “naturalistic” raceway color patterns, overhead cover and mid-water structure. These features, plus mid-water feed delivery and predator avoidance training (shown by Maynard et al (1996) to increase survival) were included in the initial SNT treatment specification.

Project 9506402, “Yakima Species Interaction Studies”, 1995 – 1998, and Project 9506424, “WDFW/YKFP supplementation monitoring activities”, 1999-present. These projects produced 13 technical reports and papers and led to significant developments in the following areas: Non-target taxa monitoring (current Objective 4 task e). Practical approaches for assessing and containing ecological risks associated with stocking anadromous salmonids were developed to facilitate decision making and direct monitoring efforts. Field studies have provided requisite information for assessing risks of steelhead and spring chinook supplementation to wild rainbow trout and spring chinook salmon. In addition, monitoring prescriptions for 16 non-target taxa of concern (NTTOC) have been developed and are being implemented to meet conservation objectives. Preliminary analyses indicate that impacts on NTTOC abundance that are detectable in 5 years (=0.1, proportional variance) range from 19% (mainstem Yakima rainbow) to 100% (sand roller). During the first two years of supplementation, all of the NTTOC are either within the containment objectives or changes are statistically undetectable. Fish predation index (current Objective 4 task b). A fish predation index has been calculated for smallmouth bass and northern pikeminnow, but is still being developed for channel catfish. Smallmouth bass and channel catfish are dominant in the lower Yakima River and pikeminnow in the mid-upper Yakima River. Smallmouth Bass Predation: We estimated the number of salmonids that smallmouth bass ate during the spring of 1998, 1999, and 2000 in the Yakima River. Daily consumption of salmonids was relatively low until late April and peaked in mid May. Smallmouth bass ate an estimated 202,722 salmonids during the spring, 2000. Only 2,832 of these were estimated to be spring chinook. The remainder was mostly fall chinook salmon. In contrast to 1998 and 1999 salmonid consumption estimates, 2000 estimates were in the middle of the range (1998 estimates: 430,698 salmonids, 2,726 spring chinook salmon; 1999 estimates: 165,125 salmonids, 3,086 spring chinook salmon). Horn Rapids Dam (Wanawish) has the potential to be the area of highest predation in the Yakima River because of the large number of bass that congregate below the Dam. Northern Pikeminnow Predation: We estimated that northern pikeminnow consumed 831,757 salmonids during the spring of 2000, of which approximately 95% were yearling salmonids, consisting mostly of spring chinook and coho. The precision of predation index was improved substantially in 2000 over 1999 by a increasing the frequency of consumption sampling. Dominance and predator avoidance experiments (current Objective 4 task e). We examined behavioral dominance and predator avoidance relationships of spring chinook salmon presmolts that were reared under optimal conventional hatchery conditions (OCT), semi-natural hatchery conditions (SNT), or natural conditions (Wild). Fish were transported from acclimation sites or Roza Dam to the Cle Elum Hatchery and introduced into behavioral arenas for seven days. Behavioral arenas had one location with highly favorable attributes (e.g., food, cover, optimal velocity). Dominance was assigned to the fish that acquired the most food, initiated the most agonistic interactions, and occupied the preferred position the most frequently. After dominance observations were completed, a model bird predator was introduced over the top of the experimental arena, and behavioral responses of the fishes were recorded. The initial behavioral responses of SNT and OCT fish to a model predator were similar. More than half of the fish showed little or no response to the model predator. Predator avoidance training (current objective 1 task x). Two tests were conducted on hatchery coho salmon to determine the survival benefits of predator avoidance training. In 1999 northern pikeminnows were used as the experimental predator and in 2000 common mergansers were used. Predators were confined to semi-permeable cages that had large enough spaces for salmon to swim in an out of. Control sections did not have predators introduced. Coho salmon were PIT tagged to determine post-release survival. No differences in detection rates at downstream dams could be attributed to predator avoidance training. The lack of a treatment effect is probably related to previous exposure of coho salmon to otters.

Project 9706200, “Development and Refinement of Natural Production Objectives and Enhancement Strategies”, 1997-1998. This project produced two technical reports and papers and led to significant developments in the following areas: Fall chinook limiting factors (current Objective 1 task a). A preliminary ecosystem diagnosis and treatment (EDT) modeling analysis of Yakima fall chinook indicated that the major factor limiting natural production was a combination of excessive temperature in the lower river and late emergence timing. Spring chinook natural production objectives (current Objective 1 task a). Used predecessor of EDT model to set natural production goals and conditions for Yakima spring chinook supplementation project. Enhancement project design (current Objective 1 task a). Currently using latest version of EDT model to integrate life history characteristics (of coho, fall chinook and steelhead) and habitat quality and quantity in order to identify limiting factors and assess alternative enhancement strategies.

Project 8812005, “Fish Passage Video Monitoring”, 1988 - 1998. Besides annual reports, this project contributed to many Yakima-related technical reports and papers and led to significant developments in the following areas: Yakima Subbasin returns and spawning escapement (current Objective 1 tasks l and m). Passage of jacks and adults are estimated by time-lapse videos shot through viewing windows in ladders on irrigation dams. Project developed videographic methods to estimate total returns to Yakima as Prosser Dam counts plus below-Prosser harvest (spring chinook, coho, steelhead and above-Prosser fall chinook); upper Yakima spawning escapement (steelhead and coho) as Roza Dam counts. Currently developing methods to estimate Naches spawning escapement for coho as Cowiche Dam counts.

Project 8812008, “Fish Technician Field Activities”, 1988-1998. Besides annual reports, this project contributed to many Yakima-related reports, and led to significant developments in the following areas: Chandler smolt passage (current Objective 1 task f). At Chandler estimated seasonal passage of all species of wild smolts and pre-smolts, and all marked groups of experimental smolts (hatchery and wild), for the years 1983 to present. In combination with return monitoring at Prosser Dam (8812005), spawner surveys and harvest monitoring (other 8812008 tasks), generated pre-supplementation estimates of egg-to-smolt & smolt-to-adult survival for all above-Prosser Yakima stocks. In-basin harvest monitoring, Yakima (current Objective 2 task b). Refined and augmented in-basin Yakima harvest monitoring methods. Yakima Subbasin spawner surveys (current Objective 1 task n). Counted redds throughout subbasin for spring chinook and estimated potential egg deposition (brood years 1981 to present); counted redds and estimated potential egg deposition for Satus/Toppenish Cr. steelhead and Marion Drain fall chinook (1989 to present); in process of developing effective redd counting/egg deposition methods for coho throughout subbasin. Roza adult facility operation (current Objective 1 task m). From 1997 to the present, operated Roza adult facility and collected and transported spring chinook broodstock, monitored demographic characteristics of wild run.

Project 9506800, “Klickitat Passage/Habitat Improvement M&E”, 1995 - 1998. As a result of the NPPC Provincial Rolling Review Process, the Klickitat activities were removed from this project and submitted as a separate proposal in the Columbia Gorge Province. This project produced portions of four technical reports and led to significant developments in the following areas: Adult monitoring/broodstock collection. Plans were developed to retrofit Lyle Falls fishway in the Klickitat Subbasin to function as an effective broodstock collection and adult monitoring facility. Passage improvements. A series of alternative plans were developed to increase adult passage at the Castile Falls complex. Fish distribution. The first series of studies of species composition and distribution of naturally-produced salmon and steelhead in the subbasin were generated.

Project 9603301, “Supplement and Enhance the Two Existing Stocks of Yakima River Fall Chinook”, 1996 - 1998. Experimental work on this project basically began in 1998. Consequently, this project has produced only one technical report to date, although a series are forthcoming in 1999 and 2000. The project has led to significant developments in the following areas: Locally-adapted broodstock (current Objective 1 tasks 1g and 1h). Began development of locally-adapted coho and fall chinook broodstocks by collecting and spawning returning adults in the Yakima Subbasin beginning in 1998 at Prosser Dam. Hatchery treatment specification (current Objective 1 task 1g). The efficacy of increasing hatchery fall chinook smolt survival by thermally accelerating incubation and growth to smolt size was tested by releasing differentially marked (left & right pelvic clips; 4,000 PIT-tagged fish) test and control (unaccelerated) smolts in the spring of 1999. Relative survival and outmigration timing to McNary Dam were monitored via PIT tags. Release sizes were based on a power analysis. Optimal supplementation reaches. (Current Objective 1 Task 1b). The suitability of various portions of the lower Yakima River for fall chinook supplementation will be determined on the basis of ability to support additional natural production. The feasibility of assessing the relative ability of three portions of the lower Yakima to support increased natural production will begin to be assessed in the spring of 2002. Previous attempts to utilize marked hatchery fish were not successful. See Section f below for methods and assumptions related to this task (Task 1b).

Project 9603302, “Evaluate the Feasibility and Potential Risks of Restoring Yakima River Coho”, 1996 - 1998. Experimental work on this project began in 1998. Annual reports were completed in 1999 and 2000. The project has led to significant developments in the following areas: Locally-adapted broodstock (Current Objectives 1h and 1g). Began development of locally adapted coho and fall chinook broodstocks by collecting and spawning returning adults in the Yakima Subbasin (eyed eggs transported to hatcheries out of basin for rearing to smolt). Coho/trout interactions. Preliminary results indicate low competitive impacts (displacement, sympatric/allopatric growth and survival) of outplanted hatchery coho parr on resident trout in the Little Naches drainage (Yakima Subbasin). Outplants of hatchery coho parr have since been discontinued by the project. Optimal supplementation areas and release timing (Current Objective 1h). In spring of 1999 began multi-year study (1999 – 2003) of impact on survival of acclimated hatchery coho smolts to Chandler and McNary of release date and release site (2X2 factorial with one rep per site). Release dates are May 7 and May 31; release sites are upper Yakima and upper Naches. Beginning in with smolt releases in 2000, all release groups of hatchery coho were marked with CWT. Releases include sufficient numbers of PIT-tagged fish to estimate differential survival to Chandler and McNary (PIT tag) and smolt-to-adult survival (CWT) with specified power (effect size =50%).

f. Proposal objectives, tasks and methods

| Although the project entails only four fundamental objectives, there are 37 sub-objectives which we have termed tasks to accommodate the structure of this document. These 37 sub-objectives and associated hypotheses/assumptions are summarized in the table below. Every sub-objective will result in one or more of the following: a BPA report, a paper in a refereed journal, a complete monitoring procedure including functional facilities and analytical techniques. |
| --- |
| OBJ. | Task, Hypothesis/Assumption, and Method |
| 1. | Objective: Natural Production: Develop methods of detecting indices of increasing natural production, as well as methods of detecting a realized increase in natural production, with specified statistical power. |
| 1.a | Task: Modeling: Design complementary supplementation/habitat enhancement programs for coho, spring & fall chinook & steelhead in the Yakima and Klickitat Subbasins. Hypothesis: Ecosystem Diagnosis and Treatment computer modeling accurately integrates habitat quantity, quality, and life history data to evaluate alternative enhancement strategies. Modeling can continue to be used throughout the Project to model the statistical power of reproductive success study designs, domestication study designs, treatment/control experimental designs, etc. Rationale: To design complementary supplementation/habitat enhancement programs for targeted stocks. Methods: To diagnose the fundamental environmental factors limiting natural production, and to estimate relative improvements in production attributable to alternative enhancement strategies, by using the “Ecosystem Diagnosis and Treatment” (EDT) model. Continue to model statistical power associated with proposed monitoring plans such as reproductive success, genetic risk assessment, adult sub-sampling frequency, etc. |
| 1.b | Task: Fall chinook survival study: Determine optimal locations within the lower Yakima Basin for increasing natural production of fall chinook, and to guide location of future acclimation/release sites. Hypothesis: The relative survival of PIT tagged wild juvenile fall chinook from candidate supplementation areas to the lower Yakima accurately reflects natural production potential of the candidate areas. Rationale: Determine areas in the lower Yakima where potential for increased natural production of fall chinook is greatest (future acclimation/release sites). Methods: Determine the feasibility of collecting naturally produced fall chinook juveniles to mark with PIT tags to estimate relative survival between groups. Relative productivity among reaches is indexed by relative fry-to-smolt survival. |
| 1.c | Task: Juvenile spring chinook micro-habitat utilization: Monitor microhabitat utilization of juvenile spring chinook salmon. Future deviations in use will suggest carrying capacity problems. Hypothesis: Changes in patterns of microhabitat utilization with supplementation will reflect spring chinook seeding in the upper Yakima. Rationale: Estimate the baseline microhabitat utilization patterns of juvenile spring chinook salmon. Even if supplementation were perfect, producing smolts and adults identical to wild fish in every way, the project could fail if existing production actually represented the carrying capacity of the Yakima Subbasin. A post-supplementation change in patterns of microhabitat use is one of the indices that will be used to monitor “carrying capacity constraints”. Methods: Under excessive densities, a significant proportion of early spring chinook parr might be displaced into sub-optimal microhabitats. Accordingly, we will monitor the relative incidence of parr in “typical” (baseline) and “atypical” microhabitats as a function of estimated egg deposition and spawning escapement. Snorkelers will mark the location of spring chinook focal positions and measure associated physical parameters. |
| 1.d | Task: Hatchery spring chinook juvenile marking: Estimate hatchery spring chinook smolt survival to Chandler & mainstem dams using PIT-tags, and smolt-to-adult survival (release to Yakima mouth) using CWTs. Hypothesis: H0: Survival of SNT-reared fish does not exceed survival of OCT-reared fish. Current release numbers of juvenile spring chinook assumes that OCT smolt-to-adult survival rates will be 0.2% or higher. Under these circumstances it will be possible to detect a 50% effect size with 90% probability, alpha = 10%. Rationale: To evaluate hatchery treatments in terms of relative smolt survival to Chandler, McNary and John Day using PIT tags, and relative smolt-to-adult survival (to Roza Dam) using multiple body-implanted CWT’s, and colored elastomer in multiple body locations denoting treatment replicates.. Methods: To estimate differences in smolt survival by treatment (OCT/SNT), acclimation site, and raceway, we will PIT-tag, ad-clip & CWT (snout) 40,000 parr, enough to detect survival differences at John Day with specified power (effect size=50%). 400,000 fish will be ad-clipped and CWT’ed in multiple body areas to uniquely code treatment, acclimation site, and raceway. Returning adults will be interrogated at Roza using hand-held CWT detectors to determine smolt-to-adult survival by group, and will then be released to spawn. Power for smolt-to-adult survival estimates is the same as for smolt survival. CWT’ed fish will also be recovered in spawning ground surveys (see task 1.q). Statistical analysis by ANOVA. |
| 1.e | Task: Roza juvenile wild/hatchery smolt PIT tagging: Capture, PIT-tag and release wild and hatchery spring chinook to estimate relative wild/hatchery smolt survival to Chandler and the McNary Dam. Hypothesis: Survival of hatchery fish is high enough to result in an increase in natural origin recruits. Rationale: Relative hatchery/wild smolt survival to Chandler and McNary is a critical mechanistic element of project evaluation. Methods: Roza Canal fish bypass will be used to capture wild and hatchery spring chinook smolts, which will be PIT-tagged and released on site. Analysis by binomial techniques. |
| 1.f | Task: Wild/hatchery survival and enumeration (Chandler Juvenile Monitoring Facility):Refine operational and analytical procedures used in estimating hatchery and wild smolt passage at Chandler smolt trap. Hypothesis: A stable relationship exists between smolt entrainment and hydraulic variables at Prosser Dam, and stock-specific proportions of smolt outmigrants can accurately be estimated by electrophoretic and/or micro satellite DNA techniques. Rationale: 1.) As referenced in the Spring Chinook Monitoring Plan, (Busack et al. 1997), Chandler is an essential element of M&E for Yakima stocks. Information wholly or partly collected at Chandler includes annual smolt production and outmigration timing, egg-to-smolt and smolt-to-adult survival rates, and relative smolt survival rates (to Chandler) between hatchery treatment groups (e.g., OCT v SNT) and between hatchery groups and marked groups of wild smolts. This information is used to determine whether post-supplementation changes in production and survival rates are consistent with a population for which natural production is increasing. This data can be gathered for all anadromous salmonids within the basin and is stock-specific for spring chinook (electrophoretic mixed stock analysis). 2.) To refine smolt passage estimates (future and historical) by increasing the precision of passage estimators and correcting for any bias associated with the estimators. Methods: 1.) Chandler is operated continuously except for brief periods of canal maintenance. Species-specific relationships between canal diversion and smolt entrainment rates have been developed, and daily passage is estimated as the ratio of raw catch to entrainment (total production is the sum over the season). A subsample of smolts are bio-sampled each day and all PIT-tagged fish are interrogated as they enter the facility. Smolt–to-adult survival for wild fish is estimated as the ratio of brood year returns to brood year smolt production. Brood year returns are estimated (for example) for spring chinook as the sum of the number of jacks the year after outmigration, the number of age 4 fish two years after outmigration, and so on. Annual age composition is estimated by analyzing scales from spawning ground carcasses and adults sampled at the Roza adult trap, and total returns are estimated as the sum of Prosser counts and below-Prosser harvest. 2.) Replicated releases of PIT-tagged smolts are used to make a series of entrainment rate estimates. Logistic regression is then used to express entrainment as a function of one or more hydraulic variables (e.g., percent discharge diverted into the canal) characterizing flow conditions at Prosser Dam at the time of release. These flow/entrainment relationships will be used to estimate future smolt production, to revise historical estimates of smolt production, and to generate confidence intervals for both. |
| 1.g | Task: Fall chinook optimal rearing treatment: Develop an accelerated rearing treatment to enable early out migration and increase overall smolt survival. Hypothesis: The survival of hatchery fall chinook can be increased to levels consistent with an increase in natural production. Rationale: Determine if hatchery fall chinook smolt survival can be increased by accelerated incubation and rearing. Methods: Incubate and rear control and accelerated groups at the Prosser Hatchery on river water and warmer well water, respectively. PIT-tag fish to evaluate relative survival McNary Dam; differentially pelvic-clip fish to estimate relative smolt-to-adult survival. Analysis by logistic analysis of variance. |
| 1.h | Task: Yakima coho stock and date of release study: Determine optimal location, date, and stock of release for Yakima coho re-introduction efforts. Hypothesis: The survival of a suitable stock of hatchery coho can be increased to levels sufficient to establish a naturalized population. Rationale: To determine the optimal date and place of release for Yakima coho re-introduction feasibility tests. Methods: A replicated factorial design is used to test for survival differences between release location (upper Yakima and Naches Subbasins) & release date (May 7 and May 31). Release date will have two replicates per drainage. Release groups will be PIT tagged to evaluate smolt survival to Chandler and McNary. Beginning in 2000, coho smolts will also be CWT’ed to monitor smolt-to-adult survival. CWTs will be recovered during broodstock collection. Statistical analysis by logistic analysis of variance. |
| 1.i | Task: Yakima spring chinook juvenile behavior: Determine differences in hatchery & wild spring chinook smolt behavior closely related to survival. Hypothesis: Analysis of relative behavior in hatchery and wild fish at release will indicate which behaviors are correlated to survival. Rationale: To quantify behavioral differences between wild, OCT & SNT smolts, and to correlate those behaviors with smolt survival. Methods: Observe (direct and video) hatchery (OCT and SNT) and wild spring chinook collected at Roza and Prosser dams in a controlled environment. Response variables will include: water column position, position to overhead cover and substrate, use of different cover types, latency to normalized behavior and feeding, time required to adopt wild behavior. Analysis by principal component analysis and ANOVA. |
| 1.j | Task: Yakima hatchery spring chinook juvenile morphometric and coloration studies: Determine whether significant differences in body shape and coloration exist between hatchery spring chinook at release. Hypothesis: Analysis of differences in coloration and morphology between OCT, SNT, and wild smolts at release will indicate which characteristics are correlated to survival. Rationale: One of the fundamental hypotheses of employing a SNT rearing treatment is to produce hatchery fish that resemble wild fish in color and body shape. This task estimates morphometric/coloration differences between OCT & SNT spring chinook juveniles. Methods: OCT and SNT fish will be photographed and truss measurements taken from the photographs will be used to characterize body shape. Color differences will be estimated from photographs taken just at release. Statistics: linear discriminant and principle component analysis. |
| 1.k | Task: Yakima hatchery/wild spring chinook smolt physiology studies: Determine whether significant physiological differences exist among wild, OCT and SNT Yakima spring chinook smolts during rearing, at release, and at Chandler and at John Day Dam. Hypothesis: Analysis of physiological differences (lipid content, ILGF-1, gill-ATPase, thyroxin, condition factor) between OCT, SNT, and wild smolts at release and after a substantial outmigration period will indicate which characteristics are tightly linked to survival. Rationale: To compare OCT, SNT and wild spring chinook in terms of physiological smolt quality. Methods: Monitor plasma concentrations of thyroxin & insulin-like growth hormone, % body lipid, gill ATP-ase, growth rate and condition factor for OCT, SNT and wild fish as pre-smolts and as (PIT-tagged) outmigrants collected at Roza, Chandler & McNary. Statistical analysis by ANOVA. |
| 1.l | Task: Adult salmonid enumeration at Prosser Dam: Estimate the total number of adult salmonids returning to the Yakima Basin by species (spring and fall chinook, coho and steelhead), including return of externally marked fish. Hypothesis: Water clarity will allow videographic species-specific passage estimates of specified precision. Rationale: To estimate passage of jacks and adults at Prosser, Roza and Cowiche Dams (spring and fall chinook, coho and steelhead), including passage of externally marked fish, and to collect biotic and abiotic data for each run. Methods: Use time-lapse video recorders (VHS) and cameras in viewing windows in all ladders at Prosser Roza & Cowiche Dams. Extract data from tapes. Monitor passage at Prosser and Roza year-round (for all species); monitor passage at Cowiche only Sept. 15 – Dec. 31 (for coho). |
| 1.m | Task: Adult salmonid enumeration and broodstock collection at Roza and Cowiche dams: Estimate the total number of adult salmonids returning to the upper Yakima (Roza), and the total number of adult coho returning to the Naches (Cowiche). Hypothesis: Water clarity will allow videographic species-specific passage estimates of specified precision at Cowiche (coho only) and Roza (coho and steelhead). Additionally, flows at Cowiche Dam force all coho to use the ladder. It will be economically possible to modify the Cowiche Dam ladder to collect coho broodstock. Rationale: To estimate the upper Yakima spawning escapement at Roza Dam for spring chinook, steelhead and coho; to estimate spawning escapement of hatchery spring chinook by experimental group (treatment\acc site\raceway) at Roza; and to estimate passage of externally marked fish at Roza. Methods: From September 15 to March 31 monitor passage videographically. From April 1 to September 14, estimate passage of steelhead and spring chinook, and collect spring chinook broodstock, by operating the adult trap. All CWT’ed spring chinook will be electronically diverted to a holding tank and interrogated with a hand-held CWT detector and a PIT-tag detector. |
| 1.n | Task: Spawning ground surveys (redd counts): Monitor spatial and temporal redd distribution in the Yakima Subbasin (spring chinook, Marion Drain fall chinook, coho, Satus/Toppenish steelhead), and collect carcass data. Hypothesis: Redd counts accurately reflect potential egg deposition and age distribution from carcass recovery can be used to estimate age structure. Rationale: To describe spatial and temporal redd distribution for Yakima spring chinook, coho, fall chinook (Marion Drain), and steelhead (Satus/Toppenish ), and to collect demographic data from carcasses. Methods: Periodic foot and/or boat surveys are conducted within the geographic range for each species (increasing for Yakima coho as acclimation sites are relocated upriver and returns increase). Redds are individually marked during each survey and carcasses are sampled for marks and to collect data on egg retention, age (analysis of scale samples), sex, and length. |
| 1.o | Task: Natural Spawning Observations: Characterize wild spring chinook reproductive behavior (adults and precocials) to serve as a baseline for future comparisons between hatchery & wild reproductive behavior. Hypothesis: Deviations from overall baseline behavioral patterns will indicate phenotypic and genotypic impacts from supplementation. Rationale: Detailed observations will allow scientists to characterize typical wild spring chinook reproductive behavior to serve as a baseline for evaluations of hatchery fish behavior. Methods: Before returns of hatchery adults in began in 2001, field activities will focus on observation and description of naturally spawning spring chinook in the upper Yakima and Naches Rivers. Knowledge of natural variation (within-year and between-year) in behavioral repertoires and the frequency of individual behaviors provide the basis for a power analysis of future studies to detect hatchery/wild differences in reproductive behavior. The presence and behavior of precocial males associated with spawning females is also recorded. Beginning with 2001 returns and continuing for at least two cycles, first-generation hatchery adults will be observed in the natural environment. Behavior, micro-habitat preferences, spawn timing, etc. of hatchery and wild spawners will be compared in the upper Yakima River. Observations will be recorded on audiotape and underwater video recordings. |
| 1.p | Task: Yakima spring chinook residuals/precocials studies: Monitor abundance and distribution of wild and hatchery residual and precocial spring chinook salmon. Hypothesis: Supplementation does not significantly change the abundance and distribution of residual/precocial spring chinook. Rationale: Estimate the baseline abundance of residual and precocial spring chinook and determine the sampling effort needed to detect post-supplementation changes. Methods: 1) Residuals – Direct counts of juvenile chinook that did not migrate as 1+ smolts will be made by snorkeling index areas. Selected individuals will be captured and examined for sexual maturity (examination of gonads) and age (scale samples). 2) Precocials - Snorkelers will count precocial spring chinook on active redds within index areas to assess supplementation-induced abundance changes. Sampling effort for monitoring abundance precocial abundance after supplementation will be based on 1998 observations. |
| 1.q | Task: Relative hatchery/wild reproductive success: Determine whether spawning behavioral and reproductive success of wild and hatchery-origin spring chinook are comparable, and estimate reproductive success of hatchery coho in a natural stream. Hypothesis: Spring Chinook: Ho: Wild- and hatchery-origin spring chinook adult reproductive competency are equivalent when compared in a controlled-flow spawning channel. It is assumed that the artificial spawning channel will not cause deviant reproductive behavior, and can therefore be used to assess relative hatchery/wild reproductive success for spring chinook throughout the Yakima Subbasin. Coho: Ho: Reproductive success of hatchery coho spawning in certain areas of the Yakima Subbasin is high enough to support a naturalized population. Rationale: The reproductive competence of hatchery-reared adults is a major uncertainty surrounding supplementation. This task addresses that question directly for Yakima spring chinook and coho. Hatchery- and wild-origin spring chinook will be compared in a controlled-flow spawning channel to determine whether their behavior and reproductive effectiveness differs significantly. Methods: 1) Spring chinook: DNA-typed wild and hatchery spring chinook adults and jacks collected at Roza Dam and precocial males will be tagged with individually numbered disk-tags and placed into Cle Elum spawning channel. Eleven pairs of size-matched wild- and hatchery-origin females (22 total females) will be placed in each of two 45m channel sections. A similar number of size-matched pairs of males will be introduced. In addition, five pairs of size-matched jacks will be included. Phenotypic and morphological traits will be collected and ethological characterizations of the reproductive behavior of individual fish will be made. The number of progeny produced by each male and female will be estimated by trapping post-emergent fry and identifying their parentage via DNA analysis. Reproductive efficiency will be determined for discrete WxW, HxW and HxH matings. Visual observations will be recorded on audio tape and, where possible, underwater video recordings will also be made. Statistical analysis will be by ANOVA. 2) Coho: We will identify optimal reaches and tributaries for natural coho production, and for future acclimation/release sites, by comparing existing, tributary- and reach-specific substrate composition data with coho reproductive performance under controlled conditions. Controlled matings will be conducted in a semi-natural channel not subject to extreme flow fluctuations. This channel will be sub-divided into segments with substrate composed of various proportions of fine particles. Groups of hatchery coho will be allowed to spawn in each segment. Weirs will be installed between segments in order to capture emergent fry, and mean egg-to-fry survival will be estimated for each segment. Observed egg-to-fry survival rates will be compared to expected rates for wild coho in order to assess the bias attributable to hatchery ancestry of the donor stock. Bias adjusted relationships between percent fines and egg-to-fry survival will then be applied to the existing data for potential coho spawning areas throughout the basin. Estimated egg-to-fry survival values for potential spawning areas will be incorporated into the EDT model to identify the most promising areas for coho re-introduction, and for locating future acclimation/release facilities. |
| 1.r | Task: Yakima spring chinook gamete quality monitoring: Estimate sex-specific fertility, in-hatchery mortality, incidence of monstrosities and fry emergence timing for upper Yakima spring chinook from a subsample of eggs. Hypothesis: H0: Supplementation will not change gamete quality. Rationale: The following demographic variables for the upper Yakima spring chinook population will be monitored: age-specific mean fecundity, the length- and weight-fecundity relationship, egg size, total reproductive effort, female size (weight and length), fertility, in-hatchery egg-to-fry survival, occurrence of monstrosities, emergence patterns, and fry size vs. female size relationship. Methods: Adult female traits and egg size will be measured at the time of spawning. Fertility, in-hatchery mortality and monstrosities will be measured on a subsample of eggs collected from individual females and incubated in separate isolettes. Emergence timing of fry from individual females will be measured by placing eyed eggs into incubation containers with substrate and an outlet with a catch basin. Fry will be counted as they volitionally exit the rearing containers on a daily basis. Hatchery returns will be sampled in the same manner in 2002 and beyond and compared to their wild counterparts. Statistical analysis will include ANOVA, ANCOVA and linear regression. |
| 1.s | Task: Scale analysis: Determine age and stock composition of juvenile and adult salmonid stocks and predator species in the Yakima basin. Hypothesis: H0: Supplementation activities will not change the age structure of YKFP target stocks. Naturalized coho can reliably be distinguished from hatchery coho using scale analysis. Rationale: 1. Spring chinook. To determine age and stock composition of juvenile and adult salmonid stocks in the Yakima Subbasin. Age structure of naturally produced upper Yakima spring chinook will be monitored to ensure that the age structure does not change as the result of supplementation. 2. Coho. So long as it is feasible to mark 100% of the hatchery coho, scale analysis to determine origin type will be unnecessary. During the period 2000-2003, we expect to mark 100% of all hatchery coho released in the Yakima. However, the prospects for marking all hatchery coho beyond 2003 are not known. It is therefore prudent to develop techniques using scale analysis to differentiate between hatchery and wild origin coho. 3. Yakima River Predators. Potential predator fish control projects are likely to be more feasible when most of the predatory impact is confined to several older age classes. We are collecting this information against the possibility of a need to implement a predator control program in the future. Methods: 1. Spring Chinook: We will determine age distribution by scale analysis. Genetic data needs to be analyzed on a brood year basis, and the age structure of the population is itself an important genetic characteristic. Thus, aging the broodstock scales samples collected at the time of trapping will provide a baseline and be used to augment the biochemical genetic data. 2. Coho: We will use scale analysis to determine the proportion of hatchery vs. wild smolt and adult Yakima coho production. Juvenile coho scales will be randomly collected at Chandler. Estimates of the proportion of hatchery and wild smolts will be applied to the estimated smolt out migration. Adult coho scales will be collected at the broodstock collection facilities to estimate the proportion of hatchery/wild escapement. Estimates of the proportion of hatchery and wild adults will be applied to estimated adult returns. 3. Yakima River Predators: Collect scale samples from piscivorous fishes collected while performing task 4b (See below). |
| 1.t | Task: Fish health monitoring: Monitor the disease status of Yakima Basin hatchery juveniles and broodstock, and determine pre-supplementation incidence of pathogens in wild Yakima spring chinook. Hypothesis: Disease related mortalities at the Cle Elum Hatchery can be kept at negligible levels. Rationale: There are two objectives to this element: to monitor the physiological health and disease status of hatchery fish in the Yakima basin (both juveniles and adult broodstock), and to establish a baseline data set describing existing levels of pathogens in wild spring chinook prior to introduction of hatchery fish. Methods: Approximately 200 hatchery juveniles will be sacrificed at regular intervals and examined for disease and incidence of pathogens. All adult broodstock will also be examined for pathogens upon spawning at the hatchery. The work will follow USFWS protocols and laboratory analyses will be conducted at a USFWS fish health laboratory. In addition, approximately 200 wild spring chinook smolts will be fully screened according to standard USFWS protocols at a USFWS fish health lab. This work will utilize fish already collected for ongoing Chandler Smolt Trap calibration work (electrophoretic stock identification). |
| 1.u | Task: Habitat inventory, aerial videos and ground truthing: Measure critical environmental variables by analyzing data extracted from aerial videos and verified by ground observations. Hypothesis: A significant proportion of the inter-annual variability in salmon and steelhead productivity is attributable to fluctuations in key environmental factors inside the subbasin that can be measured by aerial videography and hydrological data. Rationale: To measure a number of environmental variables by analyzing data extracted from periodic aerial videos. Methods: Aerial videos of the Yakima Subbasin will be conducted and analyzed. The habitat conditions (e.g. area of “watered” side channels, LWD, pool/riffle ratio, etc.) from the videos will be checked by dispatching technicians to specific areas to verify that conditions are in fact as they appear on video. |
| 1.v | Task: Out-of-basin environmental monitoring: Obtain and utilize information regarding mainstem and marine environmental and harvest-related impacts on all Yakima anadromous salmonids. Hypothesis: A significant proportion of the inter-annual variability in salmon and steelhead productivity is attributable to fluctuations in key environmental factors in the mainstem Columbia and ocean. Rationale: To obtain and utilize information from outside sources, regarding environmental and harvest-related impacts on all anadromous salmonids occurring outside the Yakima Subbasin. Methods: The method entails communicating (telephone, E-mail and occasional face-to-face meetings) with various state and federal agencies, other research programs, hatcheries, and university researchers and collecting information regarding out of basin environmental and harvest-related impacts on anadromous stocks. |
| 1.w | Task: Sediment impacts on habitat: Monitor stream sediment loads associated with the operation of dams and other anthropogenic factors (e.g., logging, agriculture and road building) affecting streams in the Yakima Subbasin. Hypothesis: Salmon and steelhead production can be limited by anthropogenic sediment loading. Rationale: To monitor stream sediment loads associated with the operation of dams and other anthropogenic factors (e.g., logging, agriculture and road building) that can increase sediment loads in streams utilized by all salmonids in the Yakima Subbasin. Methods: Excessive sediment loads can play a critical role in egg-to-fry survival, and can depress survival and productivity of many other life stages of salmonids. Representative gravel samples will be collected from throughout an impacted reach. Each sample will be analyzed to estimate the percentage of fines or small particles present. The state TFW program guidelines on sediments will then be used to specify the impacts estimated sedimentation levels have had on salmonid egg-to-smolt survival. These impacts would be incorporated in analyses of impacts of “extrinsic” factors on natural production. |
| 1.x | Task: Yakima hatchery spring chinook predator avoidance training: Determine efficacy of exposing Yakima hatchery spring chinook to predators prior to release in terms of increasing survival to Chandler Juvenile Monitoring Facility. Hypothesis: H0: Predator avoidance training will have no impact on smolt survival. Rationale: Hatchery fish have been shown to be more susceptible to predation than wild counterparts, and it has been suggested that hatchery fish lack skills required to avoid predators (Wiley et al. 1993; Maynard et al. 1995). Method: Predator avoidance training will consist of introducing a hungry predator into a cage submerged in a raceway 3 times per week for 3 weeks prior to release. The predator will be allowed to feed for a predetermined interval. The design will entail dividing PIT-tagged SNT fish randomly into control and treatment groups. Survival for both groups will be estimated at Chandler and McNary. |
| 1.y | Task: Biometrical support: Provide the services of a half- time PH.D. level biometrician for the project. |
| 2. | Objective: Harvest: Develop methods to detect increases in harvest of YKFP targeted stocks. |
| 2.a | Task: Out-of-basin harvest monitoring: Estimate group- and stock-specific harvest of hatchery and wild anadromous salmonids outside of the Yakima Subbasin. Hypothesis: H0: Supplementation will not increase out-of-basin harvest. Rationale: To develop a database to track the contribution of target stocks to out-of-basin fisheries. Methods: Coordinate with agencies responsible for harvest management (WDFW, ODFW, USFWS, CRITFIC, etc.) to estimate the harvest of target stocks. |
| 2.b | Task: In-basin harvest: Estimate group- and stock-specific harvest of hatchery and wild anadromous salmonids within the Yakima Subbasin. Hypothesis: H0: Supplementation will not increase harvest in the Yakima Subbasin. Rationale: To develop a database to track the contribution of target stocks to in-basin fisheries. Methods: Monitor tribal subsistence and sport fisheries on the Yakima rivers at designated locations. Fish will be interrogated for various marks. This information will be used along with other adult contribution data (i.e. broodstock, dam counts, spawner ground surveys) to determine overall project success. |
| 3. | Objective: Genetics: Develop methods of detecting significant pre- & post-supplementation genetic changes in targeted stocks as reflected by changes in extinction risk, within-stock genetic variability, between-stock genetic variability, and domestication. |
| 3.a | Task: DNA data collection and analysis: Augment DNA microsatellite baselines of all Yakima chinook stocks for monitoring within- and between population genetic variability. Hypothesis: Continued DNA screening of known populations within the Yakima Basin will allow detection of changes in within- and between-population genetic variability with specified precision. Rationale: Continued genetic monitoring via DNA microsatellites is needed for genetic monitoring, reproductive success monitoring, and possibly other monitoring areas as well such a domestication selection analysis. Methods: Tissues from chinook salmon will be analyzed according to protocols being refined at the WDFW Genetics Lab. Approximately 12 variable loci will be analyzed from all adult broodstock collected for Cle Elum Hatchery, from fry exiting the controlled-flow spawning channel, and from adults sampled at Roza Dam prior to being released for natural spawning. The work will be done at the WDFW Genetics Lab. We plan to do this annually at least through the first cycle of adult returns from the hatchery. This will give us a mating-by-mating measure of reproductive success, and allow very precise estimation of effective size of the population. DNA analysis has supplanted allozyme work for adult spring chinook, and may well provide a non-lethal approach for sampling juveniles at Chandler smolt collection facility. DNA use is in lace for steelhead and will be included in steelhead monitoring plans as they are developed. |
| 3.b | Task: Stray recovery on Naches and American spawning grounds: Determine the extent of gene flow from the supplemented Upper Yakima stock into the Naches and American River stocks. Hypothesis: Spawning ground recovery of strays will be complete enough to support estimation of maximum levels of gene flow with specified precision using DNA microsattelite analysis. Rationale: To determine the extent of gene flow from the supplemented Upper Yakima stock into the Naches and American River stocks. Methods: Upper Yakima fish on the American and Naches spawning grounds will be counted during normal spawning ground surveys and compared to the total run to estimate the maximum rate of gene flow. DNA baselines for American River and Naches spring chinook will be developed by analysis of tissue collected during spawning surveys. DNA analysis will then be incorporated to monitor possible impacts on population diversity resulting from straying. |
| 3.c | Task: Yakima spring chinook domestication: develop a domestication selection study for Upper Yakima spring chinook involving HxH and WxW matings that is sufficiently powerful to detect significant effects. Hypothesis: A domestication monitoring plan can be designed and carried out that will detect domestication selection impacts at several traits of interest with specified precision. Rationale: To develop a domestication selection study for upper Yakima spring chinook that is sufficiently powerful to detect effects but also does not violate broodstock composition rules. Methods: Just prior to the time of this writing, a meeting of peer scientists with expertise in genetics and reproductive ecology was convened to begin problem definition and attempt to identify research approaches. Two major threads of thought were identified. Several scientists supported an approach that would maintain lines of pure wild and pure hatchery fish to afford the opportunity to observe and measure traits diverging under presumed domestication selection. A second dominant approach would measure comparative performance of a suite of fitness traits in a controlled population made up of hatchery- and wild-origin adults. Parentage would be tracked using DNA markers. During 2001, project scientists with collaboration from peer scientists will develop a menu of feasible domestication selection monitoring plans. The approach taken will probably involve measurement of a suite of traits in the progeny of hatchery and wild matings, focusing initially on first generation effects. Ideally these test groups will be compared in wild and hatchery environments. Size of study will be determined by power analysis and by modeling the genetic effects of modifying broodstock rules to allow hatchery fish to be used as broodstock. This work will be augmented by pre- and post-supplementation comparisons of various traits. |
| 4. | Objective: Ecological Interactions: Develop methods to assess ecological impacts of supplementation on non-target taxa, and impacts of strong interactor taxa on productivity of targeted stocks. |
| 4.a | Task: Avian predation index: Develop methods to index impact of avian predation on annual smolt production of Yakima Subbasin salmon and steelhead. Hypothesis: Avian predators are capable of significantly depressing smolt production and accurate methods of indexing avian predation across years can be developed. Rationale: The loss of wild spring chinook salmon juveniles to various types of avian predators has long been suspected as a significant constraint on production and could limit the success of supplementation. The index will consist of two main components; 1) an index of bird abundance and 2) an index of consumption. Methods: An index will be calculated for each major bird predator. Methods to determine the feasibility of accomplishing these two components will be tested. Piscivorous birds will be counted from either an inflatable raft, driftboat, or jetsled depending upon water conditions. Shortly after or during bird censuses a consumption index will be developed. Observational and direct methods will be attempted to determine which methods are most appropriate for each bird species. Birds that swallow their prey above water (e.g., heron) might be evaluated using behavioral observations and those that swallow their prey underwater (e.g., merganser) might be evaluated using direct methods such as stomach content examination. |
| 4.b | Task: Fish predation index: Develop methods to index impact of piscivorous fish on annual smolt production of Yakima Subbasin salmon and steelhead. Hypothesis: Fish predators are capable of significantly depressing smolt production and simple and accurate methods of indexing fish predation across years can be developed. Rationale: Develop an index of the mortality rate of upper Yakima spring chinook attributable to piscivorous fish in the lower Yakima River. This index will be used to estimate the contribution of in-basin predation to fluctuations in hatchery and wild smolt-to-adult survival rate. Methods: The abundance of all major piscivorous fish species will be estimated during the smolt outmigration in representative reaches of the lower Yakima, and predator-specific smolt consumption data will be gathered in the same reaches. From this data, reach-specific Predation Indices will be calculated. Estimates of salmonids consumption take into account water temperature, mean weight of predator, mean number of salmonids in each predators gut, and mean weight of prey items at ingestion in the gut contents. These variables are used in the following equation (Ward et al. 1995) to estimate the predation index. Results from representative study reaches will be extrapolated from the Yakima Confluence to Roza Dam. |
| 4.c | Task: Indirect predation: Determine the impact of the abundance of hatchery smolts on the survival of commingled smolts (wild and hatchery) via alterations in the behavior of non-salmonid predators. Hypothesis: H0: Survival does not differ for groups of outmigrants that are or are not commingled with hatchery smolts. Rationale: The release of hatchery salmonids may enhance or decrease the survival of wild salmonid smolts by altering the functional or numerical response of predators. For example, predators may increase consumption of wild fish by switching prey preferences from invertebrates to fish, or may be attracted to areas where hatchery fish are released. Conversely, large numbers of hatchery fish may confuse or satiate predators resulting in enhanced survival of wild fish. Methods: To investigate this interaction, a series of release-specific environmental variables will be regressed on the Chandler to McNary survival rates of a large number of groups of PIT tagged smolts. These smolts will have been released well above Chandler, and the test groups will “define themselves”: viz., be defined after the fact, as they are detected at Chandler. A test group will consist of the minimum number of fish estimated to estimate survival to McNary with specified power. One of the independent environmental parameters will be the weighted mean number of hatchery smolts passing Chandler while test group was passing; others will include discharge, temperature and turbidity in the lower Yakima and McNary pool, and the weighted mean smolt passage index at McNary. A significant correlation coefficient for the “hatchery smolt abundance” variable will be taken as evidence consistent with indirect predation. Corroborating evidence will be sought in observations of predator congregations at Chandler, Horn Rapids Dam, and other lower Yakima predation “hot spots”, and in consumption rates observed in predatory fish and birds. |
| 4.d | Task: Yakima River spring chinook competition/prey index: Determine whether space competition or limited prey abundance restricts production of upper Yakima spring chinook smolts. Hypothesis: Space and food competition can limit upper Yakima spring chinook production. Supplementation can increase spring chinook fry abundance enough to deplete prey & diminish spring chinook productivity Rationale: The abundance of prey may limit the number of spring chinook salmon juveniles that can be produced in the upper Yakima basin. For example, spring chinook salmon may compete with one another for a limited amount of food, which may increase in density-dependent mortality rates. Methods: We will monitor stomach fullness of spring chinook salmon parr during the summer and fall in three index areas over time. Stomach fullness will be calculated by dividing the dry weight of the stomach contents by the total body weight or other relevant denominator. Full stomachs will suggest that adequate food is available and that food is not limiting spring chinook production. |
| 4.e | Task: Non-Target Taxa of Concern (NTTOC) monitoring: Determine the impact of spring chinook supplementation on the abundance, distribution or size structure of 16 NTTOC in the Yakima basin. Hypothesis: H0: Spring chinook supplementation will not depress the stock status of NTTOC below specified levels. Rationale: To determine if the spring chinook supplementation program is impacting the abundance, distribution, or size structure of non-target taxa of concern (NTTOC). Method: We will compare pre- and post-supplementation data to determine potential impacts. Field efforts will include backpack and drift boat electrofishing, smolt counts at CJMF, and snorkeling. We will use NTTOC stock status (abundance, size structure, and distribution) monitoring, interactions index monitoring, and interactions experiments to evaluate changes for 16 NTTOC. |
| 4.f | Task: Pathogen sampling: Determine the impacts of pathogens on supplementation success and supplementation impacts on the incidence of pathogens in wild Yakima spring chinook smolts. Hypothesis: H0: Spring chinook supplementation will not increase the incidence of pathogens in wild smolts and inriver pathogens will not limit the success of the supplementation project. Rationale: In order to determine if supplementation increases the incidence of pathogens, we will monitor levels of pathogens compared to a baseline data set describing existing levels of pathogens in wild spring chinook prior to introduction of hatchery fish. Method: We will collect approximately 200 wild spring chinook smolts at CJMF throughout the migration period and later examine for fish pathogens using standard fish health screening protocols at a the WDFW fish health laboratory to calculate a fish pathogen index. |

g. Facilities and equipment

Anadromous salmonids in the Yakima Subbasin can probably be monitored more thoroughly than in any other river in the Pacific Northwest.  Full implementation of this project will increase monitoring power even further. All adults and jacks are enumerated via video monitoring at Prosser Dam in the lower Yakima, as well as Roza Dam on the middle Yakima, where the entire upper Yakima spring chinook run passes up a ladder and down a flume in an adult collection facility.  Therefore, “intrusive” (hands-on) monitoring of all upper Yakima hatchery and wild adults can be conducted at Roza, allowing the detection of marked fish that cannot be identified on video.  The right-bank ladder/denil/trap complex at Prosser Dam confers a similar capability.  Stock-specific counts of migrating smolts can be made at the Chandler Juvenile Monitoring Facility (also located at Prosser Dam), which is equipped with two PIT-tag detectors.  The project has four mobile PIT-tagging stations and trained tagging crews.  Smolts can be collected at Roza Dam (and at two other dams between Roza and Prosser), so that survival and outmigration timing data can be estimated from tagged fish released above Prosser.  The project also has a number of portable PIT-tag detectors, allowing the enumeration of tagged or untagged smolts and juveniles in virtually any portion of the basin. Undeveloped but potential adult and smolt monitoring facilities also exist at Horn Rapids Dam (Wanawish) on the extreme lower Yakima, at Easton Dam on the extreme upper Yakima, and Cowiche Dam on the lower Naches.

The state-of-the-art hatchery at Cle Elum and associated acclimation sites have a capacity to produce 810,000 spring chinook smolts that can be segregated into experimental rearing treatments from the eyed egg stage through release.  An addition to the hatchery has an experimental spawning channel for evaluating differences in reproductive success and associated behaviors of hatchery and wild fish.  The hatchery and Chandler juvenile monitoring facility also includes facilities for juvenile behavior studies.  The project has  hatcheries at Prosser Dam and Marion Drain capable of rearing multiple treatment groups of fall chinook and coho.  The Prosser Dam adult trap and the Prosser hatchery are currently being used to collect returning adults in an effort to develop locally adapted fall chinook and coho broodstocks.

The project has within itself (WDFW genetics lab) or through the auspices of collaborating entities (UW genetics lab) the facilities and personnel to conduct state-of-the-art allozyme and microsatellite DNA analyses.  Similarly, the project has made arrangements with other entities (NMFS, USFWS) to conduct comprehensive physiological and pathological analyses of hatchery and wild fish.

h. References

Anonymous.  1990. Yakima Subbasin Plan.

Berejikian, B.A., E.P. Tezak, S.L. Schroder, C.M. Knudsen, and J.J. Hard.  1997.

Reproductive behavioral interactions between wild and captively reared coho salmon (Oncorhynchus kisutch).  ICES Journal of Marine Science 54:1040-1050.

Bilby, R. E., B. K. Fransen, and P. A. Bisson.  1996.  Incorporation of nitrogen and carbon from spawning coho salmon into the trophic system of small streams: Evidence from stable isotopes.  Canadian Journal of Fisheries and Aquatic Sciences 53:164-173.

BPA (Bonneville Power Administration). 1993. Yakima /Klickitat Fisheries Project Planning Status Report.

Busack, C. 1990. Yakima/Klickitat Production Project genetic risk assessment. In Yakima/Klickitat Production Project preliminary design report, Appendix A.  Report, DOE/BP-00245-2.  Bonneville Power Administration, Portland, OR.

Busack, C.A., and K.P. Currens. 1995. Genetic risks and hazards in hatchery operations: Fundamental concepts and issues. American Fisheries Society Symposium 15: 71-80.

Busack, C., and C. Knudsen. A production-function based model of supplementation.  Transactions of the American Fisheries Society (in press).

Busack, C, C. Knudsen, A. Marshall, S. Phelps, and D. Seiler. 1991.Yakima Hatchery Experimental Design.  Progress Report,  DOE/BP-00102. Bonneville Power Administration, Portland, OR.

Busack, C., B. Watson, T. Pearsons, C. Knudsen, S. Phelps, M. Johnston. 1997. Yakima Fisheries Project Spring Chinook Supplementation Monitoring Plan.  Report, DOE/BP-64878-1. Bonneville Power Administration, Portland, OR.

Chilcote, M.W., S.A. Leider, and J.J. Loch. 1986. Differential reproductive success of hatchery and wild summer-run steelhead under natural conditions.  Transactions of the American Fisheries Society 115: 726-735.

Collis, K., R.E. Beaty, and B.R. Crain. 1995. Changes in catch rate and diet of northern squawfish associated with the release of hatchery-reared juvenile salmonids in a Columbia River reservoir.  North  American Journal of Fisheries Management 15: 346-35

CRITFC (Columbia River Intertribal Fish Commission). 1995. Wy-Kan-Ush-Mi Wa-Ksih-Wit (Spirit of the Salmon). Columbia River Anadromous Fish Restoration Plan of the Nez Perce, Umatilla, Warm Springs and Yakama Tribes.

Currens, K.P., and C. Busack. 1995. A framework for assessing genetic vulnerability.  Fisheries 20:24-31.

Dunnigan J.L., and L.L. Lamebull.  2000.  Lower Yakima River Predatory Fish Monitoring: 1999 Annual Report.  Bonneville Power Administration, Portland, Oregon.

Fast, D.E., J. Hubble, M. Kohn, and B. Watson. 1991. Yakima River spring chinook enhancement study.  Final report, DOE/BP-39461-9. Bonneville Power Administration, Portland, OR.

Fleming, I.A., and M.R. Gross.  1992.  Reproductive behavior of hatchery and wild coho salmon (Oncorhynchus kisutch): Does it differ? Aquaculture 103:101-121.

Hillman, T.W. 1989. Spatial interaction of juvenile chinook salmon and the redside shiner. Pages 209-247  in Don Chapman Consultants Inc., Summer and winter ecology of juvenile chinook salmon and steelhead trout in the Wenatchee River, Washington.

Hillman, T. W. and J. W. Mullan.  1989.  Effect of hatchery releases on the abundance and behavior of wild juvenile salmonids.  Pages 265-285 in Don Chapman Consultants Inc., Summer and winter ecology of juvenile chinook salmon and steelhead trout.

Hindar, K., N. Ryman, and F. Utter. 1991.  Genetic effects of  cultured fish on natural fish populations.  Canadian Journal of Fisheries and Aquatic Sciences 48:945-957.

Hoffmann, A., C. Busack, and C. Knudsen. 1994. Experimental designs for testing differences in survival among salmonid populations.  Report,  DOE/BP-00029-3. Bonneville Power Administration, Portland OR.

ISAB (Independent Scientific Advisory Board). 1998. Review of salmonid artificial production in the Columbia River Basin as a scientific basis for Columbia River production programs.  Northwest Power Planning Council, November, 1998.

Johnston, J. H., and N. H. Ringler.  1979. The occurrence of blow fly larvae (Diptera: Calliphoridae) on salmon carcasses and their utilization as food by juvenile salmon and trout.  The Great Lakes Entomologist 12:137-140.

Kapuscinski, A.R., and L.M. Miller. 1993. Genetic hatchery guidelines for the Yakima/Klickitat fisheries project. Public review draft.  Unpublished report to Yakima/Klickitat Fisheries Project.

Levy, S.  1997.  Pacific salmon bring it all back home.  BioScience 47:657-660.

Maynard, D.J., T.A. Flagg, and C.V.W. Mahnken. 1995. A review of seminatural culture strategies for enhancing the postrelease survival of anadromous salmonids.  American Fisheries Society Symposium 15: 307-316.

McIntyre, J.D., R.R. Reisenbichler, J. Emlen, R.L. Wilmot, and J.E. Finn.1988. Predation of Karluk River sockeye salmon by coho salmon and char. Fishery Bulletin 86:611-616.

McMichael, G.A., A. Fritts, and J.L. Dunnigan.  1998.  Lower Yakima River predatory fish census:  feasibility study 1997.  Bonneville Power Administration annual project report.  Portland OR.

Michael, J. H.  1995.  Enhancement effects of spawning pink salmon on stream rearing juvenile coho salmon: managing one resource to benefit another.  Northwest Science 69:228-233.

Miller, W.H., T.C. Coley, H.L. Burge, and T.T. Kisanuki. 1990.  Analysis of salmon and steelhead supplementation: emphasis on unpublished reports & present programs. Project 88-100, U.S. Department of Energy, Bonneville Power Administration, Portland, OR.

# Mullan, J.W.  1983.  Overview of Artificial and Natural Propagation of Coho Salmon

(Onchorhynchus kisutch) on the Mid-Columbia River.  Fisheries Assistance Office, U.S. Fish and Wildlife Service, Leavenworth, Washington.  December 1983.

Mullan, J.W.  1986.  Determinants of sockeye salmon abundance in the Columbia River, 1880s-1982: a review and synthesis.  Biological Report 86(12), September 1986, U.S. Fish and Wildlife Service, Fisheries Assistance Office, Leavenworth, Washington.

Mullan, J. W., A. Rockhold, and C. R. Chrisman.  1992.  Life histories and precocity of chinook salmon in the mid-Columbia River.  The Progressive Fish-Culturist 54:25-28.

Neeley, D. 1992.  Compiled analyses of 1991-92 entrainment/survival studies at Chandler smolt trap. Unpublished reports to the Post Release Survival Task Team of the Yakima Fisheries Project.

Neeley, D.  2001.  Annual report: Outmigration year 2000.  Part 2. Chandler Certification and Calibration (Spring Chinook and Coho).  Report to Bonneville Power Administration and the Yakima/Klickitat Fisheries Project.  April 12, 2001.

Nickelson, T.E., M.F. Solazzi, and S.L. Johnson. 1986. Use of hatchery coho salmon (Oncorhynchus kisutch) presmolts to rebuild wild populations in Oregon coastal streams. Canadian Journal of Fisheries and Aquatic Sciences 43:2443-2449.

NPPC (Northwest Power Planning Council). 1994. Columbia River Basin Fish and Wildlife Program. Adopted Nov. 15, 1982, amended Dec. 14, 1994.  Northwest Power Planning Council, Portland, OR.

Pearsons, T. N., G. A. McMichael, E. L. Bartrand, M. Fischer, J. T. Monahan, and S. A. Leider. 1993.  Yakima  Species Interactions Study.  Annual Report, DOE/BP-01483-3. Bonneville Power Administration, Portland, OR.

Pearsons, T. N., G. A. McMichael, S. W. Martin, E. L. Bartrand, J. A. Long, and S. A. Leider. 1996. Yakima River Species Interactions Studies.  Annual Report, DOE/BP-99852-3. Bonneville Power Administration, Portland, OR.

Peery, C. A., and T. C. Bjornn.  1996.  Small-scale investigations into chinook salmon supplementation strategies and techniques: 1992-1994.  Idaho Cooperative Fish and Wildlife Unit, Technical Report 96-3.

Peterman, R.M. 1987. Review of the components of recruitment of Pacific salmon.  Pages 417-429 in M.J. Dadswell, R.J. Klauda, C.M. Moffitt, R.L. Saunders, R.A. Rulifson and J.E. Cooper, eds. Common strategies of anadromous and catadromous fishes.

RASP (Regional Assessment of Supplementation Planning). 1992. Supplementation in the Columbia River Basin, Parts 1-5. Report, Bonneville Power Administration.

Reeves, G.H., F.H. Everest, and J.D. Hall. 1987.  Interactions between the redside shiner

(Richardsonius balteatus) and the steelhead trout (Salmo gairdneri) in western Oregon: the influence of water temperature.  Canadian Journal of Fisheries and Aquatic Sciences 44(9): 1603-1613.

Reisenbichler, R.R.. 1997. Genetic factors contributing to declines of anadromous salmonids in the Pacific Northwest.  Pages 223-244 in D.J. Stouder, P.A. Bisson, and R.J. Naiman, eds. Pacific Salmon & their Ecosystems: Status and Future Options.  Chapman.

Sandford, B.P., and T.E. Ruehle. 1996. Juvenile salmonid PIT-tag studies at Prosser dam and Chandler canal fish collection facility, Yakima River, 1991 and 1992.  Final Report. DOE/BP-07099-2. Bonneville Power Administration, Portland, OR.

Schroder, S.L. and C.M. Knudsen.  1996.  Review of fish marking and tagging procedures suitable for the NATURES program.  Pages 128-166 in D.J. Maynard, T.A. Flagg and C.V.W. Mahnken, eds. Development of a Natural Rearing System to Improve Supplemental Fish

Shively, R.S., P.P. Poe, and S.T. Saunter. 1996.  Feeding response by northern squawfish to a hatchery release of juvenile salmonids in the Clearwater River, Idaho. Transactions of the American Fisheries Society 125: 230-236.

Shoals, W.H., and R.J. Hillock. 1979.  An evaluation of rearing fall-run chinook salmon, Oncorhynchus tshawytscha, to yearlings at Feather River Hatchery, with a comparison of returns from hatchery and downstream releases. California Fish and Game 64: 239.

Smoker, W.A. 1956. Evaluation to the potential salmon and steelhead production of the

Yakima River to the commercial and recreational fisheries. Washington Department of Fisheries. Report Number  01, 136.

Steward, C.R. and T.C. Bjornn. 1990. Supplementation of salmon and steelhead stocks with hatchery supplementation: A synthesis of published literature.  U.S. Department of Energy, Bonneville Power Administration, Project 88-100. Portland, OR.

Swain, D.P., and B.E. Riddell. 1990. Variation in agonistic  behavior between newly emerged juveniles from hatchery and wild populations of coho salmon, Oncorhynchus kisutch. Canadian Journal of Fisheries and Aquatic Sciences 47: 566-571.

Tabor, R. A., R. S. Shively, and T. P. Poe.  1993.  Predation on juvenile salmonids by smallmouth bass and northern squawfish in the Columbia River near Richland, Washington.  North American Journal of Fisheries Management 13:831-838.

Waples, R.S. 1991. Genetic interactions of hatchery and wild  salmonids: lessons from the Pacific Northwest. Canadian Journal of Fisheries and Aquatic Sciences 48(Supplement 1): 124-133.

Waples, R.S., G.A. Winans, F.M. Utter, and C. Mahnken. 1990.   Genetic monitoring of Pacific salmon hatcheries. NOAA Technical Report NMFS 92.

Ward, D. L., J. H. Petersen, and J. J. Loch.  1995.  Index of predation on juvenile salmonids by northern squawfish in the lower and middle Columbia River and in the lower Snake River.  Transactions of the American Fisheries Society 124:321-334.

Watson, B.D. 1993. Proposed natural production objectives for upper Yakima spring chinook under the Yakima/Klickitat Fisheries Project.  Internal YFP report.

Williams et al. 1996.  Return to the river: restoration of salmonid fishes in the Columbia River ecosystem.  Idependent Scientific Review Group, Northwest Power Planning Council, 10 September, 1996.

Wood, C. C.  1987.  Predation of juvenile Pacific salmon by the common merganser (Mergus merganser) on eastern Vancouver Island.  I: Predation during the seaward migration.  Canadian Journal of Fisheries and Aquatic Sciences 44:941-949.

# Section 10 of 10. Key personnel

Neal S. Burres

# EDUCATION

Post-doctoral Associate, Pharmacology, Yale University, 1987

Ph.D., Biochemistry, University of Alberta, 1985

B.S., Biochemistry, Washington State University, 1979

# RECENT PREVIOUS EMPLOYMENT

RISK CONTAINMENT BIOLOGIST, Washington Department of Fish and Wildlife, 2000-present

DIRECTOR SCREENING, Aurora Biosciences Corporation, La Jolla, CA, 1996-1997

ASSOCIATE RESEARCH FELLOW, Abbott Laboratories, Abbott Park, IL, 1989-1996

SENIOR SCIENTIST, Harbor Branch Oceanographic Institution, Fort Pierce, FL, 1987-1989

CURRENT RESPONSIBILITIES – Monitoring and evaluation of non-target taxa of concern associated with spring chinook salmon supplementation within the Yakima Klickitat Fisheries Project.  Field research, data management and analysis, including fish abundance, size and distribution in the Yakima River and its tributaries.

EXPERTISE – Over 14 years of investigating the chemistry and biology of microbes, plants and marine organisms.  Field collection, assay development and characterization of natural products.  Mark-recapture and removal-depletion methods for population estimates.  Research has resulted in 30 peer-reviewed publications and 9 patents.

# FIVE PEER-REVIEWED PUBLICATIONS

Zlokarnik G., Negulescu P.A., Knapp T.E., Mere L., Burres N., Feng L., Whitney M., Roemer K. and Tsien R.Y.  Quantitation of transcription and clonal selection of single living cells with ß-lactamase as reporter.  Science.  279:84-88, 1998.

Brill G.M., Premachandran U., Karwowski J.P., Henry R., Cwik D.K., Traphagen L.M., Humphrey P.E., Jackson M., Clement J.J., Burres N.S. and McAlpine J.P. Dibefurin, a novel fungal metabolite inhibiting calcineurin phosphates activity.  J. Antibiotics, 49: 124-128, 1996.

Burres N.S., Premachandran U., Hoselton S., Cwik D., Hochlowski J.E., Ye Q., Sunga G.N., Karwowski J.P., Jackson M., Whittern D.N. and McAlpine J.B.  Simple aromatics identified with a NFAT-lacZ transcription assay for the detection of immunosuppresants.  J. Antibiotics 48:380-386, 1995.

Clement J., Burres N., Jarvis K., Chu D., Swiniarski J. and Alder J.  Biologic characterization of a novel antitumor quinolone.  Cancer Research 55:830-835, 1995.

Gunawardana G.P., Kohmoto S. and Burres N.S. New cytotoxic acridine alkaloids from two deep-water marine sponges of the family Pachastrellidae.  Tet. Letters 30:4359-4362, 1989.

JAMES L. DUNNIGAN

Department of Natural Resources

Fisheries Program

Yakama Nation

(509) 966-4975

# BACKGROUND

1997-present:  		Fisheries Biologist, Yakama Nation, Toppenish,

Washington.

1996-1997:		Fisheries Biologist, US Forest Service, Coeur d’ Alene

Idaho.

1994-1996:  		M.S. Fisheries Resources, University of Idaho, Moscow.

1988-1993:  		B.S. Wildlife Resources, University of Idaho, Moscow.

# SELECTED PUBLICATIONS

Dunnigan, J.L., D.H. Bennett, and B.E. Rieman. 1996. The effects of forest management on cutthroat trout in the Coeur d’ Alene River system, Idaho.  Proceedings of the Forest Fish Conference. Calgary, Alberta.

# DAVID E. FAST

Fisheries Resource Management

P.O. Box 151

Toppenish, Washington    98948

Work:  509-966-5291

## Education

University of Washington, Seattle, Washington

Doctor of Philosophy in Fisheries Science, 1987.

University of Puerto Rico, Mayaguez, Puerto Rico

Master of Science in Marine Sciences, 1974.

St. John's University, Collegeville, Minnesota

Bachelor of Science in Zoology, 1969.

### Research Experience

1988-Present:  Research Manager. Fisheries Resource Management  Program, Yakima Nation. Responsible for the design, development, and implementation of a major supplementation and research facility to test the concept of using artificial production to rebuild natural spawning populations of spring

chinook salmon in the Yakima Basin. Write detailed project plans, develop short and long-term project goals and objectives, and supervise professional and technical staff.

1985-1988:  Project Leader. Spring Chinook Enhancement Study.

Responsible for research project designed to determine the best methods of enhancing the spring chinook salmon population in the Yakima Basin.  Evaluate survival through various life stages and total production of naturally producing salmon. Determine methods of supplementation with hatchery-reared fish while minimizing adverse genetic impacts.

Fast, D.E. 1987.  The Behavior of salmonid alevins in response to light, velocity and dissolved oxygen during incubation.

Pages 84-92 in Salmonid Migration and Distribution Symposium (E.L. Brannon, ed.), School of  Fisheries, University of Washington, and Directorate for Nature Management, Norway, Trondheim, Norway.

Fast, D.E., J.D. Hubble, T.B. Scribner, M.V. Johnston, W.R. Sharp.

1989.  Yakima/Klickitat Natural Production and Enhancement Program.  1989 Annual Report to Bonneville Power Administration.   Project 88-120.  107 pp.

Fast, D.E.  1989.  Supplementation Strategies For The Yakima/Klickitat Production Facility.  Pages 143-147 in Northwest Fish Culture Conference Proceedings (R.Z. Smith, ed.).

Fast, D.E., J.D. Hubble, M.S.Kohn, and B.D.Watson. 1991.  Yakima River Spring Chinook Enhancement Study.  Project Completion Report to Bonneville Power Administration.  Project 82-16.  Volume 1 - 345 pp. and Volume 2 (Appendices) 133 pp.

JOEL HUBBLE

Department of Natural Resources

Fisheries Program

Yakama Nation

(509) 966-4975

# BACKGROUND

1993-present:  		Fisheries Biologist III, Yakama Nation, Toppenish,

Washington.

1989-1993:  		Fisheries Biologist II, Yakama Nation, Toppenish,

Washington.

1979-1988:  		Fisheries Biologist I, Yakama Nation, Toppenish,

Washington

1978-1979:  		Fisheries Biologist I, Washington Department of Game

1992:  		M.S. Biology, Central Washington University

1978:		B.S. Fisheries, University of Washington

# SELECTED PUBLICATIONS

Fast D., J. Hubble, M. Kohn, B. Watson.  1991.  Yakima River Spring Chinook Enhancement Study, Final Report. Bonneville Power Administration, DOE/BP-39461-9.

MARK V. JOHNSTON

Department of Natural Resources

Fisheries Program

Yakama Nation

(509) 966-4975

# BACKGROUND

1989-present:  		Fisheries Biologist, Yakama Nation, Toppenish,

Washington.

1986-1989:		Fish Biologist, Grant County PUD, Ephrata, Washington.

1982-1986:  		B.S. Wildlife Management, Central Washington University

JOHN McCONNAUGHEY

Fisheries Resources Management

Yakama Nation

(509) 966-5156

yinykfp@wolfenet.com

BACKGROUND

1997-present:		Fisheries Biologist, Yakama Nation.

1992-1997:		Fisheries Biologist IV, Department of Marine and Wildlife Resources, Pago Pago, American Samoa.

1999-1992:		Research Analyst II, Alaska Dept. of Fish and Game, Division of Commercial Fisheries, Juneau, AK.

1984-1985:		Fisheries Biologist I, Alaska Dept. of Fish and Game, Susitna River Hydro Studies, Anchorage, AK.

1982-1984:		M.S., Fisheries Science, University of Alaska Southeast.

1974-1977:		B.S., Biology, University of Oregon.

## WILLIAM SHARP

Department of Natural Resources

Fisheries Program

Yakama Nation

(509) 966-4975

# BACKGROUND

1989-present:  		Fisheries Biologist, Yakama Nation, Toppenish,

WA

1988-1989:	Fisheries Biologist, US Fish and Wildlife Service, Vancouver,WA

1987-1987:  	Fisheries Biologist, Idaho Department of Fish and Game, Boise, ID

1983-1986:		Fisheries Biologist, US Army Corps of Engineers, Portland

1987:	B.S., Natural Resource Management, Colorado State University

BRUCE  D. WATSON

Fisheries Resources Management

Yakama Nation

(509) 966-5156

yinykfp@wolfenet.com

BACKGROUND

1984-present:		Fisheries Biologist/information specialist, Yakama Nation.

1981-1984:		Masters Program, University of Idaho (did not complete thesis).

1974-1976:		B.S. Zoology, University of Massachusetts.

1967-1971:		B.S. Psychology, Dartmouth College

SELECTED PUBLICATIONS

[Principal author of] YIN (Confederated Tribes and Bands of the Yakama Indian Nation). 1990. Yakima River Subbasin Salmon and Steelhead Production Plan.  Prepared by the Confederated Tribes and Bands of the Yakama Indian Nation, Toppenish, WA; and Washington Department of Fisheries and Department of Wildlife, Olympia, WA; for the northwest Power Planning Council and Agencies and Indian Tribes of the Columbia Basin Fish and Wildlife Authority.

Fast, D.E., J. Hubble, M. Kohn and B. Watson. 1991. Yakima spring chinook enhancement study: Final Report.  Bonneville Power Administration, Division of Fish and Wildlife, Project 82-16.

Lichatowich, J. And B. Watson. 1993.  Use of artificial propagation and supplementation for rebuilding salmon stocks listed under the Endangered Species Act.  Bonneville Power Administration, Portland, OR.

Watson, B.D. 1993. Proposed natural production objectives for upper Yakima spring chinook under the Yakima/Klickitat Fisheries Project.  Internal YFP report.

Busack, C., B. Watson, T. Pearsons, C. Knudsen, S. Phelps and M. Johnston. 1997. Yakima Fisheries Project Spring Chinook Supplementation Monitoring Plan.  Unpublished report for the Yakima/Klickitat Fisheries Project.

CRAIG A. BUSACK

Resource Assessment Division

Fish Management Program

Washington Department of Fish and Wildlife

(360) 902-2765

busaccsb@dfw.wa.gov

BACKGROUND

1988-present:  	Research Scientist, Washington Department of Fish and Wildlife (until 1994 Washington Department of Fisheries)

1983-1988: 	 Assistant Professor of Biology, University of Mississippi.

1981-1983:	NSERC Visiting Postdoctoral Fellowship, Pacific Biological Station, Nanaimo, British Columbia.

1977-1981:	Ph.D.Genetics, University of California, Davis.

1975-1977: 	M.S. Genetics, University of California, Davis.

1973-1975: 	 B.S. Genetics, University of California, Davis.

SELECTED PUBLICATIONS

Busack, C. 1990.  Yakima/Klickitat Production Project genetic risk assessment. In   Yakima/Klickitat Production Project Preliminary Design Report, Appendix A.  Bonneville Power Administration, DOE/BP-00245-2.

Hoffmann, A., C. Busack, and C. Knudsen. 1994. Experimental designs for testing  differences in survival among salmonid populations.  Report,  DOE/BP-00029-3. Bonneville Power Administration, Portland OR.

Busack, C., and K.P. Currens. 1995.  Genetic risks and hazards in hatchery operations: Fundamental concepts and issues.  AFS Symposium 15: 71-80.

Currens, K.P., and C. Busack. 1995. A framework for assessing genetic vulnerability.  Fisheries 20: 24-31.

Busack, C., B.  Watson, T.  Pearsons, C.  Knudsen, S.  Phelps, M.  Johnston.  1997.  Yakima Fisheries Project Spring Chinook Supplementation Monitoring Plan. Bonneville Power Administration, Portland, Oregon.  DOE/BP-64878-1.

Busack, C. and C. Knudsen. A production -function based model of supplementation dynamics.  Transactions of the American Fisheries Society (in review).

Busack, C., C. Knudsen, and S. Phelps.  The effective size advantage of factorial mating in fish hatcheries. (in prep)

Curtis M. Knudsen

Resource Assessment Division

Fish Management Program

Washington Department of Fish and Wildlife

(360) 902-2761

knudscmk@dfw.wa.gov

Background:

1985-present:	Fisheries Biologist, Washington Department of Fish and Wildlife

1984-1985:	M.S. Fisheries, University of Washington

1982-1983:	Fishery Biologist, Fisheries Research Institute, University of Washington

1979-1982:	B.S. Fisheries Science - University of Washington

Selected Publications:

Knudsen, C.M.  1988.  Bias and variation in stock composition estimates due to scale regeneration.  American Fisheries Society Symposium 7:63-71.

Hoffmann, A., C. Busack and C. Knudsen. 1994.  Experimental designs for testing differences in survival among salmonid populations.  Report to Bonneville Power Administration, Contract No.DEAI79-93BP00029.  71 pp.

Schroder, S.L.  C.M. Knudsen, E.C. Volk.  1995.  Marking salmon fry with strontium chloride solutions.  Canadian Journal of Fisheries and Aquatic Sciences 52:1141-1149.

Berejikian, B.A., E.P. Tezak, S.L. Schroder, C.M. Knudsen, and J.J. Hard. 1997.  Reproductive behavioral interactions between captively reared and wild coho salmon (Oncorhynchus kisutch).  ICES Journal of Marine Science 54: 1040-1050.

Busack, C., and C. Knudsen.  A production-function based model of supplementation

dynamics.  Transactions of the American Fisheries Society. (in review)

TODD N.  PEARSONS

Resource Assessment Division

Fish Management Program

Washington Department of Fish and Wildlife

(509) 925-4467

pearstnp@dfw.wa.gov

BACKGROUND

1992-present:  	Fish Biologist, Washington Department of Fish and Wildlife (until 1994 Washington Department of Wildlife)

1986-1992: 	Graduate Research Assistant, Oregon State University

1989-1994:	Ph.D., Fisheries Science, Oregon State University

1986-1989: 	M.S., Fisheries Science, Oregon State University

1981-1985:		B.S., Aquatic Biology, Univ. of California, Santa Barbara

SELECTED PUBLICATIONS

Busack, C., B. Watson, T. Pearsons, C. Knudsen, S. Phelps, M. Johnston.  1997.  Yakima Fisheries Project Spring Chinook Supplementation Monitoring Plan.  Bonneville Power Administration, Portland, Oregon.  DOE/BP-64878-1.

Pearsons, T. N., G. A. McMichael, K. D. Ham, E. L. Bartrand, A. L. Fritts, and C. W. Hopley.  1998.  Yakima River Species Interactions Studies.  Progress Report 1995-1997 submitted to Bonneville Power Administration, Portland.

Pearsons, T. N., and A. L. Fritts.  1999.  Maximum size of chinook salmon consumed by juvenile coho salmon.  North American Journal of Fisheries Management 19:xx-xx.

Pearsons, T. N., S. R. Phelps, S. W. Martin, E. L. Bartrand, and G. A. McMichael.  Accepted.  Gene flow between resident and anadromous Oncorhynchus mykiss in the Yakima basin: Ecological and genetic evidence.  In P. Howell and D. Buchannan editors, proceedings of the inland rainbow trout workshop.  Oregon State University Press, Corvallis.

Pearsons, T.N., H.W. Li, and G.A. Lamberti.  1992.  Influence of habitat complexity on resistance to flooding and resilience of stream fish assemblages. Transactions of the American Fisheries Society 121:427-436.

STEVEN L.  SCHRODER

Resource Assessment Division

Fish Management Program

Washington Department of Fish and Wildlife

(360) 902-2751

schrosls@dfw.wa.gov

BACKGROUND

1990-present:  	Research Scientist II, Washington Department of Fish and Wildlife (until 1994 Washington Department of Fisheries)

1981-1990: 	Research Scientist I, Washington Department of Fisheries

1980-1981:	Fisheries Biologist (III & IV), Washington Department of Fisheries

1973-1981: 	Ph.D., University of Washington

1971-1973: 	M.S., University of Washington

1969:				B.S., University of Washington

SELECTED PUBLICATIONS

Volk, E.C., S.L. Scroder, J.J. Grimm, and S. Ackley.  1994.  Use of bar code symbology to produce multiple thermally induced otolith marks.  Trans.  Am.  Fish.  Soc.  123:811-816.

Schroder, S.L., C.M. Knudsen, and E.C. Volk.  1995.  Marking salmon fry with strontium chloride solutions.  Can. J.  Fish.  Aquat.  Sci.  52:1141-1149.

Schroder, S.L., C.M. Knudsen, E.C. Volk, and J.J. Grimm.  1996.  Marking embryonic and newly emerged salmonids by thermal events and rapid immersion in alkaline-earth salts.  Bull.  Nat.  Res.  Inst.  Aquacult., Suppl. 2:79-83.

Maynard, D.J., T.A. Flagg, C.V.W. Mahnken, and S.L. Schroder.  1996.  Natural rearing technologies for increasing post release survival of hatchery-reared salmon. Bull.  Nat.  Res.  Inst.  Aquacult., Suppl. 2:71-77.

Berejikian, B.A., E.P. Tezak, S.L. Schroder, C.M. Knudsen, and J.J. Hard.  1997.  Reproductive behavioral interactions between wild and captively reared coho salmon (Oncorhynchus kisutch).  ICES Journal of Marine Science 54: 1040-1050.