Project ID:	200001900

Title:	Tucannon River Spring Chinook Captive Broodstock Program

Section 9 of 10. Project description

a. Abstract

The Tucannon River spring chinook salmon stock represents the lowest geographic population in the Snake River Basin.  The stock is genetically distinct from other Snake River Basin stocks, and is listed as “threatened” under the ESA.  A decline in the Tucannon River spring chinook run since 1994, and predicted low returns, will not likely be adequate enough to sustain or rebuild the population to healthy levels.  In 1997, WDFW and the co-managers believed that extreme intervention (captive broodstock) was called for to prevent extinction.  This captive broodstock project is short-term (ending in 2008) to reduce the potential negative genetic risks posed by captive broodstock programs.

This program is designed to produce additional hatchery smolts for release into the Tucannon River between 2002 and 2008.  This program, in conjunction to the existing supplementation program, which has existed since 1985, will occur concurrently with habitat restoration efforts that are addressing the limiting factors within the Tucannon River Basin.  Other out of basin limiting factors (mainstem adult and juvenile dam passage problems) are also being addressed.  As proposed by the program, a maximum of 300,000 hatchery smolts will be released into the Tucannon River annually, with the expected outcome to produce between 500-600 hatchery origin adults annually in the future (2005-2010).  All or the majority of these returning adults will be left in the river to spawn naturally to increase natural production in the Tucannon River.

For FY2002, five brood years (1997-2001) of spring chinook will be reared at Lyons Ferry Hatchery at various life stages.  Portions of the 1997-2000 brood year fish will become mature during the year.  The mature fish will be separated from the others and spawned.  The progeny will be reared at Lyons Ferry Hatchery and marked for evaluation purposes before release in the Tucannon River.

b. Technical and/or scientific background

The Tucannon River basin drains a watershed of approximately 1,295 square kilometers, and contains cropland (dry and irrigated), rangeland, and forests.  Natural resource problems include high water temperatures in the lower reaches, irrigation diversion, sedimentation, loss of riparian vegetation, and passage problems.  Over the past 50 years, farming, livestock management, recreational activities, and catastrophic flood events have degraded the habitat.  Objectives adopted by the co-managers include: 1) improve adult pre-spawning survival, 2) improve juvenile survival, and, 3) utilize hatchery supplementation to increase natural production.  General strategies currently employed to achieve these objectives include improving habitat through instream structures and riparian re-vegetation, passage improvements at barriers, and hatchery supplementation (Tucannon Subbasin Summary 2001).  Specific WDFW strategies in the Subbasin Summary that this program addresses include, but are not limited to:

Strategy 6:  Use artificial production, as necessary, to maintain, restore or enhance indigenous fish populations and harvest opportunities.

Strategy 7:  Implement artificial production practices that minimize adverse effects on fish habitat and maintain the viability and stock characteristics of hatchery fish.

Strategy 8:  Continue to monitor and evaluate the spring chinook captive brood program.

Spring chinook salmon populations in the Tucannon River have steadily declined since the construction of the four lower Snake River dams.  Historical escapements to the Tucannon Basin were estimated at 2,400 salmon annually, and exceeded 5,000 fish as recently as 1953 (Bugert et al. 1991).  Population declines have been attributed to mortalities of juveniles and adults that occur during migration through the Snake and Columbia Rivers.  Habitat loss and alteration in the Tucannon River and variable ocean conditions have also contributed to the decline.  Habitat related factors and improvements are being addressed primarily through the Tucannon Model Watershed Program (Subbasin Summary – Entity 1, Objectives 1-3, 6) and Pataha Creek Model Watershed Program.  According to the 2000 FWP Artificial Production Primary Strategy… “Artificial production can be used, under the proper conditions, to (1) complement habitat improvements by supplementing native fish populations up to the sustainable carrying capacity of the habitat with fish that are as similar as possible, in genetics and behavior, to wild native fish…”  The Columbia Conservation District (CCD) and Pomeroy Conservation District (PCD), the respective lead entities for the two model watershed programs that make up the Tucannon subbasin, work cooperatively with WDFW and local staffs to tie various assessments and monitoring activities with WDFW to maintain consistency and cost efficiency.

Legislation under the Water Resources Development Act of 1976 has provided hatchery compensation for Snake River spring chinook salmon (Onchorynchus tshawytscha) mortalities caused by the construction and operation of the four lower Snake River hydro-power projects.  As a result, Lyons Ferry Hatchery was constructed and Tucannon Hatchery (Figure 1) was modified.  One objective of these hatcheries is to compensate for the annual loss of 1,152 Tucannon River spring chinook salmon.  Since 1984, WDFW has evaluated the success of the hatcheries in meeting this objective and has identified production adjustments to improve performance of the hatchery fish.  Starting in 1985, WDFW trapped a portion of each annual run of natural fish, and later, hatchery fish, for broodstock to use in the hatchery supplementation program.  All other returning salmon (natural and hatchery origin) remain in the river for natural spawning and production.  The supplementation program requires collection of 100 salmon from the Tucannon River (50 natural and 50 hatchery), to produce 132,000 smolts for release at 15 fish/lb.  Since 1993, WDFW has been authorized by NMFS to operate the hatchery

Figure 1.  WDFW / LSRCP hatchery facilities within the Tucannon subbasin.

supplementation program and has conducted associated research activities on the Tucannon River under a Section 10 direct take permit (1993-1998 Permit #848, 1998-present #1126 and #1129) (WDFW 1999).

Tucannon River spring chinook runs were relatively stable from 1985-1993 (mean run = 550 fish).  However, from 1994 to 1998, the average run declined to 187 fish (range 54-351).   In addition to the poor adult returns, floods during the winters of 1996 and 1997, coupled with relatively low redd counts because of the depressed runs, left the river with little natural production.  The estimated number of natural smolts from brood years 1994-1996 averaged less than 3,000 fish annually bases on smolt trapping efforts in the lower Tucannon River (Bumgarner et al, 2000).  Adults returning from those brood years are estimated to total only 50-60 fish.  In addition, hatchery production was less than expected to offset low production in the river.  LSRCP evaluation studies have determined the natural population of salmon has been below the replacement level for eight of the last nine brood years.   Conversely, fish reared in the hatchery program survive about four times better than the natural fish, and have generally been above the replacement level.  Therefore, hatchery production (either supplementation or captive broodstock) is critical to any attempt to rebuild the spring chinook run in the Tucannon River.

WDFW recognizes that unless the limiting factors that are causing the poor survival are alleviated, the population will eventually go extinct.  WDFW is hopeful that recent initiatives for habitat restoration in the Tucannon Basin (Tucannon Model Watershed Program; Tucannon Subbasin Summary 2001), more favorable ocean conditions, and continual adult and juvenile passage improvements at mainstem dams will be enough to return the natural population to above replacement, and the stock will rebound to healthy and stable levels.  For all of the above reasons, WDFW believes it is necessary to use a short-term captive broodstock program to rebuild/recover the Tucannon River spring chinook salmon run.

WDFW examined other alternatives besides captive broodstock.  1) WDFW could continue current supplementation program at existing levels and try to rebuild the population from the low number of fish currently returning and expected to return over the next few years.  This action will essentially “mine” all remaining wild fish from the river (or those that are trapped) and create a nearly 100% hatchery run.  This would not be consistent with ESA requirements or WDFW’s Wild Salmonid Policy (WSP).  In addition, this action will potentially cause low genetic variability in resulting progeny due to small founder population size, thus creating a bottleneck that may increase the rate of extirpation.  2) WDFW could introduce a non-endemic stock of spring chinook to the basin for a short term to increase the number of spawners in the river for natural production.  This action would not be consistent with ESA or WSP.  3) WDFW could increase the current hatchery program by trapping more adults from the river.  This strategy would fail as there are currently too few adults returning to increase the hatchery production level.  The hatchery broodstock goal has not been met in three of the last five years.   In addition, more fish would be ‘mined’ from the river, resulting in less natural production.  4) Initiate captive broodstock program.  This strategy will provide the boost in hatchery production (with the appropriate stock) without ‘mining’ more fish from the river.  However, multiple outcomes (both positive and negative) are possible, and hatchery practices (spawning, rearing, broodstock selection) need to be carefully planned before proceeding (Flagg and Manhaken 1995).

WDFW, along with the Tucannon River sub-basin co-managers (Nez Perce and Umatilla tribes) believe that a captive broodstock strategy provides the greatest potential for rebuilding or recovering the population in the short-term.  Long-term use of a captive broodstock for this population has not been recommended.  Because of the deleterious effects and potential risks to the population by a long-term use of a captive broodstock (Hard et al. 1992), WDFW proposes this as a short-term project only.  Measures proposed to improve system survival need to be acted upon if we hope to succeed in our rebuilding and recovery efforts.

The program is projected to produce approximately 290,000 eggs on an annual basis once three brood years have obtained maturity.  With an egg viability of 70% and fry to smolt survival rate of 70-80%, WDFW has estimated 150,000 smolts (15 fish/lb) will be available for release into the Tucannon River from Curl Lake Acclimation Pond (Figure 1).  Smolt production of that magnitude will double the current spring chinook smolt releases into the Tucannon River.  Based on smolt to adult survival rates of hatchery spring chinook in the Tucannon River, WDFW estimates that 240-280 adult fish will return from each brood year.   Combining that with the hatchery supplementation program, hatchery origin spring chinook runs in the Tucannon River should once again reach 500-600 fish/year.  Natural production will also add to the annual run size.

c. Rationale and significance to Regional Programs

The 2000 Fish and Wildlife Program (FWP) states that “No single activity is sufficient to recover and rebuild fish and wildlife species in the Columbia River Basin,” and that “protection, mitigation, and recovery efforts must involve a broad range of strategies for habitat improvement and protection, hydrosystem reform, artificial production and harvest management.”  There also must be coordination among actions taken at the subbasin, province, and basin levels.   Based on the Subbasin Summary for the Tucannon River, strategies have been proposed that will cover a broad range of problems in the system.  In addition, as stated in the 2000 FWP, “when fish runs fall to extremely low levels, artificial production (i.e., such as this captive broodstock program) may be the only way to keep enough of that population alive in the short term so that it has a chance of recovering in the long term.”  Based on these two statements, and the coordinated actions currently being carried out within the Tucannon River Basin, this captive broodstock program will be significant to the regions efforts in rebuilding salmon runs.

This program is also supported by various measures in the Northwest Power Planning Council’s (NPPC) Fish and Wildlife Program (1994), and was recently supported by all managing entities within the Snake River Basin at the Columbia River Fish Management Plan (CRFMP) subbasin re-negotiations.  The program will support the native run of Tucannon River spring chinook salmon in its native habitat (2.2A), and will contribute to the rebuilding of the Snake River spring chinook salmon run (4.1A).  Further, as stated under the Council’s salmon and steelhead rebuilding principles (4.1A); 1) priority should be given to activities that aim to rebuild weak upriver populations, including populations listed under the ESA (i.e. Tucannon River), 2) this project is linked to the Model Watershed Program for the Tucannon River.

Also, this project represented a new production initiative (7.4, 7.4A, 7.4A.1) (NPPC 1994).  Therefore, WDFW satisfied the terms of the NPPC’s 3-step Process by developing and completing a Master Plan (7.4B, 7.4B.1) for the spring chinook hatchery program in the Tucannon River.  The 3-step process involved 1) conceptual planning represented under the Fish and Wildlife Program primarily by Master Plan development and approval, 2) preliminary design, cost estimation, and NEPA compliance, and 3) final design review prior to construction.  The Tucannon Master Plan (WDFW et al. 1999), conceptual designs and cost estimations were submitted to and reviewed and accepted by the Independent Scientific Review Panel (ISRP).  The ISRP then recommended to the NPPC that the program be funded for FY2000 and FY2001.

The captive brood program is also supported by RPA Action 176 -HGMP for Tucannon spring/summer chinook safety-net program.  While a Hatchery and Genetics Management Plan (HGMP) is not required until 2003 because we are currently working under a Section 10 Permit (#1126 and #1129; WDFW 1999), WDFW is in the process of writing an HGMP for the Tucannon River spring chinook.  The captive broodstock program is also supported by RPA Action 177 that states, “BPA shall implement and sustain NMFS approved safety-net projects”.

National Marine Fisheries Service’s Proposed Recovery Plan (1995) for Snake River salmon states, “Captive broodstock is primarily a procedure to prevent extinction”.  Further, “Captive broodstock, gene banks, and other supplementation programs should be considered for use in helping to conserve and maintain selected discrete populations until the predominating factors for decline can be alleviated”.  NMFS has concluded that “technology is sufficiently developed for Snake River captive broodstock programs to proceed,” and could be considered for use in recovery programs when:  1) extinction of a population is imminent or the population is at risk of severe inbreeding depression, 2) facing demographic risks; or 3) other methods of propagation are not expected to yield population stability in a timely manner.  All of those conditions exist for the Tucannon River spring chinook population.  Habitat objectives and strategies identified in the Subbasin Summary from the various entities will play critical roles in the success of the program (WDFW, Nez Perce Tribe, CRITFC, CTUIR, Columbia Conservation District, DOE, DNR, and NRCS).

A captive broodstock for Tucannon River spring chinook salmon is consistent with the broad based goals stated in the tribal recovery plan (Wy-Kan-Ush-Mi Wa-Kish-Wit 1995).  A successful captive broodstock program will, in the short term, restore the depressed spring chinook to at least pre-1994 levels in their historical range.  In addition, by returning more adults to spawn, the Tucannon River will be able to rely once again on natural production to assist in recovery.  By successfully returning more adults, there will also be a greater opportunity to provide tribal fishery harvests, honoring treaty rights.  In addition, captive broodstock programs for Snake River spring/summer chinook are supported by recommendations in the Snake River Salmon Recovery Team’s report  (SRSRT 1994).

Hatchery supplementation efforts in the Tucannon River under the LSRCP have not been able to overcome the recent limiting factors (droughts, floods, and poor ocean conditions), though it does not mean the program has failed.  The proposed captive broodstock program will not replace the current hatchery supplementation program, but the two will work in conjunction to aid in recovery.  The annual juvenile production goal for captive broodstock progeny is 150,000 smolts to be released at 15 fish/lb, in addition to the current supplementation program of 132,000 smolts released at 15/lb.  Smolt releases of this magnitude should return adult numbers to pre-1994 levels.

The information gained from this captive broodstock program will enable the scientific community to better utilize hatcheries as a recovery tool for other threatened and endangered stocks of salmon in the Columbia and Snake River basins.  This proposed project has been developed by the WDFW (Bumgarner et al. 1998a) and supported by the U.S. Fish and Wildlife Service (LSRCP), the co-managers (Nez Perce and Umatilla Tribal fishery agencies) within the Tucannon River subbasin, and NMFS through the Section 10 Permit process (WDFW 1999).

d. Relationships to other projects

The Tucannon River Model Watershed Program (Project #9401806) will play a critical role in improving habitat conditions in the Tucannon River basin.  While habitat conditions in the major rearing areas of spring chinook in the Tucannon River are considered good, improvement to the watershed in marginal areas will increase the range where spring chinook can rear and should increase the natural production potential.  However, only unless adult spring chinook return to use the current and planned habitat restoration efforts will their efforts be worth much to this program.  Other Washington State funded initiatives (HB2496) for watershed restoration activities will also improve habitat (reduced water temperatures, increased woody debris, etc.) conditions in the Tucannon River basin.  All of these habitat restoration efforts will ultimately help improve spring chinook salmon survival and run sizes in the future.

Other related projects (#9604400 - Grande Ronde Basin Spring Chinook Captive Broodstock Program, #9801001 - Grande Ronde Basin Spring Chinook Captive Broodstock Program, #9801006 - Captive Broodstock Artificial Propagation, #9305600 - Assessment of Captive Broodstock Technology, #9801002 - Captive Rearing Initiative for Salmon River Chinook Salmon - M& E, #9806700 - Manchester Spring Chinook Broodstock Project) will play important coordination roles in sharing learned information regarding captive broodstock rearing and techniques.  Failures and successes learned by these programs will benefit the Tucannon River captive broodstock program.  Success within this program will also benefit other captive broodstock programs.  Captive broodstock programs for the Grande Ronde River and the captive rearing project for the Salmon River, and the Tucannon River project, are all attempting to rebuild, recover, or conserve a listed spring or summer chinook population within the Snake River Basin.

In addition to these Snake River basin related projects, WDFW has extensive expertise and experience with captive broodstock programs within the State of Washington from the Dungeness River (Smith and Wampler 1995) and the White River (Appleby and Keown 1994).  Proven and successful operations from these two programs will be incorporated into the Tucannon River captive broodstock plan.

e. Project history (for ongoing projects)

The Tucannon River spring chinook captive broodstock program was funded through the LSRCP from FY 97-99 for $235,000.  BPA has provided funding of $134,000 for FY 2000 and $98,420 for FY 2001.

Brief summaries of progress to date of the captive broodstock program have been included in Bumgarner et al. 1998b and Bumgarner et al. 2000.  Further, brief monthly reports regarding the status of the program have and will continue to be sent to NMFS per our Section 10 report requirements.  Results from the program to date are currently being compiled into the FY 2000 Captive Broodstock report.  WDFW expects this report to be completed and ready for distribution by May 2001.

WDFW currently has four brood years (1997-2000) of adult and juvenile spring chinook on hand at Lyons Ferry Hatchery.  All four brood years are being held separately, and the 1997-1999 brood years have been marked by family groups and currently reside in 20 ft circular rearing tanks.  The 2000 brood year fish are still rearing in 4 ft circular tanks and will be marked by family group in October, 2001.  Genetic samples, from the captive brood parents, have been sent to the WDFW Genetics Lab in Olympia, WA for analysis.

The 3-Step Review process of the Master Plan and the Environmental Assessment (with associated FONSI) were completed.  Facility modifications have been completed and include installation of rearing tanks, security fencing, and pond covers.  We received funding from BPA to install a roof covering the captive broodstock rearing area, but State of Washington engineering staff deemed the amount insufficient to build to their specifications.  However, this setback will allow natural photoperiod light to help regulate timing of maturity for the captive brood.  Additional funding to complete the roof will not be pursued.

Thirteen maturing females from the 1997 BY were found in 2000.  Of those, 12 were spawned with a total eggtake of 14,577 eggs.  Mean fecundity was estimated at 1,298 eggs/female, with egg survival estimated at 47%.  High egg mortality is most likely related to age of spawners (Age 3) and was expected for 3 year old captive brood females (Dan Witczak, WDFW Hurd Creek Hatchery Manager, Dungeness River Spring Chinook captive broodstock program, pers. comm. 2000).  Production of 3 year old females is not a goal (though was expected) for the Tucannon captive broodstock program.  The main emphasis will be to produce 4 and 5 year old fish, where egg survival is anticipated to be higher.

One success that was achieved compared to other existing captive broodstock program was maturation timing in 2000.  We documented only a one week delay from the natural fish in the river.  Because of the similar maturation/spawn timing, eight of the 12 spawned females were crossed with wild (unmarked) males from the supplementation program with the remaining four crossed with males from the 1997 captive brood.  WDFW feels this will be beneficial to the overall spring chinook stock by maintaining the genetic integrity for the future.

f. Proposal objectives, tasks and methods

The overall goal of this captive broodstock program is to quickly rebuild the number of adults returning to the system.  It will be critical to use progeny from the next few brood years because of the projected low run sizes.  Without increasing the number of progeny from those original brood years, there will be little chance the stock will rebound.  Returning adults from the captive broodstock population will be allowed to spawn in the river, allowing natural selection to determine fitness of the resulting population.  Four broad based goals were identified for the project: 1) Raise captive brood fish at Lyons Ferry Hatchery, 2) Spawn mature captive brood fish, 3) Rear and release captive brood progeny, and, 4) Disseminate the information collected and learned to other managers working with captive broodstocks.  Details on how we plan to meet these goals are as follows:

Operation and Maintenance Phase

Objective #1:  Raise captive broodstock.

Task a.  Conduct daily rearing and raising of captive brood fish.

Methods.  WDFW has 15 – 4 ft rearing tanks on station at Lyons Ferry.  These small tanks are used to rear, and keep separate before marking, the 15 unique “families” from each brood year as discussed in the Master Plan (WDFW et al. 1999).  Fifteen individual families will be selected based on the following criteria: 1) based on BKD screening (ELISA results) of females and 2) origin of parents.  Only females that were given a “Low” or “Below Low” ELISA result will be selected.  Priority is also given to females that are crossed Wild x Wild, Wild x Hatchery, and Hatchery x Hatchery, in that order.  During each spawning year, great efforts are made to avoid hatchery x hatchery crosses, which could contribute to domestication of the stock.  No juvenile natural-origin fish will be collected from the Tucannon River to create or supplement the captive brood population.  WDFW believes this may be a benefit as we don’t have to get more fish from the river, and we have a disease history of every fish that contributes to the program.  Under current spawning guidelines, eggs from an individual female are split into two lots.  Each egg lot is then fertilized by a different male to increase genetic diversity and provide insurance against non-viable males.  The same two males are then used on another female.  Eggs from each female are incubated separately.  Because of the fertilization process, progeny from those two females are half-sibling related.  To reduce the potential of half-sibling crosses when the fish mature, and to increase the overall effective population that originally contributed to the captive broodstock, females fertilized with the same two males are combined to create a "family" unit.  Fifteen unique “families” will be chosen from the 2001 brood year during FY2002 to complete our captive broodstock (1997-2001 BY’s).  Daily feeding, pond cleaning, medical treatments to control mortalities, and basic hatchery record keeping will follow standard hatchery practices.

Objective #2:  Spawn mature captive brood fish.

Task a.  Sort mature fish from immature fish.  Separate mature fish to spawning tank.  Conduct weekly checks for ripeness during spawning season.  Spawn all ripe fish and incubate fertilized eggs.

Methods.  Fish are raised to maturity in the eight 20’ rearing ponds installed at Lyons Ferry Hatchery.  Once the fish have been transferred to the larger rearing tanks, they will not be moved again unless survival rates are greater than anticipated, and density limits are exceeded.  Extra measures will be taken to limit human contact as much as possible (pond covers, security fencing, minimal cleaning).  As adults mature, fish that indicate they will spawn that year will be transferred to a separate adult holding raceway.  Mature adults are given prophylactic treatments of formalin to prevent fungus growth.  To increase the genetic variability of the progeny, 2x2 factorial crosses will likely be performed (identical procedure as in the hatchery supplementation program).  If spawn timing between the captive broodstock and the supplementation fish are similar, gametes may also be shared between the two to increase variability.  In addition, cryopreserved semen (that has been tested for fertilization success) collected since 1990 from wild origin Tucannon spawners may be utilized to increase genetic variability.  If the number of maturing adults exceeds the smolt program goal, some may be released into the Tucannon River to spawn naturally.  Or, if juvenile production goals are exceeded, extra fish have been proposed, by WDFW, for re-introduction of spring chinook into Asotin Creek.  The Asotin Creek spring chinook population is believed to be extinct (Bumgarner et al. 1998b).

Objective #3:  Rear captive brood progeny.

Task a.  Pick and record all dead eggs after shocking to determine fecundity and mortality of eggs from each spawned female.  Incubate fry until ponding, and then place all captive brood progeny in standard raceways for rearing.

Methods.  Following fertilization, eggs will be placed in Heath incubation trays.  All captive broodstock progeny will be reared in standard raceways at Lyons Ferry Hatchery, but will be separated from the hatchery supplementation program until marking is complete.  Following marking, some or all of the captive broodstock progeny will be mixed with the supplementation program fish.

All captive brood progeny will be marked in September (approximately Age 1).  It is unknown at this time what specific marks/tags will be given to the fish, though it will likely be blank wire tag (BWT) with no AD clip.   The BWT and no AD clip will allow hatchery personnel to avoid collection of captive brood progeny fish for the supplementation program.  Supplementation program fish will be marked with CWT/VI and no Ad clip.  Following marking, all captive broodstock progeny will be transferred to Tucannon Fish Hatchery.  In late February or early March, a portion or all of the captive brood progeny will be transferred to Curl Lake Acclimation Pond upstream of the hatchery for a minimum of three weeks acclimation.

Objective #4:  Disseminate information.

Task a.  Attend captive broodstock meetings and workshops.

Methods.  Learn or pass on information from/to other hatcheries regarding the captive broodstock program through captive broodstock meetings, fish culture conferences, and workshops.

Monitoring and Evaluation Phase

Objective #1:  Monitor and document survival, mortality, and maturity rates of captive brood fish.

Task a.  Assist hatchery staff in monthly record keeping of mortalities and maturation (by family group) for each brood year.

Methods.  WDFW will monitor survival rates and life history characteristics of captive brood fish in the hatchery.  As evaluation activities monitor the captive broodstock, it is likely that problems in rearing or release strategies will be identified.  Between the hatchery and evaluation staffs (including the co-manager Captive Broodstock Technical Committee), these problems can be quickly addressed and new recommendations/ procedures made to improve the survival of the fish.  Adverse effects may result from intensive artificial propagation, and may include inappropriate spawn timing, and changes in age structure, fecundity, fertility, or sex ratio of the propagated population.  These variables will be assessed in the captive population through the monitoring and evaluation phase of this program.

Objective #2:  Monitor and document mortality, survival, and viability of captive brood progeny.

Task a.  Assist hatchery staff in egg picking to determine mortality, survival, fecundity, and egg viability of collected captive brood eggs that were fertilized.

Methods.  Mortality, survival, fecundity, and egg viability will be monitored for the captive brood progeny and compared to the supplementation progeny.  Staff will monitor egg to fry, fry to smolt, and smolt to adult survival.  These evaluations of in-hatchery and out-of-hatchery performance and lessons learned will be integrated into the design of the rearing program to maximize survival at all life history stages.

Objective #3:  Permanently identify all 15 families from the 2000 brood year for captive broodstock rearing.

Task a.  Assist hatchery and tagging staff with marking (CWT & VI) of 2000 brood year fish for captive broodstock rearing.

Methods.  Initially, eighty juveniles will be selected from each “family” group, which will later be reduced to 30 fish/family.  Generally, selected progeny in the captive broodstock will represent 60 spawned fish from the supplementation program, with only one or two “families” at most that are full second generation hatchery origin.

The 30 fish selected from each tank will be uniquely marked by “family”.  Marking captive brood fish will consist of a CWT in the snout and adipose fin, and an alphanumeric Visual Implant (VI) tag behind the left or right eye.  Redundancy in marks and tags will allow for tag loss and will provide quick identification during spawning to prevent in-family matings.  CWT’s will also allow tracking of  “family” survival, growth, and maturation rates.  Visual implant tags, while primarily used for easy identification during spawning, will also provide individual (within family) data.

Objective #4:  Spawn mature captive brood adults.

Task a.  Assist hatchery staff in sorting of mature captive broodstock (Objective 2, Task a, O&M phase).

Methods.  Based on survival assumptions, WDFW anticipates that 100-150 females may be spawned in a given year (assuming three different brood years mature at the same time).  Mature fish will be sorted from immature fish with mature fish placed in a separate raceway.  Weekly checks will examine fish for ripeness during the spawning season following procedures described in the Master Plan (WDFW et al. 1999).  Mature fish will be identified by tags to prevent within family mating.

Objective #5:  Conduct genetic monitoring.

Task a.  Collect and analyze DNA samples from captive broodstock spawners, from parents to captive broodstock program, and returning spawners.

Methods.  Since the late 1980’s, the Tucannon spring chinook population (natural and hatchery origin) has been monitored for genetic changes through electrophoretic analysis.  Based on analysis to date, little change has occurred between the hatchery and natural population (Craig Busack, WDFW Geneticist, pers. comm.).  Because of the genetic risk associated with captive broodstocks, genetic monitoring will continue throughout the captive broodstock program.  It is anticipated that as captive brood origin adults return, both DNA and electrophoretic analysis will be conducted for comparisons with samples of hatchery and wild fish collected in the mid-1980’s.

Objective #6:  Disseminate information.

Task a.  Attend captive broodstock meetings and workshops.

Methods.  Critical to the success of this project will be the two-way information exchange between this and other captive broodstock programs within the Northwest.  Success and failures documented from other programs will be vital to our success.  It will also be important to inform the general public about recovery efforts for the Tucannon River.  All information learned under the captive broodstock program will be shared with other agencies through Section 10 monthly reports, technical meetings (Captive Broodstock Technical Oversight Committee (BPA funded projects) and Tucannon Technical Working Group (WDFW and co-managers)), annual captive brood reports for funded years, and possible peer-reviewed journal articles in the future once the program has terminated.

g. Facilities and equipment

Lyons Ferry and Tucannon Fish hatcheries are pre-existing spawning, rearing and release facilities with on-station personnel housing and tanker trucks for moving fish.  The existing supplementation program is fully funded under the LSRCP mitigation program for Snake River spring and fall chinook salmon and steelhead.  Each facility has space and pathogen free water supplies to accommodate the captive brood program.  The increase in juvenile production from the captive broodstock program will not dramatically affect the rearing capacity of either hatchery, though some minor production adjustments of other programs may be required.  WDFW engineering and hatchery maintenance crews were used to design and conduct the site preparation and plumbing modifications.  Specific equipment purchased for this program includes plumbing materials, large fiberglass rearing ponds, pond covers, basic aquaculture supplies (nets, crowders, pond covers, etc.), and fencing for security.  Most of these were a one time cost to the program, with personnel time, juvenile marking, and operation and maintenance cost for the remaining years.  Marking trailers (for marking broodstock and resultant progeny) will be supplied by WDFW, though tags (CWT, VI) and marking personnel salaries will be provided under the captive broodstock program.  Genetic samples will be analyzed at the WDFW Genetics Lab in Olympia, WA.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Appleby, A., and K. Keown. 1994. History of White River spring Chinook broodstocking and captive brood rearing efforts. Washington Dept. of Fish and Wildlife, Olympia, WA. | N |
| Bugert, R., C. Busack, G. Mendel, L. Ross, K. Petersen, D. Marbach, J. Dedloff. 1991. Lower Snake River Compensation Plan Tucannon River spring chinook salmon hatchery evaluation program 1990 Annual Report to U.S. Fish and Wildlife Service, Aff1/LSR-91-14, Cooperative Agreement 14-16-0001-90524. Washington Department of Fisheries, Olympia, WA. | N |
| Bumgarner, J., L. Ross, and M. Varney. 2000. Lower Snake River Compensation Plan Tucannon River Spring chinook salmon hatchery evaluation program 1998 and 1999 annual report to U.S. Fish and Wildlife Service, Cooperative Agreement 1448-14110-98-J057 and CA-14110-9-J070. Washington Dept. of Fish and Wildlife, Olympia, WA. Report #FPA00-17. | N |
| Bumgarner, J., H. Harty, G. Mendel, C. Busack, and S. Roberts. 1998a. A proposal for a captive broodstock program with Tucannon River spring Chinook salmon. Washington Dept. of Fish and Wildlife, Snake River Lab, Dayton, WA. | N |
| Bumgarner, J., L. Ross, D. Milks, and M. Varney. 1998b. Lower Snake River Compensation Plan Tucannon River Spring chinook salmon hatchery evaluation program 1997 annual report to U.S. Fish and Wildlife Service, Cooperative Agreement 14-48-14110-93-J038. Washington Dept. of Fish and Wildlife, Olympia, WA. Report #H98-06. | N |
| Flagg, T.A., and C.V.W. Mahnaken. 1995. An assessment of the status of captive broodstock technology for Pacific salmon: Final report. BPA Project #93-56, Portland, OR. | N |
| Hard, J.J., R.P. Jones, Jr., M. R. Delarm, and R.S. Waples. 1992. Pacific salmon and artificial propagation under the Endangered Species Act – Technical memorandum NMFS – NWFSC-2, Seattle, WA. | N |
| National Marine Fisheries Service, U.S. Dept. of Commerce, National Oceanic and Atmospheric Administration. March 1995. Proposed Recovery Plan for Snake River Salmon. | N |
| Northwest Power Planning Council. 1994. Columbia River Basin fish and wildlife program. December 1994. | N |
| Smith, C.J., and P. Wampler, editors. 1995. Dungeness River chinook salmon rebuilding project: Progress report 1992-1993. Olympia, WA. | N |
| Snake River Salmon Recovery Team. 1994. Final recommendation to National Marine Fisheries Service, Portland, OR. | N |
| Washington Department of Fish and Wildlife, Nez Perce Tribe, Confederated Tribes of the Umatilla Indian Reservation. 1999. Master plan for Tucannon River spring chinook captive broodstock program. 34 pp. | Y |
| Washington Department of Fish and Wildlife. 1999. Biological Opinion – Tucannon River spring/summer chinook salmon supplementation, captive broodstock and remote site incubator programs - 1999-2003. 50 pp. | Y |
| Washington Fish and Wildlife Commission. 1997. Policy of Washington Department of Fish and Wildlife and Western Washington Treaty Tribes concerning wild salmonids. Olympia, WA. | N |
| Wy-Kan-Ush-Mi Wa-Kish-Wit. 1995. The Columbia River anadromous fish restoration plan of the Nez Perce, Umatilla, Warm Springs and Yakima Tribes, Volume I, Portland, OR. | N |

# Section 10 of 10. Key personnel

Other WDFW hatchery managers, fish biologists, fish hatchery specialists, and scientific technicians supervised by individuals listed below may also participate in propagation of captive broodstock fish.  WDFW’s Geneticist and Fish Pathologists will also be involved during various aspects of this project.

Michael P. Gallinat - Principle Investigator

EDUCATION:

M.S. (Fisheries)  	May, 1987 Ball State University, Muncie, IN

B.S. (Fisheries)  	May, 1985 Lake Superior State University, Sault Ste. Marie, MI

WORK HISTORY:

2000 to present  - Washington Department of Fish and Wildlife, Dayton, WA

Fish Biologist II  - Responsible for identifying, designing, conducting, analyzing, interpreting, and reporting appropriate research for Lower Snake River Compensation Plan (LSRCP) for spring chinook mitigation in southeast Washington.  Relate findings to LSRCP and fish management.  Performs as the WDFW spring chinook specialist for the LSRCP program.  Takes primary responsibility for the organization, writing and data analysis for annual Tucannon spring chinook salmon report.  Assists in routine professional biological work related to spring and fall chinook salmon production and evaluation at Lyons Ferry Hatchery.

1988 to 2000 – Red Cliff Fisheries Management Department, Bayfield, WI

Fisheries Biologist/Department Head – Responsible for managing and regulating the commercial and subsistence fishing efforts of tribal fishermen in treaty-ceded waters of Lake Superior.  Oversaw the design and construction of the tribal fish hatchery and walleye rearing ponds.  Responsible for conducting the tribal fisheries research and assessment program.  Administered the Conservation Department Bureau of Indian Affairs contract and budget.  Represented tribal interest on natural resource issues.

PROJECT EXPERTISE:

Current duties include acting as WDFW’s lead fisheries biologist for all spring chinook monitoring and evaluation in the Tucannon River under the LSRCP.  Familiar with basic aquaculture and captive broodstock rearing techniques.  Assist Lyons Ferry Hatchery in current spawning activities and tracking of spring chinook matings.  Duties will be to compile disease and mating records for captive broodstock progeny selection.  Assist in tagging and spawning of adult broodstock and all record keeping.  Disseminate information to other agencies and organizations.

RECENT REPORTS:

Gallinat, M.P., and J. D. Bumgarner. 2001.  Tucannon River Hatchery Program - 2000 ESA Section-10 Annual Report – Permits #1126 and #1129 to National Marine Fisheries Service, Portland, OR.  Washington Department of Fish and Wildlife, Fish Program/Science Division, Olympia, WA  98501-1091.  16 pp.

### Harold R. Harty - Associate Investigator

WORK HISTORY:

1995 to present - Washington Department of Fish and Wildlife, Starbuck, WA

Lyons Ferry Complex Manager - Manages a multi-species fish hatchery complex (Lyons Ferry and Tucannon Hatcheries), and maintains three satellite acclimation facilities.  Responsible for fish culture and biological program planning; budget development and tracking; supervision of full time and temporary employees; coordination and supervision of permitting and engineering efforts associated with hatchery operation and maintenance.  Coordination with various state and tribal agencies for marking and releases of spring and fall chinook salmon, steelhead trout, and rainbow trout.

1979-1995  - Washington Department of Wildlife, Statewide locations

Fish Hatchery Manager II, III, and V - Managed multi-species fish hatcheries within the state of Washington.  Responsible for fish culture and biological program planning; budget development and tracking; supervision of  employees; coordination and supervision of permitting and engineering efforts associated with hatchery operation and maintenance.  Coordination with various state agencies for marking and release of rainbow and steelhead trout. Organized, planned and executed spawning procedures and shipments of eggs to various hatcheries throughout the state; stocking of fish in lakes and streams within the region.  Successfully fulfilled enforcement, biological, and wildlife management requirements of the jobs.

PROJECT EXPERTISE:

Assisted in the development of the draft captive broodstock proposal for Tucannon River spring chinook salmon.  Provided critical information regarding hatchery and fish limitations.  Over 25 years of experience in basic and advanced aquaculture techniques.  Familiar with captive broodstock rearing techniques.  Directs Lyons Ferry Complex personnel in current spawning activities and juvenile rearing.   Specific duties will be to oversee captive broodstock program and personnel associated with the captive broodstock program at Lyons Ferry complex.  Assist with tagging and spawning of captive broodstock.

RECENT REPORTS:

Harty, H. R.  1997.  Lyons Ferry Complex Annual Report to U.S. Fish and Wildlife Service, LSRCP Office, Boise, ID.

Additional Documents (WordPerfect Format):

CBMaster Plan.wpd

nmfs biop 1129may.wpd