# Bonneville Power Administration

# FY 2002 Provincial Project Review

# PART 2. Narrative

Project ID:	199405400

Title:	Characterize the Migratory Patterns, Structure, Abundance, and Status of Bull Trout Populations from Subbasins in the Columbia Plateau.

# Section 9 of 10. Project description

a. Abstract

The goal of this project is to provide scientific information that will help develop a protection and recovery plan for threatened stocks of bull trout in the Columbia River Basin.  Information about the scale at which populations are structured and a method to effectively monitor population abundance have been identified as keys to the recovery and persistence of bull trout populations (Howell and Buchanan 1992; Rieman and McIntyre 1993; Kostow 1995; Buchanan et al. 1997).  In addition, a coordinated approach to the monitoring and evaluation of status and trends in bull trout populations is needed to support restoration efforts in the Columbia Plateau.  Currently, most research and monitoring activities do not have an overall framework for coordination of efforts or for interpretation and synthesis of results.  We propose specific objectives to 1) evaluate the population structure of bull trout in the John Day River basin, 2) assess techniques and refine guidelines to measure the abundance of bull trout spawning in Mill Creek, and 3) characterize the status, trends, movement patterns and distribution of bull trout populations at provincial and subbasin scales.  In addition, we propose to work cooperatively within the approach employed by the Oregon Plan for Salmon and Watersheds Monitoring Program (Nicholas, 1997a; 1997b; 1999) as adapted to bull trout in Oregon’s portion of the Columbia Plateau.  Each objective is addressed using established techniques (i.e. probablistic sampling of streams and microsatellite DNA analysis).  In addition, the approach applies a rigorous, Tier-2 sampling design to answer key monitoring questions.  Data will be summarized and statistical analyses performed, when appropriate, to test specific hypotheses.  These objectives were designed to complement ongoing work and, more specifically, to support other projects in the province and collaborative work that will be proposed in future provincial solicitations.  The NWPPC Fish and Wildlife Program and Subbasin Summaries, USFWS, and the Oregon Plan for Salmon and Watersheds have emphasized the need for this information to provide the real-time data to guide restoration and adaptive management in the region.

b. Technical and/or scientific background

In direct response to ISRP concerns about project coordination as well as to the advice of managers from CBFWA and BPA, this proposal now encompasses much of the bull trout work that was proposed for the Columbia Plateau.  The ISRP’s comments to projects 199405400 (ODFW), 199405400 (CTWSRO), 25088 (ODFW) and to 199801600 (ODFW) suggested that the sponsors spend more time coordinating the projects and considering the best grouping of the proposed activities.  After consultation with project sponsors and regional managers we attempted to reorganized each proposal to be as biologically meaningful, as well as administratively and economically efficient, as possible.  The reorganization includes incorporating Objective 4 from 25088 into 199405400 (ODFW).  In general, the work being proposed under Objective 4 of 25088 is a logical extension of work that has previously been done under 199405400.  One exception is the bull trout component of the juvenile inventory work proposed by project 25088.  Project 25088 proposed a unified approach to juvenile inventory work for resident and anadromous salmonids.  In addition, the majority of this juvenile inventory work would focus on species other than bull trout.  Rather than separate the bull trout component of juvenile inventory work and incorporate it under 199405400 (ODFW), all juvenile inventory work remained combined and can now be found in the revisions of 199801600 (ODFW).  These two projects will work together to coordinate all juvenile inventory work.  The reorganization also includes recombining 199405400 (ODFW) and 199405400 (CTWSRO) into one proposal.  The work being proposed in 199405400 (ODFW) and 199405400 (CTWSRO) was split into two proposals because of confusion over the provincial solicitation and review process.  However, the ongoing work that is represented in these proposals has previously been accomplished under one project number (199405400).

From a biological perspective, the reorganization of this proposal allows most of the proposed bull trout work to occur under one project.  As such, information from various activities will be exchanged frequently and regularly as well as integrated directly.  From an administrative perspective, this reorganization will allow BPA to oversee one project rather than three.  From an economic perspective, this reorganization will reduce equipment and personnel needs and would cost BPA approximately 5% less than if they funded these for each individual project.  As a result of this reorganization, the modified proposal for 199405400 (ODFW) now includes most of the bull trout work that was originally proposed by the above referenced projects.

Populations of bull trout from the Columbia and Klamath river basins were listed as threatened by the U.S. Fish and Wildlife Service under the Endangered Species Act (Office of the Federal Register 63 [June 10, 1998]: 31647).  It is estimated that bull trout occupy only 36% of their former range south of the Canadian border.  Over 78% of the historic bull trout populations in the proposed study subbasins are classified as having a moderate or high risk of extinction or are probably extinct (Ratliff and Howell 1992; Buchanan et al. 1997).  Two Reservation streams and their tributaries (Warm Springs River and Shitike Creek) support the entire lower Deschutes River (Rkm 0 – 161) metapopulation.  Bull trout are present in low numbers in the Warm Springs River and moderate numbers in the Shitike Creek (Brun 2000).  Both populations are considered to have a moderate risk of extinction due to the presence of brook trout (Buchanan et al. 1997).  The fluvial life history pattern is dominant in the lower Deschutes subbasin.  However resident bull trout are also present (Brun 1999).  Bull trout numbers have been severely impacted by harvest pressure, habitat degradation, passage barriers and interactions with exotic species.  Past and current efforts to assess, protect and restore existing bull trout populations have been limited by the lack of basic information about bull trout ecology, life history and genetics (Ratliff and Howell 1992; Rieman and McIntyre 1993; Buchanan et al. 1997; Spruell and Allendorf 1997).

Bull trout stocks in Oregon have been impacted by a variety of factors.  Migration barriers, including those from hydroelectric development in the mainstem Columbia River, the mainstem Snake River, and various tributaries, have impacted bull trout populations by limiting access to spawning and rearing habitats and by reducing the prey base.  Restricted access to or through certain habitats has also isolated small bull trout populations and prevented genetic exchange among populations.  This may lead to an increased risk of extinction of these populations from genetic factors and random events (Rieman and McIntyre 1993).  Other factors including over-harvest, non-native species introductions and habitat loss have also contributed to the decline of bull trout populations.  Spruell and Allendorf (1997) suggest that maintaining the genetic diversity of bull trout will require the continued existence of many populations throughout the Columbia Basin.  Furthermore, the ability to assess accurately the status of these populations is central to all conservation efforts.

Genetics.

Metapopulation theory has been increasingly applied to salmonid management and research in general (Rieman and Dunham 2000) and specifically to bull trout (e.g., Rieman and McIntyre 1993).  However, there is little empirical evidence to guide that application (Rieman and Dunham 2000).  Empirical estimates of dispersal that may link local populations to a larger population are one of the fundamental needs for increasing our understanding of metapopulation dynamics in bull trout (Rieman and Dunham 2000).

We previously used genetic analysis to describe the broad-scale population structure of 65 bull trout populations in the Northwest (Spruell et al. in review; Spruell and Allendorf 1997; Bellerud et al. 1997).  That analysis included populations from the Deschutes, John Day, Umatilla, and Walla Walla river subbasins in the Columbia Plateau Province as well as other populations in the Columbia Basin, the Klamath Basin, and coastal Washington.  There was substantial genetic differentiation among populations but little within populations.  Three major regional groups of bull trout, Coastal, Snake River and Clark Fork River, were identified.

The structure of metapopulations within these regional groups is still unclear.  Previous analytical methods were limited to the use of four DNA microsatellite loci.  These loci have limited resolution power to discriminate fine-scale population structuring within metapopulations.  Recently, researchers have started to use new loci in their microsatellite analyses (Spruell et al. 1999).  These loci have increased the levels of variation observed in the analysis and may be useful in providing increased resolution among bull trout populations (Spruell et al. 1999).  Rieman and Dunham (2000) suggested using DNA microsatellite analysis as a tool to estimate dispersal parameters and help define fine-scale relationships among local populations.  One objective of the study we are proposing is to evaluate the fine-scale population structure of bull tout in the John Day River subbasin using these new loci.

Rieman and McIntyre (1993) initially introduced the theory of metapopulations to bull trout conservation.  This theory has a number of potentially important biological and management implications.  However, if and how bull trout are actually organized and function as metapopulations are largely untested hypotheses.  Currently, microsatellite analysis is the best tool available to explore these hypotheses.  Our previous analysis considered broadscale population structure at the level of large subbasins to the Columbia River (e.g. John Day, Grande Ronde, and Deschutes rivers).  Given those data along with data on the extent of bull trout migration, it is reasonable to suspect that metapopulation structure, if it exists, occurs at smaller scales (i.e. within tributary basins).  Some preliminary, exploratory analysis of samples from the John Day and Grande Ronde rivers using additional loci developed since our earlier work suggests possible structuring of populations within those subbasins.  Such structuring would have significant implications for management activities and recovery efforts.  We anticipated the potential need to do finer scale analysis in our original sampling design.  Since the initial set of samples has already been collected and approximately half of the necessary loci analyzed during the original analysis, we could do the proposed analysis relatively efficiently and inexpensively.  This additional justification has been added to the proposal.

Adult Abundance.

Quantitative estimates of bull trout abundance are necessary to determine the status of populations, to monitor changes in population size, and to evaluate the effectiveness of conservation strategies .  Little data are available on bull trout abundance and population trends (Rieman and McIntyre 1993).  This type of information has been identified  as a critical research need (Rieman and McIntyre 1993; Buchanan et al. 1997).  Population status may be monitored at any or all life stages.  However; it has been difficult for biologists to accurately quantify the abundance of emergent salmonid fry (Hillman et al. 1992) or find consistent measures of juvenile bull trout abundance (Bonneau et al. 1995; Thurow and Schill 1996).  Redd counts can be made with relative ease and are an indirect measure of adult abundance.  As such; redd count information is typically used to evaluate trends in the size of local bull trout populations (Rieman and Myers 1997).

Redd counts from spawning surveys are an attractive technique to evaluate population abundance.  Since only reproductive adults produce redds, they should reflect the effective population size of a stock (Meffe and Carroll 1994).  In addition, the potential impacts to the population from spawning ground surveys are relatively low when compared to potential injuries that can occur when making population estimates based on multiple-pass removal or mark-recapture techniques using electrofishing (see Hemmingsen et al. 1996).  Thus, redd counts have been and continue to be the most commonly used method for monitoring bull trout abundance.

Despite their frequent use, the redd count information from spawning surveys may not be sufficient or appropriate to quantify the population status of bull trout.  Detection of changes in population size may not be possible using the most extensive sets of redd count data available (7-17 years), (Maxell 1999) and is unlikely for populations with more limited data sets (Rieman and Myers 1997).  The utility of redd counts may be further limited by errors, not accounted for in these earlier analyses, in the accuracy of redd enumeration.  Recent studies (Dunham et al. 2001) and results from our project (Hemmingsen et al. 2001) have shown substantial sampling error associated with redd counts for bull trout.  In addition, we have found that redd counts, which are typically used to monitor trends of larger fluvial and adfluvial adult forms of bull trout, may not account well for the component of the population consisting of smaller, resident life history forms (Hemmingsen et al. in press).  Relatively small redds, which are built by resident life history forms, can be difficult to detect.  Finally, during spawning surveys there is the potential for surveyors to unknowingly walk on redds or disrupt the behavior of spawning adults.

Standard, appropriate and powerful methods to assess bull trout abundance across all ranges of habitats have not been established (see Rieman and McIntyre 1995; Bonar et al. 1997).  Although data are beginning to accumulate (Dunham et al. 2001; Hemmingsen et al. 2001), there has not been a systematic evaluation of the utility of spawning surveys to estimate the abundance of spawning bull trout precisely and accurately.  The variability and reliability of spawning survey data may be influenced by many factors, including differences in population size, spawning distribution from year to year, time of spawning, redd characteristics of migratory versus resident life history forms, spawning habitat characteristics, and surveyor bias.  Other methods to evaluate population status and trends in population size have not been well explored.  Currently, biologists in the Pacific Northwest are proposing to explore the use of weir counts, juvenile surveys, environmental characteristics, or a combination of these methodologies to explore bull trout demograhpy (C. Brun, Confederated Tribes of the Warm Springs; B. Rieman, U.S. Forest Service; M. Taper, Montana State University; personal communications).  A second objective of the study we are proposing is to evaluate  direct (mark-recapture, snorkel counts calibrated for sampling efficiency) and indirect (redd counts, weir counts) estimating the abundance of both resident and migratory forms of spawning bull trout.  This objective is intended to complement other work that is being conducted in or proposed for the Columbia River basin.

Sampling Efficiency and Juvenile Abundance.

Bull trout abundance is difficult to monitor due to their complex habitat requirements (Pratt 1984; Goetz 1994) and variation in life histories (Rieman and McIntyre 1993; Fraley and Shepard 1989; Goetz 1991).  Juvenile abundance surveys are commonly conducted using night snorkeling in the Pacific Northwest.  Bull trout are nocturnal and readily observable at night (Goetz 1991; Shepard et al. 1984; Bonneau et al. 1995).  However researchers in the intermountain region of Idaho and Montana have found that underwater surveys may underestimate juvenile bull trout abundance (Fraley and Shepard 1989; Thurow and Schill 1996).  Sampling efficiency estimates have not been conducted in the Cascade region of Oregon and Washington (Thurow, USFS, personal commmunication).  There is a need to determine the sampling efficiency of night snorkeling in the Cascades to calibrate fish counts. The information obtained during this study will be incorporated in the analysis being done by the USFS Intermountain Research Station in association with the USFWS’s development of a presence/absence sampling protocol (endorsed by the American Fisheries Society).  Data from this project as well as from other studies throughout the range of bull trout will be used to develop a standardized juvenile bull trout abundance survey methodology that will be applicable region wide.

Migration.

Bull trout stocks in Oregon have been impacted by a variety of factors.  Migration barriers, including those from hydroelectric development in the mainstem Columbia River, the mainstem Snake River, and various tributaries, have impacted bull trout populations by limiting access to spawning and rearing habitats and by reducing the prey base.  Restricted access to or through certain habitats has also isolated small bull trout populations and prevented genetic exchange among populations.  This may lead to an increased risk of extinction of these populations from genetic factors and random events (Rieman and McIntyre, 1993).

For restoration and protection of bull trout habitats, conservation strategies depend on determining the distribution of bull trout.  However, that distribution may vary seasonally depending on the age and life history type of the fish.  Most juvenile bull trout distributions in Oregon have been determined during summer, and consequently, little is known about the distributions and movements of bull trout of any life stage during other seasons.  Most bull trout life history information comes from fluvial or adfluvial populations (Pratt 1992).  We have described migratory forms of bull trout in the John Day and Walla Walla river subbasins.  However, evidence of migratory fish is minimal or lacking for many bull trout populations in Oregon and the Columbia Basin, where they are assumed to be resident forms.  Knowledge of life history patterns, in addition to aiding habitat management, also has important implications for gene conservation.  Migratory life histories are vital for the resilience of bull trout metapopulations (Rieman and McIntyre 1993; Dunham et al. 1997).  If migratory forms are identified, their maintenance and persistence are dependent on protection of all habitats along migratory corridors.

In order to develop appropriate recovery strategies we must know the distribution and seasonal movement patterns of fluvial bull trout.  However, little is known about the life history and seasonal distributions and habitats of migrant adult bull trout in the Umatilla subbasin.  We suspect most of the adult bull trout in the Umatilla subbasin have a fluvial or migratory life history.  Generally, fluvial fish are thought to leave the headwater rearing areas at two or three years of age and take up residence in larger streams.  Fluvial adults may migrate back into headwater streams in May through July to spawn in late August through early November, then migrate back to larger streams.  Mature bull trout may spawn every year or alternate years.  Fluvial adult bull trout are believed to be the primary mechanism for gene transfer among bull trout populations.  Habitat use and spawning intervals of fluvial bull trout in the Umatilla River are unknown.

Work done in 1998 and 1999 has provided some limited results.  A better understanding has been gained of bull trout movement patterns in the upper Umatilla River, however tracking of bull trout that migrated significantly down-basin was difficult and provided limited results.  We know that some bull trout move down-basin, but we were not able to document the extent of this migration because we could not find several fish as the moved down.  The proposed efforts will be focused on tracking fish down-basin.  It is hoped that having personnel dedicated specifically to this project that better results will be obtained.  These efforts should help focus habitat restoration and enforcement efforts for Umatilla River bull trout.

The expression of migratory life history strategies by bull trout in the Columbia River Basin remains poorly understood.  It is not clear how commonly migratory forms are expressed in populations of bull trout.  In addition, little is known about the magnitude of bull trout migrations and their use mainstem habitats, including that of the Columbia River.  This information is critical to adapting management strategies and planning recovery efforts for bull trout.  One objective of the study we are proposing is to monitor the movement patterns of migratory bull trout in the John Day and Umatilla river subbasins.  We propose to conduct radiotelemetry studies of bull trout in the John Day subbasin.  This is a continuation of activities currently funded by BPA (Project 199405400).  Bull trout in the John Day subbasin have been implemented with radio tags.  Approximately seven of these tags are still active.  We propose to conduct radiotelemetry studies of bull trout in the Umatilla subbasin.  This is a continuation of activities originally funded in 1997 by the Environmental Protection Agency under the Regional Geographic Initiatives program.  As part of this study bull trout were implanted with radio tags and tracked in both 1998 and 1999.  Of the radio tags originally purchased for this project, 22 remain unused.

Population Status, Redd Surveys and Escapement.

This proposal now incorporates a Tier-2 level, monitoring and evaluation program for bull trout in the Oregon portion of the Columbia Plateau.  This proposed structure, adapted from the strategies and techniques incorporated into the Oregon Plan for Salmon and Watersheds, will enhance the rigorousness of ongoing work and a coordinated approach within and among angencies throughout the Columbia Plateau.  There is nearly universal support in the scientific and regulatory community regarding the critical role of monitoring to assure accountability, adaptive learning, and the credibility of recovery efforts for native salmonids and the watersheds that support them.  When the Oregon Plan for Salmon and Watersheds (Nicholas, 1997a) was developed for coastal watersheds, monitoring was one of the four primary elements of the Plan.  The conceptual framework and the programs that support the Oregon Plan Monitoring Program were critically reviewed and strongly supported by State, Federal, Tribal and Non-Governmental experts, along with the State of Oregon’s Independent Multidisciplinary Scientific Team prior to implementation.  The Plan received high marks for the comprehensive, integrated, and coordinated approach the State has taken to monitoring the effectiveness of the Oregon Plan.  While this program was developed for coastal watersheds, it is a model that should prove useful to bull trout recovery efforts in the Columbia River Basin.

The primary goal of this portion of this proposal is to provide a rigorous monitoring program for abundance, status and trend estimates of bull trout within the John Day River subbasin.  We propose to systematically survey areas outside traditional spawner reaches to cover potential spawning areas and implement Tier-2 level monitoring.  This monitoring would occur through the implementation of the EPA, EMAP approach.  This monitoring would support evaluations of numerous projects in the John Day River subbasin (i.e. habitat-related projects) as well as recovery planning.

In the past, bull trout redd counts within index reaches have been widely used to monitor trends in adult abundance (Shepard et al. 1982; Shepard et al. 1984; Brown 1992; Rieman and McIntyre 1996).  However variation in temporal and spatial distribution of spawning activity within streams as well as observer error have led researchers to question the accuracy of index redd counts (Dunham et al. 2001).  By continuing basin-wide redd surveys we will be able to determine if surveying selected stream reaches will provide an accurate index of bull trout spawning abundance.  Total redd counts and estimated numbers of spawning bull trout have been strongly correlated (Dunham et al. 2001).  Fish weirs have been successfully used to enumerate spawning bull trout throughout their range (Ratliff et al. 1996; Westover and Conroy 1997; Chirico and Westover 1998; Clayton 1998).  Another goal of this study is to maintain historic indices of population status and assess how they are related to more rigorous assessments of population status.

c. Rationale and significance to Regional Programs

Various measures directed under the Columbia River Basin Fish and Wildlife Management Plan (Plan) (Northwest Power Planning Council 1994; Northwest Power Planning Council 2000) addresses bull trout biology and management.  An overall objective of the Plan is to achieve a Columbia River ecosystem that sustains an abundant, productive and diverse community of fish.  The Plan calls for recovery issues identified by the Endangered Species Act to be addressed as well as for mitigation for losses of the numbers and diversity of native fishes, such as bull trout.  In addition, the Plan requires a complete assessment of fish populations and directs that the purpose of research is to resolve key uncertainties.  The Plan (Northwest Power Planning Council 1994) identifies specific measures.  Measure 2.2A emphasizes work on native species in native habitat.  Measure 3.2C.1 focuses on research that identifies key uncertainties that are most critical to the achievement of program goals.  Measure 10.1A.1 is specific to the need for assessments of resident fish populations.  Measure 10.2B.1 calls for the development of a plan to assist in conserving the genetic diversity of resident fish.  Measure 10.2C.1 is associated with habitat improvement of resident fish.  Measure 10.5 specifically addresses bull trout mitigation and measure 10.5A.2 focuses bull trout status, life history, habitat needs and limiting factors in the Grande Ronde River, John Day River, and Umatilla River subbasins.

The Fish and Wildlife Program (Chapter 9) calls for monitoring and evaluation of biological and environmental conditions at the scale of provinces and subbasins.  The four subbasin summaries this proposal addresses (Deschutes, John Day, Umatilla, Walla Walla) all call for a framework for the coordination and integration of monitoring efforts, increased monitoring of the status trends in anadromous and resident fish populations and habitats, a process to prioritize how and where restoration and protection efforts are focused, and an increased law enforcement presence to ensure compliance with laws pertaining to fish, wildlife, and habitat in their respective “Fish and Wildlife Needs” sections.  The proposed monitoring program will provide a framework for improved coordination and integration of monitoring efforts.  ODFW will monitor and evaluate the status and trends in fish populations (abundance and distribution) and habitat (quantity and quality) at the Province (Oregon Portion) and Subbasin scales.  The purpose of the monitoring and evaluation program is to assure that the effects of actions taken under sub-basin plans are measured, that these measurements are analyzed so that we have better knowledge of the effects of the action, and that this improved knowledge is used to choose future actions.

Recently the federal government published a Biological Opinion (Opinion) on the operation of the hydropower system in the Columbia River (NMFS 2000; USFWS 2000).  Summaries from the Opinions indicate that bull trout in the John Day River subbasin and in Mill Creek (Walla Walla River subbasin) are impacted by the federal hydropower system.  The Opinions discuss the need for a better understanding of the population structure of bull trout.  These Opinions contain sections on reasonable and prudent alternatives or measures.  These sections discuss research, monitoring and evaluation plans and include a goal that the abundance of populations of fish affected by the hydropower system, which would include bull trout, be monitored in a scientifically sound manner.

Both the Walla Walla River (James et al. 2001), John Day River (Knapp et al. 2001), and Deschutes (Nelson et al. 2001) subbasin plans address specific goals and objectives related to bull trout.  The subbasin plans for the Walla Walla River subbasin (WWSBP), John Day River subbasin (JDSBP), and Deschutes River subbasin (DSBP) emphasize bull trout as a key species and indicates bull trout populations have limited ability to be connected.  The WWSBP, JDSBP, and DSBP summarize the goals of various agencies with management responsibilities in the subbasin.  In general, these goals include mitigating for damages resulting from the operation of the mainstem hydropower system, recovery of a species listed as threatened under the Endangered Species Act, responsible management of bull trout, protecting and enhancing bull trout populations, as well as coordinated management.

The WWSBP defines specific goals, objectives, strategies and actions.  Relative to bull trout, these include 1) a goal to protect, enhance and restore wild and native populations of bull trout, 2) an action (1.4) to evaluate or refine methods to establish recovery goals and escapement goals, and 3) an action (12.3) to monitor adult spawning escapement.  Specific to research monitoring and evaluation, the WWSBP goals are to collect trend data for bull trout abundance, increase monitoring and assessment of bull trout to determine their abundance and population status, and refine or determine appropriate bull trout abundance levels for spawner escapement goals.

The JDSBP defines specific goals, objectives, strategies and actions.  Relative to bull trout, these include 1) a goal to restore populations to healthy levels, 2) an objective (1) to conduct population status monitoring, 3) a strategy (1.4) to improve understanding of relationships among genetic characteristics, 4) an action (1.4.3) to determine the consequences of genetic fragmentation, 5) an objective (4) to conserve genetically diverse bull trout populations, 6) a strategy (4.1) to characterize genetic diversity and gene flow, 7) an action (4.1.1) to document genetic baselines for each local population, and 8) a need to determine the degree of interchange between bull trout in the middle fork and north fork tributaries.

The DSBP defines specific goals, objectives, strategies and actions.  Recovery plans are also in the process of development at the regional and subbasin level.  A critical component of these plans is monitoring bull trout abundance to assess the effectiveness of bull trout recovery activities and determining population status.  However standardized abundance monitoring methods have yet to be developed (Deschutes Recovery Unit Team, USFWS, Bend, Oregon, personal communication).  The CTWSRO is the only organization monitoring the status of bull trout in the lower Deschutes subbasin.  The need to continue and expand bull trout research and monitoring activities within the Deschutes subbasin is noted on page 166 in the Deschutes River Subbasin Summary (Nelson et al. 2001).

In June of 1998 the FWS listed bull trout under the Endangered Species Act (ESA) as a threatened species.  Currently, a recovery plan for bull trout is being developed.  Goals of the draft recovery plan, which include a better understanding of bull trout ecology, improved populations status and delisting, can be found in the subbasin summaries.

Under the Oregon Plan (Coastal Salmon Restoration Initiative, Steelhead Supplement, Executive Order No. EO 99-01) monitoring is one of the four essential elements to implement the plan.  This monitoring proposal for the Columbia Plateau RFP is consistent and complimentary to the program ODFW has implemented in coastal watersheds.  This proposal also supports the implementation of the Oregon Plan statewide for all salmonids at-risk throughout the state.  In addition, the ODEQ is proposing water quality and biotic condition monitoring to BPA in a separate proposal that will integrate with ODFW’s Fish and Habitat Monitoring in a similar manner as on-going cooperative monitoring in coastal watersheds.

The project we are proposing is significant because it begins to fill gaps in the description of bull trout biology in general, and to update the status of specific populations.  This project focuses on information that is critical to the CRFWMP’s goals and objectives, subbasin plans and ESA issues.  Results from this project will include information on bull trout abundance, methods to assess bull trout abundance, as well as a genetic description of populations and their relationships to each other.  Information gathered will help fisheries managers assess the relative risks to populations, develop protection and recovery plans specific to each population, and prioritize resources to enable such protection or recovery.  If this information is applied properly, the expected overall outcome is long-term persistence of all bull trout populations that currently exist.  Some of the data we have collected previously have been incorporated into current recovery plans, and new data will help refine those plans.  Knowledge of bull trout biology was limited at the start of this project, and work to date has considerably enhanced that knowledge.  Efforts have also identified, and will continue to uncover, other critical areas that need further investigation.

d. Relationships to other projects

The project we are proposing focuses on bull trout abundance, methods to assess bull trout abundance, as well as a genetic description of populations and their relationships to each other.  The work we are proposing is a direct extension of the bull trout monitoring in Mill Creek that was previously conducted as part of this project (see Hemmingsen et al. 2001).  This work is also related to numerous other projects that are in progress both in the Columbia River basin and elsewhere.  Direct and indirect relationships exist between the work we are proposing and that being done by others and the work is typically supportive of, complementary to, or collaborative with the other work.

Since bull trout are listed under the Endangered Species Act as threatened, federal law requires that the USFWS develop a plan to recover bull trout.  Our project has and will continue to collaborate with the recovery team designated to develop this recovery plan.  Information from our research will feed directly into recovery planning efforts and the ultimate measures in the recovery plan.  The work we are proposing directly collaborates with recovery efforts.

The Oregon Plan for Salmon and Watersheds (OPSW) is a community-based, bottom-up effort to identify, conserve, and help restore crucial elements of natural ecosystems that support fish, wildlife, and people.  One of the four major components of the OPSW is monitoring activities for assessment purposes.  The governor of the state of Oregon has issued an executive order requiring the OPSW to be a statewide effort.  Our project will collaborate directly with the OPSW and provide information that applies specifically towards the mission of the OPSW.  The work we are proposing is directly supportive of OPSW efforts.

A coordinated approach to assessment and monitoring of bull trout populations and their habitats is needed to support restoration and recovery efforts in the Columbia Basin.  Currently, independent research projects and some monitoring activities are conducted various state and federal agencies, tribes, and to some extent by watershed councils or landowners, but there is no overall framework for coordination of efforts or for interpretation and synthesis of results.  We propose that the structure and methods employed by the Oregon Plan for Salmon and Watersheds (OPSW) Monitoring Program be extended to Oregon’s portion of the Columbia Basin.  A consistent and coordinated approach to monitoring and evaluation is a cornerstone of the NWPPC Fish and Wildlife Program and the OPSW.  This approach, successfully implemented in Oregon’s coastal watersheds, applies a rigorous statistically-based sampling design to answer key monitoring questions, provides integration of sampling efforts, and has greatly improved coordination among state agencies, federal agencies, and local watershed groups.  The goal of this proposal is to systematically implement salmonid population assessments, stream channel and riparian habitat assessments, and measurements of water quality and overall biotic condition.  This project would be responsible for the bull trout component, ODFW would have overall responsibility for the first three components with the ODEQ proposing water quality and biotic condition monitoring to the NWPPC in a separate proposal.  In addition, we wish to develop improved methods to determine the effectiveness of restoration efforts, based on quantification of survival rates throughout the salmonid life-cycle, but with emphasis on freshwater stages.  These efforts will create better understanding of the factors that influence survival rates and can be used adaptively to modify management of restoration efforts.

Federal, tribal and state fishery managers routinely conduct surveys in an attempt to assess population status.  Researchers from the CTUIR, WDFW and ODFW have begun OWEB-funded telemetry work in the Walla Walla River subbasin to begin assessing the population status of bull trout.  The work we are proposing was designed to directly complement this study.  Researchers from ODFW are proposing province-wide spawning surveys (B. McIntosh, ODFW; personal communication) to monitor the status of bull trout populations.  The work we are proposing was designed to directly complement this study.  Researchers from CTWSRO (C. Brun, personal communication), the USFS (B. Rieman, personal communication) and Montana State University (M. Taper, personal communication) are also proposing to evaluate methods to assess bull trout abundance.  The work we are proposing was designed in collaboration with or to complement, both directly and indirectly, these efforts.

Genetic analysis of local population structuring has already been completed for the portions of the Pend Oreille subbasin in Idaho (Spruell et al. 1999) and is planned for the upper Boise River subbasin (Paul Spruell, University of Montana, personal communication).  The work we are proposing was designed in collaboration with this larger, regional effort and would directly contribute to it by expanding the database into the John Day River subbasin.  Analysis of the Grande Ronde River populations will be proposed in a companion proposal for the Blue Mountain Province.  Collaborators include Paul Spruell, Wild Trout and Salmon Genetics Laboratory, University of Montana and Bruce Rieman, USDA Forest Service, Rocky Mountain Research Station.  The work we are proposing is a direct extension of bull trout telemetry studies that were previously conducted as part of this project (see Hemmingsen et al. 2001).

Bull trout research conducted by CTWSRO in the lower Deschutes subbasin began during 1998 as part of BPA funded project # 9405400 “Bull Trout Genetics, Habitat Needs, L.H. Etc. In Central And  N.E. Oregon”.  This project has been coordinated with the ODFW Native Trout Program and USFWS Deschutes Recovery Unit Chapter.  Information is exchanged at annual coordination meetings.  CTWSRO research will be done cooperatively with USFS Intermountain Research Station in determining the juvenile sampling efficiencies and developing redd survey protocols.  Data generated from this project will be provided to the Intermountain researchers to increase the range-wide data base on sampling efficiencies and redd surveys.  Results from this project will be provided to the Salvelinus confluentus Curiosity Society (SCCS) membership.  The society is composed of bull trout researchers in the U.S. and Canada.  Projects are critiqued and information is exchanged at annual meetings in order to coordinate and strengthen ongoing bull trout research.  Information obtained from the project will be used by the CTWSRO to monitor the the status of bull trout inhabiting the lower Deschutes River to determine if the Tribal Intergrated Resource Management Plan is adequately protecting this species.  The USFWS will use data from this project to assist with standardization of abundance monitoring protocols that will be used range-wide to assess recovery of bull trout.

The work we are proposing is indirectly related to numerous other ongoing efforts in the Walla Walla River subbasin.  The USACE and WDFW are working on fish passage and screening at the Bennington Lake intake on Mill Creek.  The CTUIR oversees projects on adult passage and habitat protection in Mill Creek.  Monitor and Evaluate the Natural Production, Distribution, Abundance and Genetics of Salmonids.  Each of these projects was designed, in part, to enhance the bull trout population in Mill Creek.  Our proposal to evaluate the abundance of spawning bull trout in Mill Creek is supportive of and complementary to each of these efforts.

The work we are proposing is indirectly related to numerous other ongoing efforts in the John Day River subbasin.  Numerous efforts are underway to improve habitat conditions in the John Day River.  One of the reasons to improve habitat is to achieve better fish passage and connectivity between bull trout in different areas.  These projects include the North Fork John Day Habitat project which is a multi-agency, cooperative effort, the John Day Watershed Restoration project that is a cooperative effort led by the CTWSRO, ODFW’s Streamflow Restoration Prioritization project and Northeast Oregon Fish Screening and Passage project, the USFS’s Fish and Wildlife Habitat Improvement project, and the North Fork Watershed Council project to Eliminate Gravel Push-Up Dams on Lower North Fork John Day.  Our proposal to evaluate the population structure of bull trout in the John Day River subbasin is supportive of and complementary to each of these efforts.

e. Project history (for ongoing projects)

As a result of this project we have completed annual reports for work conducted in 1995 (Hemmingsen et al. 1996), 1996 (Bellerud et al. 1997), 1997 (Hemmingsen et al. 2001) and 1998 (Hemmingsen et al. in press).  Reports and results from this project have been provided to biologists throughout the region and information from these reports has been used to help guide management decisions.  For example, results from this project have been published and included in the development of water temperature standards to protect and restore habitat for bull trout (Buchanan and Gregory 1997).  As a second example, results from this project have been used to help assess the status of bull trout, specifically in Oregon (Buchanan et al. 1997).  This information was included by the USFWS in the decision to list bull trout as threatened.  As a third example, radiotelemetry results from this project help identify problems with the city of Walla Walla’s diversion screen on their water intake.  Managers used this information to justify corrections to the diversion that were necessary for bull trout conservation.  As a final example, results from this project include experimental information on interactions between bull trout and brook trout (Gunckel 2001), which is relatively rare in the literature.  This information has been distributed to regional managers and is being used to help guide decisions regarding the potential influence of exotic brook trout in bull trout conservation efforts.  Annual reports for work conducted in 1999 and 2000 are in preparation.

Specific to bull trout abundance, we have conducted extensive and intensive redd counts in Mill Creek (Walla Walla River subbasin) and the Little Minam River (Grande Ronde River subbasin) during 1996-2000 and in Silver Creek (Powder River subbasin) during 1996-1999.  Mill Creek contained what appeared to be primarily larger (>300 mm) fluvial adults, but smaller (<300 mm) suspected resident adults were also observed and dominated Low Creek, a tributary.  All adults observed in the Little Minam River and Silver Creek were <300 mm.  Fluvial bull trout were trapped, enumerated, and PIT-tagged, and a sample was radio-tagged at the upstream ladder on the Mill Creek diversion dam.  No bull trout spawning has been observed in Mill Creek or tributaries downstream from the dam. We estimated the adult population size in Silver Creek using a combination of calibrated snorkel counts and estimates of size at maturity using endoscopy (Hemmingsen et al. in prep).  In 1998 the spawner:redd ratio was very high in Silver Creek (885:36) compared to adult dam counts:redd counts in Mill Creek (144:108) suggesting that redd counts may be a poor measure of abundance in Silver Creek and similar streams with resident adults and redds that are difficult to detect.  As previously mentioned, study results also indicated high sampling error among observers conducting redd counts, especially in streams with small adults and redds (Hemmingsen et al. in press).

Specific to the population structure of bull trout, we have sampled fish from numerous locations in northeast Oregon.  Results of the genetic analysis of bull trout populations previously completed for this project were reported by Spruell and Allendorf (1997) and can be found in Spruell et al. (In Review).  These results indicated that there was substantial genetic differentiation among populations but little within populations.  For example, there was greater genetic distance between Deschutes and John Day populations than has been reported between North American and European Atlantic salmon even though the mouths of the John Day and Deschutes rivers are less than 30 km apart.  Three major regional groups of bull trout were identified: 1. Coastal, 2. Snake River, and 3. Clark Fork.  This information was used by the USFWS to help determine appropriate conservation units for listed bull trout.

Bull trout spawning and juvenile emigration has been monitored on Reservation streams since the late-1980’s as part of the regular fisheries program.  Bull trout research in the lower Deschutes subbasin began during 1998 through BPA funded project # 9405400 “Bull Trout Genetics, Habitat Needs, L.H. Etc. In Central And  N.E. Oregon”.  Annual reports are referenced in Section H and are on file at the BPA.  Results have been presented at AFS Oregon Chapter annual meetings, USFWS Deschutes Recovery Unit meetings, BPA bull trout coordination meetings and at SCCS meetings.  Information obtained from our research has been used in USFWS recovery planning efforts in the Deschutes subbasin and juvenile presence / absence survey protocol development.

Reservation streams containing suitable juvenile rearing habitat were surveyed.  Juvenile bull trout distribution was identified and mapped in lower Deschutes tributaries: Warm Springs River, Bunchgrass Creek, Shitike Creek, Noisy Creek; and Metolius River tributaries: Whitewater River, Parker Creek and Bald Peter Creek.  Winter time juvenile distribution has been identified and mapped in Warm Springs River and Shitike Creek  Juvenile bull trout and brook trout (Salvelinus fontinalis) relative abundance and habitat use was assessed in the Warm Springs River and Shitike Creek by night snorkeling.  Juvenile bull trout were more numerous than brook trout in both streams, however, both species were found in low densities in the Warm Springs River.  Juvenile bull trout and brook trout occupied pools and glides more frequently than riffles and rapids. Juvenile bull trout were present in large numbers in Shitike Creek  Relative abundance surveys in Warm Springs River and Shitike Creek are ongoing.

Bull trout spawning grounds were identified and mapped in Warm Springs River, Shitike Creek and Whitewater River.  Large numbers of redds have been found in Warm Springs River and Shitike Creek Spawning begins in late August and continues through October. Spawning habitat and redd characteristics have been described.  Basin-wide spawning ground surveys have been conducted annually since 1998 and are ongoing. Existing adult and juvenile trap data in Warm Springs River and Shitike Creek was reviewed.  Very low numbers of migrant adult and juvenile bull trout were recorded in the Warm Springs River.  Moderate numbers of emigrating juvenile bull trout have been recorded in Shitike Creek.  Based upon review of existing data, Shitike Creek appears to be the major spawning and rearing stream for lower Deschutes River fluvial bull trout.

Juvenile emigration is monitored annually and is ongoing.  Water temperatures collected during juvenile distribution and spawning surveys indicate that juvenile bull trout are not present in water warmer than 12oC.  Peak bull trout spawning was observed when water temperatures declined to 7oC.  Water temperature monitoring in spawning, rearing and migration corridors is ongoing.  The movements of 20 adult bull trout were monitored by radio telemetry in the lower Deschutes River, Warm Springs River and Shitike Creek. Bull trout moved little in the Deschutes River during the winter and spring. During early summer they migrated to Shitike Creek.  By September they had reached the spawning grounds.  After spawning they returned to their original winter-spring holding locations in the lower Deschutes River.  Bull trout in the Warm Springs River. migrated to and held below the spawning grounds during the spring and summer.  After spawning in September and October they rapidly migrated downstream to the lower Deschutes River.  Mean water temperatures did not exceed 15.5o C during migration in both streams.

The genetic composition (mitochondrial DNA analysis) of bull trout in Warm Springs River and Shitike Creek was determined.  They were grouped with the coastal metapopulation.  There were some differences found between these fish and those in the Metolius River.  Bull trout within the zone of sympatry with brook trout in Warm Springs River and Shitike Creek were genetically tested for evidence of hybridization.  No evidence of hybridization was found.

Bull trout scales from the lower Deschutes basin were read to determine length at age.  An adult fish weir was installed during 1999 to monitor fluvial adult bull trout immigration into Shitike Creek. During 2000 the fish box design was improved and adult bull trout were captured.  Fish were enumerated and a sub-sample was radio tagged.  Weir operation is ongoing.

This project began in 1995 as project number 9405400.  Currently the project number is 199405400.  This project has been underway for six years.  To date, the project has cost approximately $1,440,166.  The work we are proposing here represents a logical extension of this project into its next phase.

f. Proposal objectives, tasks and methods

Specific Research Questions.

Objective 1.  Genetics (USFS and ODFW).

One of our goals is to improve conservation and recovery efforts for bull trout by determining whether fish within a basin are part of one metapopulation or represent multiple discreet populations.  The first objective of this project is to characterize the fine-scale population structuring of bull trout within the John Day River subbasin.  We propose to accomplish this objective by analyzing the genetic composition of bull trout collected throughout the John Day River subbasin.  The null hypothesis is that there is no genetic differentiation among bull trout collected from different tributaries in the John Day River subbasin.

Approach.

Previously, we have sampled bull trout from 10 tributaries in the John Day River subbasin, respresenting each of the three major forks.  These tributaries included (from the North Fork) South Fork Desolation Creek, Baldy Creek, South Fork Trail Creek, and Clear Creek; (from the Middle Fork) Granite Boulder Creek, Big Creek, and Clear Creek; and (from the mainstem John Day River) the upper John Day River, Call Creek, and Indian Creek).  Sample sizes ranged from 16-32 fish for each tributary.  Additional samples are needed to increase the power of the analysis for populations with previous sample sizes of  less than 25 and to test for temporal variability.  Further analysis is needed to include additional loci.  Samples would be collected during the first year of the study.  Critical assumptions include that we will be able to collect sufficient samples and that sample sizes represent the variation in allele frequencies within the population.  We anticipate results from this objective will allow us to determine potential metapopulation structure of bull trout from the John Day River subbasin.

Tasks and Methods.

Task 1.1.  Reanalyze previously collected samples that are archived (North Fork: S. Fork. Desolation, Baldy, S. Fork Trail, and Clear creeks; Middle Fork: Granite Boulder, Big, and Clear creeks.; Upper John Day: Call and Indian creeks) using a combination of data from four microsatellite loci previously analyzed and three additional loci. Samples will be analyzed by the Wild Trout and Salmon Genetics Laboratory, University of Montana, using polymerase chain reaction (PCR) and amplification of seven microsatellite loci.  Detailed methods are described in Spruell et al. (1999).

Task 1.2.  To supplement archived samples, collect fin tissue from 30 additional fish in each of Reynolds Creek, Indian Creek, South Fork Desolation Creek. To test for temporal variation in allele frequencies, collect fin tissue from 30 fish in Call Creek from the upper main stem of the John Day River; Clear Creek and Big Creek from the Middle Fork of the John Day River; Baldy Creek and Clear Creek from the North Fork of the John Day River.

Task 1.3.  Analyze genetic variation among local populations from Task 1.2 samples using seven loci.  Samples will be analyzed, likely the year following collections, by the Wild Trout and Salmon Genetics Laboratory, University of Montana, using polymerase chain reaction (PCR) and amplification of seven microsatellite loci.  Detailed methods are described in Spruell et al. (1999).

Task 1.4.  Publish results of the analysis annual reports and peer reviewed publications as well as present these results at technical meetings.

Objective 2.  Adult Abundance (ODFW and USFS).

Another of our goals is to improve conservation and recovery efforts for bull trout by determining appropriate methods to assess population status.  The second objective of this project is to compare methods that estimate the abundance of spawning bull trout in Mill Creek, a tributary with both migratory and resident spawners.  We propose to accomplish this objective by estimating the number of migratory bull trout that move upstream to spawn, the number of redds produced by bull trout, and the total number of mature bull trout spawning.  We hypothesize there is no relationship between adult bull trout abundance and redd counts and population estimates of resident adults.

Approach.

We have monitored bull trout escapement in Mill Creek for the past five years.  In general, we have accomplished this by monitoring the upstream movement of migratory fish through the fish ladder on the city of Walla Walla’s diversion dam and by conducting spawning surveys and counting redds.  Because Mill Creek appears to have resident fish that spawn, information on migratory bull trout may provide an incomplete estimate of the total spawning population.  Because redd count information can be imprecise, information from spawning surveys may provide an unreliable estimate of the total spawning population.  Thus, we propose to compare these methods with an actual estimate of the total number of bull trout that spawn in Mill Creek.  To provide sufficient analytical power, we propose to do this for each of the next three years.  Critical assumptions include that our estimate of the total spawning population will be sufficiently precise.  We anticipate results from this objective will allow us to begin determining appropriate methodologies to assess the status of bull trout population in Mill Creek as well as throughout the Columbia River basin.  Six subobjectives are included under this objective.

Subobjective 2.1.  Estimate the abundance of migratory (fluvial) adult bull trout in Mill Creek.

Tasks and Methods.

Task 2.1.1.  Count and measure upstream migrants passing the Mill Creek diversion dam.

Task 2.1.2.  Determine size at maturity and the proportion of mature individuals among upstream migrants using ultrasound or endoscopy (see Hemmingsen et al. in press).

Task 2.1.3.  Mark upstream migrants passing the diversion dam.

Task 2.1.4.  Estimate total abundance above the diversion dam using snorkel counts of marked and unmarked bull trout and mark-recapture analysis.

Subobjective 2.2.  Estimate the number bull trout redds

Task 2.2.1.  Conduct extensive bi-weekly spawning surveys (see Bellerud et al. 1997).

Task 2.2.2.  Calculate sampling error for redd counts using data from Hemmingsen et al. (in press).

Subobjective 2.3.  Determine the accuracy of redd counts and dam counts as a measure of the abundance of fluvial bull trout.

Tasks and Methods.

Task 2.3.1.  Compare redd counts to dam counts and mark-recapture estimates.

Subobjective 2.4.  Estimate the number of resident adult bull trout.

Tasks and Methods.

Task 2.4.1.  Estimate densities of bull trout (< 300 mm) in randomly selected stream reaches.  Reach length will be set at 30 times the active channel width (or approximately 100 m).  Reaches would be snorkeled and calibrated using removal or mark-recapture estimates for snorkeling efficiency.

Task 2.4.2.  Determine size at maturity and the proportion of mature individuals using ultrasound or endoscopy (see Hemmingsen et al. in press).

Task 2.4.3.  Extrapolate densities of adults to produce an estimate of total population size using area-under-the-curve techniques (Dambacher et al. 1999).

Subobjective 2.5.  Determine the accuracy and precision of redd counts as a measure of the abundance of resident bull trout.

Tasks and Methods.

Task 2.5.1.  Compare redd counts to surveys estimates of resident bull trout.

Subobjective 2.6.  Disseminate information in a timely and effective manner.

Tasks and Methods.

Task 2.6.1.  Publish results of the analysis annual reports and peer reviewed publications as well as present these results at technical meetings.

Objective 3.  Sampling Efficiency (CTWSRO).

We propose to compare the probability of detecting bull trout using day snorkeling, night snorkeling, electrofishing to an unbiased estimate of the true population.  We will also describe the influence of physical channel features including stream size, water temperature, conductivity, channel complexity and abundance of cover on probabilities of detecting bull trout.

Approach.

The methods are described in detail in Thurow and Schill (1996).  In summary 50 m stream reaches will be closed with block nets.  The study reaches will be located in different habitat types within each selected stream.  All bull trout and brook trout will be captured in the reach using electrofishing or dipnetting while snorkeling.  The fish will be marked with a caudal fin clip and released into the study reach.  Habitat parameters such as volume of large woody debris, water temperatures, substrate composition and stream channel features will be recorded.  Two or three divers will survey the reach day and night using the snorkeling procedures described by Thurow and Schill (1996).  Bull trout and brook trout will be classified into 100 mm length groups (50-100, 100-199, 200-299 mm).  Fish smaller than 50 mm will not be recorded due to the difficulty in sighting bull trout fry (Griffith 1981). The number of marked and un-marked fish will be recorded.  Four-pass electrofishing depletion will be conducted the following day (Seber LeCren 1967). All captured fish will be placed in a container for identification. After each electrofishing pass is complete the fish will be measured (total length), examined for marks and the number of marked and un-marked fish recorded.  These tasks will be performed in cooperation with bull trout researchers from the USFS Intermountain Research Station (Boise).  They will provide crew training and assist with experimental design and data analysis.

Task 3.1.  Survey approximately ten, 50 m, reaches.  Streams to be sampled include Warm Springs River, Shitike Creek and Mill Creek in the lower Deschutes basin as well as Whitewater River and Parker Creek in the Metolius drainage.  Sampling will occur during the summer of 2002.  Compare bull trout abundance estimates between day and night snorkeling and electrofishing.  For snorkeling the abundance estimate will be the total count.  The method of Seber-LeCren will be used to estimate abundance from electrofishing.  Calculate 95% confidence intervals about the mean using the method of Zar 1974.  Use ANOVA procedures to compare abundance estimates from the three techniques.  To determine size selectivity, evaluate length-frequency distributions of bull trout estimated by the three techniques.  Fish lengths will be pooled by size classes to derive a cumulative length-frequency distribution by sampling method.  A Kolmogorov-Smirnov two-sample test will be used to compare cumulative length-frequency distributions derived by the three techniques.

Task 3.2.  The influence of different habitat types will be evaluated by comparing bull trout densities observed during day and night snorkeling.  The relative densities of bull trout observed in each sampling unit will be calculated and stratified by habitat type (pool, riffle, run, pocket water).  A two-way ANOVA will be used to test for interaction between fish densities in habitat types and the type of snorkel survey i.e. day and night snorkeling.

Tier 1 and Tier 2 Monitoring.

Objective 4.  Migration (ODFW).

Another of our goals is to improve conservation and recovery efforts for bull trout by determining their seasonal use of various habitats.  The second objective of this project is to monitor the movement patterns of migratory bull trout in the Umatilla and John Day subbasins.  We propose to accomplish this objective by using radiotelemetry technology.

Approach.

We have monitored bull trout migrations in Mill Creek (Walla Walla River) and the John Day River for the past five years.  In general, we have accomplished this by monitoring movement of migratory fish using radiotelemetry.  We know that the John Day River subbasin has both migratory and resident bull trout.  Recently we have detected bull trout in the John Day River as far downstream as Spray.  However, it is unclear if and how migratory fish from different tributaries in the John Day River subbasin are connected.  We do not currently have information on whether migratory bull trout exist in the Umatilla River or on their movement patterns.  However, bull trout have been captured in the upstream trap at Three-Mile Dam.  Presumably these fish had come from the mainstem Columbia (McNary Reservoir) and were trying to move upstream in the Umatilla River.  Thus, we propose to monitor the movement patterns of bull trout in each of these subbasins to evaluate their seasonal use of various areas of the subbasins as well as their use of the mainstem Columbia River.  We anticipate results from this objective will allow us to begin to assess how bull trout from various tributaries are connected to each other as well as whether and to what extent they may be influenced by the Columbia River hydropower system.

Tasks and Methods.

Task 4.1. Capture and surgically implant radio tags into adult bull trout from the upper Umatilla River, Middle Fork John Day River, and Upper John Day River in October and November, 2001.  Fish will be captured by angling or by rotary screw traps.  The tags will be surgically implanted into fish of appropriate size.  Large adult transmitters are suitable for bull trout greater than 460 mm in length and have a life expectancy of 24 months.  The small adult transmitters are suitable for fish from 350 mm to 460 mm in length and have a life expectancy of 18 months.  The sub-adult transmitters are suitable for bull trout between 280 mm and 350 mm and have a life expectancy of approximately seven months.

Task 4.2. Use remote sensing equipment to track radio-tagged bull trout in the Umatilla and John Day river subbasins.  Tracking will be both from the ground and by fixed wing aircraft when necessary.  As fish move down-river, a drift boat may be used to gain access to the river where the road is a long distance from the river.  Tracking will be done at a frequency adequate to locate each active tag approximately every two weeks when fish are active and every two months when fish are dormant.

Objective 5.  Populations status (ODFW).

Another of our goals is to improve conservation and recovery efforts for bull trout by beginning to assess the status of various populations.  The second objective of this project is to employ methods to monitor and evaluate the status and trends in bull trout populations.  We propose to accomplish this objective by implementing an EMAP probabilistic sampling design to characterize the status, trends, and distribution of adult bull trout populations at the Provincial and Subbasin scale throughout the Oregon portion of the Columbia Plateau.

Approach.

ODFW, in coordination with the EPA Research Lab in Corvallis, Oregon, will develop the sampling frame to randomly draw sites in each of the four subbasins.  The sampling frame will consist of all streams that make up the current and potential distribution of adult bull trout in the four subbasins.  Once the sampling frame is established, up to 50 1-km sites/subbasin/year will be selected based on the EMAP process.  This procedure is based on a spatial grid design with hexagonal areas centered at grid points (EPA 1993).  Points along all streams in the sampling framework are plotted sequentially by computer and points then randomly selected.  The randomly selected points are then replotted on maps and selected for sampling.  The following web site discusses the monitoring approach/design for the OPSW project: http://www.oregon-plan.org/FCH16.html.

Subobjective 5.1.  Randomly select and survey stream sites from the current and potential range of adult bull trout in the Deschutes, John Day, Umatilla, and Walla Walla river subbasins.

Tasks and Methods.

Task 5.1.1.  At each one of the study sites, biweekly bull trout spawning ground surveys will be conducted from mid-August through mid-November.  Survey crews will be thoroughly trained in the identification of bull trout redds based on standard methods.  All surveys will be conducted walking upstream, generally in the center of the channel, or when two surveyors are required, each surveyor on opposite side of the stream.  All surveyors will be equipped with polarized sunglasses.  All redds in the survey reaches will be marked with survey flagging so they are not double-counted.  A chronological record will be kept of each redd and the visibility of each classified every survey.

Task 5.1.2.  The data will be analyzed using analytical tools developed by the EMAP program to support ODFW’s Coastal Monitoring Program.  The analysis will provide an estimate with known statistical confidence of the abundance of bull trout redds and trends in the abundance and distribution of redds at the Provincial and Subbasin scales.

Subobjective 5.2. Determine ownership of each site location and contact private landowners for access and permission to sample.

Tasks and Methods.

Task 5.2.1.  Site maps (1:24,000) are printed and locations identified as private, state, or federal ownership.  For state and federal ownership, contact and inform local land managers of sampling work.

Task 5.2.2.  For privately owned sites, determine ownership at local county courthouses and contact landowners via phone or in person to get permission for sampling.  We intentionally overdraw sample sites to account for landowner rejection.  ODFW’s Coastal Monitoring Program has experienced less than a 10% rejection rate for landowner permission after four years of monitoring, with acceptance improving over time.

Objective 6.  Juvenile Abundance (CTWSRO).

We propose to assess the utility of using “index” reaches for monitoring trends in juvenile bull trout relative abundance.  We will also conduct juvenile bull trout relative abundance surveys in Shitike Creek.

Approach.

The Warm Spring River (Rkm 56.9 – 59.3) will serve as the study location. The 2.4 km reach, which contains approximately 60% of the summer time juvenile rearing area, will be surveyed. Within the reach up to 12, 100 m long “index reaches” will be established. Bull trout will be enumerated by night snorkeling using methods described by Thurow and Schill (1996).

Tasks and Methods.

Task 6.1.  Survey the entire 2.4 km reach and index reaches on an annual basis.  Surveys will occur during late-June through early July 2002-2006. Surveys will be conducted from 22:00 – 03:00. Two or three divers will survey both the 2.4 km reach and the index reaches. Surveys will begin at the downstream end of the study area and proceed upstream. Each diver will be responsible for covering a portion of the stream to prevent duplication in counts.  Estimate and record the total length of each bull trout and brook trout encountered.  At the end of each habitat unit the fish counts from each diver will be consolidated and recorded.  Prior to commencing the surveys, divers will estimate the length of artificial fish shapes placed in the stream. Diver length estimates will be compared with the known lengths of the artificial fish to calibrate length estimates.  Tally bull trout into one of three length categories (50-200, 200-300 and >300 mm) corresponding to juvenile, sub-adult and adult life stages based upon scale analysis conducted in the Deschutes River sub-basin during 1996-2000 (Brun and Dodson, 2001).  Enumerate brook trout.  Juvenile bull trout (50-200 mm) will be grouped at the reach and index reach levels.  The relative densities (fish/m2) of juvenile bull trout and brook trout will be determined for the total surveyed area and each index reach. Two sample t-tests will be preformed among the total survey area and each index reach and combinations of index reaches to determine if relative densities are similar (( = .05). The data will be analyzed each survey year, using analysis of variance (ANOVA) (( = .05), to determine if the results repeatable on an annual basis.

Task 6.2.  Nine index reaches, established during 1998, will be surveyed by night snorkeling from 2002-2006.  Each 125 m reach is randomly located at approximately 1 km intervals between Rkm 35.8 and 48.6 (Brun, 1999 and 2000).  A total of 1.1 km. will be surveyed annually.  Survey methods are described above.  Determine the relative densities (fish/m2) of juvenile bull trout and brook trout for each index reach. The mean relative densities for the nine reaches will be added to previous years’ results to construct a time series histogram.  Trends in juvenile relative abundance and spawning abundance will be compared through time to determine if a relationship exists.

Objective 7.  Redd Surveys (CTWSRO).

We propose to determine total number of bull trout redds in each stream.  We will also determine if there is a significant difference between years in the distribution of redds within each stream.  Finally, we propose to determine if there is a significant difference among years in the timing of spawning.

Approach.

Multiple-pass spawning ground surveys will be conducted in the Warm Springs River and Shitike Creek from August through October, 2002-2004.  The entire known spawning habitat will surveyed in Warm Springs River (Rkm 52-58) and Shitike Creek (Rkm 30-44).  Suitable spawning habitat contains cold water (<120 C), low stream gradient (<3%), gravel/cobble substrate and abundant cover including large woody debris, log jams, pools and undercut banks (Buchanan and Gregory 1997; Fraley and Shepard 1989; Reiser and Bjornn 1979).

Tasks and Methods.

Task 7.1.  Survey index reaches within the total survey area established during 1998.  Surveys will be conducted at two-week intervals, 3-5 times throughout the spawning season (late-August through October).  One or two surveyors will begin the surveys at the upstream end of the reach and walk downstream in or along side the river channel sighting and recording redds.  Place flagging next to each bull trout redd to avoid double counting during later passes.  Tally redds by stream and index reach.  Record the presence of live adults and their approximate total lengths (cm).  Record water temperatures during each survey.  After the last survey for each year, compile the total number of bull trout redds by stream and within each stream reach of Warm Springs River and Shitike Creek.  Identify the two week period during which the maximum redd count occurred by stream and stream reach.

Task 7.2.  Data will be pooled with survey data beginning in 1998 to determine if bull trout utilize different stream reaches by year.  Between-year variation in the spatial distribution of redds in each stream will be evaluated using a two-sample Kolmogorov-Smirnov test.

Task 7.3.  Data will be pooled with survey data beginning in 1998 to determine if peak spawning varies by year.  Between-year variation in the temporal distribution of redds in each stream will be evaluated using a two-sample Kolmogorov-Smirnov test.

Objective 8.  Escapement (CTWSRO).

We propose to estimate the number of adult fluvial bull trout entering the spawning grounds in Warm Springs River using time-lapse underwater videography.  We will also estimate the number of adult fluvial bull trout entering Shitike Creek using a weir and fish trap.  Finally, we will determine the adult per redd ratio in the Warm Springs River and Shitike Creek and estimate the abundance of spawners from redd counts.

Approach.  Install a vertical picket weir with a time-lapse underwater video camera in the Warm Springs River (Rkm 50).  Set up a FIELDCAM TM underwater video camera system at the weir.  This system has been successfully tested under field conditions by the USFS, Mt. Hood National Forest in a cooperative project with the CTWSRO.  The system will be used during 2001 to monitor adult bull trout escapement to Clear Branch Creek in the Hood River subbasin (Chute Fiedler, USFS Hood River Ranger Station, Mt. Hood, Oregon, personal communication).  A vertical picket weir will also be installed across Shitike Creek (Rkm 0.75). Two fish boxes with a fyke entrance will be attached to the weir to capture adult immigrants and post-spawning emigrants.

Tasks and Methods.

Task 8.1.  Operate the weir and video camera continuously from June through November, 2002-2006.  Video tape spawning and post-spawning adult bull trout that pass the picket weir.  Video tapes will be reviewed in the office.  Both spawning and post-spawning bull trout will be enumerated and total lengths estimated.

Task 8.2.  Operate the weir from May through November, 2002-2004.  Record the fork length and sex of all captured immigrants. Collect scale samples from captured bull trout.  Mark each fish with an individually numbered floy tag.  Downstream emigrants recaptured at the weir will be measured, enumerated and inspected for tags. The number of the tag will be recorded for all recaptured fish.  If sufficient numbers of adults are re-captured at the weir, estimate escapement using the “Simple Peterson” population estimation methodology.  Determine the sampling efficiency of the weir using the results of the Peterson estimate.  Post spawning mortality will be estimated by subtracting the number of tagged bull trout re-captured in the weir from the number of immigrants tagged.  The rate of repeat spawning will be determined by recording the number of previously tagged bull trout captured at the weir in subsequent years.

N = (MC) / R

Where

N = Total adult population size

R = Number of tagged adults observed at the traps

M = Total number of adults tagged

C = Total adults captured at the traps

Variance will be approximated by:

where

Task 8.3.  After immigrations past the weirs are complete and redds are enumerated, calculate an adult to redd ratio for the Warm Springs River and Shitike Creek.  This will be done by dividing the number of immigrants enumerated at the weirs by the total number of redds counted in each stream (Ratliff et al. 1996).  To determine if using a fish per redd estimate is an accurate method for monitoring spawning fluvial bull trout abundance in Warm Springs River and Shitike Creek, compare the annual variances of the abundance estimates from the weir counts to the annual variances of the estimates derived from the fish per redd ratio (Bonar et al. 1997).  Estimate annual escapement in the Warm Springs River and Shitike Creek by:

E = RF

Where

E = Adult escapement past the weir.

R = Total redds counted for the year.

F = Spawners per redd.

Variance will be approximated by:

s2E = S2RF2 + s2FR2

Where

s2E = Variance of annual escapement estimate.

Sf2 = Variance of annual fish to redd ratio.

SR2 = Variance of annual total redd count.

g. Facilities and equipment

An endoscope would be required to complete the project.  Funds for this project would also be used to purchase a picket weir and underwater videography equipment.

Existing facilities at CTWSRO Department of Natural Resources are adequate for the purposes of this study. The CTWSRO will provide computers, electrofishing equipment, snorkeling gear and a weir for Shitike Creek.  A GSA vehicle will be rented.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Bellerud, B.L., S. Gunckel, A.R. Hemmingsen, D.V. Buchanan and P.J. Howell. 1997. Bull trout life history, genetics, habitat needs and limiting factors in central and northeast Oregon, 1996 annual report. Bonneville Power Administration, Portland, OR. | N |
| Bonar, S.A., M. Divens, and B. Bolding. 1997. Methods for sampling the distribution and abundance of bull trout and Dolly Varden. Washington Department of Fish and Wildlife, Olympia, WA. | N |
| Bonneau, ,J.L., R.F. Thurow, and D.L. Scarnecchia. 1995. Capture, marking, and enumeration of juvenile bull trout and cutthroat trout in small, low-conductivity streams. North American Journal of Fisheries Management, 15:563-568. | N |
| Brown, L.G. 1992. Draft management guide for the bull trout Salvelinus Confluentus on the Wenatchee National Forest. Washington Department of Wildlife Technical Report. 104 pp. |  |
| Brun, C.V. 1999. Bull trout distribution and abundance in the waters on and bordering the Warm Springs Reservation, 1998 Annual Report. Bonneville Power Administration, Portland, Oregon. |  |
| Brun, C.V. 2000. Bull trout distribution and abundance in the waters on and bordering the Warm Springs Reservation, 1999 Annual Report. Bonneville Power Administration, Portland, Oregon. |  |
| Buchanan, D.V. and S.V. Gregory. 1997. Development of water temperature standards to protect and restore habitat for bull trout and other coldwater species in Oregon. Pages 119-126 in Friends of the bull trout conference proceedings. Bull Trout Task Force (Alberta), c/o Trout Unlimited Calgary. | N |
| Buchanan, D.V., M. Hanson and B. Hooton. 1997. Bull trout status report for Oregon. Oregon Department of Fish and Wildlife. Portland, OR. | N |
| Chirico, A. and W. T. Westover. 1998. Wigwam River bull trout—habitat conservation trust fund progress report for 1997. Fisheries Project Report KO 53. Ministry of Lands and Parks, Fisheries Branch, Cranbrook, British Columbia, Canada. |  |
| Dambacher, J. 1999. Redband Trout (Oncorhynchus mykiss ssp.): Assessment of Stream Populations and Habitat of Great Basin. Species At Risk Program, Final Proposal To The Biological Resource Division, USGS, Oregon Department of Fish and Wildlife, Corvallis, OR. | N |
| Dunham, J., B. Rieman, and K. Davis. In press. Sources and magnitude of sampling error in redd counts for bull trout Salvelinus confluentus. North American Journal of Fisheries Management. | N |
| Fraley, J.J., and B.B. Shepard. 1989. Life history, ecology and population status of bull trout (Salvelinus confluentus) in the Flathead Lake and River system, Montana. Northwest Science 63:133-143. |  |
| Goetz, F. 1991. Bull trout life history and habitat study. U.S. Department of Agriculture, Forest Service, Deschutes National Forest, Bend, Oregon. |  |
| Goetz, F. A. 1994. Distribution and juvenile ecology of bull trout (Salvelinus confluentus) in the Cascade Mountains. Master's Thesis, Oregon State University. Corvallis. |  |
| Griffith, J.S. 1981. Estimation of the age-frequency distribution of stream dwelling trout by underwater observation. Progressive Fish-Culturist 43:51-53. |  |
| Gunckel, S.L. 2001. Feeding behavior and diet of native bull trout Salvelinus confluentus and introduced brook trout S. fontinalis in two eastern Oregon streams. Master of Science Thesis, Oregon State University, Corvallis, OR. | N |
| Hemmingsen, A.R., D.V. Buchanan and P. J. Howell. 1996. Bull trout life history, genetics, habitat needs and limiting factors in central and northeast Oregon. 1995 annual report. Bonneville Power Administration. Portland, OR. | N |
| Hemmingsen, A.R., S.L. Gunckel, J.S. Shappart, B.L. Bellerud, D.V. Buchanan, and P.J. Howell. 2001. Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon. 1997 Annual Report. Bonneville Power Administration. Portland, OR. | N |
| Hemmingsen, A. R., B. L. Bellerud, and S. L. Gunckel. In press. Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon. 1998 Annual Report. Bonneville Power Administration. Portland, OR. | N |
| Hillman, T.C., J.W. Mullan, and J.S. Griffith. 1992. Accuracy of underwater counts of juvenile chinook salmon, coho salmon, and steelhead. North American Journal of Fisheries Management, 12:598-603. | N |
| Howell, P.J. and D.V. Buchanan, editors. 1992. Proceedings of the Gearhart Mountain bull trout workshop. Oregon Chapter of the American Fisheries Society, Corvallis, OR. | N |
| James, G. and various contributors. 2001. Walla Walla Subbasin Summary. Prepared for the Northwest Power Planning Council, Portland, OR. | N |
| Knapp, S. and various contributors. 2001. John Day Subbasin Summary. Prepared for the Northwest Power Planning Council, Portland, OR. | N |
| Kostow. K. 1995. Biennial report on the status of wild fish in Oregon. Oregon Department of Fish and Wildlife, Portland, OR. | N |
| Maxell, B. A. 1999. A prospective power analysis on the monitoring of bull trout stocks using redd counts. North American Journal of Fisheries Management 19:860-866. | N |
| Meffe, G.K. and C.R. Carroll. 1994. Principles of conservation biology. Sinauer, Sunderland, MA. | N |
| Nelson, L. and various contributors. 2001. Deschutes River Subbasin Summary. Prepared for the Northwest Power Planning Council, Portland, OR. | N |
| Nicholas, J.W. (Principal Writer). 1997a. Monitoring Program, Chapter 16. The Oregon plan: Oregon coastal salmon restoration initiative. State of Oregon, Salem, Oregon. | N |
| Nicholas, J.W. (Principal Writer). 1997b. Monitoring Program, Addendum to Chapter 15b. The Oregon plan: revisions to the steelhead supplement. State of Oregon, Salem, Oregon. | N |
| Nicholas, J.W. (Principal Writer). 1999. Implementation of the monitoring program, Chapter 15b. The Oregon plan: draft steelhead supplement. State of Oregon, Salem, Oregon. | N |
| NMFS. 2000. Biological Opinion: Effects to listed species from operations of the federal Columbia River power system. National Marine Fisheries Service, Northwest Region, Portland, OR. | N |
| Northwest Power Planning Council. 1994. Columbia River Basin Fish and Wildlife Program. Northwest Power Planning Council, Portland, OR. | N |
| Northwest Power Planning Council. 2000. Columbia River Basin Fish and Wildlife Program. Northwest Power Planning Council, Portland, OR, document number 2000-19. | N |
| Pratt, K. L. 1984. Habitat selection and species interactions of juvenile westslope cutthroat trout (Salmo clarki lewisi) and bull trout (Salvelinus confluentus) in the upper Flathead River basin. Master's Thesis, University of Idaho, Moscow. | N |
| Pratt, K.L. 1992. A review of bull trout life history. Pages 5-9 in P.J. Howell and D.V. Buchanan, editors. Proceedings of the Gearhart Mountain Bull Trout Workshop. Oregon Chapter of the American Fisheries Society, Corvallis. | N |
| Ratliff, D. and P. Howell. 1992. The status of bull trout populations in Oregon. Pages 10-17 in: P. J. Howell and D. V. Buchanan, editors. Proceedings of the Gearhart Mountain bull trout workshop. Oregon Chapter American Fisheries Society, Corvallis, OR. | N |
| Ratliff, D.E., S.L. Thiesfeld, W.G. Weber, A.M. Stuart, M.D. Riehle and D.V. Buchanan. 1996. Distribution, life history, abundance, harvest, habitat and limiting factors of bull trout in the Metolius River and Lake Billy Chinook, Oregon, 1983-1994. Information Report, Oregon Department of Fish and Wildlife, Portland. | N |
| Reiser, D.W. and T.C. Bjornn. 1979. Habitat requirements of anadromous salmonids. U.S. Forest Service, General Technical Report DNW-96. Pacific Northwest Forest and Range Experiment Station. Portland, Oregon. | N |
| Rieman, B.E. and J.D. McIntyre. 1993. Demographic and habitat requirements for conservation of bull trout. General Technical Report INT-302, Intermountain Research Station, Ogden, UT. | N |
| Rieman, B.E. and J.D. McIntyre. 1995. Occurrence of bull trout in naturally fragmented habitat patches of varied size. Transactions of the American Fisheries Society, 124:385-296. | N |
| Rieman, B. E. and J. D. McIntyre. 1996. Spatial and temporal variability in bull trout redd counts. North American Journal of Fisheries Management 16: 132-141. | N |
| Rieman, B.E. and D.L. Myers. 1997. Use of redd counts to detect trends in bull trout (Salvelinus confluentus) populations. Conservation Biology 11(4): 1015-1018. | N |
| Rieman, B.E., Dunham J.B. 2000. Metapopulations and salmonids: a synthesis of life history patterns and empirical observations. Ecology of Freshwater Fish 9:51-64. | N |
| Seber, G.A.F. and E.D. LeCren. 1967. Estimating population parameters from catches relative to the population. Journal of Animal Ecology 36:631-643. | N |
| Shepard, B., T. Weaver, J. Fraley and P. Graham. 1982. Flathead River fishery study. Montana Department of Fish, Wildlife and Parks, Kalispell, Montana. | N |
| Shepard, B., K. Pratt and P. Graham. 1984. Life histories of westslope cutthroat and bull trout in the upper Flathead River Basin, Montana. Montana Department of Fish, Wildlife and Parks, Kalispell. | N |
| Spruell, P. and F.W. Allendorff. 1997. Nuclear DNA analysis of Oregon bull trout, Report 97/5. Oregon Department of Fish and Wildlife. Portland, OR. | N |
| Spruell P., B.E. Rieman, K.L. Knudsen, F. M. Utter, Allendorf F.M. 1999. Genetic population structure within streams: microsatellite analysis of bull trout populations. Ecology of Freshwater Fish 8: 114-121. | N |
| Spruell, P, A.R. Hemmingsen, P.J. Howell, N. Kanda, and F.W. Allendorf. In review. Conservation genetics of bull trout: geographic distribution of variation at microsatellite loci. Conservation Genetics. | N |
| Thurow, R.F. and D.J. Schill. 1996. Comparison of day snorkeling, night snorkeling, and electrofishing to estimate bull trout abundance and size structure in a second-order Idaho stream. North American Journal of Fisheries Management, 16:314-323. | N |
| USFWS. 2000. Biological Opinion: Effects to listed species from operations of the federal Columbia River power system. United States Fish and Wildlife Service, Regions 1 and 6, Portland, OR. | N |
| Westover, W. T., and D. Conroy. 1997. Wigwam River bull trout—habitat conservation trust fund progress report for 1996/7. Fisheries Project Report KO 51. Ministry of Lands and Parks, Fisheries Branch, Cranbrook, British Columbia, Canada. | N |
| Zar, J.E. 1974. Biostatistical Analysis. Prentice-Hall, Englewood Cliff, New Jersey. | N |

# Section 10 of 10. Key personnel

Chistopher Brun, Project Leader, Confederated Tribes of the Warm Springs Reservation of Oregon.

Education:

B.S., Environmental Studies, Lewis and Clark College, 1988.

Post Bac., Oregon State University, 1991.

Professional Experience:

1996 - Present, Confederated Tribes of the Warm Springs Reservation of Oregon, Fisheries Biologist.  In addition, Mr. Brun also worked for the USFS for six years as a fisheies biologist.

Qualifications:

Mr. Brun is currently the project leader for bull trout research and fall chinook abundance estimation in the lower Deschutes subbasin (BPA project 1994-054-00 and NOAA contract 11-438)  He is experienced with field sampling techniques is both large and small rivers.  Parts of this project will be implemented by the CTWSRO Department of Natural Resources.  Mr. Brun will secure necessary permits, provide logistical support, supervise field work and data analysis and take the lead for project reporting.  Rebekah Dodson, field biologist, will assist with project logistics and planning, supervise the field crew during  project implementation and assist with data analysis and final report preparation.

Relevant Publications:

Brun, C.V. 1999. Bull trout distribution and abundance in the waters on and bordering the Warm Springs Reservation, 1998 Annual Report. Bonneville Power Administration, Portland, Oregon.

Brun, C.V. 2000. Bull trout distribution and abundance in the waters on and bordering the Warm Springs Reservation, 1999 Annual Report. Bonneville Power Administration, Portland, Oregon.

Brun, C.V and R.L. Dodson. 2001. Bull trout distribution and abundance in the waters on and bordering the Warm Springs Reservation, 2000 Annual Report. Bonneville Power Administration, Portland, Oregon.

Stephanie L. Gunckel, Fisheries Research Biologist, Oregon Department of Fish and Wildlife.

Education:

B.S., Biology, Lewis and Clark College, 1989.

M.S., Fisheries Science, Oregon State University, 2000.

Professional Experience:

1994 - Present, Oregon Department of Fish and Wildlife, Fisheries Research Biologist.

For the past seven years Ms. Gunckel has worked for the Oregon Department of Fish and Wildlife conducting investigations on native trout.  She has assisted with planning and implementation of field studies on native trout populations in Oregon.  Her responsibilities included summary and analysis of data as well as written and oral communication of results.

Qualifications:

Ms. Gunckel is currently researching the feeding ecology and interactions of co-occurring juvenile bull trout and brook trout.  This research involves the collection, analysis, and interpretation of stomach contents, and behavioral observations.  Her experience also includes the collection and analysis of trout abundance estimates and quantitative stream habitat assessments, and collection of bull trout genetic data and redd count information.  Much of Ms. Gunckel’s experience and expertise are directly applicable to the research of native trout populations in Oregon.

Relevant Publications:

Gunckel, S.  2001.  Feeding behavior and diet of native bull trout Salvelinus confluentus and introduced brook trout S. fontinalis in two eastern Oregon streams.  Masters Thesis, Oregon State University, Corvallis, Oregon.

Hemmingsen, A.R., B.L. Bellerud, S.L. Gunckel, and P.J. Howell.  In Press.  Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon.  1998 Annual Report. Project Number 199405400, Bonneville Power Administration, Portland, Oregon.

Hemmingsen, A.R., S.L. Gunckel, J.K. Shappart, B.L. Bellerud, D.V. Buchanan and P.J. Howell.  2001.  Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon.  1997 Annual Report.  Project Number 199405400, Bonneville Power Administration, Portland, Oregon.

Bellerud, B.L., S. Gunckel, A.R. Hemmingsen, D.V. Buchanan and P.J. Howell.  1997. Bull trout life history, genetics habitat needs, and limiting factors in central and northeast Oregon, 1996 Annual Report.  Project Number 199405400, Bonneville Power Administration, Portland, Oregon.

Alan R. Hemmingsen, Fisheries Research Biologist, Oregon Department of Fish and Wildlife.

Education:

BS, Fisheries and Wildlife Biology, Iowa State University, 1971.

Professional Experience:

For the past 13 years Mr. Hemmingsen has worked for the Oregon Department of Fish and Wildlife as an Assistant Project Leader conducting investigations on native trout.

Qualifications:

Since 1988 Mr. Hemmingsen has conducted or assisted various investigations on native trout in Oregon.  Those investigations were designed to describe the diversity among native trout, determine threats to their sustainability, and foster awareness of their value.  Specific projects involved genetic characterization of populations, description of life history traits, definition of migration patterns, and identification of critical habitat needs.  Since 1994 he has served on a research project that has studied the biology and ecology of bull trout in central and northeast Oregon.

Relevant Publications:

Bellerud, B.L., S. Gunckel, A.R. Hemmingsen, D.V. Buchanan and P.J. Howell.  1997. Bull trout life history, genetics habitat needs, and limiting factors in central and northeast Oregon, 1996 Annual Report.  U.S. Department of Energy, Bonneville Power Administration, Portland, Oregon.

Hemmingsen, A.R., D.V. Buchanan, and P.J. Howell.  1996.  Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon.  Annual Report 1995.  Prepared for the U.S. Department of Energy, Bonneville Power Administration.  Project Number 94-54.  Portland, Oregon.

Hemmingsen, A.R., S.L. Gunckel, J.K. Shappart, B.L. Bellerud, D.V. Buchanan and P.J. Howell.  2001.  Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon.  1997 Annual Report. Project Number 199405400, Bonneville Power Administration, Portland, Oregon.

Hemmingsen, A.R., B.L. Bellerud, S.L. Gunckel, and P.J. Howell.  In Press.  Bull trout life history, genetics, habitat needs, and limiting factors in central and northeast Oregon.  1998 Annual Report.  Project Number 199405400,  Bonneville Power Administration, Portland, Oregon.

Spruell, P., A.R. Hemmingsen, N. Kanda, P.J. Howell and F.P. Allendorf.  Submitted.  Conservation genetics of bull trout: geographic distribution of variation at microsatellite loci.

Philip J. Howell, Fisheries Biologist/Aquatic Ecologist, USDA, Forest Service Pacific Northwest Research Station.

Education:

M.A., University of Missouri, 1976

B.A., cum laude, Rockhurst University, 1972

Professional experience:

Currently, Mr. Howell has responsibility as a project manager, BPA project 199405400, bull trout genetics, life history, habitat needs and limiting factors in central and northeastern Oregon, principal investigator of a study of the genetic characteristics of westslope cutthroat trout in eastern Oregon and Washington, and as an aquatic scientist with the Science Advisory Group for the Interior Columbia Basin Ecosystem Management Project.  Previously, Mr. Howell was employed by the Oregon Department of Fish and Wildlife as a project leader for native trout research studies.  Mr. Howell has also instructed classes at Oregon State University.  His duties have included project design and development, management of field studies, data analysis and reporting, as well as coordination with the U.S. Forest Service.

Qualifications:

Mr. Howell has been extensively involved in the design and implementation of BPA-funded study of bull trout genetics, life history, habitat needs and limiting factors in eastern Oregon since the project began.  In 1992 he and Don Ratliff completed the first assessment of bull trout distribution, status and management in Oregon.  He currently provides aquatic science oversight for the development of a management plan for federal lands in the interior Columbia Basin, which addresses the habitat management needs of bull trout and other aquatic species.   For that project other scientists and he has completed an assessment of the status, distribution and management of bull trout and other aquatic species east of the Cascades and developed models to evaluate the effects of proposed management alternatives on bull trout and other species.   Mr. Howell is currently chair of a panel of bull trout research biologists for the Western Division of the American Fisheries Society who are developing a sampling protocol for determining bull trout presence/absence.

Relevant publications:

Spruell, P., A. R. Hemmingsen, P. J. Howell, N. Kanda, F.W. Allendorf. In review. Conservation genetics of bull trout: geographic distribution of variation at microsatellite loci. Conservation genetics.

Peterson, J., J. Dunham, P. Howell, R. Thurow, S. Bonar. 2001. Protocol for determining bull trout presence. Peer review draft. Western Division of the American Fisheries Society.

Stowell, R., P. Howell, B. Rieman, and J. McIntyre.  1994.  An assessment of the conservation needs for bull trout.  USDA Forest Service, Missoula, MT.

Ratliff, D.E. and P.J. Howell.  1992.  The status of bull trout populations in Oregon.  Pages 10-17 in Howell, P.J. and D.V. Buchanan, editors.  Proceedings of the Gearhart Mountain bull trout workshop.  American Fisheries Society, Corvallis, OR.

Howell, P.J. and D.V. Buchanan, editors.  1992.  Proceedings of the Gearhart Mountain bull trout workshop.  American Fisheries Society, Corvallis, OR.

Bruce A. McIntosh, Oregon Plan Monitoring Coordinator, Oregon Department of Fish and Wildlife.

Education:

B.S., Wildlife Biology, University of Montana, 1982.

M.S., Forest Ecology, Oregon State University, 1992.

Ph.D., Forest Ecology, Oregon State University, 1995.

Professional Experience:

Dr. McIntosh has been employed by the Oregon Department of Fish and Wildlife since 2000 as the Oregon Plan Monitoring Coordinator.  He also has an appointment at Oregon State University as an Assistant Professor (Courtesy) in the departments of Fisheries and Wildlife and Forest Science.  From 1999 to 2000 he held the position of Assistant Professor at Oregon State University in the Department of Forest Science.  While at Oregon State University, Dr. McIntosh worked as a Research Associate in the Department of Forest Science from 1996 to 1999 and held a Faculty Research Assistantship in the Department of Forest Science from 1992 to 1996.

Qualifications:

During his career, Dr. McIntosh has been involved in the assessment of the structure, function, and dynamics of aquatic ecosystems.  He has also evaluated historical changes in aquatic ecosystem structure and function and the influence of anthropogenic and natural disturbance on these changes.  Dr. McIntosh has worked with multi-scale methods to assess aquatic condition and community structure of watersheds.  He also has extensive experience with the freshwater ecology of fish assemblages of the Pacific Northwest and the use of remote sensing techniques for across scale assessments and watershed monitoring.

Relevant Publications:

Torgersen, C.E., R.N. Faux, B.A. McIntosh, N.J. Poage, and D.J. Norton.  in press.  Airborne Thermal Remote Sensing for Water Temperature Assessment in Rivers and Streams.  Remote Sensing of Environment.

Faux, R.N., and B.A. McIntosh.  2000.  Stream temperature assessment using forward-looking infrared (FLIR).  Conservation Biology in Practice, 1(10): 38-39.

McIntosh, B.A., J.R. Sedell, R.F. Thurow, S.E. Clarke, and G.L. Chandler.  2000.  Historical changes in stream habitats in the Columbia River basin.  Ecological Applications, 10(5): 1478-1496.

Torgersen, C.E., D.M. Price, B.A. McIntosh, and H.W. Li.  1999.  Multiscale thermal refugia and stream habitat associations of chinook salmon in northeastern Oregon.  Ecological Applications, 9(1): 301-319.

McIntosh, B.A., J.R. Sedell, J.E. Smith, R.C. Wissmar, S.E. Clarke, G.H. Reeves, and L.A. Brown. 1994.  Historical changes in fish habitat for select river basins of eastern Oregon and Washington.  Northwest Science, 68(Special Issue): 36-53.

Paul M. Sankovich, Fisheries Research Biologist, Oregon Department of Fish and Wildlife.

Education:

B.S., Biology, University of Nevada, 1987.

M.S., Fishery Resources, University of Idaho, 1995.

Professional Experience:

Mr. Sankovich is currently employed by the Oregon Department of Fish and Wildlife.  He is responsible for conducting and overseeing life history studies on bull trout and Oncorhynchus mykiss with an emphasis on bull trout spawning and the interaction between resident and anadromous forms of O. mykiss.  He oversees and coordinates data collection and necessary project operations.  Mr. Sankovich is responsible for coordinating ESA and other research activities in eastern Oregon.  He prepares manuscripts, study plans, budgets, reports, permits, detailed sampling plans, and schedules.  He also assists supervisor in personnel activities.  Mr. Sankovich has presented project results at numerous professional meetings and to public interest groups.  From 1992-1995 he worked as a fisheries research scientist for the Idaho Department of Fish and Game.

Qualifications:

Since 1994 Mr. Sankovich has conducted or assisted in various investigations on listed salmonids and native trout.  He has extensive experience studying the life history and spawning behavior of salmonids, particularly chinook salmon, steelhead, and bull trout. He has also worked extensively with federally-listed species.

Relevant Publications:

Jonasson, B. C., J. V. Tranquilli, P. Sankovich, E. S. Van Dyke, M. Keefe, and R. W. Carmichael.  In press.  Investigations into the early life history of naturally produced spring chinook salmon in the Grande Ronde River Basin.  Annual Progress Report.  Bonneville Power Administration, Portland, OR.

J. V. Tranquilli, P. Sankovich, E. S. Van Dyke, B. C. Jonasson, M. Keefe, and R. W. Carmichael.  1998.  Investigations into the early life history of naturally produced spring chinook salmon in the Grande Ronde River Basin.  Annual Progress Report.  Bonneville Power Administration, Portland, OR.

Sankovich, P., R. W. Carmichael, and M. Keefe.  1997.  Smolt migration characteristics and mainstem Snake and Columbia River detection rates of PIT-tagged Grande Ronde and Imnaha River naturally-produced spring chinook salmon.  Annual Report.  Bonneville Power Administration.

Sankovich, P., R. W. Carmichael, and M. Keefe.  1996.  Smolt migration characteristics and mainstem Snake and Columbia River detection rates of PIT-tagged Grande Ronde and Imnaha River naturally-produced spring chinook salmon.  Annual Report.  Bonneville Power Administration.

Sankovich, P., R. W. Carmichael, and M. Keefe.  1995.  Smolt migration characteristics and mainstem Snake and Columbia River detection rates of PIT-tagged Grande Ronde and Imnaha River naturally-produced spring chinook salmon.  Oregon Department of Fish and Wildlife, Fish Research Project 95-37, Annual Progress Report, Portland.

Timothy A. Whitesel, Fisheries Scientist, Conservation Biology Section, Oregon Department of Fish and Wildlife.

Education:

Ph.D., Biological Sciences, University of Rhode Island, 1990.

M.S., Zoology, University of Rhode Island, 1987.

B.A., Philosophy, State University of New York, College at Fredonia, 1985.

B.S., Biology, State University of New York, College at Fredonia, 1983.

Professional Experience:

For the past 10 years Dr. Whitesel has worked for the Oregon Department of Fish and Wildlife.  In that capacity he has served as the program leader for native trout studies, the coordinator for endangered species activities, and as a supervisory biologist for studies on threatened and endangered salmon and steelhead.  His work has focused on basic research with salmonids.  Dr. Whitesel currently has faculty status at Portland state University and has held faculty status at Eastern Oregon University and Stockton State College (NJ).

Qualifications:

Currently, Dr. Whitesel has responsibility for the design and implementation of a BPA-funded study of bull trout genetics, life history, habitat needs and limiting factors in eastern Oregon as well as a project funded by the USFWS to evaluate movements and habitat requirements of westslope cutthroat trout.  He has coordinated activities for the state of Oregon that were associated with fish species listed as endangered or threatened.  He has also designed, implemented and conducted projects to evaluate chinook salmon and steelhead trout compensation, supplementation, and recovery efforts.  These programs focused on the use of hatcheries and revolved around traditional production projects, projects to supplement natural populations, and captive broodstock projects.

Relevant Publications:

Keefe, M., T.A. Whitesel and P. Angelone.  2000.  Induced mortality and sublethal injuries in embryonic brook trout from pulsed DC electroshocking.  N. Amer, J. Fish. Manag. 20: 320-327.

Whitesel, T.A., R.W. Carmichael, M.W. Flesher, and D.L. Eddy.  1998.  Summer steelhead in the Imnaha River basin, Oregon.  In, Lower Snake River Compensation Plan Status Review Symposium (D. Herrig, ed.); U.S. Fish and Wildlife Service, Boise.  p. 32-42.

Jonasson, B.C., R.W. Carmichael, and T.A. Whitesel.  1996.  Residual hatchery steelhead: Characteristics and potential interactions with spring chinook salmon in northeast Oregon.  Oregon Department of Fish and Wildlife, Fish Research Project, Annual Progress Report, Portland, Oregon.

Whitesel. T.A.  1993.  Comparison of juvenile Atlantic salmon (Salmo salar) reared in a hatchery and introduced into a stream:  a two-size-threshold model of smoltification.  Can. Spec. Publ. Fish. Aquat. Sci. 118: 239-247.

Keefe, M., T.A. Whitesel and H.E. Winn.  1992.  Learned predator avoidance behavior and a two-level system for chemosensory recognition of predatory fishes in juvenile brook trout.  In, Chemical Signals in Vertebrates, VI (R.L. Doty and D.D. Muller-Schwarze, eds.), Plenum Press, New York. p. 375-381.

# Comments

Enter the project ID from Part 1, or leave blank if blank in Part 1

Enter project title from Part 1

Provide project detail for headings a through h. It is important to clearly identify ties to the subbasin summaries, at www.cbfwf.org/province.htm.

Describe the project and work to be accomplished in the next few years. Please limit to 300 words.

Clearly identify the problem your project addresses. Describe the background, history, and location of the problem. Identify and, if necessary, expand upon the problem as it is described in the subbasin summary. For habitat-related projects, summarize and cite relevant watershed assessments. For research-related projects, include a scientific literature review which should cover the most significant previous work history related to the project, including work of key project personnel on any past or current work similar to the proposal. The purpose of the literature review is to place the proposed research in the larger context of what work has been done, what is known, and what remains to be known. All references should be concisely summarized, cited, and listed in section h below.

Describe why your project is needed. Specifically, describe the relation of your proposed project both to the objectives identified in the subbasin summary and to the goals and objectives of the 1994 Fish and Wildlife Program (FWP), NMFS Biological Opinion, or other plans. Make a convincing case for how the proposed work will further goals of the FWP and the subbasin summary. Relate project objectives and hypotheses as specifically as possible to the subbasin summary, FWP objectives and measures or to other plans. Show how the proposed work is a logical component of an overall conceptual framework. Any particularly novel ideas or contributions offered by the proposed project should be highlighted and discussed.

Describe the relationships and links between your project and other relevant projects in progress in the Columbia Basin and elsewhere. Put your project into the context of other work funded under the FWP and specifically those in the subbasin summary. Indicate how your proposed project relates to, complements or includes collaborative efforts with other proposed or existing projects, specifically those in your watershed, subbasin and province. If the proposed project requires or includes collaboration with other agencies, organizations or scientists, or any special permitting to accomplish the work, such arrangements should be fully explained. If the relationship with other proposals is unknown or is in conflict with another project, note this and explain why.

This will supplement the Relationships table in Section 3, so some information may be repeated. You have more space here than in Section 3 to detail the relationships.

This is intended to supplement the Relationships table in Section 3, consequently, some information will need to be repeated from Section 3. This narrative section allows for more detailed descriptions of relationships, includes non-interdependent relationships, and includes those not limited to BPA funded projects.

If the project is continuing from a previous year, the history must be provided. This includes projects that historically began as different numbered projects (identify number and short title). For continuing projects, the proposal primarily will be an update of this section. List the following: a) project numbers (if changed), b) adaptive management implications, c) project reports and technical papers, d) years underway, e) summary of major results achieved	, f) past costs

Special attention should be paid to reporting of results (expand upon the results reported in Past Accomplishments, Part 1, Section 2.) Reporting of results needs to be more than a list of tasks accomplished. Wherever possible, results need to be provided in biological terms quantifying benefits and other impacts to fish and wildlife. If applicable, show results in graphs, tables, or maps.

Include an objective assessment of factors that may limit success of the project. Discuss any particularly novel methods offered by the proposed project.

Present your project’s objectives, tasks, and methods to implement the tasks (use and expand upon the objectives and tasks from the Budget Tables in Part 1, Sections 4-7). Present these in a numbered list; outline and link by objective, task, and method; and group appropriately to avoid redundancy. See instructions document for thorough definitions and examples of “objectives” and “tasks and methods”

All major facilities and equipment to be used in the project should be described in sufficient detail to show adequacy for the job. For example, the proposal should indicate whether there are suitable (based on contemporary standards) field equipment, vehicles, laboratory and office space and equipment, life support systems for organisms, and computers. Any special or high-cost equipment to be purchased with project funds should be identified and justified. This section should be no longer than a few paragraphs.

If you have key technical documents specifically related to your project that are cited and summarized in the proposal form, you may submit these as background reference material for the peer reviewers. These documents may include project master plans, monitoring and evaluation plans, watershed assessments, and peer-reviewed articles generated from the project. Please note that the ISRP and CBFWA will evaluate your project based on the proposal, so all critical information needs to be provided in the proposal. Simply referencing another document will not suffice. It is not necessary to send in cited material, but if you do, please note it in the right hand column of the reference table. If your document is available on the web (e.g. through BPA) please provide the web address. If not on the web, but you have an electronic copy please provide it by email or disc. If only available in hard copy send that. Send all materials to the same address you send the proposal form.

Include names, titles, FTE/hours, and one-page resumes for key personnel (i.e. principal investigators, project managers, key subcontractors), and describe their duties on the project. Emphasize qualifications for the proposed work. Resumes should include name, degrees earned (with school and date), certification status, current employer, current responsibilities, list of recent previous employment, a paragraph describing expertise, and up to five recent or especially relevant publications or job completions.