# Bonneville Power Administration

# FY 2002 Provincial Project Review

# PART 2. Narrative

Project ID:	200122

Title:	Walla Walla Subbasin LSRCP Summer Steelhead Production and Evaluation Program

# Section 9 of 10. Project description

a. Abstract

The LSRCP is funded through the USFWS with power production revenues provided by the Bonneville Power Administration.  The LSRCP provided specific goals that include “in-place” and “in-kind” replacement of adult steelhead in the Walla Walla basin.  Specific goals include: 1) establishing broodstock(s),  2) maintaining and enhancing natural populations,  3) returning adults to the LSRCP area, and 4) improving or re-establishment of sport and tribal fisheries.  The existence of the LSRCP within the basin continues to raise questions about effects to listed species from hatchery fish, the desire to develop new broodstocks, and monitoring the status of natural populations relative to the hatchery program and goals.  Answers to these questions must be obtained and integrated into existing management documents if managers are to make informed decisions that benefit natural populations.

LFH releases summer steelhead smolts into the Walla Walla Subbasin in the Walla Walla and Touchet rivers.  NMFS has determined that releases of LFH summer steelhead stock constitutes jeopardy to natural steelhead populations within the basin, and that WDFW should switch to local stocks.  Currently, new broodstock sources are being investigated within the basin, with broodstock trapping in the Touchet River following completion of a Draft Hatchery and Genetics Management Plan (HGMP).  WDFW also provides LSRCP rainbow trout for put-take fisheries (lakes) within the Walla Walla Subbasin.  For summer steelhead released into the basin, extensive monitoring and evaluation programs exist to ensure the continued existence of steelhead populations within the basin as steps are taken under the FWP to correct habitat problems and survival problems associated with the FCRPS.

b. Technical and/or scientific background

The Lower Snake River Project was authorized by Congress on March 2, 1945 by Public Law 14, 79th Congress, First Session. The project was authorized under the Rivers and Harbors Act of 1945.  It consists of Ice Harbor Dam (IHR), completed in 1962; Lower Monumental Dam, 1969; Little Goose Dam, 1970 and Lower Granite Dam, 1975. The project affected over 140 miles of the Snake River and tributaries from Pasco, Washington to upstream of Lewiston, Idaho. The authorized purposes of the project were primarily navigation and hydroelectric power production. The original authorizing legislation for the project made no mention of fish and wildlife measures needed to avoid or otherwise compensate for the losses or damage to these important resources.

The Fish and Wildlife Coordination Act (FWCAR) of 1958 (48 Stat. 401, 16 U.S.C. 661 et seq. as amended) requires an analysis of fish and wildlife impacts associated with federal water projects as well as compensation measures to avoid and/or mitigate for loss of or damage to wildlife resources (refer to Section 662 (b) of the Act).  The U. S. Fish and Wildlife Service (USFWS) and NMFS provided the U.S. Army Corps of Engineers with a FWCAR on the Lower Snake River Project in 1972. Using the FWCAR, the U.S. Army Corps of Engineers (COE) wrote a report to Congress in 1975 (COE 1975) detailing losses of fish and wildlife attributable to the Project.  Congress authorized the LSRCP as part of the Water Resources Development Act of 1976 (Public Law 94-587).

The LSRCP is funded by the USFWS through the LSRCP with power production  revenues provided by the Bonneville Power Administration.  The WDFW administers and implements the Washington portion of the program. Specific mitigation goals include “in-place” and “in-kind” replacement of adult salmon and steelhead.  The LSRCP program for steelhead and trout in Washington was begun in 1982 and for salmon in 1984.  The LSRCP program in Washington has been guided by the following objectives: 1) Establish broodstock(s) capable of meeting egg needs,  2) Maintain and enhance natural populations of native salmonids,  3) Return adults to the LSRCP area which meet designated goals, and 4) Improve or re-establish sport and tribal fisheries.  The Lyons Ferry Complex is comprised of Lyons Ferry (LFH) and Tucannon hatcheries, and a system of WDFW and Tribal operated acclimation ponds throughout southeast Washington and western Idaho.  These facilities rear and release juvenile fish to compensate the State of Washington for (return) 18,300 Snake River fall chinook, 1,152 Tucannon River spring chinook, 4,656 Snake River summer steelhead, and 67,500 angler days of recreation on resident fish.  Management intent for each species is different and will be discussed as appropriate below.

No spring chinook or fall chinook are released directly into the Walla Walla River or its tributaries.  Only steelhead and trout production and evaluations for the subbasin will be addressed further.  Historically, all steelhead and trout production for the Walla Walla River subbasin occurred at LFH.  Fish were released directly into the Walla Walla  River and Mill Creek (Figure 1), or acclimated and then released into the Touchet River from an acclimation pond in the Town of Dayton (see facilities below).  Rainbow trout plants for area lakes and stream also came from LFH or Tucannon Hatchery.  Evaluations of the program success at returning adult summer steelhead has occurred simultaneously.  While reintroduction of spring chinook has been identified as a subbasin goal, it is not addressed under the original LSRCP program, and thus will be incidental to primary LSRCP directed actions.

c. Rationale and significance to Regional Programs

There are four core goals for the management of the Walla Walla River subbasin which were summarized in the Subbasin Summary.  They are:

- Protect, enhance and restore wild and natural populations of summer steelhead, bull trout, shellfish and other indigenous fish in the Walla Walla subbasin.

- Reestablish runs of extirpated spring chinook and Pacific lamprey (CTUIR) into historically occupied habitat in the Walla Walla River subbasin.

- Provide sustainable ceremonial, subsistence and recreational anadromous and resident fisheries; non-consumptive fish benefits such as cultural and ecological values.

- Maintain genetic and other biological characteristics of indigenous populations and genetic viability of reintroduced populations.

These goals closely mirror the policies which guide implementation of the LSRCP program and are consistent with the vision, policies and planning assumptions laid out by the NWPPC in their 2000 Fish and Wildlife Program.   Further, identification of depressed steelhead stocks (Busby et al. 1996) and their subsequent ‘Threatened’ listing under the ESA has mobilized greater interest in Walla Walla subbasin salmonid populations.  Management within the subbasin (and fish production levels) is also affected by regional discussions required by the U.S. v Oregon court decision, which result in a Columbia River Fish Management Plan (CRFMP).

Figure 1.  Primary streams in the Walla Walla Subbasin (Walla Walla Subbasin Summary 2001).

The existence of LSRCP hatchery mitigation within the basin continues to raise questions: what are the effects on listed species of continuing the hatchery steelhead program, should new broodstocks be developed for the program to reduce the potential for negative impacts of hatchery production and serve as a more appropriate source of supplementation fish, are wild populations within the basin healthy enough to be used for broodstock development without serious damage.  Answers to these questions must be obtained and integrated into existing management documents if managers are to make informed decisions that benefit natural populations.   More data are needed to most effectively meet requirements outlined in the FWP, by the ESA, the LSRCP program, and by Washington’s Wild Salmonid Policy (1997).  The USFWS, charged with implementing the LSRCP program through cooperation with the states of Oregon, Washington and Idaho, and the tribes, recognized that the program must be adaptable if it was to succeed.  To ensure that adaptive nature, monitoring and evaluation programs were identified as critical to program success.

The NWPPC’S 1995 Fish and Wildlife Plan (FWP) identified the need to halt the decline and rebuild populations to sustainability (Sect. 4.1), and promote the funding of projects directed at critical unknowns or uncertainties (3.2 C, 4.1 A, 4.2 A).  Here-to-fore hatchery supplementation (7.0 A, 7.3) such as currently practiced in the Walla Walla under the LSRCP program strives to achieve maximum return of fish to meet LSRCP goals and sustain fisheries, while habitat and other productivity problems within the basin are addressed the FWP to recover ESA listed populations.  Uncertainties associated with using hatcheries to compensate for dam-related losses along with other needs have resulted in a large, ongoing evaluation program (USFWS 1998).  To ensure that the LSRCP program is responsive to the changing landscape, evaluation programs have also assumed responsibility for development of HGMPs, and compliance with ESA.  These efforts will continue to be a priority (see Objectives below).   Following is a summary of steelhead and trout production and evaluation actions planned within the Walla Walla subbasin under the LSRCP for FY2002 and beyond.

Summer Steelhead - Annually, approximately 250,000 – 300,000 hatchery summer steelhead smolts have been reared and released into the Walla Walla River subbasin.  The original intent of these releases was to return adults which met the LSRCP goal, and reestablish successful steelhead fisheries.  Although maintaining populations of wild steelhead in the basin was and is a management intent of the co-managers, no specific supplementation goals for Walla Walla Subbasin populations were identified when the LSRCP Program was initiated.  Stocks of fish released into the Walla Walla River from Lyons Ferry Hatchery generally have been of Wells (1983-86), Wallowa (1984-89) and Lyons Ferry (1987-present) origin.  However, during the life of the LSRCP program, wild populations throughout the Walla Walla subbasin generally declined (except for run years 1999 and 2000, see Walla Walla Subbasin Summary (WWSS)).

The LSRCP program has successfully returned adult steelhead that meet or exceed LSRCP goals, and these fish have created and supported successful sport fisheries. Releases of summer steelhead within Washington decreased in 2000, but are currently under discussion in the CRFMP negotiation process.  Concurrent with this mitigation success (Strategy 8 – WWSS) has been increasing concern with possible effects of hatchery returns on wild populations as they return to their release site, or stray into adjacent subbasins which support natural populations.

Evaluations have focused on increasing survival of hatchery reared steelhead and assessing contribution of LFH released fish to Columbia and Walla Walla basin fisheries (Strategy 8 – WWSS).  Areas of concern include straying rates of hatchery stock steelhead into tributary rivers where natural steelhead stocks exist, the degree of incidental hooking mortality on natural adults, whether hatchery steelhead are contributing to the decline in wild populations, and whether a more appropriate stock for compensation and proposed supplementation in the basin is available.  Evaluations will continue to monitor steelhead releases and harvest in regional fisheries (Action 9.5 – WWSS), and focus on ways to minimize effects (such as straying) of the compensation program on natural populations, such as size and time of release studies or other release strategies that may decrease the potentially negative interactions between hatchery and wild fish.  In addition, expanded genetic evaluation of hatchery and naturally produced steelhead has begun to more fully describe the genetic stock structure within the basin, and possibly the availability of an acceptable locally adapted broodstock for use in the program.  To that end, WDFW personnel funded through the LSRCP program led co-managers in drafting an HGMP (RPA: Action 176) for the development of a Touchet River steelhead stock (Action 8.4 – WWSS).

Trout – Production of catchable size trout for put-take fisheries has been an integral part of the LSRCP program since its beginning.  These fish have been used to provide recreational opportunity for Washington residents as originally agreed to under the LSRCP.  The majority of trout are outplanted into small lakes and ponds throughout SE Washington.   Before 1999, WDFW planted some rainbow trout into the Touchet River.  However, with the advent of ESA listings for steelhead and bull trout in the late 1990s, and the adoption of Washington’s Wild Salmonid Policy (WDFW 1997), this practice has ceased.  The LSRCP funded an evaluation of the persistence of planted rainbow trout and residual hatchery steelhead (Martin et al. 1993), and their potential effect on wild salmonids.  This study help managers understand the degree of residualism from direct and acclimated hatchery steelhead releases, and also led to the decision to discontinue trout planting in anadromous fish bearing streams of SE Washington.

d. Relationships to other projects

The LSRCP was the first effort of Federal authorities to mitigate for damages caused to populations of fish and wildlife within the Lower Snake River as a result of construction of the four lower Snake dams (part of the FCRPS).  Although the Walla Walla Subbasin is not part of the Snake River Basin, it was included as part of the LSRCP in an attempt to ensure adequate survival of artificial production to attain adult goals.  As such the program may be central to ensuring the continued existence (and recovery under ESA) of steelhead populations within the subbasin as steps are taken under the FWP to correct habitat problems and survival problems associated with the FCRPS.  The infra-structure of hatcheries and evaluation programs provided by LSRCP has been instrumental in defining the problems facing anadromous fish in the subbasin (USFWS 1998).

As previously stated, WDFW (under the LSRCP program) developed an HGMP for Touchet River steelhead to be reared at the LFH.  This action was consistent with the FWP, with RPA actions associated with the FCRPS Biological Opinion (Action 176) and with goals and objectives described in the Subbasin summary.  Further investigation of populations within the subbasin, and an assessment of the potential benefits to steelhead from actions described in the HGMP, need to occur before additional decisions can be made concerning steelhead in the rest of the subbasin, and whether other local broodstocks should be developed.  These management needs have been identified in the Subbasin Summary (Strategies 6, 7, 8, 9, 10, 11, 15).  Ongoing LSRCP evaluation actions coordinate with current BPA funded projects such as the Assess fish habitat and salmonids in the Walla Walla River of Washington (BPA Project # 199802000) and complement the data collection actions of that project to measure fish densities, collect genetic samples and conduct steelhead spawning ground surveys.  Actions funded under the LSRCP will directly complement the proposed FY2002 expansion of the Walla Walla Assessment project by assisting with adult steelhead trapping and operating a proposed rotary screw trap on the Touchet River to capture migrating smolts.  These actions can be expanded in a cost efficient manner because of existing LSRCP funding and staff, and will further the timely collection of needed subbasin population data.  Results from LSRCP funded evaluation actions have provided substantial data for Washington Conservation Commission’s Limiting Factors Analysis, the development of the recent subbasin summary, and the Draft Subbasin Master Plan (CTUIR 1993).  It is also likely that if expanded supplementation actions are considered advisable to recover depressed populations, that LSRCP facilities could be used for some of that expanded production.

Hatchery steelhead production releases into the Walla Walla River subbasin have decreased in recent years to reduce their potential impact to native steelhead populations.  The LSRCP evaluations program continues to investigate straying to systems by including CWT study groups in all major releases within the subbasin, and documenting adult straying behavior.

e. Project history (for ongoing projects)

- Project # - not applicable

- Monitoring and evaluation activities of LSRCP production provides near real time recommendations for refining, changing and adapting production and management practices (eg.  M&E has allowed managers to adjust size at release of steelhead smolts to improve survival and decrease residualism without affecting population age structure).  Consistent M&E staffing has also allowed the LSRCP program to respond timely to the changing landscape of Columbia River management under ESA driven restrictions.

- Annual project reports for summer steelhead (Schuck et al. 1999, Martin et al. 2000) are provided in published form throughout the Columbia Basin.  Reports provide production and evaluation assessments in a formalized format that is readily available to managers, and provides continuous long term data sets for hatchery and natural production within the basin.

- Steelhead and trout production and monitoring and evaluation have been in effect since 1982, with annual reports provided since 1984.

- Past Accomplishments:

- Annual production of salmon and steelhead for release into the basin (yearly - see attachment 1).

- Document adult steelhead returns to the Walla Walla subbasin (and Snake River basin and disposition of  returning adults).  Progress toward meeting LSRCP goals (yearly in reports).

- Document and report harvest of steelhead within the Columbia Basin (yearly).

- Conducted size at release studies of yearling steelhead.  Adjusted production protocols to improve survivals.

- Assessed level of residualism of hatchery reared steelhead in the Touchet River (1992-99).

- Investigated methods of acclimation pond use to reduce residualism within rivers (1992-99) (Viola and Schuck 1995)

- Document adult steelhead spawning in portions of the subbasin (yearly)

- Sample juvenile population distribution and densities in portions of the basin.  Track and report trends (yearly).

- Trap, sample for genetic material and pass wild Touchet R. steelhead at the Dayton trap (1993-95, 1999-present)

- Collect genetic samples from juvenile steelhead in the upper basin.  Analyze and/or archive samples for genetic characterization.

- Draft an HGMP for Touchet River endemic steelhead broodstock development (2000, 2001)

- Collect and spawn endemic steelhead for experimental stock development under Draft HGMP (2000, 2001)

f. Proposal objectives, tasks and methods

Following are the objectives for the 2002 LSRCP production and M&E programs associated with the Walla Walla subbasin.  For complete details, including a discussion  of assumptions and approaches for evaluation actions, see Attachment 1 (Lyons Ferry Complex Annual Operations Plan) and Attachment 2 (Proposed 2002 Monitoring and Evaluations Plan).

- Produce summer steelhead to meet goals defined in the LSRCP mitigation plan, Columbia River Fish Management Plan and ESA recovery and management plans.

- Monitor and evaluate the quality and release of hatchery summer steelhead produced from LFC.

- Evaluate hatchery release strategies from all release sites (downstream survival rates).

- Estimate the degree of residualism of endemic origin juvenile steelhead in the Touchet River.

- Determine natural production and estimate freshwater survival rates for spring chinook and summer steelhead in Southeast Washington streams.  Compare natural survival rates to hatchery survival rates for spring chinook and summer steelhead.

- Conduct, monitor, and evaluate adult trapping/collection of summer steelhead for broodstock. (endemic broodstock development)

- Estimate adult returns and return rates, collect life history and genetic characteristics, and document distribution of adult salmon, and summer steelhead to southeast Washington streams and facilities.  Provide lower Columbia Fishery contributions by LSRCP produced fish.

- Maintain phenotypic and genotypic characteristics of salmon and steelhead stocks used at Lyons Ferry Complex.

- Where appropriate, cryogenically archive salmon and steelhead semen for future use.

- Assess LSRCP hatchery evaluation actions to determine potential effects on species listed under the Endangered Species Act.  Represent WDFW during formal ESA consultation between NMFS and the FWS.  Coordinate and integrate Washington's anadromous fish management and research with the Section 7 LSRCP Biological Assessment, subsequent Biological Opinions and Management Plans, NMFS' Recovery Plan, and develop and submit Hatchery and Genetic Management Plans (HGMPs) for stocks produced at LFC.

- Complete annual reports to summarize results of all LSRCP funded work conducted during the contract period.  Disseminate to interested parties in Columbia Basin.

g. Facilities and equipment

Lyons Ferry Hatchery (LFH) is located on the Snake River (Rk 95) near its confluence with the Palouse River, and lies between Lower Monumental and Little Goose dams.  LFH has pathogen free 100% well water of near constant temperature and a capacity of 60,000 gpm.  The hatchery has adult trapping and holding facilities for returning fall chinook and summer steelhead broodstock.  There are two separate incubation buildings (one for steelhead and one for spring and fall chinook) and early life rearing troughs and raceways for all species.  There are also three 2.1 acre ponds for smolt rearing (fall chinook and summer steelhead).  LFH provides all of the steelhead for release in the Lower Snake Basin, and all of the fall chinook presently released in the entire Snake River.

TFH is located at Rk 58 on the Tucannon River, has an adult steelhead and salmon collection trap, standard hatching troughs and raceways, and a earthen rearing pond for rearing juvenile rainbow trout.  The hatchery has well, spring and river water to use for various rearing strategies.  The adult collection trap has been used primarily to trap returning spring chinook salmon for broodstock, though since 1998, WDFW also used the trap to assess the summer steelhead return in the Tucannon River.  TFH rears rainbow trout for release in Walla Walla subbasin lakes and ponds.

One remote steelhead acclimation facility (Dayton AP) serves as the release structure for steelhead production from LFH for the Touchet River.  A temporary adult steelhead trap at the Dayton AP is operated by Evaluations staff as part of the program to develop and assess a local broodstock.  A USFWS owned office facility in Dayton, WA houses Evaluation staff.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Busby, P.J, T.C. Wainwright, G.J. Bryant, L. J. Lierheimer, R.S. Waples, F.W. Waknitz, and I.V. Lagomarsino. 1996. Status review of west coast steelhead from Washington, Idaho, Oregon and California. NOAA Tech. Memo. NMFS-NWFSC-27. | n |
| COE (U.S. Army Corps of Engineers) District, Walla Walla, Washington. 1975. Special Report: Lower Snake River Fish and Wildlife Compensation Plan. 95 pgs. Plus appendices. | n |
| CTUIR. Walla Walla River Basin Master Plan (draft) 1993. Prepared for the NW Power Planning Council. Portland, OR. | n |
| Martin, S., M. Schuck, J. Bumgarner, J. Dedloff, and A. Viola. 2000. Lyons Ferry Hatchery Evaluation Trout Report: 1997-1998 Annual Report to U.S. Fish and Wildlife Service. Lower Snake River Compensation Plan Office. Boise, ID #FPA00-11. | n |
| Martin, S.W., A.E. Viola, and M.L. Schuck. 1993. Investigations of interactions among hatchery reared summer steelhead, rainbow trout, and wild spring chinook salmon in southeast Washington. Washington Department of Wildlife Report to the USFWS. Report # AFF1/LSR-93-1 | n |
| NWPPC (Northwest Power Planning Council). 1995. Columbia River Basin Fish and Wildlife Program. NPPC, Portland, OR. | n |
| Schuck, M., A. E. Viola, J. Bumgarner, J. Dedloff. 1998. Lyons Ferry Trout Evaluation Study: 1996-1997 Annual Report to U.S. Fish and Wildlife Service. Lower Snake River Compensation Plan Office. Boise, ID #H98-10. | n |
| USFWS. 1998. Proceedings of the Lower Snake River Compensation Plan Status Review Symposium. Lower Snake River Compensation Plan Office. Boise, ID. 276 pgs. | n |
| Viola, A. and M. Schuck. 1995. A Method to Reduce the abundance of Residual Hatchery Steelhead in Rivers. North American Journal of Fisheries Management 15(2) 488-493. | n |
| WDFW Wild Salmonid Policy. 1997. Policy of the Washington Department of Fish and Wildlife and Western Washington Tribes Concerning Wild Salmonids & Additional Policy Guidance on Deferred Issues Concerning the Wild Salmonid Policy. Olympia, WA. | n |

# Section 10 of 10. Key personnel

Harold R. Harty – Production Manager / Associate Investigator

Washington Department of Fish and Wildlife – Lyons Ferry Complex

PO Box 278, Starbuck, WA  99359

### (509) 646-3454  FAX (509) 646-3400

WORK HISTORY:  1995 to present - Washington Department of Fish and Wildlife, Starbuck, WA

Lyons Ferry Complex Manager - Manages a multi-species fish hatchery complex (Lyons Ferry and Tucannon Hatcheries), and maintains three satellite acclimation facilities.  Responsible for fish culture and biological program planning; budget development and tracking; supervision of full time and temporary employees; coordination and supervision of permitting and engineering efforts associated with hatchery operation and maintenance.  Coordination with various state and tribal agencies for marking and releases of spring and fall chinook salmon, steelhead trout and rainbow trout.

1979-1995  - Washington Department of Wildlife, Statewide locations

Fish Hatchery Manager II, III, and V - Managed multi-species fish hatcheries within the state of Washington.  Responsible for fish culture and biological program planning; budget development and tracking; supervision of  employees; coordination and supervision of permitting and engineering efforts associated with hatchery operation and maintenance.  Coordination with various state agencies for marking and release of rainbow and steelhead trout. Organized, planned and executed spawning procedures and shipments of eggs to various hatcheries throughout the state; stocking of fish in lakes and stream within the region.  Successfully fulfilled enforcement, biological and wildlife management requirements of the jobs.

PROJECT EXPERTISE:

Assisted in the development of the draft captive broodstock proposal for Tucannon River spring chinook salmon.  Provided critical information regarding hatchery and fish limitations.  Over 25 years of experience in basic and advanced aquaculture techniques. Directs Lyons Ferry Complex personnel in current spawning activities and juvenile rearing for all species at the hatchery.   Specific duties will be to oversee the fall chinook and steelhead production programs and personnel associated with the program at Lyons Ferry complex.

RECENT REPORTS:

Harty, H. R.  1997.  Lyons Ferry Complex Annual Report to U.S. Fish and Wildlife Service, LSRCP Office, Boise, ID.

###### Mark L. Schuck – Principle Investigator

Washington Department of Fish and Wildlife – Snake River Lab.

401 South Cottonwood, Dayton, WA.  99328

(509) 382-1004  FAX (509) 382-2427

EDUCATION:

B.S. Fish Biology	Colorado State University, 1974

WORK HISTORY:

1994-present - Project Leader; Lower Snake River Compensation Plan hatcheries

evaluation program.  Responsible for overseeing WDFWs evaluation of a federal

compensation/mitigation program designed to replace fish resources lost due to

construction of the four Snake River power dams.  Evaluation activities are currently

being undertaken for spring and fall chinook salmon and steelhead in several rivers in

S.E. Washington.  Duties include assisting with experimental design and implementation

of studies, budgeting and report writing.  Reports are submitted in both annual progress

report and final refereed journal formats.

1982-1994:  Served as District Fish Management Biologist for WDFW in Asotin,

Columbia, Garfield and Walla Walla counties.  Concurrently served as Project

Leader for LSRCP trout evaluations in Washington.

1978-1982:  Research Biologist with WDFW on Lower Columbia River steelhead stock

evaluation study, and assessing effects of Mt. St. Helens eruption on steelhead

populations within the Toutle River drainage.

PROJECT EXPERTISE:

Has managed or researched the fish resource in S.E. Washington since 1982.  Has

been actively involved with evaluation of the LSRCP compensation program since its

inception in 1982 and with salmon and trout under the mitigation program since 1995.

Helped conduct an evaluation of instream habitat improvements in Asotin Creek and

Tucannon River in 1989 as part of the mitigation program.

RECENT REPORTS:

Martin, S., M. Schuck, J. Bumgarner, J. Dedloff, and A. Viola.  2000.  Lyons Ferry

Hatchery Evaluation Trout Report: 1997-98.  Washington Department of Fish and

Wildlife Report # FPA00-11.

Schuck, M.L.. 1998.  Washington’s LSRCP Trout Program .  In: Proceedings of the

Lower Snake River Compensation Plan Status Review Symposium.  Compiled by the

U.S. Fish and Wildlife Service, Lower Snake River Compensation Plan Office, Boise,

Idaho.  September 1998. 276p.

Schuck, M., A. Viola, J. Bumgarner and J. Dedloff.  1998.  Lyons Ferry Trout Evaluation Study: 1996-97 Annual Report.  Washington Department of Fish and Wildlife Report # H98-10.

Viola, A.E. and M.L. Schuck.  1995.  A Method to Reduce the Abundance of Residual Hatchery Steelhead in Rivers.  North American Journal of Fisheries Management 15(2) 488-493.

Joseph D. Bumgarner – Associate Investigator

Washington Department of Fish and Wildlife – Snake River Lab.

401 South Cottonwood, Dayton, WA.  99328

(509) 382-1710  FAX (509) 382-2427

EDUCATION:

M.S. (Fisheries)  	June, 1993 University of Washington, Seattle, WA

B.S. (Fisheries)  	December, 1987 University of Washington, Seattle, WA

WORK HISTORY:

June, 1993 to present	Washington Department of Fish and Wildlife, Dayton, WA

Fish Biologist II and III - Responsible for identifying, designing, conducting, analyzing, interpreting, and reporting appropriate research for Lower Snake River Compensation Plan (LSRCP) program in southeast Washington.  Relate findings to LSRCP and fish management needs in area rivers.  Performed as the WDFW spring chinook specialist (1993-2000) and steelhead specialist (2000-present) for the LSRCP program.  Takes primary responsibility for the organization, writing and data analysis for annual reports.  Assists in routine professional biological work related to spring and fall chinook salmon production and evaluation at Lyons Ferry Hatchery.

PROJECT EXPERTISE:

Current duties include acting as WDFW’s lead fisheries biologist for all spring chinook monitoring and evaluation in the Tucannon River under the LSRCP.  Developed draft captive broodstock proposal for Tucannon River spring chinook salmon.  Familiar with basic aquaculture and captive broodstock rearing techniques.  Assist Lyons Ferry Hatchery in current spawning activities and tracking of spring chinook matings.  Compile disease and mating records for captive broodstock progeny selection.

RECENT REPORTS:

Bumgarner J.D. 1998.  Washington’s LSRCP Spring Chinook Program - Tucannon River. In:: Proceedings of the Lower Snake River Compensation Plan Status Review Symposium.  Compiled by the U.S. Fish and Wildlife Service, Lower Snake River Compensation Plan Office, Boise, Idaho.  September 1998. 276p.

Bumgarner, J., D. Milks, L. Ross, and M. Varney   1998.  Tucannon River Spring Chinook Hatchery Evaluation. 1997 Annual Report, #H98-06 to U.S. Fish and Wildlife Service, LSRCP Office, Boise, ID.

# ATTACHMENT 1

# LYONS FERRY COMPLEX ANNUAL OPERATION PLAN

OCTOBER 1, 2000 — SEPTEMBER 30, 2001

Prepared by:

Washington Department of Fish and Wildlife

Nez Perce Tribe

Confederated Tribes of the Umatilla Indian Reservation

November 20, 2000

I.	INTRODUCTION

Fish production began at Lyons Ferry Hatchery Complex (LFC) in 1983 when phase I construction of trout facilities at the Lyons Ferry Hatchery site was completed.  Phase II construction of salmon facilities and steelhead acclimation facilities was completed in 1985.  Since inception, production has been directed toward meeting established Lower Snake River Compensation Plan (LSRCP) goals of returning 18,300 adult fall chinook, 1,152 adult spring chinook, 4,656 adult summer steelhead and providing 64,000 angler days of fishing opportunity from 84,000 pounds of rainbow trout (at 3 fish/lb).

A.	Facilities

LFC consists of several facilities (Table 1) throughout SE Washington and also provides fish to facilities constructed as a result of the Hatfield Amendment and operated by the Nez Perce Tribe (NPT), and to Idaho Department of Fish and Game (IDFG) as part of the LSRCP mitigation program.

Table 1.	Design Capacities of the Lyons Ferry Hatchery Complex.

| Facility | Location River (mile) | Water source | Species | Capacity (# fish) | Pounds |
| --- | --- | --- | --- | --- | --- |
| Lyons Ferry (LFH) | Snake (58) | wells | fall chinook spring chinook steelhead rainbow | 9,100,000 a 132,000 b 931,200 260,000 | 101,800 8,800 116,400 84,000 |
| Tucannon H. (TFH) | Tucannon (36) | wells, springs, Tucannon R. | spring chinook rainbow brown | 132,000 210,000 15,000 | 8,800 39,285 5,250 |
| Cottonwood AF | Grande Ronde (28.7) | Cottonwood Ck. | steelhead | 250,000 | 31,250 |
| Curl Lake AF | Tucannon (41) | Tucannon R. | steelhead | 160,000 c | 32,000 |
| Dayton AF | Touchet (53) | Touchet R. | steelhead | 125,000 | 25,000 |

a	Current capacity of 1.1 million yearlings and 2.2 million sub-yearlings.

b	For transfer to Tucannon Fish Hatchery.

c	Original design capacity.  The facility is now used for acclimation of up to 150,000 spring chinook as specified in a NMFS Section 10 permit.

B.	Fish Production

Annual hatchery production (Table 2) is intended to meet LSRCP adult return goals for several species.  Numbers of fish released in 2000 and proposed for 2001 and 2002 (Table 2) represents the program as negotiated by the co-managers and agreed to through the Production Advisory Committee (PAC), but are in variance to numbers listed for production  under the former Columbia River Fish Management Plan (CRFMP), Appendix B.  The co-managers recognize that negotiations are ongoing in the development of a new CRFMP and these numbers will likely change.

Monitoring and Evaluation (M&E) has been ongoing since 1983 and 1985 for trout and salmon programs respectively.  Recent emphasis has centered around meeting Endangered Species Act (ESA) permitting and recovery planning requirements

Table 2.	Lyons Ferry Hatchery Complex fish production numbers.

| Species | Original LSRCP Target a | Former CRFMP Goal | 2000 Planned | 2000 Actual | 2001 Planned | 2002 Proposed |
| --- | --- | --- | --- | --- | --- | --- |
| Fall Chinook Sub-yearlings Yearlings Eyed Eggs | 9,100,000 - 0 -1,200,000 f | 1,900,000 900,000 | 1,000,000 900,000 | 2,437,780 868,203 | 2,250,000 900,000 625,000 | 2,300,000 900,000 1,100,000 |
| Spring Chinook Yearlings Sub-yearlings Captive Brood Adults Smolts | 132,000 - 0 - - 0 - | 132,000 1,200,000 b - 0 - - 0 - | 128,000 1,169,000 1,250 | 127,939 - 0 - 1,139 - 0 - | 104,500 - 0 - 900 - 0 - | 120,000 - 0 - 1,300 15,000 |
| Steelhead Yearlings Fingerling | 931,200 - 0 - | 931,200 - 0 - | 770,000 - 0 - - 0 - | 770,010 88,372 c 30,717 b | 725,000 - 0 - - 0 - | 720,000d - 0 - - 0 - |
| Rainbow Trout Mitigation Catchables Fry Fingerling State Program Catchables | 237,500 150,000 e 50,000 e |  | 237,500 150,000 50,000 3,500 | 237,016 151,776 50,600 8,172 | 237,500 150,000 50,000 4,000 | 237,500 150,000 50,000 4,000 |

a	Based on adult return goals

b	Ringold Springs Hatchery/Mitchell Act spring chinook and steelhead programs discontinued.

c	Fingerling stocked into landlocked waters.

d	Under review for compliance with WSP and ESA; may be reduced.

e	Fish for transfer to Idaho Fish and Game.

f	Eyed eggs.  See Idaho Power Company (IPC)attachment for rearing and release goals.

C.	Production Plan

The proposed salmon, steelhead and trout production plan at LFC (Table 3) generally meets program goals for steelhead and trout but remains broodstock limited for both races of chinook.  Fall chinook production is increasing after several years of low production.

Table 3.	Excepted Lyons Ferry Complex 2001 Salmon, steelhead and trout production profile. a

| Species/Stock | Rearing Site b | Number | Pounds | Fish/ lb | Age | Release/ Transfer Time | Release Location |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Fall chinook/ Snake River | LFH LFH LFH LFH LFH LFH LFH LFH LFH | 450,000 150,000 150,000 150,000 200,000 1,000,000 1,000,000 46,500 625,000 | 45,000 10,000 10,000 10,000 4,000 13,333 16,667 650 350 | 10.0 12.0 12.0 12.0 50.0 75.0 60.0 50-110 Eggs | 1+ 1+ 1+ 1+ 0+ 0+ 0+ 0+ Eyed | April Mar (trans) Mar (trans) Feb (trans) June May (trans) June (trans) June (trans) c Jan. - Feb. | Site/Snake R. NPT/B. Canyon NPT/Pittsburg NPT/C. John’s Lyons Ferry/Site NPT/C. John’s NPT/B. Canyon Above L. Granite IPC/Hells Canyon |
| Spring chinook/ Tucannon Yearlings CBd (BY97) Yearlings CB (BY(98) CB (BY 99) CB (BY 2000) Rapid River | TFH LFH LFH LFH LFH LFH LFH | 104,500 175 - 0 - 298 408 1,200 1,500,000 | 6,967 400 359 31 24 810 | 15.0 Eggs | 1+ 3+ 2+ 1+ 0+ Eyed | March - April Sept. - Oct. | TFH/Curl Lake NPT/Idaho |
| Rainbow trout/Spokane State Program Kamloops | LFH LFH TFH TFH TFH | 100,000 150,000 137,500 4,000 50,000 | 40,000 3,750 39,300 6,000 3,333 | 2.5 40.0 3.5 0.75 15.0 | 1+ 0+ 1+ 1+ 0+ | Feb.- April May April - June April - May October | Lowland Lakes (Transfer to IDFG) Lowland Lakes Lowland Lakes (Transfer to IDFG) |
| Summer steelhead Lyons Ferry Touchet Tucannon Wallowa | LFH LFH LFH LFH LFH LFH LFH | 100,000 60,000 135,000 125,000 40,000 65,000 200,000 | 25,000 15,000 33,750 31,250 10,000 16,250 50,000 | 4.0 4.0 4.0 4.0 4.0 4.0 4.0 | 1+ 1+ 1+ 1+ 1+ 1+ 1+ | March - April April April April April April March - April | Touchet River Site/Snake River Lower Tucannon Walla Walla River Touchet River Tucannon River Grande Ronde R. |

a	Release numbers and pounds for acclimated releases are as measured at LFC.

b	LFH = Lyons Ferry Hatchery; TFH = Tucannon Fish Hatchery .

c	Research fish to be provided to NPT and NMFS.

d	Tucannon Spring Chinook Captive Broodstock Program.

D.	Satellite Facilities

Lyons Ferry Complex utilizes three remote acclimation facilities(AF) to release fish for WDFW’s program.  Size at release goals for AF released steelhead is 4 fish/lb, and 15 fish/lb for spring chinook.  Additionally, LFC provides 450,00 yearling and 2,000,00 sub-yearling fall chinook to three acclimation facilities operated by the NPT;  Pittsburg Landing and Captain John Rapids, on the Snake River between Asotin and Hells Canyon Dam, and Big Canyon on the Clearwater River (Attachment 1).  Size at transfer to AF’s is 12 fish/lb for yearlings and 50 - 75 fish/lb for sub-yearlings.  Size at release goal for acclimated fall chinook yearlings is 10 fish/lb and 50 fish/lb for sub-yearlings.

II.	SPRING CHINOOK

Two Tucannon spring chinook programs are currently reared at LFC.  Tucannon stock spring chinook are reared through release into the Tucannon River.  Up to 100 adult chinook (50 hatchery : 50 wild) are trapped from the Tucannon River for broodstock as part of the LSRCP supplementation program.  Adults are held at LFH to reduce pre-spawning mortality.  All fish are spawned, producing an egg take of approximately 165,000 green eggs which provide for the release of 132,000 yearling smolts (Tables 2 & 3).  A captive brood program has been initiated to aid in the recovery of Tucannon Spring chinook.  Small groups of distinct family groups have been selected from the supplementation program fish and are being held as part of the captive brood population.  At full production the captive brood program is designed to annually produce 150 spawning females which will provide an estimated 294,000 eggs (150,000 smolts annually).

During 1999 a new temporary spawning and incubation program for Rapid River spring chinook was added at LFC at the request of the NPT.  All adult and jack salmon trapped at Lower Granite Dam will be hauled to LFH and spawned.  Eggs will be incubated through the eyed stage at LFH, and then transferred to other facilities for hatching and rearing.  The program at LFH is anticipated to continue through the 2002 run year.  There is no egg take goal for the program. However, 988,000 green eggs (BY2000) from 269 females were taken in August and September, 2000.

The Ringold spring chinook (Carson stock) program was terminated at LFH in 1999.  No further culturing of these fish is anticipated at the facility.

A.	1999 Brood Supplementation Program

1.	Rearing/releases.

Fish will receive a Adipose fin clip and Coded Wire Tag (CWT) in September at LFH and then transferred to Tucannon Fish Hatchery (TFH) in October when water temperatures have decreased.  At TFH they will be reared in the large concrete raceway on straight river water except when well water is needed to maintain mid-winter water temperatures above 400 F to prevent pond freezing.  Checks for CWT retention, other marks or fin clip condition will be conducted prior to transferring the fish to Curl Lake AF in mid-February.   Fish in Curl Lake AF will be fed throughout the two month acclimation period.  Volitional release will begin March 1-15 with all fish released by April 25 at 15 fish/lb.  The release of 104,000 smolts at 15 fish/lb. is planned (Table 4).

B.	2000 Brood Supplementation Program

1.	Trapping/spawning.

Two hundred and five adult chinook (168 hatchery origin, 21 wild origin) and 9 hatchery jacks and 7 wild jacks were trapped at TFH trap May-September 2000.  Only a portion (66 hatchery and 15 wild) were taken for broodstock to LFH to be held in well water .  Externally marked strays (9 males, 8 females) were killed at the adult trap and the carcasses returned to the stream for nutrient enhancement.  All other fish were passed upstream for natural spawning.  Adults collected for broodstock were injected at transfer with oxytetracycline and erythromycin and with erythromycin every 30 days thereafter.  Adults received formalin treatments every-other day to control fungus and decrease pre-spawning mortality.   During September, 38 females (35 hatchery and 3 wild) females yielded an estimated 136,500 green eggs.  Fertilized eggs are water hardened in 100 ppm iodophore.  Semen from wild male chinook was cryo-preserved during spawning.  Genetic monitoring of the samples may occur in the future and will be coordinated with NPT.  Cryo-preserved semen may be used during future brood years to increase the diversity of the spawning population if broodstock numbers are very low or contribute to the captive broodstock program in the coming years to increase diversity.  Following picking at eye-up, and expected sac-fry mortality (5 %), we estimate that 129,675 fry will remain from the 2000 brood.  All spring chinook carcasses are frozen after spawning (captive brood and supplementation) and hauled to the upper Tucannon River for nutrient enhancement.

Rapid River Program: LFH received 568 Rapid River spring chinook from Lower Granite Dam, May/June 2000 (see Attachment 2).  Adults were injected at transfer with oxytetracycline and erythromycin.  All fish were spawned at a male to female ratio of 1:1 in August/September, yielding an estimated 988,000 green eggs.  Carcasses were  buried at LFH.  Eggs are to be incubated to the eyed stage and then transferred to rearing facilities in Idaho.

2.	Rearing/releases.

Fry are ponded in raceways at LFH at 1,600 fish/lb during December and January where they rear throughout the following spring and summer.  They will receive a CWT and AD clip during September, 2001 at 40 fish/lb, be held for three weeks, then transferred to TFH.  At TFH they will be reared in concrete round ponds or raceways on river water, except when well water is added mid-winter to maintain water temperatures above 400 F to prevent pond freezing.  Checks for CWT retention will be conducted prior to transferring the fish to Curl Lake AF in February.  A release of 120,000 fish is planned (Table 4).  All fish will be released from Curl Lake AF in March/April 2002.  Fish will be fed during the two month acclimation period.

Table 4.	Proposed Tucannon spring chinook releases from 1999 and 2000 brood years.

| Site(BY) | Number | Size #/lb | Age | Mark/CWT | PIT tags |
| --- | --- | --- | --- | --- | --- |
| Curl Lake (99) | 104,000 | 15 | 1+ | 100% AD/CWT | 900 |
| Curl Lake (00) | 120,000 | 15 | 1+ | 100% AD/CWT | 900 |
| Curl Lake (00 CB) | 15,000 | 15 | 1+ | 100% No Ad/BWT in snout | 900 |

C.	2001 Brood Supplementation

1.	Trapping/spawning

An estimated 200 adult and jack chinook (110 hatchery origin, 90 wild origin) are expected to return to the Tucannon River in 2001.  Of those, about 140 will be trapped at TFH trap May-September 2001.  Up to 100 adults and jacks total will be collected for broodstock, while remaining adults and jacks are counted and released.  Trapping and broodstock selection protocol will follow guidelines established in WDFW’s Section 10 permit (see footnote #1 above).  Adults will be injected at transfer with oxytetracycline and erythromycin and with erythromycin every 30 days thereafter.  Adults will receive formalin treatments every-other day to control fungus and decrease pre-spawning mortality.   Fish will be spawned during September, and are expected to yield 160,000 green eggs.  Fertilized eggs will be water hardened in 100 ppm iodophore.  Semen from wild male chinook will be cryo-preserved during spawning as available.  Genetic monitoring of the samples may occur in the future and will be coordinated with NPT.  All spring chinook carcasses are frozen after spawning, and hauled to the upper Tucannon River for nutrient enhancement.

Rapid River Program: An estimated 1,020 Rapid River spring chinook adults and 200 jacks are expected to be trapped at Lower Granite Dam, May through August 2001 (see Attachment 2).  Adults and jacks will be transported, by NPT staff, to LFH and held for spawning.  Adults will be injected at transfer with oxytetracycline and erythromycin.  All fish are spawned at a male to female ratio of 1:1 in August and September, yielding an estimated 2,000,000 green eggs.  Carcasses are buried at LFH.  Eggs are to be incubated to the eyed stage and then transferred to rearing facilities in Idaho.

D.	Tucannon Captive Brood

1.	1997 Brood Rearing:  Continue to hold and rear 179 three year old spring chinook adults.  These fish will be sorted in May or June 2001 for maturing fish.  Mature fish will be held in a adult spawning raceway with supplementation fish to encourage similar maturation rates.  Mature fish will be spawned in September 2001.  Wild origin males may be used in the fertilization process.  All immature fish will be held in one 20 foot circular tank until the following year when fish mature at 5 years of age.  Fish are currently in two 20 foot circular ponds at LFH.

2.	1998 Brood Rearing:  Continue to hold and rear 298 two year old spring chinook adults.  Sorted and removed 118 jacks in September, 2,000.  These fish will be sorted in May or June 2001 for maturing fish.  Mature fish will be held in a adult spawning raceway with supplementation fish to encourage similar maturation rates.  Mature fish will be spawned as three year old in September, 2001.  Wild origin males may be used in the fertilization process. All immature fish will be split into two 20 foot circular rearing tanks until the following year.

3.	1999 Brood Rearing: Continue to hold and rear 408 one year old spring chinook juveniles.  These fish will tagged by family unit (30 fish per family) in October 2000.   Tagged fish will be placed in one 20 foot circular rearing tank.  All fish will be sorted in June or July of 2001, and two year old mature males will be sacrificed.

4.	2000 Brood Rearing: Fry from the 2000 supplementation brood spawning will be ponded to the 4 foot circular starting tanks in December and January.  About 1200 fry, representing 15 distinct families will be selected for rearing in the captive brood program.  These fish will rear in the 4 foot circular tanks until September, 2001, when the family sizes will be reduced to 30 (450 total fish).

5.	2000 Captive Brood Progeny Spawning and Rearing: A total of 12 females from the 1997 Brood were spawned during September, 2000.  Total estimated egg take was 16,200 green eggs.  Natural origin males from the Tucannon River and captive brood males (1997 brood) were used to fertilize the eggs.  Survival of these eggs is currently unknown.  Eggs will be incubated following standard procedures as prescribed for the supplementation program.  Fry are ponded in raceways at LFH at 1,600 fish/lb during December and January where they rear throughout the following spring and summer.  They will receive a BWT in the snout during September, 2001 at 40 fish/lb, be held for three weeks, then transferred to TFH.  These fish will not be adipose fin clipped.  At TFH they will be reared in concrete round ponds or raceways on river water, except when well water is added mid-winter to maintain water temperatures above 400 F to prevent pond freezing.  Checks for BWT retention will be conducted before fish are transferred to Curl Lake AF in February.  A release of 15,000 fish is planned (Table 4).  All fish will be released from Curl Lake AF in March/April 2002.  Fish will be fed during the two month acclimation period.

III.	FALL CHINOOK

The LFH fall chinook program is presently below its LSRCP mitigation goal.  All LFH origin fall chinook that return to the hatchery are used for broodstock.  Additionally, some LFH origin fall chinook captured at Lower Granite Dam are transported to LFH for spawning in accordance with an agreement under the Columbia River Fish Management Plan.  Annual adjustments to the agreement are expected.  The production goal of 900,000 yearlings and 1.9 million sub-yearlings was achieved in BY 1999.  The program has expanded to include eggs for the Idaho Power program in BY 2000.  Assuming a fecundity of 3,100-3,500 eggs/female, 1,387 females would be required in BY 2000 to provide the 4.3 million eggs for the production program.  An additional 50,000 eggs are required to fulfill the anticipated research production.

A.	1999 Brood

Approximately 951,000 parr are on hand. The 450,000 fish to be released at LFH will receive a AD/CWT/VI (Left Red elastomer) tag during September/ October 2000.  Fish are tagged at 30-40 fish/lb and transferred directly into Lake 2.  Smolts will be volitionally released from the rearing pond to the Snake River, March 23 - April 15, 2001, at 10 fish/lb (Table 5).  After April 15, all remaining fish in the lake will be forced out.  Release by April 15 is required to allow for steelhead releases to begin, which uses  common release structures at LFH.  QC checks for CWT and elastomer tags will be completed before release.

A transfer to acclimation facilities above LGR of 480,000 fish at 12 fish/lb. is planned to achieve a release of 450,000 yearlings upstream of Lower Granite Dam (LGR) in the spring of 2001 (Table 5).  After marking and tagging, all fish are reared in raceways, until they are  transported to AF’s in February/March 2001 at 12 - 20 fish/lb., and acclimated on surface water until release in April.

Table 5.	Proposed LFC Transfers of BY99 Snake River Fall Chinook in 2001.

| Site | Number | Size #/lb | PIT tags | Mark/CWT/ Elastomer | Release dates |
| --- | --- | --- | --- | --- | --- |
| LFH | 450,000 | 10 | 1,000 | AD/CWT/ left red | April 1-15 |
| Capt. John | 150,000 | 12 | 2,500 | AD/CWT/left blue | Feb 1 (transfer) |
| Pittsburg Land. | 150,000 | 12 | a | AD/CWT/ right green | Mar 1 (transfer) |
| Big Canyon | 150,000 | 12 | a | AD/CWT/left green | Mar 1 (transfer) |

a	see Attachment 1: NPT Acclimation Facilities AOP.

B.	2000 Brood

1.	Trapping/spawning

Adult fall chinook were trapped at Lower Granite Dam commencing August 29 and at LFH starting September 1, 2000.  All chinook that enter LFH are retained for spawning.   Females that voluntarily return to LFH are injected with erythromycin and oxytetracycline before the first spawning.  Adults received formalin treatments every-other day to control fungus and decrease pre-spawning mortality.  Known LFH origin and unknown origin (non-Snake River basin) hatchery chinook will be transported from LGR to LFH for holding and spawning after receiving injections of erythromycin and oxytetracycline.  Trapping at LFH and LGR will continue throughout the spawning season, generally ending by late November.

Coho are occasionally identified at LFH during fall chinook trapping and spawning operations.  WDFW does not propagate coho in the Snake River, but will contact NPT representatives for proper disposition of these fish (Attachment 3).

Spawning will occur weekly on Tuesdays starting October 24, and run through December 5.  All recovered CWTs will be read or elastomer tags identified to ensure separation of LFH origin from unknown fish.  Fertilized eggs will be water hardened for one hour in 100 ppm iodophore, and incubated in Heath trays.  Estimated egg take of BY 2000 LFH Snake River fall chinook is expected to be similar to BY 1999 or about  4.3 million.  Eggs from stray hatchery fish will be disposed of or transferred, as directed, by decision reached within PAC.  Fall chinook carcasses may be hauled and released above LGR (free-flowing reaches of the Snake or Clearwater River) for nutrient enhancement.  Carcasses may be frozen at LFH and removed weekly by NPT staff.

2.	Rearing/releases.

Idaho Power Company (IPC) will receive up to 625,000 eyed eggs from the program as was agreed upon in the 1980 settlement agreement (Attachment 7).

After hatching, fry (known LFH origin) will be moved to outside raceways at 1,600 fish/lb.  Fish remain in raceways throughout the winter and the following spring and summer.

A release of 450,000 yearling fish from LFH at 10 fish/lb. is planned.  Fish to be released at LFH will receive a AD/CWT/VI (left red elastomer) (100% mark rate) during September/October 2000 and placed into a rearing pond.  Fish will be volitionally released from the rearing pond to the Snake River, April 1-15, 2002 at 10 fish/lb.  On or after April 15, all remaining fish in the lake will be forced out.  QC checks for CWT and elastomer tags will be completed before release (see Attachment ?? For details).  PIT tags will be inserted immediately before or at release.

Remaining yearling production fish are scheduled for release from three acclimation facilities in spring 2002 (Table 6).  After marking/tagging, fish will be transported to AF’s in February or March 2002 at 15-20 fish/lb., and acclimated on surface water until release in April.

According to the Interim1999 CRFMP agreement, production in excess of the 900,000 yearling program would be released as sub-yearlings upstream of LGR, unless otherwise agreed to by the co-managers.  In 2001, sub-yearling chinook will be released at LFH and upstream of LGR in accordance with agreements between NMFS and the co-managers (Table 6).  Studies to determine optimum size at release for sub-yearling fall chinook will be an integral part of the releases (Attachment 4).  A projected 2,250,000 sub-yearlings, which includes the 500,000 IPC program, will be released in 2001.

Two groups of fish are provided to NPT and NMFS researchers (Table 6).  Unmarked fish are reared to a specified size and transferred to the appropriate agency for juvenile migration research in April.  This program is expected to continue through the release of BY2000 yearlings.

Table 6.	Proposed LFC Releases/Transfers of BY 1999 Snake River Fall Chinook.

| Site | Number | Size #/lb | Age | Mark/CWT/ Elastomer | PIT tags | Release/ Transfer dates |
| --- | --- | --- | --- | --- | --- | --- |
| LFH | 450,000 | 10 | 1+ | 100 %AD/CWT/ left red | 1,000 | April 1-15 2002 |
| Capt. John | 150,000 | 12 | 1+ | 100% AD/CWT/left blue | 2,500 | Feb. (trans) 2002 |
| Pittsburg Land. | 150,000 | 12 | 1+ | 100% AD/CWT/ right green | a | March (trans) 2002 |
| Big Canyon | 150,000 | 12 | 1+ | 100% AD/CWT/left green | a | March (trans) 2002 |
| LFH | 200,000 | 50 | 0+ | 100% AD/CWT | 1,000 | June-July 2001 |
| Idaho Power | 625,000 | Eyed Eggs | 0+ |  |  | December 2000 |
| Snake River above LGR | 2,000,000 | 50 | 0+ | 1.6 Million unmarked 400K CWT only | a | June-July 2001 |
| Research b | 50,000 | 50-110 | 0+ | unmarked | 100% | June-July 2001 |

a	see Attachment 1: NPT Acclimation Facilities AOP.

b	24,000 to NPT; 26,000 to NMFS

C. 2001 Brood

1.	Trapping/spawning

Adult fall chinook will be trapped at LFH starting September 1, 2001.  All chinook entering LFH will be retained for spawning.   Hatchery adults and jacks which are not externally identifiable may also be trapped at LGR and transported to LFH for spawning.  Unknown hatchery origin chinook will be transported from LGR to LFH for holding and spawning after receiving injections of oxytetracycline and erythromycin.  Adults will receive formalin treatments every-other day to control fungus and decrease pre-spawning mortality.  Females that voluntarily return to LFH will be injected with erythromycin and oxytetracycline before the first spawning.   Trapping at LFH and LGR continues throughout the spawning season, generally ending by late November or early December.  Estimated spawning population for 2001 at LFH is 3,000- 5,000 fish.  The NPTH facility is expected to be on line September 1, 2001.  The facility is designed to produce 1.4 million sub-yearlings for the Clearwater system.  The NPTH production is additive to the LSRCP goals and may affect the number of adults transported from LGR.

All recovered CWTs will be read or elastomer tags will be identified to ensure separation of LFH origin and unknown fish.  Fertilized eggs will be water hardened for one hour in 100 ppm iodophore, and incubated in Heath trays.  Projected egg take of BY 2001 LFH Snake River fall chinook is 4-5 million.  Fall chinook carcasses may be hauled and released above LGR (free-flowing reaches of the Snake or Clearwater River) for nutrient enhancement.

IV.	SUMMER STEELHEAD

Lyons Ferry Complex currently uses three stocks of steelhead in the Snake River basin; LFH, Tucannon, and Wallowa, and two stocks in the Walla Walla basin (Touchet and LFH).

Trapping of the LFH stock begins at LFH on July 1 and continues intermittently through November.  Approximately 700 adult steelhead (350 males/350 females) are retained for broodstock.   Pre-spawning mortality, the potential for IHN virus, and the failure of some females to ripen, require a 100% contingency group of females be kept.  Spawning is conducted from January - February at a ratio of 1:1.  Males are not reused, thereby requiring a similar contingency of males for broodstock.  Trapping is conducted over the summer period to collect broodstock and returning CWT test groups.  All LFH origin CWT fish (ADLV and AD+CWT) are retained for broodstock, with AD-only fish making up any shortfall.  All wild and unneeded hatchery origin steelhead (AD only) are returned to the Snake River in fall (after water temperature drops below 65o F) to spawn or contribute to fisheries.  Of the 700 broodstock retained until spawning, we expect to spawn 175 females to provide 915,000 green eggs for the program of 470,000 smolts.  Adults not spawned are returned to the river.  Eggs or fry excess to the program needs that have been found to be clear of IHN virus are either planted in out-of-basin waters or destroyed.

Trapping of Tucannon Stock begins in September at a temporary trap located in the lower Tucannon River.  Currently, the goal is to collect 16 pairs for the broodstock (wild/natural in origin), with all other fish (both wild/natural and hatchery origin) passed upstream for natural spawning.   Some wild fish may also be collected at the Tucannon Adult trap (rkm 59) if broodstock collection in the lower river fails.  The HGMP resolution will determine if all hatchery origin fish, collected at the Tucannon Adult trap, will not be passed upstream, but marked and released downstream to spawn naturally.  The interim smolt production goal for the Tucannon Stock program is 50,000.  Of the 16 pairs selected for broodstock, we expect to spawn 15 females to provide 75,000 green eggs for the program.  Smolts in excess to the interim program smolt goal will be planted into the Tucannon River

Trapping of Wallowa stock begins at Cottonwood trap and the outlet of the acclimation pond in early February.  Because of low egg survival rate and IHN virus, 68 females are needed to provide 340,000 green eggs for the program of 200,000 smolts.  Eggs or fry excess to the program needs are destroyed.

Trapping of Touchet River stock begins in February at the Dayton adult trap.  Currently, the goal is to collect 16 pairs for the broodstock (wild/natural in origin), with all other wild fish passed upstream for natural spawning.  Hatchery fish will be returned to the stream below the trap to spawn naturally or contribute to the local sport fishery.  The interim smolt production goal for the Touchet Stock program is 50,000.  Of the 16 pairs selected for broodstock, we expect to spawn 15 females to provide 75,000 green eggs for the program.  Smolts in excess to the interim program goals will be planted into the Touchet River.

2000 Brood rearing/releases

Release information is provided in Table 7

LFH stock: Fish are AD clipped in August and 510,000 LFH stock placed in a rearing pond at LFH.  Release of 420,000 smolts at 4 fish/lb. is planned.  All other proposed releases correspond to numbers submitted in the LSRCP Section 7 Biological Assessment.  During December fish are transferred from the rearing pond to raceways and in January 60,000 will receive AD/CWT/BRAND for study groups.

In  February 105,000 LFH stock pre-smolts will be transferred to Dayton AF.  Fish will be contained and fed until March 25 when outlet screens will be removed.  Volitional release and feeding will continue through April 20.  After that date feeding will be curtailed and pond levels slowly lowered until the ponds are completely drained on May 1, 2001.  PIT tags to monitor out-migration and for comparison of within-year variation of migration performance between release groups will be inserted before any migration occurs.

Starting April 15, remaining marked and unmarked LFH stock steelhead will be released directly from LFH or hauled to area rivers (Tucannon and Walla Walla rivers) and released (Table 7).  All fish will be released by May 1, 2001.

Wallowa stock: Fish were AD clipped in August and 258,000 Wallowa stock fish placed in one of the rearing ponds at LFH.  In December 50,000 will be removed from the lake and placed in two raceways.  During late January and February, 40,000 fish will receive a CWT/LV/BRAND.  In early February, 210,000 Wallowa stock juveniles will be transferred to Cottonwood AF.  Fish will be contained and fed until March 25 when outlet screens will be removed.  Volitional release and feeding will continue through April 20.  After that date feeding will be curtailed and pond levels slowly lowered until the ponds are completely drained on May 1, 2001.  PIT tags will be inserted before any migration occurs to monitor out-migration, and for comparison of within-year variation of migration performance among release groups.

Tucannon Stock: All Tucannon River stock are reared in standard raceways at LFH.  Fish will be CWT and VI tagged in January 2001.  Approximately, three weeks after tagging all fish will be transferred to TFH into the large acclimation raceway (formerly used for spring chinook holding/acclimation).  Following 6 weeks of acclimation at TFH, fish will be direct stream released into remote areas above the hatchery (Panjab to Beaver/Watson lake), at about 4-6 fish/lb.  PIT tags will be inserted before any releases occur to monitor out-migration, and for comparison of within-year variation of migration performance among release groups.

Touchet Stock: All Touchet River stock are reared in standard raceways at LFH.  Fish will be CWT and VI tagged in January 2001.  Fish will be held at LFH until 15 March-1 April, then direct stream released into the upper basin above the WDFW trap on the Touchet River.  PIT tags to monitor out-migration and for comparison of within-year variation of migration performance between release groups will be inserted before the groups are released.

Table 7.	Proposed 2001 summer steelhead releases for rivers in SE Washington.

| Location | Number of fish | PIT tags | Stock | Release time (type) |
| --- | --- | --- | --- | --- |
| Grande Ronde River (Cottonwood AF) | 200,000 | 350 | WA | March-April |
| Snake River (LFH) | 60,000 | 350 | LFH | April 15-30 |
| Touchet River (Dayton AF) | 100,000 | 350 | LFH | March-April |
| Touchet River | 40,000 | 350 | Touchet | April 1- May 1 |
| Tucannon River a | 135,000 | 350 | LFH | April 15-30 |
| Tucannon River (Above TFH) | 65,000 | 350 | Tucannon | April 15- May 15 |
| Walla Walla River b | 125,000 | 0 | LFH | April 15-30 |

a	Released at Enrich Road (RM 17.4) or Marengo (RM 24.8).

b	Fish will be released between Touchet River and Mill Creek (RM 23-33) Proposed reduction from 175K to address NMFS jeopardy concerns

A.	2001 Brood

1.	Trapping/spawning

LFH Stock:  Expected run size at LFH is 5,000 fish.  Spawning will occur in January-February on a weekly basis.  Due to the IHN virus and based on average fecundity of 5,230 eggs/female, 175 females will be spawned to produce 915,250 green eggs which will yield approximately 645,000 eyed eggs after shocking and  picking.  Any eggs excess to projected program needs will be destroyed.  All carcasses from spawned or un-spawned fish will be buried on site.

Wallowa Stock: Trapping for Wallowa broodstock will occur at Cottonwood AF starting early February 2001.  Expected run size to the trap is 250-400 adult hatchery steelhead.  Because of potential low egg survival rate and/or IHN virus which have been experienced in the past, 70 females are needed to provide 348,000 green eggs for the program of 200,000 smolts. No wild steelhead are retained for spawning, but passed upstream to spawn naturally.  Fish not utilized for spawning or distribution for food, will be killed and the carcasses returned to Cottonwood Creek and the Grande Ronde River for nutrient enhancement.  Adult trapping will continue through mid May.

Spawning occurs in late March and April on a weekly basis.  All fish are spawned on site at a 1:1 ratio of males to females and the gametes transported to LFH for fertilization incubation, and rearing.  Eggs excess to projected program needs will be destroyed.

Test trapping, in Rattlesnake Creek, for endemic populations commenced in the year 2000.

Touchet Stock: Trapping of Touchet River stock begins in February at the Dayton adult trap.  Currently, the goal is to collect 16 pairs for the broodstock (wild/natural in origin), with all other wild fish passed upstream for natural spawning.  Hatchery fish will be returned to the stream below the trap to spawn naturally or contribute to the local sport fishery.  The interim smolt production goal for the Touchet Stock program is 50,000.  Of the 16 pairs selected for broodstock, we expect to spawn 15 females to provide 75,000 green eggs for the program.  Smolts in excess to the interim program smolt goals will be planted into the Touchet River.

Tucannon Stock: Trapping of Tucannon Stock begins in September at a temporary trap located in the lower Tucannon River.  Currently, the goal is to collect 16 pairs for the broodstock (wild/natural in origin), with all other fish (both wild/natural and hatchery origin) passed upstream for natural spawning.   Some wild fish may also be collected at the Tucannon Adult trap (rkm 59) if broodstock collection in the lower river fails.  All hatchery origin fish collected at the Tucannon Adult trap will not be passed upstream of the trap, but marked and released downstream to spawn naturally.  The interim smolt production goal for the Tucannon Stock program is 50,000.  Of the 16 pairs selected for broodstock, we expect to spawn 15 females to provide 75,000 green eggs for the program.  Smolts in excess to the interim program smolt goal will be planted into the Tucannon River

2.	Rearing/releases

LFH Stock: approximately 645,000 eyed eggs will produce 465,000 fry that will provide 420,000 smolts for release.  Each female’s eggs are held in individual colanders to the eyed stage to allow time for IHNV checks to be completed.  Eggs from females that have high levels of virus particles in ovarian fluid are discarded.  Upon agreement of the Pathologist and Complex Manager, eggs from females that had low or medium levels of virus may be retained for rearing.  Eventually, eyed eggs are placed in hatching baskets in shallow troughs.  Decisions made in the HGMP process may affect production numbers.

Alevins are reared in small troughs until 900 fish/lb, when they are transferred to intermediate inside troughs.  At 500 fish/lb. fish are moved to outside raceways where they rear until being AD clipped and placed in rearing ponds at 60 fish/lb. in August.  Fish are then either transferred to acclimation facilities in February, or reared on-station until release in April.  Fish will be 4 fish/lb. at release.

Wallowa Stock: approximately 348,000 green eggs will assure production of  200,000 smolts for release.  Rearing strategy is identical to that followed for LFH stock.  All Wallowa stock will be released from Cottonwood AF March through April.

Tucannon and Touchet Broodstocks: Groups of Tucannon and Touchet river origin juveniles will be reared at LFH or Tucannon hatcheries in raceways/ponds.  All fish will be uniquely tagged with CWT’s and VI tags prior to release, but will not be AD clipped.  Fish will be acclimated and/or direct stream released during April 2002, at a size of 4-6 fish/lb in their respective rivers.  Limited aspects of NATURES rearing techniques may be adopted for each group.

B.	2002 Brood

1.	Trapping/spawning

LFH Stock:  Trapping begins at LFH on July 1 and continues intermittently through November.  Broodstock needs will be dependant on decisions made by NMFS through the HGMP/Biological Opinion process.  See HGMP.

Tucannon Stock:  Trapping of Tucannon Stock commences in September and will continue through March 2002 at a temporary trap located in the lower Tucannon River.

Broodstock needs will be dependant on decisions made by NMFS through the HGMP/Biological Opinion process.  See HGMP.

V.	Resident Fish

Rainbow trout are reared to fulfill the resident fishing opportunity mitigation under LSRCP.  Eggs are obtained from WDFW’s Spokane Hatchery and from Idaho’s Hayspur Hatchery (Kamloops stock).  The production of 237,500 yearling and 150,000 sub-yearling Spokane Stock rainbow, and 50,000 fingerling Kamloops rainbow requires 545,000 eyed Spokane stock rainbow trout eggs and 62,000 eyed Kamloops stock eggs.  Kamloops trout are provided by IDFG to meet part of their mitigation requirement within Idaho.  They prefer to use Kamloops for certain releases because of a survival advantage over the Spokane stock.  A small State funded program at Lyons Ferry Complex utilizes Spokane stock rainbow reared to 1½ lbs each to provide a unique fishing opportunity in local lakes.

A.	1999 Brood

1.	LFH

A release of 100,000 yearling Spokane stock rainbow at 2.5 fish/lb is planned.  Yearling fish are being reared in raceways and will be planted into numerous waters of SE Washington in February and March 2001, in numbers similar to 2000 (Attachment 5).

Sub-yearling (BY 99) Kamloops (50,600) are being reared in raceways and will be provided to Idaho in early October at 15 fish/lb.

2.	TFH

LSRCP Program

A release of 137,500 yearling Spokane stock fish at 3.5 fish/lb. is planned for 2001.  Fish are currently in a semi-natural rearing pond and two round ponds, where they will remain until release into waters in SE Washington in March - October in numbers similar to 2000 (Attachment 5).

WDFW Program

A state program will rear 4,000 rainbow trout to 1.5 lbs/fish for release in SE Washington lakes in April - May, 2001.

B.  2000 Brood

1.	LFH

Receive 325,000 eggs from Spokane Complex during January.  Eggs placed in hatching jars, fry emerge into intermediate rearing tanks and are transferred to outside raceways in March at 200 fish/lb.  A planned 150,000 fingerling at 50 fish/lb will be transferred to IDFG in May, 2001.  Remaining fish will be reared in outside raceways until February/March, 2002 when 100,000 fish at 2.5 fish/lb are to be planted in SE Washington waters.

Receive 56,000 Kamloops fry (45 fish/lb) from TFH during August.  Rear and right ventral (RV) fin clip fingerling for transfer to IDFG in October 2001 at 15 fish/lb.

2.	TFH

LSRCP Program

Receive 220,000 eggs from Spokane Complex during December.  Eggs placed in hatching baskets to hatch.  Fry transferred from starter troughs to outside raceways in April at 400 fish/lb.  Fish are reared in outside raceways until August, 2001 when 150,000 fish will be transferred to the rearing pond.  A planned 137,500 fish at 3.5 fish/lb. are to be planted in SE Washington waters, March-May, 2002.

Receive 62,000 eyed Kamloops eggs from Idaho’s Hayspur Hatchery during January 2001.  Hatch and rear fry to 50 fish/lb.  Transfer 55,000 fish to LFH in August 2001.

WDFW Program

Rear 4,000 Spokane stock to 1.5 lbs/fish for release into waters in SE Washington April-May 2002.

VI.  Hatchery Monitoring and Evaluation

A detailed monitoring and evaluation (M&E) proposal (Attachment 6) for the LFC is developed and submitted annually to the LSRCP office for funding.  All aspects of ongoing or proposed M&E are discussed in detail in that document.

VII.  Fish Pathology and Fish Health Monitoring.

A.	Co-Managers Salmonid Disease Control Policy and Integrated Hatchery Operations Team (IHOT)

All fish production at Lyons Ferry Hatchery is conducted according to the Co-Managers Salmonid Disease Control Policy and Integrated Hatchery Operations Team (IHOT) fish health policy.

Specially, all lots of fish are monitored for fish health, all broodstock are annually inspected, strict hatchery sanitation procedures and fish culture practices (rearing criteria) are followed, and egg and fish transfer and release requirements are met. In addition, bacterial kidney disease management strategies for chinook salmon stocks and infectious hematopoietic necrosis management strategies for steelhead stocks are employed.

B.	Fish Disease Outbreaks

The fish health specialist will respond to all fish disease outbreaks at the request of the fish hatchery staff.

C.	Monthly Monitoring

The fish health specialist will visit Lyons Ferry and Tucannon hatcheries at least once a month. Mortality records and fish in all rearing containers will be inspected.  Approximately 12-15 fish of each species will be killed and examined at the discretion of the fish health specialist.

D.	Annual Broodstock Viral Inspections

At spawning, all broodstock will be annually tested for viral pathogens.  All spawned female fish will have ovarian fluid sampled and tested.  Additionally, 60 fish will have kidney/spleen samples taken and sampled for viral pathogens.

E.	Specific Fish Health Management

1. Bacterial Kidney Disease (BKD) Management

a.	All female chinook broodstock will receive a pre-spawning injection with erythromycin and oxytetracycline.

b.	All female chinook broodstock will be tested for BKD via ELISA (enzyme linked immuno-sorption assay).

c.	Juvenile chinook may be reared separately based on the BKD-ELISA results.

d.	All juvenile chinook will be reared at a density index of less then 0.18 lbs\ft 3\in.

e.	Prophylactic feeding of erythromycin may be employed.

2. Infectious Hematopoietic Necrosis (IHN) Management

a.	All female steelhead broodstock will be tested for IHN virus via cell culture and the IHN virus levels in the ovarian fluid will be determined.

b.	Eggs from females with high levels of IHN virus (>103) will be destroyed. Eggs from negative and low IHN virus (101 to 103) females will be reared separately.

c.	If IHN outbreaks occur, fish from the affected rearing container will be promptly isolated and destroyed.

3. Broodstock and Egg Fungus Management

a.	Broodstock - All chinook broodstock will be treated with formalin every other day to control fungus. As needed , steelhead broodstock may be treated with formalin.

b.	Eggs - All eggs will be treated with formalin daily to control fungus.

# ATTACHMENT 2

WASHINGTON DEPARTMENT OF FISH AND WILDLIFE

600 CAPITOL WAY NORTH

OLYMPIA WASHINGTON  98501-1091

LOWER SNAKE RIVER COMPENSATION PLAN

HATCHERY EVALUATION PROGRAM

FISCAL YEAR 2002 PROJECT PROPOSAL

Study Period:  1 April 2002 to 31 March 2003

Fish Program - Science Division

Snake River Laboratory

401 South Cottonwood

Dayton, Washington  99328

INTRODUCTION

Congress authorized the Lower Snake River Fish and Wildlife Compensation Plan (LSRCP) in 1976.  As a result of that Plan, Lyons Ferry Complex (LFC), which includes Lyons Ferry Hatchery (LFH), Tucannon Hatchery (TFH), and several satellite acclimation facilities, were designed and constructed.  All of those facilities are currently under operation.  The objectives of the LSRCP program in Washington are to compensate for the loss of 18,300 adult fall chinook salmon, Snake River stock, 1,152 adult spring chinook salmon, Tucannon River stock, 4,656 adult steelhead of various origins in southeast Washington and 67,500 angler days of lost resident fish recreational opportunity.

Integral with the compensation production facilities has been an evaluation program.  An important purpose of the program has been, and continues to be, the ongoing investigation of whether production as outlined in the LSRCP program is meeting mitigation goals and to make recommendations based on the best available science for improving the program.  Recently however, proposed recovery plans for Endangered Species Act (ESA) listed species have increasingly directed LSRCP actions.  Faced with these changes, evaluation programs and staff have provided an important link between the state management agency, and the federal management and funding agencies that ensures a consistency between ESA/LSRCP goals and state management principles and guidelines.

Evaluation activities are directed by four sets of guidelines: 1) evaluation guidelines as written by the U.S. Fish and Wildlife Service; 2) specific yearly objectives and activities contained herein; 3) fish management policies of the Washington Department of Fish and Wildlife (WDFW) and most recently, 4), by the constraints associated with species listed under the ESA.  Many of the proposed actions assume that some form of mitigation production will occur.

This evaluation proposal includes a detailed proposal of work and budget (Attachment A) for spring and fall chinook and steelhead studies. Objectives for the year are:

1)	Monitor and evaluate the quality and release of hatchery spring and fall chinook salmon and summer steelhead produced from LFC.

2)	Evaluate hatchery release strategies from all release sites (downstream survival rates).

3)	Estimate the degree of residualism of endemic origin juvenile steelhead in the Tucannon and Touchet rivers.

4)	Determine natural production and estimate freshwater survival rates for spring chinook and summer steelhead in Southeast Washington streams.  Compare natural survival rates to hatchery survival rates for spring chinook and summer steelhead.

5)	Assess and quantify the juvenile out-migration of natural and hatchery-origin spring and fall chinook salmon, and summer steelhead from the Tucannon River.

6)	Conduct, monitor, and evaluate adult trapping/collection of spring chinook and summer steelhead for broodstock.

7)	Estimate adult returns and return rates, collect life history and genetic characteristics, and document distribution of adult spring and fall chinook salmon, and summer steelhead to southeast Washington streams and facilities.

8)	Maintain phenotypic and genotypic characteristics of salmon and steelhead stocks used at Lyons Ferry Complex.

9)	Where appropriate, cryogenically archive salmon and steelhead semen for future use.

10)	Assess LSRCP hatchery evaluation actions to determine potential effects on species listed under the Endangered Species Act.  Represent WDFW during formal ESA consultation between NMFS and the FWS.  Coordinate and integrate Washington's anadromous fish management and research with the Section 7 LSRCP Biological Assessment, subsequent Biological Opinions and Management Plans, NMFS' Recovery Plan, and develop and submit Hatchery and Genetic Management Plans (HGMPs) for stocks produced at LFC.

11)	Complete annual reports to summarize results of all LSRCP funded work conducted during the contract period (1 April 2002 to 31 March 2003).

SECTION 1:  STUDY PLAN

WDFW shall furnish all supervision, labor, services, materials, tools, and equipment necessary to conduct an evaluation of LSRCP hatchery operations and related fishery management programs at LFC to fulfill the objectives as follows:

Objective 1.  Monitor and evaluate the quality and release of hatchery spring and fall chinook salmon and summer steelhead produced from LFC.  WDFW will evaluate hatchery marking, and releases of juvenile salmon and steelhead to determine survival rates between various life stages and examine potential variables that may influence observed adult survival estimates.

Task 1.1.  Evaluate mark/tag quality and retention [adipose/ventral fin clip, Coded-Wire tag (CWT), freeze brand, and Visual Implant elastomer tag (VI)] before release.

Task 1.2.  Document and report release size, general condition, degree of smoltification, sexual precocity, and blood hematocrit levels (fall chinook only) prior to release.

Task 1.3.  Summarize hatchery records for each brood year to document and report egg-to-fry, fry-to-smolt, and egg-to-smolt survival rates at LFC.

Objective 2.  Evaluate hatchery releases strategies from all release sites (downstream survival rates).

Approach:  Spring chinook: WDFW annually plans for a release of 132,000 yearling spring chinook into the Tucannon River.  The 2002 release (120,000) is slightly below program goals and limited evaluation will be conducted.  All fish will be marked (VI/CWT and no adipose clip), and planted in Curl Lake in February 2002.  Acclimating fish in Curl Lake was initiated primarily for the following reasons: 1) to increase survival of fish planted upstream of the hatchery, and 2) to increase adult salmon spawning distribution in the upper sections (Wilderness and HMA) of the Tucannon River.  WDFW will evaluate the effect of the acclimated release on subsequent adult spawning distributions in the Tucannon River (see Sub-objective 7.1), provided runs are large enough that fish are passed upstream of the TFH adult trap. For the 2003 release, 132,000 fish are expected to be released.  All fish will be marked (VI/CWT) and volitionally released from Curl Lake in March and April, 2003.  In 2002 and 2003, migration behavior will be monitored and PIT tagging will be conducted at the smolt trap located at Rk 3 to monitor the downstream migrants success.

Based on the size of the 2000 adult return and agreement among the co-managers, a portion (up to 50,000) of the 2002 release will be used for an exercise experiment at TFH.  The exercise experiment will be used to evaluate moderate exercising of the fish to improve their downstream survival rate, and would complement an experiment conducted in 1998.  The exercise experiment will likely be conducted in 2003 as well.

Also in 2002, the release and evaluation of captive broodstock origin spring chinook smolts will begin.  These actions (funded directly by BPA) will be closely coordinated with the production/supplementation releases and evaluation.  Comparison of absolute and relative performance of captive brood origin smolts to natural origin and normal hatchery production smolts will be important.  Captive brood progeny will be marked with a blank wire tag (BWT) in the snout, allowing them to be differentiated from supplementation fish when they return as adults.

Sub-objective 2.1:  Evaluate spring chinook release, release site, smolt out-migration timing, exercise experiment, and relative juvenile survivals from the Tucannon River.

Task 2.1.1.  Document 2002 out-migration from Curl Lake (see Task 5.1).

Task 2.1.2.  Repeat an exercise experiment that was conducted in 1997/1998 for a portion (up to 50,000) of the supplementation fish.  Document juvenile survival and tag uniquely to monitor their survival from release to adult return (SAR).  Compare results of survivals between exercised and un-exercised fish (in the future).

Task 2.1.3.  Recommend marks (VI/CWT and no adipose fin clip) for all 2001 brood year fish for determination of survival, ocean distribution, fishery contribution, and adult returns (exercise experimental group will need unique marks/tag).

Task 2.1.4.  From November 2001 through February 2002, use two forty-foot circular rearing ponds at TFH to exercise up to 50,000 spring chinook.  Water velocity within the circular rearing ponds will be approximately one body length/second (BL/S).  The remaining fish will be reared in a standard rearing raceway with water velocity of approximately 0.2 BL/S.

Task 2.1.5.  Coordinate releases and evaluation of production spring chinook with captive brood origin smolt releases.  Compare performance.

Task 2.1.6.  PIT tag study groups of hatchery reared and naturally produced spring chinook. Compare and report their relative migration survival to downstream collector dams.

Approach: Fall Chinook: WDFW’s current program goal is to annually release 900,000 yearling, and up to 2.4 million subyearling, fall chinook into the Snake River Basin.  For 2002, about 450,000 yearlings will be released at LFH, and about 450,000 yearlings will be released upstream of Lower Granite Dam (LGD) at three acclimation facilities (Big Canyon, Capt. John, and Pittsburg Landing).  In addition, approximately 2.0 million subyearlings (2001 brood year) will be released either on station or above Lower Granite Dam.  Exact number of subyearlings are not available at this time.  All yearling releases are 100% marked (AD/CWT/VI).  Only portions of the subyearling releases will be marked (AD/CWT or CWT-only).  Specific details of the monitoring and evaluation of LFH origin fall chinook that are released upstream of LGD, are included in an interagency/tribal cooperative project description.

For 2003, approximately 450,000 yearling fall chinook will be released from LFH, and approximately 450,000 yearlings will be released from the three acclimation sites (Capt. John, Pittsburg Landing, and Big Canyon).  The number of subyearling to be released and locations are unknown at this time, and will depend on 2001 broodstock abundance.

Along with the standard external marks, portions of each release group (at LFH or upstream of LGD) will receive PIT tags.  For 2002 releases, WDFW will PIT tag 1,000 yearlings at LFH and provide assistance to Nez Perce Tribe (NPT) by helping tag 7,500 yearlings at Pittsburg Landing and Capt. John acclimation facilities.  NPT will PIT tag 7,500 yearlings from the two remaining acclimation facilities.  Single releases of subyearling fall chinook will occur from Big Canyon, Capt. John and Pittsburg Landing acclimation facilities.   NPT staff will PIT tag representative groups from each release from above LGD, and WDFW will tag (1,500) the group released from LFH.  PIT tagged fish will enable WDFW and NPT to jointly compare migration timing and relative survivals among release locations.

Sub-objective 2.2:  Evaluate fall chinook release strategies, release sites, smolt out-migration timing and relative survivals from LFH releases and upstream acclimation sites above LGD to downstream collection sites.

Task 2.2.1.  Recommend marks (Ad/CWT/VI) for all yearlings for release at LFH and upstream acclimation sites above LGD.  Recommend marks (AD/CWT) for a portion of sub-yearlings for release at LFH (200,000).  Each release group will receive a unique CWT code.

Task 2.2.2.  Continue to coordinate and participate in cooperative study plans with the USFWS Fisheries Resource Office, National Marine Fisheries Service, Idaho Power, Idaho Department of Fish and Game, and the NPT for evaluating off-station releases in 2002/2003.

Task 2.2.3.  PIT tag yearlings and subyearlings at LFH before release.  Document migration timing and relative survivals.

Approach: Summer Steelhead: WDFW’s current program goal is to annually release 720,000  yearling smolts into the Tucannon, Touchet, Walla Walla, Grande Ronde, and Snake rivers from LFH.  Up to 420,000 LFH stock and 200,000 Wallowa stock steelhead will be released with a size goal of 4 fish per pound.  Up to 200,000 fish will be tagged (CWT) and freeze branded, or VI tagged (see attached tagging table) in combination with the standard ad-clip production mark. In addition to the standard production of LFH or Wallowa stock, WDFW will release about 50,000  endemic brood smolts into the Tucannon River, and 50,000 endemic brood smolts into the Touchet River.  For all stocks released (LFH, Wallowa, and Endemic) coded-wire tag groups will be used to identify distinct type of release groups and external freeze brands, PIT tags, and VI elastomer tags will be used to monitor out-migration timing and relative success rates.  Monitoring and evaluation of the out-migration and smolt-to-adult survival of endemic broodstock origin juveniles will rely on CWT, PIT and visible implant elastomer tags (VI) to minimize any negative effects or harvest associated with fin clips.

Sub-objective 2.3: Evaluate summer steelhead (LFH, Wallowa, and Endemic stock) release strategies, release sites, smolt out-migration timing and relative survivals from LFC releases, upstream acclimation sites above LGD to downstream collection sites.

Task 2.3.1.  Recommend marks (AD, ADLV\CWT\freeze brand, CWT+VI) for a portion of the steelhead reared at LFC to determine survival, ocean distribution, contribution to various fisheries, and returns to the LSRCP area.  Unique CWT tag codes and elastomers will be used to indicate release location.

Task 2.3.2.  Implant PIT tags in a sample of fish from each release site (before release) for identification at collection facilities at lower Snake and Columbia river dams.

Task 2.3.3.  Monitor migration timing, migration rates and relative recapture rates of PIT tagged and freeze branded fish at juvenile collection facilities at lower Snake and Columbia river collector dams.

Task 2.3.4.  Compare relative survival estimates between release groups.

Objective 3.  Estimate the degree of residualism of endemic origin juvenile steelhead in the Tucannon and Touchet rivers.

Approach:  WDFW will utilize electrofishing surveys (objective 4) on the Touchet River to document the degree of residualism from endemic brood releases within the Touchet River.  Surveys will provide only a minimum estimate of residualism.  WDFW will utilize electrofishing surveys (objective 4), and smolt trapping (objective 5) on the Tucannon River to estimate the number of residual endemic brood fish in the Tucannon River.

Task 3.1: Supplement traditional electrofishing surveys in the Touchet River (mainly the mainstem Touchet from South Fork confluence downstream) to document and provide densities and an estimated population of endemic brood summer steelhead that residualized after release.

Task 3.2: Collect, record and estimate the number of endemic brood hatchery steelhead releases that are captured in the Tucannon River smolt trap.

Task 3.3: Compile all records of endemic brood hatchery steelhead that are captured in electrofishing surveys in the Tucannon River.  Calculate a mid-summer population.

Task 3.4: Use smolt trap and electrofishing data to estimate a minimum percent residualism for the Tucannon endemic brood release.

Objective 4.  Determine natural production and estimate freshwater survival rates for spring chinook and summer steelhead in southeast Washington streams.  Compare natural survival rates to hatchery survival rates for spring chinook and summer steelhead.

Approach:  Natural and hatchery origin adult spring chinook salmon and summer steelhead from Washington's LSRCP program are known to utilize overlapping spawning areas.  It is currently unknown to what extent natural and hatchery origin fish interbreed, and what effect that interbreeding may have on natural production.   While the spring chinook program was developed from endemic fish, the steelhead program was not.   Index areas of the Touchet and Tucannon rivers and Asotin Creek will be sampled for juvenile chinook and steelhead.  Distribution, abundance and survival of naturally produced juveniles will be tracked over time as returns of natural and hatchery origin adults change.  Survival information is collected through estimated egg deposition from redd counts, parr production estimates from snorkel and electrofishing surveys, and smolt trapping.  In addition, stream temperatures throughout salmonid spawning and rearing areas will be monitored and compared to juvenile densities and distribution.

Sub-objective 4.1: Estimate egg-to-fry-to-smolt survival rates for naturally produced spring chinook in the Tucannon River.

Task 4.1.1.  Estimate egg deposition in the Tucannon River based on redd counts and fecundity estimates from the supplementation program.

Task 4.1.2.  Determine parr densities and a population in the Tucannon River through snorkel surveys at index sites.

Task 4.1.3.  Estimate the number of natural smolts emigrating from the Tucannon River using a smolt trap (see objective 5).

Task 4.1.4.  Compare egg-to-fry and fry-to-smolt survival rates between naturally produced spring chinook from the Tucannon River, and the hatchery program.

Sub-objective 4.2:  Estimate egg-to-fry survival rates for naturally produced summer steelhead in the Tucannon and Touchet rivers, and Asotin Creek.

Task 4.2.1.  Estimate egg deposition in the Tucannon and Touchet rivers, and Asotin Creek based on redd counts, and fecundity estimates from endemic broodstock.

Task 4.2.2.  At index sites, conduct electrofishing or snorkel surveys to calculate population sizes and densities of 0 and >0 age classes of natural steelhead juveniles.

Task 4.2.3.  Compare juvenile densities, populations sizes and spawning escapement with previous information in these areas.

Sub-objective 4.3: Document stream temperatures in the Tucannon River, and Asotin Creek.  Compare temperature data to juvenile salmonid densities and distribution.

Task 4.3.1.  Monitor stream temperatures at several locations Tucannon River and Asotin Creek using continuous data recorders.

Objective 5.  Assess and quantify the juvenile out-migration of natural and hatchery-origin  spring and fall chinook salmon, and summer steelhead from the Tucannon River.

Approach:  WDFW operates a juvenile migrant trap in the lower Tucannon River.  Information about naturally produced spring and fall chinook salmon, and summer steelhead migrants obtained from this trap includes: 1) smolt out-migration timing, 2) duration, 3) magnitude, and 4) smolt quality and ages.  WDFW uses data from the trap to determine smolt yield, and to determine fry-to-smolt and smolt-to-adult (SAR) survival rates for naturally produced salmon and steelhead. The data will be also form the basis to compare relative survivals of endemic stock hatchery reared steelhead with naturally reared steelhead.

Task 5.1.  Operate a juvenile migrant trap on the Tucannon River to collect downstream migrating spring and fall chinook, and summer steelhead.

Task 5.2.  Collect length, weight, and scale samples on all naturally produced salmonids.  Use scales to determine ages of different smolts for brood year estimates, and species origin.

Task 5.3.  Estimate trap efficiency using partial fin clips.  Use efficiency tests to calculate smolt population estimates for spring and fall chinook and summer steelhead migrating from the Tucannon River.

Task 5.4.  Determine duration and peak migration of all smolts.

Task 5.5.  Document smolt health through such indices as condition factor, fin condition, and descaling.

Task 5.6.  When migrant numbers are large enough, PIT tag a sample of natural and hatchery produced spring and fall chinook salmon, and summer steelhead at the Tucannon River smolt trap. Compare PIT tagged detection rates (relative survival) between natural and hatchery fish at downstream detection facilities.

Objective 6.  Conduct, monitor, and evaluate adult trapping/collection of spring chinook and summer steelhead for broodstock.

Approach:  WDFW evaluation staff will continue to conduct or monitor broodstock collection of spring chinook at the TFH adult trap and steelhead trapping on the Touchet and Tucannon rivers during endemic broodstock development.  In addition, radio tracking and/or radio tagging may be conducted unilaterally or in coordination with other agencies to provide information about run timing, movements, holding and spawning areas, and behavior near traps/obstructions.

WDFW will work cooperatively with other agencies where appropriate (e.g. ODFW and CTUIR) to assess the success of locally adapted broodstocks being developed for the Touchet and Tucannon Rivers.  WDFW believes that broodstocks developed from river-specific natural adults (chinook or steelhead) may have behavioral characteristics that allow them to be more successful at returning to point of release.  Where an endemic origin broodstock is used, it may also decrease the potentially negative effects of hatchery fish on the gene pool of natural fish.  Adult traps are currently operated on the Tucannon and Touchet rivers to collect broodstock.  WDFW will continue to evaluate the effectiveness of these traps and their location for use in broodstock development.

In 2001 a temporary trap was operated on Menatchee Creek, a tributary to the Grande Ronde River.  Trapping will continue during spring of 2002 and maybe 2003 on Menatchee Creek.  Genetics samples will be collected (DNA fin clips) and population status and make up (% hatchery strays) documented.  This work is part of a multi-agency assessment of the status of steelhead populations in the Lower Grande Ronde River, which might contribute to the development of a local broodstock to replace the current Wallowa Stock being used in the LSRCP program.

Sub-objective 6.1: Monitor and evaluate adult trapping/collection of spring chinook on the Tucannon River for broodstock.

Task 6.1.1.  Summarize all external injuries on fish captured at the trap (e.g. head burns) for continued evaluation of passage problems at the trap or that may have resulted from problems in the mainstem Columbia or Snake Rivers.

Task 6.1.2.  Monitor numbers of adults holding upstream or downstream of the adult trap through periodic snorkel or carcass recovery surveys.

Task 6.1.3.  Track radio tagged adults from the lower Columbia River that enter the Tucannon River.  Use a fixed site receiver and mobile tracking to determine movements, run timing, and behavior near the adult trap in the Tucannon River.

Sub-objective 6.2: Operate temporary adult steelhead traps on tributary rivers.

Task 6.2.1.  Evaluate the effectiveness of the existing TFH, Touchet River, lower Tucannon River, Cottonwood Creek, and Menatchee Creek adult traps for collecting naturally produced steelhead.

Task 6.2.2.  Recommend modifications to improve the effectiveness of each trap.

Task 6.2.3.  Collect endemic origin naturally reared steelhead for broodstock where appropriate.

Task 6.2.4.  Record the origin of all fish captured in steelhead traps, document mortalities, and collect biological samples on natural origin steelhead for stock profile.

Objective 7.  Estimate adult returns and return rates, collect life history and genetic characteristics, and document distribution of adult fall and spring chinook and summer steelhead to southeast Washington streams and facilities.

Approach:  Adult returns are the goal of the LSRCP program, therefore measuring adult returns to the point of release and to other intermediate areas is necessary to determine program success.  Downriver and within-area harvest of adults occurs primarily on fall chinook and steelhead, with limited or no harvest of spring chinook.  Catch record cards and CWT expansions can be used to estimate the number that would have returned to the project area.

WDFW monitors the returns of spring and fall chinook and summer steelhead throughout southeast Washington through adult trapping (Tucannon River, LFH, and LGD, Touchet River, Cottonwood Creek), and spawning ground and creel surveys; all of which provide CWT recoveries of marked fish for evaluation purposes.  Trapped and/or spawned broodstock fish and carcasses provide data concerning origin, stray rates, sex ratios, age composition, and mean fecundity of each year’s run.  Spawning surveys provide numbers of redds, spawn timing and distribution of fish in each of the rivers WDFW surveys.  Sampled carcasses also provide the genetic (electrophoretic or DNA) data to define stock characteristics, monitor possible introgression of hatchery stock genes into these populations, and evaluate our success at maintaining stock integrity.

Sub-objective 7.1:  Estimate adult returns and return rates, collect life history and genetic characteristics, and document distribution of adult spring chinook to the Tucannon River and Asotin Creek..

Task 7.1.1.  Summarize adult trap and broodstock records for spring chinook.

Task 7.1.2.  Conduct spawning ground surveys to count numbers of redds, determine distribution of spawners, and collect carcasses to document life history characteristics of spring chinook in the Tucannon River and Asotin Creek.

Task 7.1.3.  Utilize trap and redd counts to estimate adult escapement into the Tucannon River.

Task 7.1.4.  Sample adult spring chinook at LFH or in the Tucannon River for length, age, sex, fecundity, scales, and genetic (electrophoretic and/or DNA) data.

Task 7.1.5.  Process scales and CWT’s for age composition.

Task 7.1.6.  Obtain estimates of down river harvest of Tucannon River spring chinook from the PSMFC coded-wire tag database.

Task 7.1.7. Utilize age composition data and adult escapement estimates to calculate smolt-to-adult and parent-to-progeny survival rates on hatchery and naturally produced spring chinook.

Sub-objective 7.2:  Estimate adult returns and return rates, collect life history and genetic characteristics, and document distribution of adult fall chinook to southeast Washington streams and facilities.

Task 7.2.1.  Document the magnitude, return distribution, run timing, peak spawning, fish size, age, sex, and genetic information of the fall chinook returning to LFH.   Document the same information for fish hauled from Lower Granite Dam (LGD) to LFH for spawning.

Task 7.2.2.  Recover and process CWTs (Objective 8) from hatchery fall chinook returning to LFH and hauled from LGD.

Task 7.2.3.  Obtain estimates of down-river harvest of LFH origin fall chinook.

Task 7.2.4.  Conduct fall chinook spawning ground surveys in the Tucannon River, and recover carcasses for age, origin, and genetic samples.

Task 7.2.5.  Participate with USFWS and NPT in a cooperative radio telemetry study of fall chinook returning from hatchery releases upstream of LGD.

Task 7.2.6.  Utilize age composition data and adult escapement estimates to calculate smolt-to-adult survival rates on hatchery fall chinook from LFH.

Sub-objective 7.3:  Estimate adult returns and return rates, collect life history and genetic characteristics, and document distribution of adult summer steelhead to southeast Washington streams and to LSRCP facilities.

Task 7.3.1.  Document hatchery returns to LFH, the traps on the Tucannon and Touchet rivers, Cottonwood Creek, Menatchee Creek and LGD.

Task 7.3.2.  Conduct spawning ground surveys to count numbers of redds, determine distribution of spawners, and collect carcasses (where possible) to document life history characteristics of summer steelhead in the Tucannon and Touchet rivers, Asotin Creek, and some tributaries of the Grande Ronde River in Washington State.

Task 7.3.3.  Estimate spawning escapement of LFH origin steelhead in LSRCP rivers.

Task 7.3.4.  Sample adults (natural and hatchery origin) at LFH, in the Tucannon and Touchet rivers, Asotin Creek, and tributaries to the Grande Ronde for length, age, sex, fecundity, and genetic (electrophoretic and/or DNA) data.

Task 7.3.5.  Process recovered CWTs (Objective 8), and scales for age composition.

Task 7.3.6.  Conduct creel surveys on the Snake, Touchet, Walla Walla, Tucannon, and Grande Ronde rivers to collect information on harvested untagged and CWT tagged LFH origin adult steelhead.

Task 7.3.7.  Use WDFW catch record card estimates and samples of adult CWT codes collected during creel surveys and redd counts to estimate the return and sport harvest of all groups of released LFH origin steelhead within the LSRCP area of Washington.  Obtain commercial and sport harvest estimates of LFH origin adult steelhead.

Task 7.3.8.  Calculate the number of LFH origin steelhead that were present in the sport catch on each river within the LSRCP area for which creel survey results and/or adult trapping data are available.

Task 7.3.9.  Utilize age composition data, adult escapement estimates, and creel data to calculate smolt-to-adult survival rates on hatchery steelhead produced from LFC.

Task 7.3.10.  Assess the nature and extent of straying of LFH origin steelhead within the Snake River basin and provide recommendations to minimize straying.

Objective 8.  Maintain phenotypic and genotypic characteristics of salmon and steelhead stocks used at LFC.

Approach:  WDFW currently identifies and removes stray hatchery fish from spring and fall chinook broodstock at the hatchery before spawning.  WDFW uses two strategies to accomplish this action: 1) CWT reading during spawning to identify known Tucannon River spring chinook stock and LFH fall chinook stock from known or unknown origin fish, and 2) marking hatchery progeny of known LFH fall chinook with external marks to allow identification upon return.  Similar actions will be followed to maintain the genetic integrity of local endemic steelhead broodstocks being developed.

Task 8.1.  For all AD clipped adult salmon, determine origin by identifying VI tag, or by extracting and reading CWT before spawning fish.

Task 8.2.  For all non-AD clipped adult salmon, examine fish for marks (i.e. ventral fin clip) and collect scales (spring chinook only) to determine hatchery or natural origin after spawning.

Task 8.3.  For all steelhead, examine fish for marks (i.e. Ad or ventral fin clip, or VI) and scan with a hand held or tunnel type tag detector.   Collect scales from natural origin fish to document the life history pattern of each stock.

Objective 9.  Cryogenically archive salmon and steelhead semen for future use.  WDFW has investigated the use of cryopreserved semen in an effort to improve techniques and increase management options for use in standard hatchery production at LFH.  Cryopreservation can be valuable to WDFW for the maintenance of genetic stock integrity as well as a means to potentially increase effective breeding size in the hatchery, and aid in ESA recovery, if used judiciously.

Task 9.1. Cryopreserve semen from Tucannon River spring chinook (natural origin) and steelhead (where sufficient local broodstocks are available) to potentially increase effective population size in succeeding years.

Objective 10.  Assess LSRCP hatchery evaluation actions to determine potential effects on species listed under the Endangered Species Act; represent WDFW during formal ESA consultation between NMFS and the USFWS;  coordinate and integrate Washington's anadromous fish management and research with the Section 7 LSRCP Biological Assessment, subsequent Biological Opinions and Management Plans, NMFS' Recovery Plan, and develop and submit Hatchery and Genetic Management Plans (HGMPs) for stocks produced at LFC.

Approach:  Operation of the LSRCP program in Washington requires close cooperation between WDFW and USFWS personnel to ensure that production and evaluation actions conform to guidelines established by NMFS under ESA.  Moreover, it is the responsibility of evaluation staff to integrate production and evaluation research with existing state management goals and principles.  These actions are expressed in the completion of Sections 7 and 10 Biological Assessments and Hatchery and Genetic Management Plans (HGMP) that must be submitted to NMFS for approval.  WDFW will ensure that pertinent state and federal management policies are considered and that recommendations to minimize deleterious effects of programs on listed species are provided.

WDFW will help the USFWS-LSRCP Office to ensure that the Section 7 Biological Assessment and Section 10 permit applications are coordinated.  Further, WDFW will continue to provide data for ESA concerns to other agencies, and program tasks and objectives will be modified as necessary to minimize adverse impacts to listed species.  WDFW will be involved in the USFWS/NMFS consultations for the LSRCP Program under the ESA.

Sub-objective 10.1:  Assess LSRCP hatchery evaluation actions to determine potential effects on species listed under the Endangered Species Act.

Task 10.1.1. Obtain quantitative data necessary to evaluate LSRCP funded programs.

Task 10.1.2.  Coordinate and assist WDFW and USFWS-LSRCP research staff with quantitative analysis for the development or modifications of Biological Assessments and HGMPs.

Task 10.1.3.  Assess effects of all proposed actions and estimate direct and indirect takes of listed species using tasks and results listed in proposal and any relevant literature.

Task 10.1.4.  Develop and recommend alternatives to reduce deleterious effects on all listed species within the program.

Task 10.1.5.  Document all spring chinook production, monitoring and evaluation actions in monthly Section 10 reports.  Provide an annual Section 10 report to NMFS by January 31.

Sub-objective 10.2: Represent WDFW during formal ESA consultation between NMFS and the FWS .

Task 10.2.1.  Act as the liaison between the USFWS and WDFW during the formal consultation period to fulfill the cooperator's role in the process.

Task 10.2.2.  Provide additional documentation, as requested, for the LSRCP Section 7 formal consultation between NMFS and the USFWS-LSRCP Office.

Sub-objective 10.3: Coordinate and integrate Washington's anadromous fish research with the Section 7 LSRCP Biological Assessment, subsequent Biological Opinions and Management Plans, HGMPs, and NMFS' Recovery Plans.

Task 10.3.1.  Recommend changes in Washington’s fish management and research plans to ensure compliance with decisions made during consultations between NMFS and FWS.

Task 10.3.2.  Review special conditions of Section 10 permits, special conditions of Section 7 consultations, and coordinate with WDFW personnel who will implement the actions to ensure that all actions are permitted and consistent with permit requirements.

Task 10.3.3.  Integrate appropriate LSRCP-funded actions described in Biological Assessments and Biological Opinions into a WDFW salmon recovery strategy.

Task 10.3.4.  Where appropriate, provide input to WDFW responses to the NMFS Biological Assessments, Opinions, and Recovery Plans.

Objective 11.  Complete annual reports to summarize results of all LSRCP funded work conducted during the contract period (1 April 2002 to 31 March 2003).

Task 11.1.  Summarize results from objective tasks, assemble into species specific reports.

Task 11.2.  Submit a draft report on Tucannon River spring chinook research and activities to U.S. Fish and Wildlife Service within 60 days after contract is completed (due 1 June).  After formal review, submit a final report within 120 days of contract completion (due 1 July).

Task 11.3.  Submit a draft report on Lyons Ferry fall chinook research and activities to U.S. Fish and Wildlife Service within 60 days after contract is completed (due 1 June).  After formal review, submit a final report within 120 days of contract completion (due 1 July).

Task 11.4.  Submit a draft report on summer steelhead research and activities to U.S. Fish and Wildlife Service by 31 May 2002.  After formal review, submit a final report by 30 June 2002.

# Footnotes

WDFW’s trapping protocol was developed under constraints listed in a Section 10 permit from NMFS which stated, “WDFW is authorized to retain all of the adult, ESA-listed, Snake River spring/summer chinook salmon that return to the Tucannon River fish Hatchery adult trap each year if the total annual adult returns to the trap is less than 105 fish.  If the total annual adult returns to the trap are 105 fish or more, WDFW is authorized to retain up to 70 percent of the adult, ESA-listed, Snake River spring/summer chinook salmon that return to the trap each year and must release at least 30 percent of the adult, ESA-listed, Snake River spring/summer chinook salmon that return to the trap above the hatchery trap for natural spawning.”  WDFW strives to collect adult salmon throughout the duration of the run in proportions consistent with these restrictions, based on run predictions.

# Comments

Thank you for completing the form. Email this document and Part 1 per instructions.