# Bonneville Power Administration

# FY 2002 Provincial Project Review

# PART 2. Narrative

Project ID:   28059

Title:	Restoring anadromous fish habitat in the Lapwai Creek Watershed.

# Section 9 of 10. Project description

a. Abstract

Lapwai Creek historically provided spawning and rearing habitat for A-run wild summer steelhead in the Clearwater River Subbasin (Fuller, 1986).  However, the regular occurrence of extreme high runoff events and low summer flows, high summer water temperatures, poor instream/riparian cover, and siltation of spawning gravels are limiting factors in the watershed.  Low stream flows and a lack of adequate multi-layered riparian vegetation along with excessive sediment have reduced the suitability of Lapwai Creek and tributaries as quality spawning and rearing habitat for anadromous and resident cold water fish.  In addition, sediment, nutrients, and bacteria from existing land-use practices adversely impact water quality.  The primary pollutant sources and habitat degradations are agricultural, livestock, forestry and road practices (NRCS, 2000).  The large percentage of private land and low agricultural commodity prices prohibit landowners from implementing BMPs to solve problems.

The Nez Perce Soil and Water Conservation District developed this proposal to enhance steelhead trout natural production within the Lapwai Creek watershed by improving salmonid spawning and rearing habitat. The project funds coordination, planning, technical assistance, BMP design and implementation, monitoring, and educational outreach to identify and correct problems associated with agricultural and livestock activities impacting water quality and salmonid habitat.  The project accelerates the implementation of the Lapwai Creek Public Law 566 small watershed program.  It also addresses specific needs identified in the Clearwater Subbasin Summary 2001 Draft and the 2000 Columbia River Basin Fish and Wildlife Program documents.

This proposal was coordinated with the Natural Resources Conservation Service (NRCS), Idaho Fish and Game (IDFG), Idaho Department of Environmental Quality (DEQ), University of Idaho (U of I), Nez Perce Tribe (NPT), Clearwater Focus Program, Clearwater Basin Weed committee, and Nez Perce County Board of Commissioners.

This proposal meets objectives outlined in the NPSWCD Resource Conservation Plan. Project implementation will reduce erosion by 30%, sediment delivered to streams by 30%, reduce stream temperature along treatment areas, and improve watershed hydrology.

b. Technical and/or scientific background

###### Watershed Description

Lapwai Creek is a tributary to the Clearwater River and is located 10 miles east of Lewiston, Idaho.  The watershed originates at Mason Butte in Lewis County.  The stream flows north through rolling cropland and pastureland into Winchester Lake at the town of Winchester, Idaho.  North of Winchester Lake, Lapwai Creek parallels highway 95 through steep canyons of forest and rangeland.  The watershed drains approximately 174,600 acres.  (Figure 1.).

The major tributaries of Lapwai Creek include Sweetwater, Webb, Tom Beall, Mission, Rock, and Garden Gulch Creeks.  Forested areas characterize the higher watershed elevations, with rangeland predominant in canyon lands, and non-irrigated cropland on the plateaus.  Table 1 summarizes the land use types and extent within the watershed.

Table 1.  Land Use

Land Use	Total watershed acres

Non-irrigated cropland	58,090

Rangeland	60,100

Dry pastureland	4,290

Forestland	48,790

Recreation	940

Urban Areas	1,040

Wildlife	860

Water	310

Irrigated pastureland	180

The Lapwai Creek watershed is primarily Columbia River Group basalt.  Elevations range from 856 feet to 4,800 feet.  Soil types vary within the watershed and are placed into 6 groups for BMP treatment purposes.  Soils range from cutover timber to loess soils.  Soils in the upper watershed are limited by a fragipan, which results in a shallow water table and ponding.  Erosion rates on cropland range from 2 to 26 tons per acre per year.  Roads associated erosion and streambank erosion are also major contributors to sediment in the stream.  Sediment delivery rates range from 30 to 60% depending on lanscape position and proximity to drainageways.

Precipitation ranges from 18 inches at Lapwai to more than 26 inches at the higher elevations.  Rain-on-snow events are common from January through April and often result in flash-flood conditions, which scour stream floodplains and deposit large quantities of debris.

Approximately 1,800 people reside within the project area, with many living on a single-family farms.  The community of Lapwai, with a population of approximately 935 is the largest settlement in the watershed.  Lapwai is also the headquarters of the Nez Perce Tribe.  Private lands are the primary land ownership within the watershed (86%).  Table 2 lists the land ownership within the watershed.

Table 2.  Landownership

Ownership	Total Watershed Acres

Private	150,000 (86%)

Nez Perce Tribe	20,700 (12%)

BLM	1,970 (1%)

State Lands	1,620 (1%)

Water	310

Total	176,400

### Problem Identification

Several watershed and resource assessments have been completed for the Lapwai Creek watershed.  These assessments were used by the NPSWCD in developing this proposal.

The Supplemental Watershed Protection Plan-Environmental Assessment, Supplement No.2 (NRCS, 2000) lists four detrimental factors to steelhead spawning and rearing in the Lapwai Creek watershed:

- the regular occurrence of extreme high runoff events and extreme low summer flows;

- high summer water temperatures;

- poor instream and riparian cover; and

- siltation of spawning gravels.

These factors decrease survival of steelhead eggs, larvae, and juveniles and decrease the streams carrying capacity for adult (resident) rainbow and juvenile steelhead (NRCS, 2000).  This project proposal is focused on steelhead and Chinook salmon and directly addresses the limiting factors listed above.

The soil and water resource problems within the watershed include the loss of fishery habitat caused by deposition of sediment from cropland, forestland, grazing lands, animal feeding operations, urban construction sites, streambanks, and roads.

Low stream flows and a lack of adequate multi-layered riparian vegetation along with excessive sediment have, in part, reduced the suitability of Lapwai Creek and tributaries as quality spawning and rearing habitat for anadromous and resident cold water fish.  In addition, sediment, nutrients, and bacteria from existing land-use practices are adversely impacting water quality.

Figure 1.  Lapwai Creek watershed location.

Ecological problems identified by Kucera et al. (1983) include:

- Low summer flows

- Wide fluctuation in annual stream flows

- High summer water temperatures

- Lack of instream cover

Water quality has also been reported as marginal with frequent high fecal coliform bacteria levels, seasonally high turbidity, suspended sediment and nutrient concentrations (Thomas et al. 1985).  The StreamNet database lists Lapwai Creek with 31.5 Km of anadromous fish habitat (spawning and rearing).  The overall habitat quality has been assessed as 20.9 km fair (66.4%) and 10.6 km (33.6%) as poor.  Despite habitat conditions rainbow-steelhead production currently occurs in the middle reaches of Lapwai Creek

Species at Risk

Lapwai Creek provides habitat for multiple anadromous and resident fish species.  A 1980’s survey conduced by the Nez Perce Tribe identified 10 fish species.  The anadromous stocks include wild A-run steelhead and Chinook Salmon.  In addition, the NPT has recently reintroduced coho.  Lapwai Creek and its major tributaries are important habitat for Snake River Basin steelhead which were listed by the National Marine Fisheries Service (NMFS) as threatened unde rthe ESA (February 5, 1999, 56 FR 5740).  Snake River fall chinook salmon are also listed as threatened (December 28, 1993, 58 FR 68543).  Resident fish include sculpin, rainbow trout, suckers, northern pikeminoow, chiggermouth, and dace.  Like many anadromous streams in the Columbia River Basin, salmon and steelhead populations have significantly declined from historic levels (NRCS 2000).

Critical Habitat and Essential Fish Habitat (EFH)

Critical habitat for Snake River fall Chinook salmon include the Clearwater River from its confluence with the Snake River upstream to its confluence with Lolo Creek.  Lapwai Creek flows into the Clearwater River approximately 10 miles above the confluence of the Snake and Clearwater Rivers at Lewiston, Idaho.  Although not within the designated critical habitat for fall chinook salmon, as a major tributary to the Clearwater River, activities within the project area influence habitat quality downstream.  Critical habitat for threatened steelhead includes the Clearwater River, which includes the project watershed (NRCS 2000).

### Problem Background

###### Low flows and variable flow problems

The Lapwai Creek watershed is characterized by extreme fluctuations in stream flow.  The flows are greatest from January through April and are lowest from July through September.  During the winter and spring high flow period, it is not unusual for peak flows to increase several thousand fold over summer base flows.  Because streams are confined to narrow, deep canyons with moderate to steep gradients, a 10-year precipitation event can cause a large flash flood event that will scour floodplains and deposit large quantities of bedload materials.  This tendency for large flow fluctuations places considerable stress on aquatic and riparian resources in the watershed.

Vegetative cover changes and subsequent land use and management can result in dramatic changes to stream base flows.  NRCS Engineering Technical Release No. 55 (TR-55, Urban Hydrology for Small Watersheds) was used to compare the relative difference between existing watershed hydrologic conditions with hydrologic conditions that may have existed during presettlement.  The TR-55 hydrologic model does have limitations for this type of analysis, but using the model demonstrates that peak flows have been increased as a result of land use changes, which generally results in reduced base flows.  The degree and extent of low flows in the steam is the most limiting habitat factor for salmonid populations in the watershed.

Hydrology also plays an important role in determining the composition and distribution of fish, both anadromous and resident, as well as other aquatic organisms.  Large runoff events, such as the 1996 event, move massive quantities of bedload materials and large woody debris resulting in dramatic changes in stream channel morphology and stream flow behavior.  New channels are created as old channels are abandoned or are filled with coarse bedload materials.  The pattern of coarse material scour and deposition alters the occurrence of surface and subsurface stream flows; this in turn alters the composition and distribution of fish and other aquatic organisms.

The change in land cover from predominantly grass/herbaceous/tree cover to cropping systems has dramatically impacted the hydrological aspects of the Lapwai Creek watershed resulting in a change in the timing and magnitude of spring peak flows.  The higher peak flows during spring runoff indicate less water is remaining in the basin either as soil moisture or deep percolation.  This in turn results in less water available for late season base-flow creating low summer flow conditions in the streams.

Implementation of water retention practices such as sediment basins, constructed wetlands, ponds, and changing tillage practices to Direct seeding will assist in modifying the hydrology of the watershed by improving water retention and reducing peak flows.  The NRCS Engineering Field Manual Chapter 2 small watershed hydrology computer model was used to compare a conventional cropping system on a cropland field with that of a field which will implement the Direct seeding system.  Direct seeding is a new technology for this area and is not widely adopted at this time.  Direct seeding is a combination of crop rotation length, contour farming, and no-till seeding systems.  The majority of agriculture producers within the watershed have wheat/summer fallow rotations or two-year rotations and use inversion tillage practices to seed their crops.  The amount of runoff on a field in this condition is 0.6 inches for every inch of rainfall.  By adopting a 3-year rotation, eliminating summer fallow and inversion tillage practices, the average runoff is estimated to be 0.3 inches per every inch of rainfall for direct seeding systems.  The reduction in surface runoff will not contribute to peak flows but will allow water to infiltrate and be available for summer base flows.  The implementation of direct seeding systems could significantly impact the hydrology of this watershed by reducing peak flows and providing more water retention in uplands.

Adoption of this new technology is limited by social acceptance and by the poor financial outlook for agriculture commodities.  Providing cost-share to implement this practice and demonstrating the effectiveness of the practice will encourage adoption.   Several landowners have expressed an interest in adopting this practice.

###### Sediment and high stream temperature problems

Erosion and associated sediment deposition in Lapwai Creek is caused by;

- Conventional tillage practices which pulverize the soil surface, leaving inadequate crop residues

- Lack of enduring land treatment practices to control or reduce concentrated flow and gully erosion

- Improper livestock grazing practices in riparian and wetland areas and upland range areas

- Improper forest road and skid trail construction

- Lack of riparian cover and protection

- Agronomic practices, which result in degraded, soil quality and health

- Improper road construction and maintenance

- Improper rural development construction activities

The Army Corps of Engineers estimates that approximately 2,000,000 cubic yards of sediment are deposited annually in the Lower Granite pool.  Of this, about 389,000 cubic yards (19.5%) is contributed from the Clearwater River.  It has also been estimated that approximately 2.5% of the Clearwater River portion, or some 9,800 cubic yards (7,000 tons) are contributed annually by the Lapwai Creek watershed.  The large amount suspended sediment and bedload movement affect anadromous fisheries by absorbing sunlight and increasing stream temperatures during critical migration periods.  Silt and sand are deposited in spawning beds, reducing the salmonid reproductive capacity of the stream.  Fine sediments are also deposited in pool habitat used by rearing salmonids.

The majority of off-site sedimentation is caused by a combination of detrimental agricultural practices:

- Conventional tillage practices that pulverize the soil surface leaving inadequate crop residue for protection;

- Inversion tillage, such as plowing, which tends to create a moisture-restrictive layer at a depth of 8-10 inches; and

- Continued use of excessively steep and erodible lands for crop production.

Additional benefits to the adoption of a direct seeding system include a drastic reduction in soil erosion and associated sediment delivered to the stream.  The Revised Universal Soil Loss Equation (RUSLE) (NRCS, 1995) calculations indicate that up to a 50% reduction in erosion can be achieved on cropland acres, which implement direct seeding systems.  Additional BMPs will be installed along with the direct seeding to provide a total resource protection system.

By installing the BMPs outlined in this proposal erosion will be reduced by 30% (up to 55% if the project continues for 6 years) and off-site sediment by 30% (67% if project continues for 6 years).

Additional Studies

An animal feeding operation inventory (NPSWCD 1998) indicates that 59% of the livestock operations within the watershed have direct access to streams.  Livestock operations include cattle (76%), horses (21%) and sheep (3%) for a total of 3,186 animals in the watershed.  Due to the mild climate Lapwai Creek is used for winter grazing and feedlots along the streams at lower elevations.  The livestock are moved to higher elevations in the summer to graze pasture and timber areas.  The inventory counted 166 different livestock operations.  The majority of these operations (75%) have less than 20 animals per site.  The small animal numbers indicate that these operations are not used as the sole source of income for these operators.  The livestock operations are contributing sediment, nutrients, and bacteria to Lapwai Creek.  In addition, livestock grazing along riparian areas removes woody vegetation, impacting stream temperature.  The analysis performed concluded that Garden Gulch and lower main stem Lapwai Creek were at a high risk for degraded water quality from sediment, nutrients, and bacteria from livestock operations.  Medium priority drainages included Rock Creek, Sweetwater Creek, Tom Beall, and Mission Creeks.

The Draft Clearwater Subbasin Summary (page 139) on a subbasin scale states one of the primary limiting factors for resident and anadromous salmonid populations are impacts of land management activities on hydrology, sedimentation, habitat distribution and complexity, and water quality.  The Lapwai Creek watershed is a part of the Lower Clearwater assessment unit scale.

A study completed in 1986 by Kucera states that problem areas that may limit fish production were a lack of yearling habitat, low summer stream flow, and potential elevated stream temperatures and heavy sedimentation.  The amount of sediment in the Mission Creek study areas reduced the amount of available habitat, especially during the winter period.  A cobble emmbedness value of 44.4 percent indicated that sediment was filling many of the interstices that fish may potentially utilize as cover, and may affect aquatic insect production.

Wild steelhead trout historically occupied all major drainages and the majority of the tributaries within the Clearwater Subbasin (Clearwater Subbasin assessment pg 84).

Lapwai Creek has been identified having wild A-run steelhead populations.  Wild steelhead of the upper Snake River drainage have generally declined in abundance in recent years due to dam construction, public water supply projects, poor land management practices, and overfishing.  Raymond (1978) estimated that 60-80% of the Snake River steelhead returns are the result of Dworshak and Pahsimeroi hatchery releases (Kucera and Johnson 1986).  Protection of current Lapwai Creek wild A-run steelhead populations is important for genetic and biological diversity.

It has been suggested a study by Kucera and Johnson (1983) an enhancement plan of riparian revegetation and placement of instream structures would substantially increase the smolt yield in Mission Creek, a major tributary to Lapwai Creek. This study estimated that about 55 percent of the Mission Creek system is currently producing steelhead.  The projected smolt yield from this area is 1,700 fish.  If enhancement measures are implemented, it is estimated that the current low smolt yield could conservatively be tripled or quadrupled.  Thomas et al. (1985) estimate smolt production in the Mission Creek system to be as high as 11, 366 fish.

Spawning and salmonid rearing occur within all major tributaries to Lapwai Creek.  Steelhead are the most suited anadromous fish to the Lapwai Creek system, and have been recorded in all major tributaries to Lapwai Creek.  Steelhead are listed as threatened under the Endangered Species Act (ESA).

Lapwai Creek is listed as water quality impaired for sediment, nutrients, habitat alterations, flow alterations, temperature, and bacteria on the EPA Clean Water Act 1998 303(3) list.

The local economy is driven by both the agriculture and timber industries.  Area wide, 80% of the average annual net farm income is generated from annuals crops;  10 % from pasture, and the remaining 5% from timber. Due to consecutive years of poor agricultural prices, the agricultural producers have limited financial resources for the installation of BMPs.  Conservation programs available through federal and state resources provide cost-share for a portion of selected BMP installation.  Cost-share is not available for all of the BMPs needed to improve fisheries habitat.  In addition, landowners do not have the financial resources to provide their part of the installation.  The NPSWCD proposes to use BPA funds to install BMP practices in cooperation with private landowners.  Other cost-share programs will be utilized first with BPA funds providing an additional incentive to install BMPs, which have mostly off-site benefits.

###### Organization Description

The NPSWCD is an organization promoting the protection of natural resources on a watershed basis.  The NPSWCD consists of seven locally elected members.  The NPSWCD boundaries are Nez Perce County, Idaho.  The NPSWCD’s five-year Resource Conservation Plan, which identifies specific needs and goals to address local resource concerns.  One of the goals in this plan is to Protect, Enhance and Restore priority fish habitats within the District.  In addition, the NPSWCD conducts a public input process to develop its goals and objectives.  One of the top ten resource concerns within the District according to a Conservation Needs Assessment Survey was the protection of wildlife and fisheries habitat.  The NPSWCD has over 60 years of experience in resource conservation, design and implementation of BMPs, and working with local landowners to install on-the-ground conservation practices.  As a result of current and past efforts the NPSWCD has an excellent working relationship with local landowners and elected officials.

###### Project Description

This project proposal consists of implementing BMPs on agricultural lands to reduce sediment and nutrient delivery to the stream, reduce steam temperature and improve water retention in the watershed uplands.  BMPs selected for installation include erosion control systems, sediment basins, channel vegetation, prescribed grazing, grass seeding, fencing, pest management practices, nutrient management, forest stand improvement, direct seeding and livestock waste management systems.

This project has been coordinated with the Nez Perce County Board of Commissioners, Idaho Department of Fish and Game (IDFG), Idaho Soil Conservation Commission (ISCC), Idaho Department of Environmental Quality (IDEQ) and the Nez Perce Tribe (NPT).

BMP selection will follow the BMPs outlined in the Supplemental Watershed Protection Plan-Environmental Assessment Supplement no. 2 (NRCS, 2000).  All BMPs will be designed following the NRCS Field Office Technical Guide standards and specifications. This project will be coordinated with other available conservation programs to maximize funds and implement the most on-the-ground conservation practices.  Other programs include the NRCS Public Law 566 small watershed program, Wildlife Habitat Improvement Program (WHIP), Wetland Reserve Program (WRP), Conservation Reserve Program (CRP), and the Idaho state funded Water Quality Program for Agriculture.

BPA funds will be used to complement and provide additional cost-share to existing conservation programs for erosion control and fish habitat enhancement practices when feasible.  The NPSWCD staff will inventory, design, and provide construction inspection for the installation of BMPs.

The NPSWCD is submitting this proposal to obtain funds to provide technical assistance in developing, designing, and installing BMPs as well as providing cost-share dollars to landowners for BMPs not funded through other programs.  In addition, the NPSWCD plans to use the BPA funds to supplement the PL566 cost-share on erosion reduction and riparian enhancement BMPs.  BMP types and extents have already been identified in the Environmental Assessment plan (NRCS, 2000).  In addition, National Marine Fisheries Service (NMFS) has already consulted and concurred with the Biological Assessment (BA) completed by NRCS for this project.

The NPSWCD plans to collect additional watershed inventory data for roads and streambank stability.  The inventory results will help prioritize and focus the BMP installation locations.  A reconnaissance level riparian assessment was completed in 2000.  However, a detailed on-the-ground stream assessment is needed to prioritize site specific project locations within the watershed.  The NRCS stream visual assessment protocol will be used to complete this need.   The protocol provides an assessment based primarily on the physical conditions within the assessment area.  Site specific data is collected on channel condition, hydrologic alteration, riparian zone, bank stability, water quality, barriers to fish movement and instream fish cover.

c. Rationale and significance to Regional Programs

Mission-Lapwai Creek Watershed - Supplemental Watershed Protection Plan – Environmental Assessment Supplement No. 1 & 2

The original watershed Protection Plan was completed in 1990 by the NRCS.  The original plan focused on water quality improvements in the Lapwai Creek watershed.  Two supplements to the original plan were completed to address fish habitat issues.  The supplements were completed in 1994 and 2000 and include treatment strategies to enhance and protect riparian vegetation, address hydrologic modifications, reduce sediment production and delivery, and reduce stream temperatures.  The watershed plan purpose is to improve anadromous and resident cold-water fish habitat and water quality through;

- Riparian area enhancement and protection;

2) Enhancement of in-stream habitat;

3) Reductions in sediment, nutrient, and bacterial loadings; and

4) Improvement of base stream flow conditions.

Project Goals:

- Improve anadromous and resident cold-water fish habitat through riparian area enhancement and sediment reduction.

- Reduce stream temperatures through riparian enhancement (lower the maximum mid-summer water temp. by 5 degree centigrade).

- Enhance degraded hydrologic conditions and decrease sediment yield in the upper watershed through runoff retention and detention practices.

This proposal addresses the goals of the Mission – Lapwai PL566 project by installing BMPs on agricultural lands, which address stream temperature, and reduce erosion.  By implementation of the BMPs outlined in this plan a 30% reduction in erosion and associated sediment delivered to the stream is expected.  This reduction will increase if the project is extended to 6 years.

## Clearwater Subbasin Summary

The Lapwai Creek proposal’s restoration and protection efforts meet the stated goals and objectives of several entities within the Clearwater Subbasin. This proposal addresses the following goals and objectives which NPSWCD included in the Clearwater Subbasin Summary:

### Goals:

- Cooperate and coordinate in developing watershed plans for watersheds located within multiple conservation districts

- Implement BMPs identified in the watershed plans on all land uses

- Coordinate technical/financial resources for the implementation of BMPs on private lands

- Reduce erosion and improve water quality and fisheries habitat on cropland, forestland, and rangeland resources

- Assist landowners, communities, and tribes in meeting state, local, and federal regulations including the Clean Water Act, Endangered Species Act, and NEPA regulations

- Improve the condition of fisheries habitat including riparian and wetland areas

- Improve grazing land and cropland productivity

- Establish fish and wildlife habitat, water quality and resource condition monitoring programs

- Develop and promote public awareness programs to promote good stewardship

##### Objectives

- Conduct one meeting annually to coordinate watershed efforts and technical/financial resources for BMP implementation with local stakeholders

- Implement 50% of the identified BMPs to improve priority fish habitats within 10 years

- Reduce erosion and identified pollutants by 60% in identified priority areas in 10 years

- By 2010, improve water quality to meet TMDL standards in identified watersheds

- By 2010, improve riparian and wetland areas to proper functioning condition

- By 2015, improve rangeland condition from “fair” to “good”

- By 2015, reduce cropland and urban erosion to “T”

- By 2005, complete 25% of the identified animal feeding operation improvements

- By 2005, 50% of the streams within the District will be monitored for stream temperature

This project addresses many limiting factors specified in the Clearwater Subbasin Summary.  Refer to the technical and/or scientific background section for a review of the limiting factors.

The Clearwater Subbasin Summary identified aquatic and terrestrial needs, fisheries/aquatic needs, and wildlife needs.  This proposal addresses the following specific “Needs.” Each “Need” number references back the number used in the Summary.  After the “Need” is the means by which the NPSWCD intends to address the “Need” with the Big Canyon Creek watershed proposal.

### Combined Aquatic and Terrestrial Needs

- Develop and implement BMPs on agricultural, mining, grazing, logging and development activities to protect, enhance, and/or restore fish and wildlife habitat, streambank stability, watershed hydrology, and floodplain function. – The primary goal of this project is to develop and implement BMPs. Objective one lists the tasks to achieve this goal.

5.	Continue ongoing, and establish new, monitoring and evaluation programs for fish supplementation, habitat restoration and improvement, habitat baseline conditions, water quality and water quantity improvements, conditions and trends.  These M&E activities are critical to evaluating the effectiveness of projects in improving habitat, watershed health and enhancing production of target species. – Objective 8 proposes to yearly complete BMP Effectiveness, Stream Temperature, and photomonitoring at BMP implementation sites.

7.   	Complete road inventories and assess impacts to aquatic and terrestrial resources.  Use information to facilitate transportation planning and to reduce road densities. Support planned road closures on public land and encourage closure of other roads. – Objective 1, states that the NPSWCD  will inventory watershed roads, then incorporate the road information as a GIS layer.

8.  		Continue and expand the cooperative/shared approach in research, monitoring and evaluation between tribal, federal, state, local and private entities to facilitate restoration and enhancement measures.  Protection and restoration of fish and wildlife populations and habitat will not be successful without the interest and commitment by all. – Objective 5 addresses interagency and public organization and cooperation in research, monitoring and evaluation.  Development of this proposal involved coordination with NRCS, and NPT Fisheries watershed Program and Water Resource Department.

- Protect existing pristine and key fish and wildlife habitats directly threatened by subdivision, recreation, or extractive resource uses. – This is met through the completion of identified BMPs, as stated in Objective 1.  The habitats are identified on specific land during the conservation plan development.

Fisheries/Aquatic Needs

Water Quality:

1.	Continue coordinated temperature monitoring throughout the subbasin. –The NPSWCD currently deploys six temperature monitoring site in the watershed.  Objective 10, Task A would continue the work.

2.  	Reduce stream temperature, sediment and embeddedness to levels meeting appropriate standards for supporting self-sustaining populations of aquatic species. –The purposes of installing the agricultural, livestock, and riparian BMPs are to address temperature, sediment, and embeddedness problems.  BMP installation is address in Objective 1.

4.  	Reduce impacts from agricultural sediment, fertilizer, pesticide loading, confined animals operations, stormwater and road runoff, wastewater effluent, mining and logging. – The purpose of installing the agricultural, livestock, and riparian BMPs is to decrease or stop these impacts.  BMP installation is address in Objective 1.

Habitat / Passage:

1. 	Protect and restore riparian and instream habitat structure, form and function to provide suitable holding, spawning and rearing areas for anadromous and resident fish. – The purpose of installing the agricultural, livestock, and riparian BMPs is improved water quality and habitat.  BMP installation is address in Objective 1.

2. 	Protect, restore and create riparian, wetland and floodplain areas within the subbasin and establish connectivity. – When appropriate at specific settings, BMPs may be installed to complete this need.  Field visits to site determine the resources’ needs.  BMP design and installation is address in Objectives 1.

4. 	Restore a more normal hydrograph to altered watersheds by addressing land use activities through implementation of BMPs and other restoration strategies. – BMP design and installation is address in Objective 2.

5. 	Inventory natural and artificial passage barriers within the subbasin and evaluate if removal or modification is warranted. – NPTFWP addresses this need with BPA proposal number 199901600.  NPSWCD will assist the NPTFWP with their proposal by assisting in coordinating private landowner agreements and cost sharing opportunities.

6.  	Investigate connectivity between populations and the role of natural and artificial barriers in population isolation.  Remove or modify identified natural or artificial passage barriers where aquatic considerations have been met. – NPTFWP addresses this need with BPA proposal number 199901600.  NPSWCD will assist the NPTFWP with their proposal by assisting in coordinating private landowner agreements and cost sharing opportunities.

7.  	Complete culvert inventory and assess associated passage and flow issues.  Evaluate whether removal or modifications are warranted. – NPTFWP addresses this need with BPA proposal number 199901600.  NPSWCD will assist the NPTFWP with their proposal by assisting in coordinating private landowner agreements and cost sharing opportunities.

Enforcement / Education:

1.  	Better educate the public on issues and policies important to natural resource restoration, protection, and enhancement to encourage meaningful public participation. – Public outreach education and technology transfer are addressed in this proposal.   From experience in working with private landowners over the years, the NPSWCD has found the most effective means of an individual landowner’s education and participation is through face-to-face meetings and discussions with the landowner on his/her land.  Much time is spent with landowners during the conservation planning and implementation process.  This one-on-one time has created an excellent working relationship between landowners and the NPSWCD.

Wildlife / Terrestrial Needs

General:

- Cooperate on threatened, endangered, and sensitive species recovery or conservation strategy efforts in the subbasin. – The conservation planning process addresses this need..

Prairie Grasslands:

8.	Develop conservation plans for Jessica’s aster and Palouse goldenweed. –Both of these species may be found within the watershed.  The conservation planning process addresses this.  When the species are known to occur near the BMP implementation area, construction sites are field checked for the presence/absence of the species.

Riparian Communities:

- Inventory, map, and assess the distribution of riparian communities and associated wildlife and plant species. – This is completed on a landowner’s field or farm basis.  The conservation planning process addresses this need.

- Protect, restore, and create wetland and riparian habitat in areas of greatest need. - When appropriate at specific settings, BMPs may be installed to complete this need.  Field visits to site determine the resources’ needs.

- Noxious Weeds:

- Inventory and map the distribution of noxious weeds. - meets this need map working with the Clearwater Basin Weed Committee to meet this need and compile the information on a GIS overlay.

- Develop and use restoration techniques for noxious weed infested communities. –This is completed on a landowner’s field or farm basis through BMP implementation as stated in and through the conservation planning process.

- Continue control program for noxious weeds to restore natural habitat conditions and communities for wildlife species and improve watershed function. -This is completed on a landowner’s field or farm basis through BMP.

- Develop an information and education stewardship program for noxious weeds. This is completed on a landowner’s field or farm basis through BMP implementation.  The proposal also calls for conducting a noxious weed workshop in conjunction with the NPT Bio-Control Center.

NPPC 1994 Fish and Wildlife Program

The project will work towards 7.6 Habitat Objective of the NPPC Fish and Wildlife Program to limit the percent of fine sediment in salmon and steelhead redds to no more than 20 percent and limit cobble embeddedness (CE) to less than 30 percent or documented historic condition (NPPC, 1994).  This project proposal will directly aide in decreasing CE within the Lapwai watershed streams by implementing a variety of agricultural and livestock BMPs.

NPPC 2000 Fish and Wildlife Program

The program is habitat based focused on rebuilding healthy, naturally producing fish and wildlife populations by protecting, mitigating, and restoring habitats and the biological systems within them.  This project proposal works towards accomplishing the vision and objectives of the program by protecting and restoring the ecological functions, and habitats of the Lapwai Creek watershed.

Salmon Recovery Strategy (SRS)

The Washington State Joint Natural Resources Cabinet (1999) stated their primary goal of the Agricultural Habitat element of the SRS is to “Improve farm and sector-based practices to provide the water quality, water quantity, and functional riparian habitat needed for salmon recovery in the agricultural sector.”  The Lapwai proposal intends to pursue this goal by implementing BMPs, which thereby improves farming practices.  The proposal also promotes the stated SRS objective to “Raise the awareness and understanding in the agricultural community of salmon recovery and watershed health, and build support for the agricultural strategy and its implementation” by promoting objectives and tasks to incorporate public education and technology transfer throughout the timeframe of this proposal.

Spirit of the Salmon- The Columbia River Anadromous Fish Restoration Plan of the Nez Perce, Umatilla, Warm Springs and Yakama Tribes

In 1996, the Columbia River Inter Tribal Fish Commission developed an anadromous fish restoration plan which includes the Clearwater Subbasin.  This Lapwai Creek watershed proposal supports several of the actions identified in the Recovery Plan for the Clearwater River System including restoring riparian areas, restoring riparian vegetation, restricting and grazing, enforcing the Clean Water Act, reduce instream and fish diversions, and controlling land use in highly erodible areas.  NPSWCD support for the Plan is through the installation of BMPs on private, tribal, county, and state lands.

###### Clearwater Basin Noxious Weed Committee

This proposal supports and implements the goals of the Noxious Weed Committee to control and eradicate noxious weeds in the county.  One of the objectives of this proposal is to work with the Committee to develop a GIS overlay on noxious weeds for the watershed.

USDA- Natural Resources Conservation Service Strategic Plan 2000 – 2005

Goals identified in the NRCS’s Strategic Plan and which are addressed by the NPSWCD’s Big Canyon Creek watershed proposal include:

- Enhance natural resource productivity to enable a strong agricultural and natural resource sector by maintaining, restoring, and enhancing cropland, grazingland, and forestland productivity.

- Reduce unintended adverse effects of natural resource development and use to ensure a high quality environment by protecting water and air resources from agricultural non-point sources of impairment, enhancing animal feeding operations to protect the environment, and maintaining, restoring, or enhancing wetland ecosystems and fish and wildlife habitat.

- Deliver high quality services to the public to enable natural resource stewardship by delivering services fairly and equitably, strengthening the conservation delivery system, and ensuring timely, science-based information and technologies.

NMFS Biological Opinion

The proposed project complies with the following BiOp objectives:

- This project will help restore watershed health and degraded habitat.

- This project is designed to help recover the ESU of Snake River summer steelhead.

- This project helps avoid the jeopardy standard for the steelhead ESU.

- This project complies with the Reasonable and Prudent Alternative selected by NMFS to avoid the jeopardy standard.

- This project will help eliminate future road failures/landslides and protect the watershed from future degradation.

- This project will help to meet water quality standards and comply with the Clean Water Act.

- This project will be cost-shared through federal, state and private sources using programs such as the NRCS administrated PL-566, Environmental Quality Incentivies Program (EQIP), Wetland Reserve Program (WRP), and Wildlife Habitat Improvement Program (WHIP).

- Restoring riparian habitats—re-vegetation of riparian areas and removal of streamside roads.

This project proposal directly addresses the following RPA actions:

Action #149:  …Under the NWPPC program, BPA addresses passage, screening, and flow problems, where they are not the responsibility of others….

The agricultural and livestock BMPs implemented under this project concentrate on the quality and quantity of stream flows. These BMPs will be installed primarily on private and tribal lands. This proposal also coordinates and cooperates with NPT’s BPA proposal number 1999-1700 to remove and replace fish road and culvert fish passage barriers.

Action #150:  In subbasins with listed salmon and steelhead, BPA shall fund protections of currently productive non-Federal habitat, especially if at risk of being degraded, in accordance with criteria and priorities BPA and NMFS will develop by June 1, 2001.

In the Lapwai Creek watershed, listed ESA anadromous fish include the “threatened” steelhead trout and fall chinook salmon. This project proposal protects, restores, or enhances currently productive fish habitat by implementing BMPs, which improve fish habitat, riparian areas, and water quality and quantity.

Action #152  The Action Agencies shall coordinate their efforts and support offsite habitat enhancement measures undertaken by other Federal agencies, states, Tribes, and local governments….  Support development of state or Tribal 303(d) lists and TMDLs….

Assist by sharing data from continued temperature monitoring and annual BMP effectiveness studies.  Provide noxious weed GIS data through the Clearwater Basin Weed Committee.

Using or building on existing data management structures….

Coordinate development of website to house and disperse fish, wildlife, and BMP information based on watersheds.  Distribute proposal’s final report to interested entities.

Participating in NWPPC’s …meetings….

Project would allow NPSWCD continued involvement in NPPPC and Clearwater Subbasin meetings.

Sharing technical expertise and training….

Providing technical assistance and training to landowners is an essential component of this proposal.  One-on-one meetings with landowners to provide them with the information and options necessary to implement and maintain BMPs involves the bulk of the project’s time.  The more information landowners have, the greater the “buy-in” to restoring and protecting anadromous fish habitat.  The proposal also incorporates technology transfer in the form of two public educational workshops, two annual newsletters, and a tour of the project sites at the project proposal’s end.

Leveraging funding resources through cooperative projects, agreements, and policy….

Leverages funding resources by seeking out other cost funding sources such as WQPA,WRP,WHIP, PL-566, and CRP.  Project funds installed BMP costs by requiring landowners provide operation and maintenance services.  NPSWCD has working agreements with the Nez Perce County Commissioners, NPT, Idaho State Correctional program, and the NPT Salmon Corps.

Action #153: BPA…shall negotiate and fund long-term protection for 100 miles of riparian buffer….

Riparian forest buffers and filter strips (ie-grassed riparian buffers) are listed agriculural and livestock BMPs.  The project estimates installing a total of 9 acres of riparian buffers.  Priority areas will be determine by a riparian multi-layer assessment.  In this area, riparian buffers are often combined with livestock use exclusion fencing and off-site livestock watering facilities. The federally funded CRP will be used when applicable.

Salmon Recovery Strategy

The SRS habitat plan includes 1) immediate actions – restore water quality, remove passage barriers, secure high quality habitat, 2) Manage federal lands to protect fish, 3) Protect and improve tributary habitat (Federal Caucus 2000).

This project proposal fits into this plan by implementing immediate actions in erosion reduction, sediment reduction, stream temperature reduction, bacteria and nutrient reductions which will restore water quality and return quality habitat to key fisheries species.  All aspects of this project are coordinated with NRCS, NPT, IDFG, DEQ, Nez Perce County, and private landowners.

Spirit of the Salmon Fish Restoration Plan

Protecting and restoring the Lapwai Creek Watersheds is called for in the objectives and goals of the Spirit of the Salmon Anadromous Fish Restoration Plan of the Nez Perce, Umatilla, Warm Spring, and Yakama Tribes (Volume II).  This proposal address the following recommends actions for the Clearwater River System including:  (1) Eliminate or severely restrict logging, road building, restore riparian areas, (2) Restore riparian vegetation, reduce or eliminate mining, (3) Eliminate or severely restrict logging and grazing, restore riparian area, (4) Enforce Clean Water Act, reduce diversions, reduce or eliminate grazing, reduce roads, and (5) Control land use in highly erodible areas.

d. Relationships to other projects

NPTH Satellite Facility and Coho Salmon Outplants

Under BPA project #83350, Nez Perce Tribal Hatchery, a hatchery satellite facility is currently under construction and is plan to be in operation by 2002.  The satellite facility is located 0.8 miles upstream of its confluence with the Clearwater River.  The facility will be used for rearing of fall Chinook salmon and released into Lapwai Creek (BPA et al. 1997).  Fall Chinook rearing would not fully utilized the capacity of this facility.  It is the intent to maximize production at this facility, in which rearing of coho salmon for release into Lapwai Creek is being highly considered (NPT).

The Nez Perce Tribe Fisheries program has began reintroductions of coho salmon into Lapwai Creek since 1998 in an attempt to restore their populations into the Clearwater River Subbassin.  Table 3 lists the number of coho outplants and returns into Lapwai Creek.  A final Long-Term Coho Salmon Management Plan for the Clearwater River is tentatively set for completion by the end of 2001 and implementation to begin in 2002, which includes Lapwai Creek.  In order for this project to be successful, restoration of stream, riparian, and watershed functions is extremely important.

e. Project history

Historical activities in the watershed include one BPA funded project and numerous other watershed projects.  The USDA NRCS completed a watershed assessment in 1995, 2000, and a River Basin Study in 1983.  Other on-going efforts in the watershed include stream temperature monitoring and installation of BMPs through the Conservation Reserve Program, Lapwai PL566 watershed project and Environmental Quality Incentives Program.

f. Proposal objectives, tasks and methods

Objective 1. Initiate landowner contact and participation.

Task A. Identify eligible landowners.

Methodology: Obtain landowner names and addresses from Nez Perce and Lewis County Assessor office.  Ensure all names and addresses are entered into the NPSWCD customer database using Outlook software.  The NPSWCD has a customer database, which lists landowners by watershed.  The Lapwai watershed database was last updated in 1999.  The majority of the labor to complete this item is already done.

Timeframe:  August 2002

Task B.   Develop a GIS based land ownership coverage identifying specific landowners and tracts.

Methodology: Digitize land ownership boundaries using Nez Perce County and Lewis County Assessor maps and USDA-Farm Service Agency tract maps.  FSA protocols will be used for digitizing tract and field boundaries.  FSA quality control for this task.  This information will be used to develop conservation plans for the implementation of identified BMPs.

Timeframe:  September 2002

Task C.   Conduct an initial public informational meeting.

Methodology: Using mass mailing, radio, and television techniques inform the Lapwai Creek watershed landowners about the project and meeting specifics.  The agenda will include other agencies who have activities within the watershed.  At the meeting, applications will be taken for project participation.

Timeframe:  November 2002

Task D.  Accept applications for project participation.

Methodology: Applications for project participation will be collected by using the project application format developed for the NPSWCD’s BPA project number 199901500.  Applications will be accepted by mail, fax, or phone following established NPSWCD guidelines.

Timeframe:  November 1 – December 31, 2002.  January 1 – February 28th for all other fiscal years.

Task E. Develop outreach materials to assist in obtaining landowner participation, general education of habitat needs, and implementation of BMPs.

Methodology: Revise existing NPSWCD fact sheets to explain project contracting and administration procedures. The NPSWCD developed fact sheets to explain payment procedures, contracting procedures, BMP maintenance requirements, and general project goals for the NPSWCD BPA project number 199901500.  These fact sheets will be revised to reflect information specific to the Lapwai Creek watershed.

Timeframe:  September 2002.

Task F. Develop information materials to explain project goals and specific fisheries needs.

Methodology: Work with the IDFG and NPT to develop one-page informational fact sheets on the fish species present and habitat needs. Provide an initial project media overview by presenting information on the KLEW Channel 3 morning show, KOZE radio show, and Lewiston Morning Tribune.

Timeframe:  August-September 2002

Objective 2. Collect additional watershed planning information to prioritize BMP installation locations in tributaries.

Task A. Prioritize stream reaches for treatment and develop site specific treatment alternatives.

Methodology: Follow NRCS stream visual assessment protocol along 40 miles of stream in Lapwai Creek.  Data will be collected in a GIS format.

Timeframe:  May 2003

Task B. Complete GIS road layer information.

Methodology: Complete a road assessment to identify private road locations and identify specific road segments contributing excessive sediment to priority fish habitat.

Timeframe:  Inventory will be completed on Tom Beall, Garden Gulch and lower mainstem Lapwai Creek by December 2002.  Inventory will be completed on Sweetwater Creek and Thiessen Gulch by June 2003.  Inventory will be completed on Mission Creek and Rock Creek by December 2003.

Task C. Develop GIS layer for known structure and project work.

Methodology: Identify locations of existing BMPs using a GPS unit.  Develop a GIS coverage for this activity.

Timeframe:  December 2003

Task D. Inventory and prioritize for treatment noxious weed locations within the watershed.

Methodology: Working with the Clearwater Basin Weed Committee, inventory, assess and prioritize noxious weed locations within the watershed.  All data will be in a GIS format and available through the Clearwater Basin Weed committee.

Timeframe:  December 2003

Objective3.  Complete BMP plans and Ensure regulatory compliance.

Task A. Select project applications for site evaluations and plan development.

Methodology: Rank project applications using an established ranking protocol.  Ranking criteria will follow the already established PL566 watershed project ranking.  Additional criteria will be added for fish habitat needs.  This criterion will ensure that the applications with the most impact on fish habitat are selected and processed.  The PL566 watershed advisory team consisting of NPT, IDFG, DEQ, NMFS.  Will be used to establish ranking criteria.

Timeframe:  January 2003 for FY02, and March for subsequent years

Task B. Complete initial site reviews and collect resource data.

Methodology: Visit project sites and complete inventory data for approved project applications. Site inventory will follow NRCS FOTG procedures and methods.

Timeframe:  May 2003 for FY02, July for subsequent years

Task C. Develop conservation plans, which identify site specific BMPs to address fish habitat needs.

Methodology: Follow NRCS FOTG procedures. All plans will be developed using ArcView software and NRCS developed Customer Service Toolkit software (specialized software for conservation plan development).  Obtain landowner signatures and plan approval.

Timeframe:  September 2003

Task D. Design identified BMPs.

Methodology: Follow NRCS FOTG procedures and specifications.  NRCS engineers will approve all Job Class III and above project designs.

Timeframe:  December of each fiscal year

Task E. NEPA, SHIPO, and other regulatory compliance.

Methodology: Follow BPA, NRCS, and Idaho state regulations involving regulatory compliance.  Each project will be approved.  NMFS has reviewed and provided comment on the Lapwai PL566 watershed plan.  All conservation plans will follow this overall watershed plan.  Site specific consultation is needed for BMPs installed along, in, or near the stream.

Timeframe:  December of each year

Objective 4.  Supervise and inspect BMP installation.

Task A. Revise the existing contractor list and prepare contractor agreements

Methodology: Advertise the contractor list and add additional contractors as needed.  Modify existing contractor agreements used for the NPSWCD’s BPA proposal number 199901500 for specific needs in the Lapwai Creek watershed.

Timeframe:  on-going

Task B. Install and inspect BMPs.

Methodology: Layout projects, meet with landowners and contractors, and complete construction inspection for all installed BMPs.  All BMPs will be designed and constructed following NRCS FOTG standards and specifications.  Construction inspection will follow NRCS protocol.

Timeframe:  On-going

Task C.  Implement noxious weed control BMPs.

Methodology: Using Orofino correctional institute labor through an agreement with the NPSWCD, mow, hand-pull, and spray noxious weeds in identified critical areas. Release bio-control agents at identified locations.  Cooperative effort is with the Nez Perce Tribe Bio-control center.  The NPSWCD will obtain landowner permission.  The NPT-BioControl center will release the insects and monitor their survival through a subcontract.

Objective 5.  Complete interagency coordination activities.

Task A.  Conduct interagency coordination meeting.

Methodology: Using the Clearwater Focus watershed coordinators, conduct an interagency coordination meeting to share information on specific watershed activities.  This meeting will be held at least once per year during the project lifespan to ensure all parties are aware of each entities’ activities.

Timeframe:  on-going

Task B.  Develop a web-based information sharing process for Lapwai watershed activities.

Methodology: Develop and maintain a web page describing Lapwai Creek resource status and fish habitat related activities.  The web page will be housed on the Idaho NRCS web page.  NPSWCD staff will develop and update the Lapwai Creek web page on a quarterly basis.  Information from the interagency meeting will be placed on this web page.

Timeframe:  on-going

Objective 6.  Coordinate with the Nez Perce Tribe Fisheries Watershed Program (NPTFWP) to complete culvert inventory, restore 15 miles of anadromous fish habitat, and complete topographic surveys.

During BPA project proposal development the NPSWCD agreed to complete the following tasks for the NPTFWP proposal number 199901700.  Although both NPSWCD and NPTFWP proposals are separate and distinct they work in conjunction to treat resource needs identified in two watershed assessments. In addition the tasks have been divided so that there is not a duplication of fund requests from BPA.

Task A.  Coordinate landowner access agreements in order for the NPTFWP to complete culvert inventories on private land.

Methodology:  The NPSWCD will distribute a mass mailing to all landowners within the watershed informing them of the culvert inventory and asking for their participation.  Personal contacts will be made where appropriate.

Timeframe:  August 2002

Task B. Complete cultural resource surveys and topographic surveys for 10 BMP projects focusing on tribal lands.

Methodology: Through a mutual agreement, the NPTFWP will complete topographic surveys on 10 BMP projects within the Lapwai watershed.  The NPSWCD will coordinate with the NRCS and NPT-Land Services to select and design BMPs on tribal lands. Topographic survey data is needed to complete design work.   Cultural resource surveys will be used to ensure NEPA and SHPA compliance.

Timeframe:  on-going

Task C. Remove bridge barrier preventing fish passage along 15 miles of Lapwai Creek.

Methodology: The NPSWCD will coordinate with the NRCS and NPTFWP to obtain landowner permission and permits for bridge replacement and restoration of riparian areas.  NRCS FOTG standards and specifications will be used for project implementation.

Timeframe:  on-going

Objective 7.  Provide public education and technology transfer in order to increase the public awareness of resource problems and solutions.

Task A.  Conduct two noxious weed educational workshops for watershed landowners.

Methodology:   Coordinate with the Nez Perce Tribe Bio-control Center and the Clearwater Basin Weed Advisory Committee to conduct the workshop.  Inform landowners by newsletters, newspaper, and newsletter advertisements.  Based on high landowner interest, we estimate 50 landowners will receive direct educational benefits.

Timeframe:  June 2003

Task B.  Conduct a water quality and fisheries habitat workshop.

Methodology: Bob Mahler and Extension service.

Timeframe:  February 2003

Task C.  Publish 2 newsletters per year.

Methodology:  The NPSWCD will develop and distribute newsletters.

Timeframe:  On-going

Task D.  Technology transfer tour.

Methodology: Following NRCS social Science protocol for conducting watershed tours, the NPSWCD will advertise a project results tour.  The tour will show implemented BMPs to address fish habitat.  The NPSWCD will arrange transportation, speakers, and obtain all agreements to conduct the tour.

Timeframe:  April 2004

Task E.  Meet one-on-one with landowners in the watershed.

Methodology:   Meet with landowners on their property to discuss project goals, fish habitat resource needs, and discuss opportunities for habitat improvement on their land.  The NPSWCD staff has been using this method of landowner education for over 60 years and has established a trust relationship with landowners in the watershed.

Timeframe:  June 2003

Objective 8.  Complete BMP effectiveness on selected BMPs.

Task A.  Collect site specific BMP effectiveness data relating to sediment reductions, stream temperature, riparian restoration, erosion control, and stream morphology changes as appropriate.

Methodology:  Using NRCS FOTG protocols evaluate the effectiveness of implemented BMPs in improving fisheries habitat.  Data collection will occur annually on selected sites.  Representative BMPs will be selected after installation.

Timeframe:  On-going

Objective 9.  Monitor stream temperature within the Lapwai Creek watershed.

Task A.  Collect stream temperature data.

Methodology: Deploy HOBO stream temperature data loggers at 6 locations within the Lapwai Creek watershed.  Location selection and deployment will follow Idaho Department of Environmental Quality Protocols.

Timeframe:  on-going

Task B.  Compile stream temperature data and distribute report.

Methodology: Compile and summarize data using approved statistical analysis methods.  Distribute the report to watershed partners and post on Lapwai Creek web page.

Timeframe:  on-going

Objective 10.  Complete required project administration.

Task A.  Complete quarterly and end of year project status reports and financial report.

Methodology: Following BPA protocol complete required progress reports.

Timeframe:  Quarterly during project life.

g. Facilities and equipment

Activities for this project will be based out of the Nez Perce Soil and Water Conservation District office in Lewiston, Idaho.  Adequate office space and field survey equipment exists to complete identified project tasks.  However, the following items are needed to complete the tasks outlined in this proposal;

- GPS unit

- Lap Top Computer

- ArcView Software Extensions for 3-D mapper and spatial analyst

- GIS computer upgrade (additional harddrive storage)

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Fuller, R.K., P.A. Kucera and D.B. Johnson. Synopsis of Three Years of Stream Inventory on the Nez Perce Reservation. Final report submitted to Bonneville Power Administration. 1986. | n |
| Nez Perce Soil and Water Conservation District. Nez Perce Soil and Water Conservation District Resource Conservation Plan. December 2000. | n |
| Kucera, P.A., D.B. Johnson. A Biological and Physical Inventory of the Streams within the Nez Perce Reservation. 1986. | n |
| Kucera, P.A., J.H. Johnson, and M.A. Bear. A Biological and Physical Inventory of the Streams within the Nez Perce Reservation. 1983. | n |
| Nez Perce Soil and Water Conservation District. Confined Animal Feeding Operations Inventory and Analysis. 1998. | n |
| Nez Perce Tribe and Idaho Fish and Game. Salmon and Steelhead Production Plan. 1990. | n |
| USDA, Soil Conservation Service, SCS State Office, Boise, Idaho. Salmon Recovery Initiative. 1990. | n |
| USDA, Natural Resources Conservation Service. Field Office Technical Guide. 1999. | n |
| USDA – Natural Resources Conservation Service. Stream Visual Assessment Protocol. National Water and Climate Control Center Technical Note 1999-1. December 1998. | n |
| USDA – Natural Resources Conservation Service. The Practical Streambank Bioengineering Guide. May 1998. | n |
| USDA – Natural Resources Conservation Service. The Practical Streambank Bioengineering Guide. May 1998. | n |
| USDA – Natural Resources Conservation Service. The Practical Streambank Bioengineering Guide. May 1998. | n |
| USDA-Natural Resources Conservation Service. Stream Corridor Restoration Principles Processes and Practices. October 1998. | n |
| Espinosa. Biological Assessment on the effects of Lapwai Creek Restoration on the ESA Listed Snake River Fall Chinook Salmon and the Proposed for listing summer steelhead trout (Draft). 1997. | n |

# Section 10 of 10. Key personnel

Name:  Lynn Rasmussen

Title:  District Conservationist

Agency: Natural Resources Conservation Service

Hours:  FTE

Project Duties: Technical assistance to ensure conservation planning standards and specifications are followed.  Project coordination to eliminate duplication of efforts and maximize cost-share opportunities through NRCS administrated conservation programs.

Current Responsibilities: Responsible for managing NRCS programs in Nez Perce County, liaison with the Nez Perce Tribe, Contracting officer for PL566 program, watershed and area-wide planning, coordination with state, tribe and local governments on priority conservation issues, supervise and train staff, develop and design conservation BMPs.

Education: 	B.S. Crop Science, University of Idaho

Range, chemistry credits, New Mexico State University

M.S. Soils, University of Idaho

Relevant Training:

NRCS Area-wide planning, hydrology, stream morphology, water quality indicators guide, stream corridor restoration, conservation practice engineering design, construction inspection, nutrient management, bio-engineering applications, NEPA and ESA documentation, soil physics, stream visual assessment evaluation, BMP effectiveness evaluation, statistics, conservation program management, personnel management, locally led conservation and public involvement, conservation salesmanship, project management

Previous Employment:

- October 1995 – Present	Natural Resources Conservation Service

District Conservationist

- August 1993-September 1995	Natural Resources Conservation Service/Watershed

Enhancement Team

Resource Conservationist

- July 1990 – July 1993	Natural Resources Conservation Service

Soil Conservationist, St. Maries Field Office

- June 1988 – June 1990	Natural Resources Conservation Service

Soil Conservationist, Moscow field office

June 1986-May 1988	University of Idaho

Research Assistant

Expertise: water quality planning, watershed planning, erosion calculation and analysis, conservation practices design

Relevant Job Completions: (5 max) – 1)  Developed, coordinated and principle author on the Big Canyon Creek Environmental Assessment.  2)  Conducted a 5 year BMP effectiveness study evaluating the erosion reduction from grass waterways and sediment control structures. 3)  Responsible for resource inventory collection, data analysis, alternative development, NEPA compliance for the Lapwai Creek PL566 watershed project. 4)  Serve as the NRCS liaison to the Nez Perce Tribe.  5)  Completed the inventory and analysis for watershed resource assessments on Cottonwood Creek, Hatwai Creek, and Lindsay Creek.

Name:  Sue Izard

Title:  Outreach Coordinator

Agency: Nez Perce Soil and Water Conservation District

Hours: FTE

Education:  B.S. Zoology, M.ed. Science Education,

M.S.Resource Recreation & Tourism (expected 1/02)

Current Responsibilities:  Technical report editing;  report layout and design;  general publication layout/design;  text writing including newsletters, legislative briefings, and brochures; public event display development, assisting with major event coordination/ organization, newsletter production and distribution processes, grant writing, volunteer recruitment/supervision, customer service.

Relevant Trainings:  Soil Quality (NRCS 6/01), Home A*SYST program (4/01), Grant Writing (9/00), Forest Management (8/00), BioControl (7/00).

Previous Employment:

Jul 2000 -  Present, Outreach Coordinator, Nez Perce SWCD, ID

Jan 2000-  June 2000, Curriculum Designer, Idaho Water Resources Research Institute,  Moscow, ID

Mar 2000- May 2000, Tour Guide (contractor) Dworshak Dam, Ahsahka, ID

Jun 2000-  Dec 2000, Park Ranger, Dworshak Dam and Reservoir, Ahsahka, ID

Jan 2000-  June 2000, Environmental Educator (Internship), Disney World, Orlando, FL

Jun 1999-  Aug 1999, Interpretive Ranger, MT Saint Helen’s Nat’l Volcanic Mnmt, WA

May 1998- Aug 1998, Island Naturalist, Stan Stephens’ Cruises, Valdez, AK

Sep 1996-  June 1998, Instructional Aid (p/t), University of Idaho, Moscow, ID

Mar 1994- June 1996, Secondary Science Teacher, Buffalo Public Schools, Buffalo, NY

Jun-Aug   1995, 1996, Naturalist, Tifft Nature Preserve, Buffalo, NY

Sept 1993-Mar 1994, Zoo Science Liaison, Buffalo Zoological Gardens, Buffalo, NY

May 1993-Aug 1993, Seasonal Naturalist, Hunting Island State Park, St Helena, SC

Apr 1991-July 1991, Peace Corps Trainer, Univ of South Carolina, McClellanville, SC

Jun 1990- Aug 1990, Trips Counselor, Carrie Murray Outdoor Ed Center, Baltimore, MD

Jul  1987- Nov 1989, Peace Corps Volunter/Inland Fisheries Extension Agent,  Sierra

Leone, West Africa

Jun-Aug 1981-83, Camp Counselor, Goshen Scout Camps, BSA, Goshen, VA

Expertise: Ms. Izard’s background is in education and communication, with specific emphasis on natural resource education. This includes topics such as zoology, ecology, geology, marine ecology, fisheries, parks and recreation, and youth leadership.

Relevant Job Completions: 1) Extensive revision of District Five Year Plan;  2) Draft Outreach plan 3) Public Outreach Grant  4) Soil Quality Grant (obtained) 5) Instruction and pre-event coordination activities for two day youth education program 6)Two technical reports (in progress).

Name: Michael Lattig

Title: Resource Conservationist

Agency: Nez Perce Soil and Water Conservation District

Hours:  FTE

# Education:  B.S. Environmental Studies, The Evergreen State College, WA, 1998

Current Responsibilities: Work with agricultural and rural landowners to promote conservation of natural resources.  Administer contracts for the Water Quality Program for Agriculture in the Big Canyon Creek watershed.  Inventory landowner resources to develop a comprehensive conservation plan that meets NRCS resource management system criteria. Develop contracts based on conservation plans and implement best management practices to improve water quality and mitigate other resource concerns.

Relevant Trainings:

(  Plant Materials Training (NRCS 7/01)

(  Nutrient Management Training (NRCS 1/01)

(  Confined Animal Feeding Operation Training, Asotin County (10/00)

(  Wetland Delineation and Management, Richard Chinn Environmental Training (1/00)

(  Principles of Conservation planning

Duties on project: Work with agricultural and rural landowners to address resource concerns.  Provide technical assistance to implement resource management practices that will improve water quality and wildlife habitat.  Inventory resources and prioritize projects.  Participate in monitoring best management practices to determine their efficacy.

Previous Employment:

( July 2000-Present, Resource Conservationist, Nez Perce SWCD, ID

( November 1999- April 2000, Bioengineering Technician, Nez Perce SWCD, ID

( June 1998- October 1999, Biological Technician USFS, Blue River Ranger District, OR

Expertise: Mr. Lattig’s background is botany and forest ecology.  His experience includes vegetation monitoring and assessment; selection and installation of native plant materials for riparian restoration projects; conservation planning; wetland delineation; and native plant propagation.

Relevant Job Completions: 1) Inventoried and developed conservation plans for 3000 acres in the Big Canyon Creek watershed; 2) developed contracts/conservation plans for the Continuous Conservation Reserve Program (CCRP); 3) planted and assisted with design of riparian restoration for the Wapshilla Creek Emergency Watershed Program; and 4) assisted the NRCS with the implementation of the Peck Mitigation Project.

Name:  Deborah Koziol

Title:  Resource Conservationist

Agency:  Nez Perce Soil and Water Conservation District

Hours:  FTE

Project Duties: Project manager for all proposal activities.  Duties would remain the same as current project responsibilites, but over a larger project area.

Current Responsibilities:  Project manager for NPSWCD’s BPA project number 199901500. Responsible for landowner field inventories, contract writing, surveying, BMP designing, construction inpector, contract administration, BMP effectiveness monitoring, report writing, assist in stream surveying, supervise NPSWCD BPA field project crews.

Education:   B.S. Wildlife Biology, B.S. Wildland Management;

University of Idaho, Moscow, Idaho. 1992.

Relevant Training:

- Field Inventory Processes

- Macroinvertabrate and Water Quality Indicators

- Principles of Conservation Planning

- Wetland and Riparian Ecology

- RUSLE Uses in Agronomic

- Poplar Vegetation as an Alternative Crop

- Chemical Pesticide Consultant Training

- Pond Survey, Design, and Construction

- ArcView and GIS Field Application Training.

- Pond Survey, Design, and Construction

- Agriculture Economics

- Nutrient Cycling

- Nutrient Management

- Road Inventory Analysis

- Hydrology

- Cultural Resources

- Conservation Compliance

- Soil Quality Test Kit as a Field Tool

- PLGR training (GPS)

Employment:

- Nez Perce Soil and Water Conservation District.

Resource Conservationist; October 1999-present.

- Sublette County Weed and Pest District.  Assistant Supervisor. April 1996-October 1999.

Assisted with biocontrol programs. Identified, mapped, and controlled noxious weeds.  Completed long term contracting duties with federal, state, county and private landowners. Trained and supervised temporary staff.

- Wyoming Game and Fish Department.  Assistant State Spawning Specialist.  March 1994-November 1994.  Captured and spawned various species of wild broodstocks throughout the state.  Completed gill netting and electroshock fish inventories.  Assisted hatchery spawning.

- University of Idaho; Fish and Wildlife Department; FDA Drug Registration Project for Erythromycin to Control Bacterial Kidney Disease in Chinook Salmon. Laboratory Technician.  August 1990- March 1994.  Performed various specific analytical analysis.  Completed behavioral study on adult chinook in lab.  Assisted with wet lab operations.

Expertise:   Field application experience with fish habitat restoration, wildlife habitat enhancement, noxious weed control, and BMP design and construction.

Relevant Job Completions:

- Completed riparian and stream health inventory on Big Canyon Creek (1993).  2.)  Developed a conservation education curriculum for use at an environmental awareness program. 3.) First field office person in Idaho to receive nutrient management planner certification. 4.)  Received NRCS certification job approval authority for planning and designing BMPs. 5.)  NRCS certified conservation planner.