# Bonneville Power Administration

# FY 2003 Provincial Project Review

# PART 2. Narrative

Project ID:	29019

Title:	Characterize and Assess Wildlife-Habitat Types and Stuctural Conditions for the Okanogan sub-basin

# Section 9 of 10. Project description

a. Abstract

As ecological assessments of the Columbia River Basin step down in geographic scale to the sub-basin level, the need for fine-scale wildlife habitat depiction and assessment rises markedly. The Northwest Habitat Institute, working with the Northwest Power Planning Council’s Framework Process, developed 32 wildlife-habitat types and an associated wildlife habitat relationships data set to depict the current conditions of the Columbia River Basin.  We are proposing that the same mapping methodology and wildlife-habitat types be reviewed and mapped at a finer level of resolution (4 ha minimum mapping unit, (mmu) (10 acres)) for the Okanogan sub-basin. Current Landsat Thematic Mapper imagery will form the basis for map analysis and interpretation. Supporting this finer level of mapping will help resource managers, scientists, and policy makers make better decisions, predictions, plans, and models for the Okanogan sub-basin because these new wildlife-habitat maps will depict not only the composition of the habitat but also the current structural condition(s) of the habitat (this should directly support Goal #1 (p.19); Statement of Fish and Wildlife Needs – Wildlife Needs #1, #2, and #3 in the Spokane River Sub-basin Summary in Appendix 1).  For example, most all sub-basin plans call for assessing or identifying wildlife-habitat(s) for conservation purposes, like protection or enhancement (e.g. San Poil Subbasin Summary. Statement of Fish and Wildlife Needs, Point # 11 in Appendix 1).  To be successful with conservation actions, strategies, habitat restoration and mitigation projects having the ability to predict species associations, map wildlife-habitat types and structural conditions and putting that information into context with existing landscapes, will allow for a more comprehensive assessment of individual sub-basins and successful design .

Our proposal plans to:  (1) map wildlife-habitat types at a refined resolution (4 ha mmu), (2) map wildlife habitat structural conditions (4 ha mmu), (3) validating the mapping effort by field visits, and (4) evaluate the current conditions for wildlife using the wildlife-habitat relationships data set in conjunction with the wildlife-habitat types and structural conditions mapping information

b. Technical and/or scientific background

## Introduction

In the Pacific Northwest, there is a great demand for the development and dissemination of data-rich and verifiable information that links landscapes with current vegetation and structural conditions and also can identify wildlife associated with them.  For the past 5 years, the Northwest Habitat Institute (NHI) in collaboration with the Washington Departments of Fish and Wildlife and other natural resource agencies has been working to build public and private partnerships to address this need.  The results of these efforts have resulted in a book (Wildlife-Habitat Relationships in Oregon and Washington released in December 2000) that builds a common understanding about our wildlife resources. The findings in the book build upon existing regional works of Thomas (1979), Maser et al. (1984) and Brown (1985) and gives standard definitions for more than 300 habitat and environmental elements.  This cumulative effort resulted in the first statewide wildlife-habitat type maps of Oregon and Washington that now has been expanded to the entire Columbia River Basin.

Since sub-basin planning requires a finer resolution of mapping than what currently exists, we are proposing to map the wildlife-habitats types that have been identified in the Northwest Power Planning Council’s Framework Process and as defined in the book, Wildlife-Habitat Relationships in Oregon and Washington, at a fine resolution.  To do so, will allow fish and wildlife planners the ability to evaluate proposed actions in relationship with spatial patterns within a landscape context at an appropriate scale.  We would use LANDSAT Thematic Mapper (TM) imagery to map wildlife-habitats types at a resolution of about 4 ha (10 acres) as a minimum mapping unit (mmu).  The technical aspects of this approach are discussed below.  Additionally, once the LANDSAT map is created it will allow for monitoring future land changes, develop and evaluate conservation and land-use plans, and to predict the effects of different management scenarios on wildlife species and habitats.

The data that is created from this project will be utilized by multiple programs within the Colville Confederated Tribes Natural Resource Department.

Technical Background

The primary objective of this proposal is to create a fine-scale map of current conditions of wildlife-habitat types and structural conditions for the Okanogan sub-basin using LANDSAT (TM) imagery.  Steps required to develop a fine scale map are: a) develop and classify spectral groups that would most closely represent wildlife-habitats type, b) develop and classify spectral groups that would most closely represent structural conditions, and c) validate mapping classifications via field visits. We would ground truth the wildlife-habitat map so that each mapped class has an accuracy of 75% and an overall map accuracy of 80%.  The second objective of our proposal is to write a sub-basin assessment about wildlife as they relate to the wildlife-habitat types and structural conditions that have been mapped.  The Tasks to complete this objective would be to link composition and structural from the wildlife-habitat mapping effort to the wildlife-habitat relationships data sets so that wildlife species predictions can be made.

Determining Wildlife-Habitat Types and Structural Condition Classifications

In this step, we are using the results from O’Neil and Johnson (2000) cluster analysis to identify wildlife-habitat types for Oregon and Washington that has been expanded to the Columbia River Basin in the Framework Process.  Similarly, we would use the structural conditions for forests, rangelands, agriculture and urban areas that have are also identified in the book, Wildlife-Habitat Relationships in Oregon and Washington by O’Neil et al. 2000.

Developing and Verifying the LANDSAT Map

The mappable structural conditions identified in Task 1 will be used in conjunction with the wildlife habitat types to develop the mapping classification.  A step-by-step approach will be followed to process, classify, and label the imagery.  The first phase of work envisioned would be the initial image processing.  Each scene of TM imagery used will undergo a series of imagery previews for radiometric quality and subsequent processing tasks.  Specific tasks in this image-processing phase include:

- Writing each image to tape.  Imagery will be written to an 8 mm backup tape with copies stored off site.

- Radiometric quality preview.  This will provide analysts a preliminary determination of the extent and location of transmission errors and the impact of atmospheric conditions, especially clouds, haze, and smoke from slash burning has upon scene quality.  If there are substantial areas of degraded scene quality then other ancillary information like aerial photography, other imagery, and airborne videography will be substituted as the interpretive base for classification purposes.

- If multiple Images with different dates are used then an image-to-image registration will be done.  TM imagery scenes are geocoded and will need to be rectified to a UTM Zone coordinates that covers the sub-basin.  Each scene acquired will be registered directly to its companion scene.  Our initial imagery already has a ground control points file where we previously fine tuned registration discrepancies.  Co-registration of the images will use a nearest neighbor algorithm, and then be checked for positional accuracy.

- Partitioning imagery into the Okanogan sub-basin.  The TM imagery will be clipped slightly larger than the sub-basin.  Previous mapping efforts by the NHI have demonstrated that whenever classification takes place, the problem of signature extension from surrounding areas can compromise the classification effort.

- Construct derivative bands.  A normalized difference vegetation index (NDVI) and the first three principal component bands of a Tasseled Cap Transformation algorithm will be 	incorporated with TM bands 1-5 and 7 to form a 10 band image.  This image will be the basis of all subsequent spectral analysis.

- Conversion of TM imagery to TIFF format files.  A three band (bands 3, 4 and 5) image will 	be subset from the 10 band image and converted to a TIFF which then can be 	downloaded to a lap top computer for field reconnaissance purposes.

- Conversion of vector format ancillary data.  Coverage’s which assist the analyst during field verification, especially the road and stream networks will be converted to a DXF format and brought into the lap top computer to display over the TIFF images.

After the steps outlined above are completed, the image will be classified and then field verified.  These processes are described briefly below.

- Unsupervised classification of the 1999 scene.  Initial classification procedures start with a sufficiently large number of spectral clusters (generally between 100-150), to form mutually exclusive spectral signatures.  These signatures are then run through a maximum likelihood classifier to produce the initial spectral cluster map.

- Preliminary assignment of spectral class to vegetation class.  Linking spectral clusters to information classes is first done through an on-screen examination of the clusters overlaid on the image.  In many cases the information class is spectrally distinct enough that cluster labeling is very straightforward.  However, there will always be a number of spectral clusters that are indeterminable at this stage, as well as, information classes that do not readily lend themselves to an identification (like palustrine forest).  Which is the reason for the iterative process to determine spectral/information class relationships.

- Field verification of spectral-vegetative condition.  This process involves recording vegetation identity at known points within the image.   Basically this entails linking our GPS unit to the TIFF version of the TM scene through Field Notes software and recording field-training sites.  A database will be developed for the sub-basin using the Field Notes software that includes XY coordinates, the land cover class, and environmental variables that may be useful to the analyst in future processing iterations.  The database will be brought into ARC/INFO as a point location file and displayed over the various thematic classifications.  Other ancillary data, especially the NWI and stream network data will be available as vector files displayed over the TIFF to assist in cover type identification.

- Refinement-reclassification of spectral class to vegetative condition.  This step begins the process of windowing the scene into identifiable and unidentifiable, or problem spectral classes.  Once the analyst is confident of the relationship between spectral cluster and wildlife/habitat cover class that class is masked out of succeeding classification iterations.  Once the problem spectral classes are identified, separate classifications are performed where a class will be broken into many spectral classes and, if possible, those classes are related to probable land cover types and masked out.  Further refinement of spectral cluster/land cover type can be accomplished through the use of ancillary data as logical operators.   For example, deep shadows in mountainous terrain typically are confused with water signatures, by using a digital elevation model the analyst can overlay that spectral class on all slopes less than 1 % and quickly ascertain those areas which are to steep to pond water.

- Field verification of problem spectral-vegetation classes.  If the analyst cannot confidently relate spectral cluster to land cover class, another field visit will be necessary to uncover the spectral cluster identity.

- Editing the refined coverage.  As a last step in the classification phase the analyst will hand edit those areas, which are too obscure to classify by conventional image processing techniques.  Typically, these are the cloud, cloud shadow, or smoke obscured areas, and ancillary information will be used to help refine these areas.

- Accuracy assessment of 1999 scenes.  Accuracy assessment will follow the approach identified by Bruner and O'Neil (1998).   We do envision a stratified random design, weighted by a per-class basis, with the minimum number of sample points to achieve a

70% accuracy by class standard.

Biological/Recovery Justification:

Conservationists have advocated two approaches to counter the accelerating loss of biodiversity.  One operates in a crisis mode, rescuing species about to become extinct.  The other focuses on protecting communities of plants and animals not yet in serious jeopardy, but which are likely to be driven towards extinction with increased habitat loss.  These two complementary approaches have been described as "fine filter" and "coarse filter" strategies for maintaining biodiversity (Noss 1987).  Given the complex ways in which species interact with their ecosystem, proactive coarse filter strategies present a greater hope for maintaining large-scale biodiversity (Scott et al.  1993).  Coarse filter strategies depend on our ability to classify ecosystems and map species distributions.

Distinguishing and mapping wildlife habitats is an integral part of any conservation effort; thus the accuracy with which wildlife-habitat associations are determined can affect the extent and accuracy of conservation planning.  Conservation and management plans developed by natural resource agencies typically include wildlife-habitat associations in their assessment of biological diversity (Thomas 1979, Scott et al. 1993).  In doing so, these agencies often look to protect certain vegetation or habitat types in hopes that they will also protect the wildlife species associated with them. This premise implies that vegetation or habitat serves as a satisfactory indicator of the environmental variables that interact on a particular site (Specht 1975, Thomas 1979), and as such, assumes that plant communities can serve as adequate substitutes for ecosystems.  Thus, structural and composition characteristics of Oregon's vegetation are needed in order to depict its ecological function.

Our proposal will relate structural and composition characterization to wildlife-driven habitat optimization schemes, not a forest inventory driven classification and to examine any differences that may be related to scale.  Presently the Forest Service's attempt to produce wildlife habitat maps requires lumping the 39 size-structure classes into groups to represent various aggregated conditions.  This "bottom-up" approach of lumping of site specific variables into larger "generalist" conditions really was a departure from the more common "top-down" methodology of first breaking out the larger "generalist" cover types and then focusing on the more discreet conditions.  The only comparison to date of the two techniques for the northwest is reported in Cohen et al. (in press) where Pacific Meridian Resources' (Congalton et al. 1993) and the Wilderness Society, (Morrison et al. 1991) both mapped the extent of old growth for Forest Service lands west of the Cascades.  The amount of acres of old growth between the two studies differs tremendously.  Estimates of old growth for some forests appear to vary by over 100%.

The mapping effort proposed here will be vegetative (habitat) based and will include private and public lands.  As vegetative communities evolve, either through natural, or altered, successional processes, a large number of the structural and composition attributes change, including species mixture, basal area, plant density, and crown density.  Many of these vegetation changes are associated with habitat changes that, in turn, are key to assessing vertebrate diversity (Hof and Raphiel, 1993, Ruggiero et al., 1991).  Consequently, vegetation-mapping efforts that incorporate structural characteristics will increase the maps utility for species distribution, habitat analysis and planning.  Additionally, understanding the influence of scale will also contribute to our knowledge of how accurate a coarse versus fine filters approach to conservation planning really might be.

c. Rationale and significance to Regional Programs

The wildlife-habitat types (and structural conditions) that would be mapped are the same as those used in the Framework Process by the Northwest Power Planning Council.  The assessment that would be done would also use the wildlife-habitat relationship data set (also used in the Framework Process) to describe the current conditions within the Okanogan sub-basin.   The mapping, and hence assessment, would be done at a finer scale that could be aggregated (mapping wise) to basin level information. In doing so, this would help correct or modify the existing basin map(s) and also be in-step with a hierarchical (i.e. ecosystem-based management) approach.

d. Relationships to other projects

If a finer resolution of mapping available the project, Establishing Baseline Key Ecological Functions of Fish and Wildlife for Sub-Basin Planning [BPA project no. 2000-74-2], would depict with greater accuracy those areas where ecological functions are thought to have increased or decreased.  Hence, enhancement efforts could be more tightly focused.

e. Project history (for ongoing projects)

New Project (N/A)

f. Proposal objectives, tasks and methods

Objective 1- Task A and B.

Our proposal is for a fine resolution map that would at a 4 ha (MMUs).  Vegetation types less than the MMUs will be incorporated into appropriate polygons based on parameter input to the Merge program developed and written by the University of Montana to create minimum mapping units for vegetation.  We also will preserve the more heterogeneous (smaller pixel clusters) classification to examine the sources of spectral variability at a later date, or as funding allows.  To summaries the Tasks and Methods, as previously stated in the Technical Background section of this proposal, they are:

- Create unsupervised classifications for wildlife-habitat types and structure for the LANDSAT TM scenes that will encompass the entire Okanogan sub-basin.

- Examine spectral statistics produced for each pixel signature and determine suitability for inclusion in subsequent classifications. Pixel signature suitability will be a function of signature divergence and overlap. Divergent signatures are desirable because the more spectrally unique a signature is from other signatures the more likely they represent distinct sets of pixels and distinct classes. When signatures spectrally overlap, then several signatures represent similar pixels, which increases the probability of misclassification.

- The unsupervised classification has identified spectral classes and assigned pixels to those classes.  Ideally, each unique spectral class will represent a unique forest structure/vegetation type and one will simply determine the appropriate cover type label.  Problems arise when the information content (i.e. vegetation cover types) span several to many spectral classes.  To resolve conflicts between information content and spectral classes we will verify pixel cluster identity through ancillary data such as aerial photography and orthophotography.

- The polygon coverage will be edited to combine those polygons that may be spectrally, but not informational unique (i.e. heterogeneous mixes of shadowed and sunlit polygons within a consistent vegetation cover type).

Objective 1 – Task C

- Field-based ground truth will further clarify the identity of pixel clusters.  We will download imagery and unsupervised classifications onto a laptop computer for the field research.  Along with the raster image data we will overlay vector coverage of roads, land ownership, hydrology, and other ancillary data to provide location data that can be cross-referenced U.S. Geological Survey 1:100,000-scale maps.  The advantage of bringing interactive computer data to the field is that in many cases spectrally confused areas can be corrected through  "heads up" digitizing of the classification, or correcting label information.  Field site locations will also be digitized in spectrally confused situations and incorporated into a hybrid unsupervised-supervised set of signatures to classify the study area.

- Should certain land cover classes not meet acceptable accuracy standards (each mapped class must have an accuracy of 75% and a overall map accuracy of 80%), a second iteration of processing where the correctly identified polygons are masked out of the image will occur.

- The process of unsupervised classification, spectral editing, and polygon labeling for the "incorrect" image may go through several iterations before map accuracy standards are achieved.

Objective 2- Task A.

- Developed the necessary computer programs, subroutines, and queries to tie the Wildlife-Habitat Relationships data set with the LANDSAT mapping final products using ARC/INFO and a geographic information system.

- Conduct a wildlife evaluation based on the portions and amounts of wildlife-habitat types and structural conditions found within the Okanogan sub-basin.  Items specifically addresses will include but not limited to: a list of potential wildlife species and habitat associations occurring in the sub-basin; an assessment of the key ecological functions; an identification of wildlife species and habitats that are limiting within the sub-basin.

- Once this map has been created it will be available in digital and hard copy form.  The map will be accessible via the INTERNET along with a complete data dictionary and quality control information.

## Reporting

Quarterly reports will be written to depict the amount of progress being made and highlighting any significant issues.   NHI is an educational and scientific non-profit institute dedicated to developing and disseminating high-quality verifiable data.  Therefore, all products developed by the NHI, including those developed through this proposal will be posted at an interactive World Wide Web sites and disseminated through additional methods including books, CD-ROMs, maps, and tools that will facilitating the evaluation and conservation of biodiversity.  The NHI specializes in developing World Wide Web sites for both data dissemination (www.nwhi.org) and data collection. Our information is available to the general public but probably most useful to natural resource managers, land-use planners (city, county, and state), conservation groups, watershed councils, and students and educators at all educational levels

g. Facilities and equipment

NHI is a non-profit organization that rents a portion of a building at: 355 NW 7th in Corvallis, Oregon.  Our computer equipment that would be available to conduct this proposal is (at a minimum):  1 Sun Workstations, 3 PC computers, 1 laptop computer, GPS unit, HP 755 CM Plotter, scanner, and tape backup systems.  Available software that is specific to the grant needs is ESRI 's ARC/INFO and ERDAS's Imagine. The Colville Confederated Tribes, Resource Inventory & Analysis Program is a tribally funded organization that is stationed in Nespelem, WA. Our computer equipment that would be available to conduct this proposal is (at a minimum): 3 Windows NT workstations, 1 laptop computer, one Trimble GPS unit, one HP 1055CM plotter, one CalComp 810C Wide Scanner, and tape backup systems. Available software that is specific to the grant needs is ESRI’s ArcGIS and ERDAS’s Imagine. Finally, neither organization intends to purchase any equipment with the direct costs of this proposal, however, indirect costs may go to cover leases or maintenance of equipment.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |

Brown, E. R., technical editor.  1985.  Management of wildlife and fish habitats in forests of western Oregon and Washington (Volume 1 & 2).  U.S. Forest Service, Publication R6-F&WL-192-1985. Pacific Northwest Region, Portland, Oregon, USA.

Bruner, H., and T.A. O'Neil.   1998.  Assessing Vegetation Mapping Accuracy for the Willamette Valley, Oregon.   Oregon Department of Fish and Wildlife, Pittman-Robinson Report (under grant 87-R from U.S. Fish and Wildlife Service, Federal Aid Program).  Corvallis, OR  pp. 13.

Cohen,W.B., Spies, T.A., and Fiorella, M. (in press) Estimating the age and structure of forests in a multi-ownership landscape of western Oregon, USA. International Journal of Remote Sensing.

Congalton,R.G., Green, K. and Teply,J. (1993) Mapping old growth forests on National Forests and Park Lands in the Pacific Northwest from remotely sensed data.  Photogrammetric Engineering and Remote Sensing 59:529-535.

Hof, J.G. andf Raphiel, M.G. (1993).  Some mathematical programming techniques for optimizing imber age class distributions to meet multispecies wildlife population objectives.  Canadian J. of Forest Research 23:828-834.

Johnson, D. H. and T.A. O=Neil. 2000.  Wildlife-Habitat Relationships in Oregon and Washington.  Oregon State University Press. Corvallis, OR.

Maser. C.J., J. W. Thomas, and R. G. Anderson.  1984.  Wildlife habitats in managed rangelands-the Great Basins of southeastern Oregon.   U.S. Forest Service, Pacific Northwest Forest and Range and Experiment Station, General Technical Report PNW-172. Portland, Oregon, USA

Morrison, P.H. (1991) Ancient forests in the Pacific Northwest, The Wilderness Society, Washington, D.C.

Noss, R. F. 1987.  From plant communities to landscapes in conservation inventories: a look at The Nature Conservancy (USA). Biological Conservation 41: 11-37.

O’Neil, T. A., R. J. Steidl, W. D. Edge, and B. Csuti.  1995.  Using Wildlife Communities to Improve Vegetation Classification for Conserving Biodiversity.  Conservation Biology, Volume 9 No. 6, 1482-1491.

O=Neil, T.A., K.A. Bettinger, M. Vander Heyden, B.G. Marcot, T.K. Mellen, W. M. Vander Haegen, D.H. Johnson, P.J. Doran, L. Wunder, C. Barrett, and K. Boula.  2000.  Structural conditions and habitat elements of Oregon and Washington.  In D.H. Johnson and T.A. O=Neil (Manag. Dirs.) Wildlife-Habitat Relationships in Oregon and Washington.  Oregon State University Press. Corvallis, OR.

Ruggiero,L.F., Jones, L.L.C., and Aubry, K. (1991).  Plant and animal habitat associations in Douglas-fir forests of the Pacific Northwest: an overview, in Wildlife and Vegetation on unmanaged Douglas-fir forests.  USDA Forest Service, Gen. Tech. Rep. PNW-GTR-285, Portland,Or. pp447-462.

Scott, J., F. Davis, B. Csuti, R. Noss, B. Butterfield, C. Groves, H. Anderson, S. Caicco, F. D'Erchia, T. Edwards, Jr., J. Ulliman, and R. Wright.  1993.  Gap analysis: a geographic approach to protection of biological diversity.  Wildlife Monographs 123:1-41.

Sprecht, R.  1975.  The report and its recommendations.  Pages 11-21 in F. Fenner, editor.  A national system of ecological reserves in Australia.  Australian Academy  of Science, Report Numbe 19, Canberra.

Thomas, J.  1979.  Wildlife habitats in manged forests: the Blue Mountains of Oregon and Washington.  U.S.  Department of Agriculture, Forest Service, Agriculture Handbook No.  553, Washington, D.C.

# Section 10 of 10. Key personnel

Christen Kiilsgaard – Director of Remote Sensing, full-time employee of the Northwest Habitat Institute.

Charley Barrett – Senior Geographic Information System Analyst, full-time employee of the Northwest Habitat Institute.

Thomas O’Neil – Executive Director and Senior Wildlife Ecologist, full-time employee of the Northwest Habitat Institute.

Kelly Bettinger – Leader of Avian Research, part-time employee of the Northwest Habitat Institute.

Grant Timentwa – GIS Database Administrator, full-time employee of the Colville Confederated Tribes.

Richard Rooney – GIS Analyst, full-time employee of the Colville Confederated Tribes.

Yvonne Passmore – GIS Technician, full-time employee of the Colville Confederated Tribes.