# Bonneville Power Administration

# FY 2003-5 Provincial Project Review

# PART 2. Narrative

Project ID:	198906201

Title:	Fish and Wildlife Program Implementation

# Section 9 of 10. Project description

a. Abstract

The fish and wildlife agencies and tribes (managers), responsible for managing fish and wildlife resources in the U.S. portion of the Columbia River Basin, established the Columbia Basin Fish and Wildlife Authority (Authority) in 1987 to facilitate discussion among the fish and wildlife managers in a effort to find consensus, improve the quality of fish and wildlife decision-making, and to influence other regional decision-makers.  This proposal intends to continue the Authority’s core functions by helping the managers produce a variety of regionally important items.  These include draft annual start-of-year Program budgets, draft recommendations for within-year project changes, comments on Program amendments and other regional issues, and comments on projects in the rolling Provincial Review.  The managers also propose to continue to use the Authority to facilitate information exchange and their involvement in regional planning initiatives.  New tasks proposed here include using the Authority to compile information on the status and trends of fish and wildlife as a contribution to a Program “report card,” coordinate manager input to regional research and M&E activities, and facilitate a regional Habitat Evaluation Procedure team.

b. Technical and/or scientific background

In 1980, in response to growing concerns about the declining fish and wildlife populations and a predicted energy deficit, Congress passed the Pacific Northwest Power Planning and Conservation Act (Act).  The Act created the Northwest Power Planning Council (Council) and charged it with creating a program to

“…protect, mitigate, and enhance fish and wildlife…on the Columbia and its tributaries, affected by the development, and operation of [hydroelectric projects] while assuring the Pacific Northwest and adequate, efficient, economical, and reliable power supply…” [Section 4.(h)(5)].

The Act, in Section 4.(h)(10)(A), directed Bonneville Power Administration (BPA) to provide funding to implement the program.

The Act established the process by which the Council would create and amend the Fish and Wildlife Program and preserved the fish and wildlife agencies’ and tribes’ authorities.  The legislative history indicates that Congress was specifically concerned that the Council not become a “super fish and wildlife agency.”   The Act sets standards that Program measures must meet, including that they will –

“complement the existing and future activities of the Federal and region’s State fish and wildlife agencies and appropriate Indian tribes” [Section 4.(h)(6)(A)]; and,

“be consistent with the legal rights of appropriate Indian tribes in the region” [Section 4.(h)(6)(D)].

In reviewing amendments to the Program, “the Council, in consultation with appropriate entities, shall resolve …[any] inconsistency in the program giving due weight to the recommendations, expertise, and legal rights and responsibilities of the Federal and the region’s State fish and wildlife agencies and appropriate Indian tribes” [Section 4.(h)(7)].

Finally, the Act directs BPA to

“exercise such responsibilities [for operating the hydropower system]…to adequately protect, mitigate, and enhance fish and wildlife, including related spawning grounds and habitat, affected by such projects or facilities in a manner that provides equitable treatment for such fish and wildlife with other purposes for which such system and facilities are managed and operated” [Section 4.(h)(11)(A)].

Section 4.(h)(11)(B) directs BPA to consult with the fish and wildlife agencies and tribes “in carrying out the provisions of this paragraph [Section 4.(h)(11)(A)] and shall, to the greatest extent practicable, coordinate their actions.”

To ensure success, Section 4.(g)(3) of the Act states that, “…the Council and the [BPA] Administrator shall encourage the cooperation, participation, and assistance of appropriate Federal agencies, State entities,… and Indian tribes.” This section goes on to state that the Council and BPA can contract with the fish and wildlife agencies and tribes individually, “or through associations thereof,” to “provide technical assistance in establishing …fish and wildlife objectives.”

In other words, the Act set up what is sometimes referred to as the “three-legged stool” where the Council, BPA, and the fish and wildlife managers cooperatively implement the Program.  In this model, the Council is responsible for developing and amending the Program and to make final recommendations to BPA about which projects to fund under the Direct Fish and Wildlife Program in any given fiscal year. BPA is responsible for funding it.  And the Authority members are responsible for carrying it out.  Each of these “legs” has opinions regard the other “legs’” efforts.

The Council adopted the first Columbia River Basin Fish and Wildlife Program (Program) in 1982 and, with extensive public outreach efforts, amended it in 1984,1987, 1991-93, 1994, 1995, and 2000.  The goal of the Program is “a healthy Columbia Basin, one that supports both human settlement and the long-term sustainability of native fish and wildlife species in native habitats where possible, while recognizing that where impacts have irrevocably changed the ecosystem, we must protect and enhance the ecosystem that remains.”  Throughout its evolution, the Program has recognized and institutionalized the central and unique role of the managers. The Program now consists of a large number of measures that translate into approximately 300 individual projects that protect, mitigate and/or enhance fish/wildlife in the Columbia River Basin.  A 1996 amendment to the Act established an Independent Scientific Review Panel (ISRP), under the auspices of the Council, to evaluate projects proposed for funding.

To support its leg of the stool, BPA executes, funds and administers the contracts which support the projects in the Program.  Under the previous Memorandum of Agreement (MOA) spanning fiscal years 1996-2001, BPA provided up to $252 million dollars annually to cover three cost categories; 1) $127 million to support the Program (Direct Program); 2) $40 million to reimburse Congress for appropriations to fund the Corps of Engineers, US Fish and Wildlife Service, and Bureau of Reclamation fish and wildlife activities (Reimbursable Program); and, 3)  $85 million to fund Corps improvements to the hydro-power system for fish and wildlife purposes (Capital Investment Program).  Currently, there is not a comparable agreement with BPA, but BPA has indicated that it will make up to $186 million available annually to fund projects implementing the Fish and Wildlife Program and to meet its responsibilities under the Endangered Species Act.

The managers’ leg of the stool has evolved since 1980. The managers are unique in the basin in that they have responsibility (based on federal and state statutes, treaties, Executive Orders and court actions) for managing the fish and wildlife resources of the Columbia River Basin. By law, the managers must oversee the fish and wildlife mitigation activities outlined in the Program.  In the early years of the Program, the managers participated as a disparate collection of individual organizations. As the program gained momentum and grew more complex, the managers recognized the need to coordinate their activities and speak with one voice.

In 1987, the following 19 organizations established, the Columbia Basin Fish & Wildlife Authority (Authority) by charter and became Members of it: Burns-Paiute Tribe, Coeur d’Alene Tribe, Confederated Salish and Kootenai Tribes, Confederated Tribes and Bands of the Yakama Indian Nation, Colville Confederated Tribes, Confederated Tribes of the Umatilla Indian Reservation, Confederated Tribes of the Warm Springs Indian Reservation of Oregon, Idaho Department of Fish and Game, Kalispel Indian Tribe, Kootenai Tribe of Idaho, Montana Department of Fish Wildlife and Parks, National Marine Fisheries Service, Nez Perce Tribe, Oregon Department of Fish and Wildlife, Shoshone-Bannock Tribe, Shoshone-Paiute Tribe, Spokane Tribe, U.S. Fish and Wildlife Service, and Washington Department of Fish and Wildlife.

The Authority was  established to help the federal and state fish and wildlife agencies and the tribes coordinate their efforts, develop Program amendment recommendations, respond to regional fish and wildlife issues, and help them balance the demands on the hydropower system such that fish and wildlife are treated equitably with the other uses of the system.

Authority is a forum for the managers (listed above) to exchange information and develop unified positions on issues affecting fish (both anadromous and resident) and wildlife in the Columbia River Basin.  The mission of the Authority is:

To facilitate discussion among the fish and wildlife managers in a effort to find consensus, improve the quality of fish and wildlife decision-making, and to influence other regional decision-makers.

All actions and decisions supported by Authority are developed through a consensus process in order to protect all members’ sovereignty.

Although the Authority is highly effective in building consensus, it is not a legally recognized entity. Thus in 1993, the managers formed the Columbia Basin Fish and Wildlife Foundation (Foundation) to serve as the administrative-fiscal arm of the Authority. The Foundation (a non-profit corporation legally registered with the State of Oregon under the Oregon Nonprofit Corporation Act) manages projects approved by the managers. This proposal describes those projects in more detail.

The members of the Authority function in a hierarchical system having three main levels: caucuses and ad hoc committees, Members Management Group (MMG), and Members. At the working level, the Authority uses the Anadromous Fish, Resident Fish and Wildlife committees to develop draft policies, evaluate proposals/projects, prepare draft reports specific to their functional area. The committees, consisting of senior program managers from each member organization, meet once per month (or as needed) in person and/or via teleconference.  Each committee (including the MMG) has a staff coordinator/technical analyst (and associated administrative support) that are responsible for facilitating all activities and ensuring that work products are completed on time and within budget. When completed, the committees forward draft products to the MMG for consideration.  The MMG and the Members operate by consensus where only products or policies supported by all 19 members go forward.

The MMG provides the link between the committees and the Members. At monthly meetings, representatives of the Members (senior policy staff) review draft policies, products and budgets and either refer the issue back to the committees for further discussion or recommend approval by the full membership.

At the highest level, the Members (Directors/Chairs of member organizations) meet as needed (but not less than annually) to develop policies and approve work products. When meetings are not timely, the Members approve products (letters, comments, reports, and budgets) through the Consent Mail process in which they have five days to respond. After the Members approve policies and products, they (or designated Authority staff) present them (orally and in writing) to the Council or other appropriate regional entities for consideration.

The Fish Passage Advisory Committee (FPAC), a standing committee of Authority, works closely with the Fish Passage Center to review technical aspects of mainstem issues and proposals.

To keep the regional machine running, Authority staff provides a variety of critical but invisible services such as meeting coordination and logistics, travel arrangements and expense account processing, document production, record keeping, note taking, facilitation, etc.

The Authority managers and staff also work closely with the BPA, the Council, and other bodies in a number of different settings. For example, monthly Coordination Meetings provide a forum where the four parties define significant policy questions and discuss concerns arising from program implementation.  Authority members and staff regularly attend the Quarterly Review where BPA presents the most current information about program and project budgets on a quarterly basis.

c. Rationale and significance to Regional Programs

The Act, as discussed above, defines a specific role for the fish and wildlife agencies and tribes in amending the Fish and Wildlife Program.  The Act also recognizes the fish and wildlife managers special expertise and directs BPA and the Council to pay it particular respect.  The fish and wildlife agencies and tribes have chosen to coordinate their efforts under the Act through the Columbia Basin Fish and Wildlife Authority, covered by this proposal (in Objectives 4, 5, and 7 specifically).

The Draft Regional Support Program Summary (NWPPC, 2000) outlines twelve “elements” or projects that provide support for regional activities.  The Authority efforts are integral to the implementation of eight of them as described below.

A)  Columbia River Basin Fish and Wildlife Program (p.3) – the managers have chosen to coordinate their implementation of the Program through the Authority.  This proposal outlines the managers’ efforts to:

- Review and recommend projects to implement the Program (Objective 1);

- Assist the Council by compiling a draft annual budget for the Program (Objective 2);

- Provide recommendations on any within-year changes to projects (Objective 3);

- Make recommendations for Program amendments (Objective 4);

- Comment on Program issues (Objective 5);

- Help the managers provide their expertise (Objective 7);

- Coordinate managers’ assessment of subbasin plans (Objective 8);

- Coordinate managers’ involvement in regional research, monitoring and evaluation activities (Objective 9).

A critical issue identified as a future need in this section of the Regional Support Program Summary is providing adequate funds to implement the Program in a timely fashion.  Under Objective 5, the Authority proposes to provide the managers’ recommendations for adequate budgets to ensure “equitable treatment” for fish and wildlife.

B)  Independent Scientific Advisory Board (p.4) – The Authority has administered the ISAB contracts in an efficient manner for seven years.  This proposal will maintain the structure to continue to that service.

C)  Independent Scientific Review Panel (p.6) – The ISRP is mandated to review projects relative to defined criteria.  The rolling provincial review process, successfully facilitated by the Authority for the Council, is the mechanism by which the ISRP becomes acquainted with the individual projects and which provides the larger context for the projects.  The managers propose to continue this service through the Authority (Objective 1).  By continuing to coordinate this project review with the other reviews in the basin, the managers intend to minimize the procedural burdens to project sponsors as identified in the Regional Support Program Summary.

D)  Subbasin Planning (p. 8) – The fish and wildlife managers are expected to provide essential contributions to the Council’s subbasin planning process.  The managers have elected to coordinate their input through the Authority (Objectives 1 and 7).  The managers also propose to assist the Council in the subbasin planning process by offering contract administration services (Objective 6).

E)  Columbia Basin Fish and Wildlife Authority (p. 10) – The managers propose to continue coordinating their efforts through the Authority.  The Regional Support Program Summary focuses on the needed future actions of  the Authority continuing to facilitate the rolling provincial review (proposed to be done in Objective 1) and coordinating the fish and wildlife managers’ technical and policy input to: the Council development of a regional research, monitoring, and evaluation plan; NMFS and USFWS technical recovery planning; BPA implementation of the Five-Year Implementation Plan (proposed in Objectives 5 and 7).

d. Relationships to other projects

The Authority provides specific services for the following projects:

1.  Project 9403300 Fish Passage Center is funded through a separate contract with Pacific States Marine Fisheries Commission and operates under the policy oversight of the Fish Passage Center Board of Directors. The Authority’s Executive Director provides day-to-day supervision of the Fish Passage Manager.

2. CBFWA provides contract administration and administrative support to Project 9600500 ISAB (Independent Scientific Advisory Board).

The Authority is a focal point for the fish and wildlife managers to exchange information, develop unified positions, and create the work products outlined in the objectives in this proposal. In this capacity, the Authority staff provides coordination, logistical, and technical support for all of the project sponsors who respond to BPA’s project solicitations. In addition, the fish and wildlife managers coordinate policy development, program budgets, and within-year adjustments to the work plan through the Authority. Whenever a budget or overarching policy issue comes up, the Council has relied upon the Authority to make a consensus-based recommendation.

e. Project history (for ongoing projects)

This project began in 1989 as project number  8906200, titled CBFWA Coordination Grant.  At that time the major activities involved the cooperative coordination and facilitation of the fish and wildlife managers’ activities on regional issues.  Over the years the project has picked up (and dropped) other tasks beyond these “core” functions, including: developing the Integrated System Plan; supporting the Fish Screen Oversight Committee and the Integrated Hatchery Operations Team; managing the Northern Pikeminnow (formerly known as “Squawfish”) Management Program; organizing the Implementation Planning Process; and coordinating the Multi-Year Implementation Plan.

In 1994, the Authority took over responsibility from BPA for compiling the Draft Annual Implementation Work Plan (DAIWP), guiding regional implementation of the Fish and Wildlife Program.  Its structure and content has evolved to meet the Council’s specific needs and the region’s general needs.  In FY 1996, BPA changed the Authority contract from a service-based one to one delivering documents or products.  In FY 1998, the managers outlined a set of objectives and tasks for Authority that were reflected in the FY 1999 project Statement of Work.  This proposal continues the product-based approach.

f. Proposal objectives, tasks and methods

In the Operations and Maintenance phase, this proposal intends to continue the operation of the Columbia Basin Fish and Wildlife Authority (Objectives 1 through 7) and in the Monitoring and Evaluation phase, to launch some new efforts to strengthen the Authority’s support for the Council’s Program evaluation.

Objective 1.  Produce a draft compilation of project proposals and review comments from the second round of the Rolling Provincial review.

The first round of the Council’s rolling Provincial Review will be completed this summer.  Those provinces reviewed first (Gorge, Intermountain and Mountain Columbia) will need updating for FY 2004, and the other provinces in subsequent years.

The Authority proposes to continue its role of facilitating the ISRP and public review of proposals to implement the Council’s Program.  To accomplish this objective, the Authority, working closely with Council staff, proposes to organize and facilitate the ISRP, fish and wildlife, and public review, as we have done for the first provincial reviews (Tasks 1.1, 1.2, 1.3).  The Authority proposes to evaluate groups of projects recommended in each province to ascertain the extent to which they meet the F&W Program goals and objectives (Task 1.4).  The Authority staff will facilitate the compilation of plans (Task 1.5) for the various programs that comprise the Mainstem and Systemwide provinces. Finally, the Authority, working closely with Council staff, will compile the results of these provincial reviews as input to the Council decision making process (task 1.6).

Task 1.1  Arrange, facilitate, and record actions of meetings.

Task 1.2  Make appropriate materials available to project sponsors and the public.

Task 1.3  Organize proposal presentations and site visits.

Task 1.4  Coordinate fish and wildlife manager assessment of the adequacy of provincial suites of proposals to address F&W Program goals and objectives.

Task 1.5  Facilitate development of Program Plans for the Mainstem/Systemwide province.

Task 1.6  Work with NWPPC staff to draft a compilation of the results of the second provincial reviews.

Objective 2.  Produce a draft compilation of up-to-date project budgets for the annual Start-of-Year Program budget.

In the summer of each year, the Council assembles a list of projects to form the Start-of-Year (SOY) budget for the upcoming fiscal year.  While these projects have been reviewed and selected in the rolling provincial review process, the status of their implementation and budgets need to be re-examined in detail, before the Council recommends the specific budget amounts to Bonneville for funding.  An important part of this specific review for capital projects is comparing their funding needs in an annually updated capital plan.

The Authority proposes to assist the Council in developing the annual SOY by coordinating the fish and wildlife managers’ review and “scrubbing” of project budgets (Task 2.1) and updating a regional capital budget (Task 2.3).  The Authority proposes to maintain data on ongoing project budgets (Task 2.2) and to work with Council staff to complete a draft SOY (Task 2.4) with review by the fish and wildlife managers (Task 2.5).

Task 2.1  Coordinate the fish and wildlife managers in conducting an annual status review of  ongoing project implementation and budgets.

Task 2.2  Cooperate with BPA and Council staff to track project budgets at the province and regional scales.

Task 2.3  Assist project sponsors to update budget needs for capital projects.

Task 2.4  Work with NWPPC staff to develop a draft annual capital plan and start-of-year budget for the F&W Program

Task 2.5   Facilitate the fish and wildlife manager review of a draft capital plan and SOY budget.

Objective 3.  Produce fish and wildlife recommendations on within-year modifications to project scopes-of-work and budgets.

Each year, after the adoption of the SOY, the situation changes for numerous projects, necessitating changes in their scopes-of-work and budgets.  The Authority proposes to continue assisting project sponsors with their within-year modification requests by answering questions, reviewing documents and facilitating sponsor coordination (Task 3.1).  The Authority then proposes to coordinate the fish and wildlife managers’ review of these changes and help the Council staff with their presentation to the Council (Tasks 3.2 & 3.3).

Task 3.1  Assist project sponsors in developing modification requests.

Task 3.2  Facilitate fish and wildlife manager review of requests.

Task 3.3  Work with Council staff to coordinate fish and wildlife manager presentation to the Council.

Objective 4.  Produce coordinated fish and wildlife manager recommendations on Program amendments.

The Northwest Power Planning and Electric Conservation Act (The Act) accords special status to the “fish and wildlife agencies and tribes” in making recommendations to the Council regarding Fish and Wildlife Program amendments.  The Authority proposes to continue its role of coordinating the development and presentation of the fish and wildlife managers’ Program amendment recommendations.

Task 4.1  Facilitate discussion of fish and wildlife manager views.

Task 4.2  Assist fish and wildlife managers to develop consensus (or at least coordinated) positions.

Task 4.3  Coordinate the fish and wildlife managers’ presentation of the recommendations.

Task 4.4  Work with Council staff and others to achieve regional support for the recommendations.

Objective 5.  Produce coordinated fish and wildlife manager comments on regional issues.

Regional fish and wildlife decisions benefit from review and comments of the fish and wildlife managers.  As the single organization where all nineteen of the region’s fish and wildlife managers come together, the Authority proposes to continue its role of helping the managers develop and present consensus opinions on regional issues.  Where consensus is not attained, the Authority’s efforts still add value by focusing the issues and coordinating the responses.

Task 5.1  Facilitate fish and wildlife discussion of regional issues.

Task 5.2  Assist fish and wildlife managers to develop consensus (or at least coordinated) comments.

Task 5.3  Coordinate fish and wildlife managers’ presentation of the comments.

Objective 6.  Facilitate the collective involvement of the fish and wildlife managers in regional planning.

With the numerous fish and wildlife planning efforts underway or planned, great demands for the fish and wildlife managers’ technical expertise can be anticipated.  Among the efforts are subbasin planning, technical recovery planning, subbasin assessment ground-truthing, hatchery planning for the Council’s Program and ESA recovery planning, and production and harvest planning under the U.S. v. Oregon jurisdiction.  The Authority proposes to assist the fish and wildlife managers in coordinating these various demands on their staffs’ time.

Task 6.1  Work with Council and BPA staff to identify activities requiring the collective expertise of the fish and wildlife managers.

Task 6.2  Coordinate the appropriate fish and wildlife managers to provide the needed expertise.

Objective 7.  Facilitate information exchange on regional fish and wildlife matters.

The Authority proposes to continue its efforts to make information available to all parties in the Columbia River Basin.  The Authority has a web site with information on activities, criteria, schedules, and policy issues for the rolling Provincial Review, Council Program amendment processes, and subbasin planning (developing).  As a part of these efforts, the Authority maintains a variety of data bases of project and proposal information, budget data, a regional calendar, addresses, etc.  The proposal intends to assist the region in developing an Internet-based project data base.  The Authority staff proposes to continue efficiently distributing documents, notices, and information to interested parties.

Task 7.1  Maintain CBFWA Internet web site

Task 7.2  Maintain databases of  current and past project budgets and objectives, addresses, and regional calendar of activities

Task 7.3  Distribute fish and wildlife documents

Task 7.4  Assist BPA and NWPPC in developing Internet-based project data base

Objective 8.  Compile an Annual Report on the status and trends of fish and wildlife populations in the Columbia River Basin

The Council’s 2000 Fish and Wildlife Program on calls for “a program to evaluate whether the individual actions in the various subbasins are achieving the objectives of the program stated at the basin and province levels” (p. 33).  The Program also states “The goal should be for the Council to produce an annual evaluation report of the success of the program in meeting its objectives.”  The purpose of this objective is to develop a draft document to assist the Council in their implementation of the above parts of the Program.  The fish and wildlife managers, facilitated through the Authority, will assemble the fish, wildlife and habitat objectives for the subbasins and will compile and analyze the available data on their status and trends.

Task 8.1  Facilitate managers technical and policy input to the Annual Report

Task 8.2  Conduct and assemble analyses of the current status and trends in fish and wildlife populations and/or their habitats

Objective 9.  Coordinate technical and policy input by the fish and wildlife managers to regional research, monitoring and evaluation activities

Subbasin planners need to have some means of determining the relative chance of success for alternative recovery strategies in order to make informed choices.  The Authority proposes to coordinate the fish and wildlife managers’ draft recommendations to the subbasin planning process by providing an analysis of the likelihood of success for proposed recovery strategies.

Task 9.1  Provide technical support and facilitate managers' input to identification of objectives, performance standards and attributes for subbasin plans.

Task 9.2  Provide technical support and facilitate managers input to evaluation activities to determine whether proposed subbasin strategies and resultant processes will achieve basin and province level objectives and performance standards.

Objective 10.  Facilitate regional Habitat Evaluation Procedure team

The managers propose providing funding for a regional Habitat Evaluation Procedure (HEP) team to consolidate the HEP activities currently being carried out by individual wildlife mitigation projects.  The purpose of this team is to provide more consistent, accurate and cost effective estimates of habitat units measured through the HEP.  HEP is called for in the Fish and Wildlife Program and is used to determine credit for BPA wildlife mitigation activities.

Task 10.1  Manage HEP team subcontract

Task 10.2  Assist HEP team with logistical support and schedule coordination

Methods

The Authority and its staff have developed a network of relationships that allow the organization to develop consensus points-of-view among all of the organizations (federal, state, tribal) having authority for the management of fish and wildlife in the Columbia River Basin.  To accomplish the objectives and tasks listed, the Authority uses the following methods.

- Provides a forum for the fish and wildlife managers to discuss issues of mutual concern and formulate unified recommendations.

- Coordinates a hierarchy of committees of fish and wildlife managers able to address technical and policy issues.

- Maintains a web site for posting information, schedules, documents, and meeting agendas and action notes.  The web site also serves as an access point to Authority data bases of addresses, project proposals, subbasin summaries, data, and links with other sites within the fish and wildlife community.

- Has staff and facilities to distribute materials by mail, email, fax, and web, organize and facilitate meetings, resolve disputes, conduct technical and policy analyses, and provide educational and outreach services.

- The Foundation is a non-profit non-governmental organization (NGO) that can enter into contracts with public and private entities and can collect and maintain financial records.

g. Facilities and equipment

The CBFWA is centrally located in downtown Portland.  Meeting facilities include two conference rooms with teleconferencing equipment, onsite parking, and reception/clerical services.  Office equipment includes a high speed copier/scanner, networked computers with up-to-date software, broadcast faxing, email, telephone system, Xerox copier, and a web page with current calendar and directory information.  CBFWA also maintains a comprehensive filing system, archives and a library.  In addition, a fully equipped office is available for manager or meeting participant use.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| (Replace this text with your response; use regular Word commands to add/del/move rows) |  |

# Section 10 of 10. Key personnel

# JANICE M. ECKMAN

## Assistant Director

### WORK EXPERIENCE

Possesses over 27 years in administrative and managerial experience.  Training includes formal education in business, ongoing education and training through management and human resource classes and seminars, and on-the-job training classes offered.

1/2002 – Present

### Acting Executive Director, CBFWA

- Coordinates agendas for all meetings.

- Maintains a close liaison with the CBFWA Members through frequent individual visits, phone conferencing and periodic meetings in conjunction with the NWPPC meetings, and maintains a liaison between the Members and the natural resource interest groups.

- Assures the CBFWA staff represents all Members equally, performing duties with competence and initiative, but within the limits prescribed by the Authority’s positions and Charter.

- Supervises CBFWA staff and the fiscal affairs of the CBFWA, including preparing annual budgets in consultation with the Fiscal/Contract Administrator of the CBFWA, and supervises through the Assistant Director(s) of operations and administration of CBFWA contracts.

- Carries out all policy decisions of the CBFWA Members as they relate to the Program.  Responsible for the implementation and monitoring of the policy decisions developed directly between BPA, CBFWA, and NWPPC.

- Performs other duties as directed by the CBFWA Chairperson.

6/95 – 1/2002

Assistant Director for Administration, CBFWA, and Vice President, Columbia Basin Fish and Wildlife Foundation (CBFWF)

Works in concert with the Executive Director to establish and implement the management objectives, priorities, and deadlines to accomplish the objectives of the Members as described in the CBFWA Work Plan.  Serves as the Executive Director’s representative at professional meetings and contract negotiations as directed.  Oversees the activities and work flow of the administrative support staff to ensure quality and timely work products.  Performs all duties associated with personnel administration and management, i.e., performance evaluations, position reviews, work plans, development and preparation of performance descriptions and performance review for all CBFWA support staff.  Analyzes office operations and procedures for uniformity and efficiency.  Maintains office operating standards and policies.  Oversees comprehensive administration of group benefit policies and reporting requirements.  Administers the fiscal staff and approves funding requests, contract proposals, budgets, and statements of work to assure consistency of project requirements.  Responsible for assurance that the Foundation’s legal requirements are met in fiscal operations, personnel, employment practices, and general liability coverage’s.

10/87 – 6/95

Executive Assistant , CBFWA

Serves as the office manager, overseeing information flow and interoffice work assignments.  Supervises the administrative assistant, clerical receptionist and the work products of the data manager.  Interprets necessary action on CBFWA correspondence, determines distribution and assigns responses to appropriate CBFWA staff or committees.  Oversees the maintenance of the CBFWA calendar.  Develops and distributes the assignment calendar.  Responsible for researching and establishing a network system and an accounting system.

#### THOMAS G. GIESE

## Funding Coordinator

### EDUCATION

B.A. in Chemistry, Reed College

M.A. in Chemistry, University of Oregon

M.A. in Environmental Biology, University of Colorado

### WORK EXPERIENCE

1993 – present

Funding Coordinator, Columbia Basin Fish and Wildlife Authority (CBFWA)

Responsible for coordinating and facilitating the development of an annual work plan by the CBFWA members to implement the Fish and Wildlife Program.  This requires continuous liaison with the fish and wildlife agencies and tribes, the Bonneville Power Administration, and the Northwest Power Planning Council.  Serves as the staff liaison to the Independent Scientific Advisory Board.

1990 – 1993

### Fish and Wildlife Manager, Pacific Northwest Utilities Conference Committee (PNUCC)

In addition to the duties listed below, supervised three staff, managed consultant contracts, and did related work planning, scheduling, and budgeting.

1983 - 1990

### Senior Planner, Pacific Northwest Utilities Conference Committee

Formulated and presented policy on a wide range of issues for a regional electric utility trade organization.  These issues included fish and wildlife, hazardous waste, and alternative electric power generation.  Managed projects in technically complex and politically sensitive areas, such as declining salmon runs on the Columbia River and PCB contamination from utility equipment.  Organized volunteer committees, assisted in member relations and represented PNUCC before political and regulatory bodies, such as the Northwest Power Planning Council and Bonneville Power Administration.

1981 – 1983

### Environmental Specialist, Bonneville Power Administration

Wrote agency policies and procedures to instruct employees on complying with the Clean Water Act, Safe Drinking Water Act, and the Resource Conservation and Recovery Act.  Reviewed BPA’s Environmental Impact Statements to assure the agency’s compliance with state and federal environmental laws.

1978 – 1981

### Consulting Environmental Scientist

Worked and subcontracted on a variety of major energy and resource development projects.  Responsible for business development, study design, staff supervision, budgeting, and quality assurance.  Projects included biological assessments, water chemistry studies, and hydrologic impacts for the Northern Tier Pipeline EIS, Amax molybdenum mine studies, EIS for Columbia River Interstate highway bridge, 500kV transmission line in southern Oregon, and studies of forest land management.

1976 – 1978

### Staff Scientist, Oregon Student Public Interest Research Group

Responsible for organizing, directing, and presenting the results of environmental and health care research for a statewide public policy research group.  In addition to research and technical studies, the job involved numerous press conferences, delivering speeches, moderating public meetings, and working with volunteers.

#### FRANKLIN R. YOUNG

## Wildlife Coordinator

### EDUCATION

1962 – 1964	M.S. Fisheries Science, Oregon State University

1958 – 1962	B.S.  Wildlife Science, Oregon State University

### WORK EXPERIENCE

1993 to present	Resource Coordinator, Columbia Basin Fish and Wildlife 					Authority, Portland, Oregon

1964 – 1993		Fisheries Biologist, Oregon Department of Fish and Wildlife

### PUBLICATION

Ward, David L., Raymond R. Boyce, Franklin R. Young, and Frederick E. Olney.  A Review and Assessment of Transportation Studies for Juvenile Chinook Salmon in the Snake River.  North American Journal of Fisheries Management 17:652-662.  1997.

TOM K. IVERSON

Anadromous Fish Analyst

EDUCATION

- M.S. in Fisheries Management, University of Washington, Seattle, Washington

- B.S. in Fisheries Management, University of Washington, Seattle, Washington

WORK EXPERIENCE

2/1999 to Present

Columbia Basin Fish and Wildlife Authority, Portland, Oregon

Provides technical and policy assistance to the Anadromous Fish Caucus (AFC) in support of its planning and implementation activities:

- Assist in the development of elements of work plans for various components of the anadromous fish programs, e.g., research, monitoring, and evaluations; capital improvements at dams; subbasin plans.

- Assist in tracking and reporting of the implementation of Authority work plans;

- Assist in the annual reporting and evaluation of implementation activities.

- Assist in updating the Multi-Year Plan, providing a technical and analytical assessment of strategies and objectives.

Attends AFC meetings, assists in development of meeting agendas, ensures timely notification of meetings, and completion and distribution of meeting notes, maintains a record of Anadromous Fish Managers (AFM) actions, and provides other administrative assistance in support of AFC meetings at the request of the caucus chair.

Assists in preparing issue, information, and response papers, presentations to the Northwest Power Planning Council (NWPPC) and others.  Makes presentations to the AFC and informs the other caucuses of AFM actions.  At the specific request of the caucus chair, makes presentations to NWPPC and others.

Compiles and analyzes information summarizing anadromous fish management accomplishments, including those under the fish and wildlife program, and prepares a comprehensive summary of project priorities and program needs.

Coordinates with other CBFWA staff to ensure AFM materials are distributed and AFC support requirements fulfilled.

1994 – 1999

Hydroacoustic Technology, Inc., Seattle, Washington

Fisheries Biologist / Project Leader

Responsible for hydroacoustic evaluations of salmon and trout distributions and migrational characteristics at dams on the Columbia River, and in rivers in Washington, Alaska, and elsewhere in North America.  Also conducted mobile hydroacoustic surveys of fish in lakes and at sea. Duties included study plan development, budget review, equipment deployment, staff hiring and scheduling, data collection, data analysis, and report writing.  In addition, this position involved instructing hydroacoustic theory and applications at short courses and as guest lecturer at the University of Washington, managing a large equipment lease pool, and performing transducer calibrations.  Certified SCUBA diver, and holds U.S. Fish and Wildlife Service Electrofishing certification.

1987 – 1993

University of Washington, Seattle, Washington, School of Fisheries

Fisheries Biologist III – Harvest Technology Study, Columbia River

Project Leader for investigation of potential commercial harvest techniques for the removal of northern pikeminnow (previously known as northern squawfish) from the Columbia River.  Developed research goals, established budgets, monitored spending, hired, scheduled and supervised employees.  Established remote field stations.  Performed fish sampling using baited longlines, purse seines, beach seines, floating and sinking gillnets, baited pots, Merwin traps, several different lake traps, electrofishing, and angling.  Also responsible for data collection, data entry, report writing and editing, meeting with public and other agencies, developing new fishing gear, and conducting training seminars.

Technician – Cooperative Fisheries Research Unit.  Grass Carp Research Project.  Collected data by performing various tasks with the Co-op including hydroacoustic surveys in small lakes, stomach content analysis, benthic invertebrate population analysis, gill netting, scale reading, and plant biomass estimations.

1983 - 1988

Commercial Fisherman – Cook Inlet and Bristol Bay, Alaska

Foreman/Deckhand.  Set gillnets targeting sockeye salmon.

NEIL E. WARD III

Resident Fish Technical Analyst

EDUCATION

- MS – Wildlife and Fisheries Sciences (Fisheries Management), South Dakota 	State University, Brookings, SD

1990	BS – Wildlife and Fisheries Sciences (Fisheries Management), Texas A&M 		University, College Station, TX

WORK EXPERIENCE

8/1991 to Present

Resident Fish Committee

Provides technical and policy assistance to the Resident Fish Committee (RFC) in support to its planning and implementation activities:

- Assists in development of detailed work plans.

- Assists in tracking implementation of specific program activities, evaluation, and annual reporting at the request of the caucus chair.

- Attends meetings as assigned by the RFC chair, and identifies issues affecting Resident Fish Managers (RFM) and provides information and recommendations back to the RFM.

- Assists in preparing issue and information papers, presentations to the NWPPC and others.  Makes presentations to the RFC.  At the specific request of the RFC chair, makes presentations to the NWPPC and others.

- Facilitates scientific review of resident fish projects by the RFM and other interested parties.

- Provides technical analysis for policy recommendations and related issue papers to address resident fish issues.

- Coordinates schedules, priorities, and work tasks with the RFC chair throughout the month.

- Attends RFC meetings, and prepares and distributes timely meeting notices/agendas.  Prepares and distributes minutes/action notes.  Includes background information, action items, tasks and a calendar of time-sensitive issues.

- Assists with other projects as assigned by the RFC chair.

Rolling Provincial Review

Facilitates various aspects of the NWPPC Rolling Provincial Review:

- Works with other CBFWA staff and NWPPC staff to develop meeting agendas and review process guidelines.

- Coordinates and facilitates meetings, site visits, and project reviews.

- Works with potential project sponsors at their request to educate and involve them in the process.

Artificial Production Advisory Committee

Represents the CBFWA in the NWPPC’s Artificial Production Advisory Committee.

- – 1999

Research Coordinator, Texas Parks and Wildlife Department, Athens, Texas

Developed and supervised a fish genetics, health, and water quality laboratory, and planned, organized, directed, and performed associated research.

- Prepared research proposals, technical reports, manuscripts, and presentations addressing fisheries management, conservation genetics, fish health, and hatchery issues.

- Determined policies and procedures and explored technology applications.

- Coordinated with regulatory authorities to execute appropriate lab procedures.

- Supervised and coordinated daily activities of two laboratory technicians.

- Served on the department’s research committee, manuscript review committee, and genetics committee.

Planned, organized, promoted, and implemented a public ourtreach program.  Credited by management for resurrecting the program’s image among scientists, media, and the public.

- Established productive relationships with the media.

- Promoted the program via radio, television, newspaper, and magazine interviews, trade shows, educational seminars, and public meetings.

- Liaison to science, public, and media groups.

1993 – 1996

Genetics Research Assistant, Oregon Cooperative Fishery Research Unit, Department of Fisheries and Wildlife Sciences, Oregon State University,

Corvallis, OR

Conducted genetic and morphological research of wild and hatchery salmonid populations.

- Analyzed and interpreted data.

- Prepared and edited scientific manuscripts.

- Communicated findings to diverse audiences.

- Supervised, trained, and assisted student workers and graduate students.

1993

Teaching Assistant – Ichthyology, Department of Fisheries and Wildlife Sciences, Virginia Polytechnic Institute and State University, Blacksburg, VA

Designed and implemented teaching outlines for an ichthyology laboratory.

- Prepared and presented weekly lectures.

- Provided instruction on the safe and proper use of fish collection equipment.

- – 1992

Graduate Research Assistant – Department of Wildlife and Fisheries Sciences, South Dakota State University, Brookings, SD

Designed, developed, and maintained a fish genetics laboratory.

- Performed genetic and morphological analyses.

- Prepared progress reports and manuscripts.

- Assisted with electrofishing, netting, telemetry, fish aging, and food habit studies.

- Supervised a student worker.