## Task Descriptions
Sheldon & Associates, Inc |  | SCOPE OF WORK
Tillman Creek Wetland Mitigation Construction
Prepared on 10/20/03 for the Bonneville Power Administration
Task 1 - Permitting Assistance
Provide continued permitting assistance for the Biological Evalaution and JARPA and respond to agency revisions and changes to BE.
Task 2 - Project Planning and Support
Provide construction details as needed by contractors to allow more detailed planning for construction. Coordinate and attend site meetings with agency staff, BPA/YN staff, and contractors during the planning and permitting phase (pre-construction). Ongoing coordination for construction planning and implementation with tribal and BPA staff.
Assumptions: up to 4 site meetings with agency staff and BPA/YN staff, 1 site meeting with contractors; bid documents will not be necessary for project construction
Task 3 - Construction Oversight
Provide construction oversight and coordination for all phases of construction
Assumptions: up to 2 pre-construction meetings; 8 working days for sitework (perfomed by sub) with oversight provided every day; travel and per diem assumed for overnight stays during sitework phase of work; 10 working days for plant installation (performed by sub) with 2 full days of oversight and 4 half-days of oversight; travel without overnight stays assumed for plant installation phase of work; 1 day or 2 half days of oversight for irrigation installation (performed by sub); travel without overnight stays assumed for irrigation installation phase of work. Materials for habitat features will be purchased and delivered to construction site by tribal staff (cost not included under this contract).
Note: Cost of sitework based on cost estimate provided by Concord Construction (Wapato, WA) in July 2003. Concord Construction assumptions are shown on attached sheet with estimate (no tax is included).
Note: Cost of plant installation and irrigation installation provided by TerraDynamics (Tukwila, WA) & Wray Irrigation (Ellensburg, WA).
Costs are based on the assumption that project construction will occur in 2004.
Task 4 - As-Built Site Survey and Report
Provide as-built topographic site survey (1' contour interval)of project area. Establish monitoring parameters (plots, transects, wells, photo-points etc.). Prepare as-built report which also includes mapping of installed plant communities.
Note: Cost of site survey based on estimate provided by Don Wilton Surveying (Yakima, WA)
Task 5 - Project Management
Provide coordination and project management
Assumptions: project construction will occur in late summer/fall 2004
Task 6 - Monitoring for 3 Years
S&A will perform monitoring services necessary to assess whether the mitigation site will meet performance goals. These services will include monitoring for vegetation (twice annually), hydrology (twice annually), invertebrates (annually), wildlife (annually), and stream temperature (continuous from March through September). Data will be collected, compiled, and analyzed by S&A staff. S&A will also provide services necessary to manage the project, including phone calls, emails, billing, agency coordination and internal staff coordination. Site monitoring and maintenance will not be needed until the Spring following construction.
S&A will prepare a monitoring report summarizing our findings and recommendations for the mitigation site after all annual monitoring has been completed. The report will provide detailed information on the conditions at the mitigation site, an assessment of progress toward the project goals, and recommendations, as needed, for improving conditions at the site.
S&A will perform contingency site visits, write memos, and coordinate with agency staff and contractors to address problems that may arise. These site visits may be necessary to meet with contractors, check on additional work that is done, or to increase the frequency of site visits due to problems at the site that need to be monitored more frequently.
Assumptions: project construction will occur in late summer/fall 2004. Contingency site visits will only be performed if needed - if no additional site visits are required, time budgeted for this task will not be used.
Task 7 - Maintenance for 3 Years
TerraDynamics, as subconsultant to S&A, will perform services to maintain the mitigation site. This will include controlling invasive and noxious weeds, protecting installed plants from animal damage, re-planting as instructed by S&A as per TerraDynamic's warranty, and collecting garbage from the site. Wray Irrigation will provide regular site visits during the growing season (Years 1 and 2 only unless, watering continues into Year 3 due to additional planting) to check on system and trouble-shoot any problems. Wray Irrigation will report to S&A or directly to TerraDynamics to discuss problems or irrigation system adjustments that may be neccessary.
Assumptions: set-up and operation of temporary irrigation system is not included in TerraDynamics cost. TerraDynamics will perform 6 maintenance visits in Year 1 and 4 visits in Years 2 and 3 with 2 days per visit. Troubleshooting of irrigation system under this cost estimate assumes maintenance due to normal wear and tear and winterizing of system.
* Expenses Include: Mileage, Parking/Tolls, Travel, Per Diem, Copies, Reproduction, Mylars, Oversized Prints, Fax, Film, Maps, & Field Supplies.
* See cost estimate for staff hours and subconsultant costs.

## Total Cost By Task
CLIENT : |  | Bonneville Power Administration
PROJECT : |  | Tillman Creek Wetland Mitigation Construction | [7 empty] | Proj. No.: | 03-777
SCHEDULE : |  | Begin In November 2003 - End in December 2007 | [7 empty] | Date: | 2003-10-20
LEVEL OF EFFORT – STAFF HOURS
|  |  | PHASE/TASK DESCRIPTION |  |  | Wildlife | Designer/ | Biologist/ | Concord | Terra | **Wray | Don Wilton
[5 empty] | Principal | Biologist | Biologist | Hydrologist | Construction | Dynamics | Irrigation | Surveying
|  |  |  | Year 2004-05 | 105 | 80 | 85 | 85 | SUB | SUB | SUB | SUB
|  |  |  | Year 2006-07 | 110 | 85 | 87 | 87
Task 1 | PERMITTING SUPPORT
| Permit support for JARPA and BE, BE revisions |  |  |  | 4 | 10 | 12 | 8
[5 empty] | 420 | 800 | 1020 | 680
[9 empty] | Labor & Subs | 2920 |  | 3070
[9 empty] | Expenses | 150 |  | TOTAL TASK 1
Task 2 | PROJECT PLANNING & SUPPORT
| Site meetings with agency staff, client, contractors |  |  |  | 16 |  | 40
[5 empty] | 1680 | 0 | 3400 | 0
[9 empty] | Labor & Subs | 5080 |  | 5625
[9 empty] | Expenses | 545 |  | TOTAL TASK 2
Task 3 | PROJECT CONSTRUCTION & OVERSIGHT
| Pre-Construction Meetings |  |  |  | 8 | 8 | 8 | 8 |  |  |  |  | 2840 |  |  | 2840
| Site work (assumes 8 working days/plus travel) |  |  |  |  | 22 | 60 | 24 |  |  |  |  | 8900 | 35000 | 4800 | 48700
| Plant Installation: plants & materials, installation | [5 empty] | 40 | 19 |  |  |  |  | 5015 | 31000 | 3100 | 39115
| Irrigation installation | [5 empty] | 12 | [5 empty] | 1020 | 8000 | 800 | 9820
[5 empty] | 8 | 30 | 120 | 51 | [7 empty] | 100475
[5 empty] | 840 | 2400 | 10200 | 4335 | 35000 | 31000 | 8000
[9 empty] | Labor & Subs | 91775 |  | 100475
[9 empty] | Expenses | 1300 |  | TOTAL TASK 3
[9 empty] | Sub Mark-up Fee of 10% | 7400
Task 4 | AS-BUILT SITE SURVEY & REPORT
| Provide as-built topographic site survey | [11 empty] | 0 | 5000 | 500 | 5500
| Establish monitoring parameters | [5 empty] | 20 | 20 |  |  |  |  | 3400 |  |  | 3400
| Prepare as-built report | [6 empty] | 24 |  |  |  |  | 2040 | 400 |  | 2440
[5 empty] | 0 | 0 | 20 | 44 | [7 empty] | 11340
[5 empty] | 0 | 0 | 1700 | 3740 |  |  |  | 5000
[9 empty] | Labor & Subs | 10440 |  | 11340
[9 empty] | Expenses | 400 |  | TOTAL TASK 3
[9 empty] | Sub Mark-up Fee of 10% | 500
Task 5 | PROJECT MANAGEMENT
| Project management and coordination with |  |  |  | 6 | 6 | 78 | 12
| contractors, client, tribal, and agency staff |  |  |  | 630 | 480 | 6630 | 1020
[9 empty] | Labor & Subs | 8760 |  | 10060
[9 empty] | Expenses | 1300 |  | TOTAL TASK 4
Task 6 | MONITORING FOR 3 YEARS
| Year 1 (2005): Monitor & prepare annual report |  |  |  | 6 | 79 | 56 | 43
| Year 2 (2006): Monitor & prepare annual report |  |  |  | 6 | 79 | 56 | 43
| Year 3 (2007): Monitor & prepare annual report |  |  |  | 6 | 79 | 60 | 43
| Contingency site visits (for all three years combined) |  |  |  | 8 | 8 | 30 | 8
[5 empty] | 26 | 245 | 202 | 137
|  |  |  | [This subtotal reflects billing rate increases in year 2006/07] | 2830 | 20430 | 17462 | 11833
[9 empty] | Labor & Subs | 52555 |  | 56855
[9 empty] | Expenses | 4300 |  | TOTAL TASK 3
Task 7 | MAINTENANCE FOR 3 YEARS
| Year 1 (2005): Maintain mitigation site |  |  |  | 0 | 0 | 0 | 0
Year 2 (2006): Maintain mitigation site
Year 3 (2007): Maintain mitigation site
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 |  | 19500 | 4000
[9 empty] | Labor & Subs | 23500 |  | 26350
[9 empty] | Expenses | 500 |  | TOTAL TASK 3
[9 empty] | Sub Mark-up Fee of 10% | 2350
|  |  |  | TOTAL HOURS | 60 | 291 | 472 | 252 | 0 | 0 | 0 | 0
|  |  |  | SUBTOTAL | 6400 | 24110 | 40412 | 21608 | 35000 | 50500 | 12000 | 5000
TOTAL DIRECT LABOR | [11 empty] | 92530
EXPENSES (Includes Mileage, Parking, Per Diem Travel, Copies, Reproduction, Mylars, Fax, Film, Maps, Field Supplies) | [11 empty] | 8495
SUBCONTRACTORS (Concord Construction, Terra Dyanamics, Wray Irrigation, Don Wilton Surveying) | [11 empty] | 102500
SUBCONTRACTOR MARK-UP FEE OF 10% | [11 empty] | 10250
TOTAL COMPENSATION | [10 empty] | 213775
*This cost estimate for professional services is based on assumptions detailed in the scope of work.
** No actual cost estimate was received from Wray Irrigation. Estimate was made by Sheldon & Associates, Inc. for the purposes of expediting this contract.

## Total Cost
CLIENT : |  | Bonneville Power Administration |  |  |  |  | Proj. No.: | 03-777
PROJECT : |  | Tillman Creek Wetland Mitigation Construction |  |  |  |  | Date: | 2003-10-20
SCHEDULE : |  | Begin November 2003 - End December 2007
LEVEL OF EFFORT – STAFF HOURS
|  |  | PHASE/TASK DESCRIPTION |  |  | Wildlife | Designer/ | Biologist/
[5 empty] | Principal | Biologist | Biologist | Hydrologist
Task 1 | PERMITTING ASSISTANCE
| Permit Support for JARPA and BE, BE Revisions |  |  |  | 4 | 10 | 12 | 8
Task 2 | PROJECT PLANNING & SUPPORT
| Site meetings with agency staff, client, contractors |  |  |  | 16 | 0 | 40 | 0
Task 3 | PROJECT CONSTRUCTION & OVERSIGHT
| Pre-Construction Meetings |  |  |  | 8 | 8 | 8 | 8
| Site work (assumes 8 working days/plus travel) |  |  |  | 0 | 22 | 60 | 24
| Plant Installation: plants, mulch, installation |  |  |  | 0 | 0 | 40 | 19
| Irrigation installation |  |  |  | 0 | 0 | 12 | 0
Task 4 | AS-BUILT SITE SURVEY & REPORT
| Provide as-built topographic site survey |  |  |  | 0 | 0 | 0 | 0
| Establish monitoring parameters |  |  |  | 0 | 0 | 20 | 20
| Prepare as-built report |  |  |  | 0 | 0 | 0 | 24
Task 5 | PROJECT MANAGEMENT
| Coordination with contractors, client, tribal, & agency staff |  |  |  | 6 | 6 | 78 | 12
Task 6 | MONITORING FOR 3 YEARS
| Monitor site in 2005 & prepare annual monitoring report |  |  |  | 6 | 79 | 56 | 43
* | Monitor site in 2006 & 2007 & prepare annual monitoring report |  |  |  | 12 | 158 | 116 | 86
| Contingency site visits |  |  |  | 8 | 8 | 30 | 8
Task 7 | MAINTENANCE FOR 3 YEARS
| Provide maintenance and irrigation for 3 years (Terra Dyanamics, Wray) |  |  |  | see below | 0 | 0 | 0
|  |  |  | TOTAL HOURS | 60 | 291 | 472 | 252
|  |  |  | 2004/05 HOURLY RATE | 105 | 80 | 85 | 85
|  |  |  | *2006/07 HOURLY RATE | 110 | 85 | 87 | 87
|  |  |  | SUBTOTAL | 6400 | 24110 | 40412 | 21608
TOTAL DIRECT LABOR | [7 empty] | 92530
EXPENSES (Includes Mileage, Parking, Per Diem Travel, Copies, Reproduction, Mylars, Fax, Maps, Field Supplies) | [7 empty] | 8495
SUBCONTRACTORS (Concord Construction, Terra Dyanamics, Don Wilton Surveying & Wray Irrigation) | [7 empty] | 102500
SUBCONTRACTOR MARK-UP FEE OF 10% | [7 empty] | 10250
TOTAL COMPENSATION | [6 empty] | 213775
*This cost estimate for professional services is based on assumptions detailed in the scope of work.

## Concord Cost Estimate
Our total cost to construct the two wetlands area on Tillman Creek located south of Cle Elum is $34,545.00. This cost include the mobilization, development of haul routes, stream crossing protection, moving of the material to ECP’s waste pond located just south of the stream crossing and the demobilization and rehabilitation of the site. We did not include the transportation of trees, tree rootballs, etc. as we are not sure where these are presently located. If they were on the site, we could place them prior to leaving without additional cost. Following is our cost breakdown of the specific activities mentioned above for your information:
1. Mobilization and set up of site | 1768
2. Demobilization and rehabilitation of site | 1768
3. Temporary Crossing @ creek | 2717
4. Clear, excavate and haul material | 24695
5. Dust control | 3597
TOTAL: | 34545