Response to the ISRP Review of FY 2007-2009 Proposals

Captive Broodstock Artificial Propagation

BPA Project Number 199801006

Response to General Comments:

We thank the ISRP for their review and comment on this project proposal and commend their efforts. We agree that the penultimate goal for this program is the return of F1 adults with the ultimate goal being naturally produced smolts from the spawning F1 adults. In the 19 December 2003 Review of Blue Mountain and Mountain Snake Province Captive Propagation Programs: Response to the Northwest Power and Conservation Council, we stated that “we recognize that the final measure of success of the program will be the production and return of an F2 generation.”  We also agree with the ISRP’s program assessment found in its “Programmatic Issue 12” review. The Panel concluded that:

“The Grande Ronde experimental design has the potential to provide meaningful insight into whether or not captive propagation can provide anything more than hatchery-origin adults retuning from the ocean. The ISRP recommends that the experimental design remain intact.” (ISRP 2004-14).

We acknowledge that captive broodstock technology is largely unproven and that uncertainty exists in terms of its application to preserve threatened Chinook salmon populations. Limiting factors extrinsic to the captive broodstock program may preclude program success. Yet the captive broodstock program is an attempt to maintain these populations. NPT and ODFW insist that monitoring and evaluation accompany their supplementation programs.  Since the captive broodstock program is experimental in nature it will attempt to answer many uncertainties as the project progresses.

Response to Specific Comments:

Reviewer Comment – “A response is requested that clarifies the tasks performed by each of these projects. Further, on page 17 of the narrative sub-objective 2.2, Monitor and evaluate captive broodstock post smolts reared at Bonneville Hatchery and Manchester Research Station; it is not clear whether this task is performed by NPT, ODFW, or NOAA Fisheries, this should be identified in a response.”

Proposer Response – The Nez Perce Tribe (NPT) is funded by BPA to participate in the Grande Ronde Captive Broodstock Program through Project #199801006 entitled, Captive Broodstock Artificial Propagation. The Tribe’s involvement is focused on the monitoring and evaluation of the fish taken into captivity and their F1 offspring and in serving on the Captive Broodstock Technical Oversight Team (TOT). Tasks associated with this assessment effort and program oversight are accomplished by a team of individuals from ODFW and NPT and sometimes the Confederated Tribes of the Umatilla Indian Reservation (CTUIR) and NOAA Fisheries. Fish culture activities at Wallowa Fish Hatchery, Bonneville Fish Hatchery, Manchester Research Station, Oxbow Fish Hatchery or Lookingglass Fish Hatchery are undertaken primarily by production crews from ODFW or NOAA Fisheries.  Fish culture activities at the Lostine Acclimation Facility, Catherine Creek Acclimation Facility and the upper Grande Ronde facility are provided by the NPT and CTUIR.

Specific tasks performed by NPT and ODFW are described in the proposal as “Milestone Specifications” on pages 15-20. For clarity’s sake, the following tables are provided to illustrate what NPT staff do, when and where. This 2006 schedule is typical of prior years as well. Data is collected by NPT staff and others during each activity. The TOT meetings are attended by the NPT project biologist and project leader. The “how” of these activities are described in the Captive Broodstock Annual Operating Plan (AOP) which is developed in December and formalized in January of each year.

Table 1. 2006 Field Activities Schedule

| Dates | Activity | Location |
| --- | --- | --- |
| Jan 23-27 | Quarterly sample (20/25%) | Wallowa Hatchery (WFH) Enterprise, Oregon |
| Feb. 13-17 | Prerelease Sampling of F1s | Lookingglass Fish Hatchery |
| Apr 10-14 | Inventory & vibrio inoculations (2004 cohort) Sample 2005 cohort from eyed eggs | Wallowa Hatchery Enterprise, Oregon |
| Apr 17-21 | 1ST maturity sort - ultra sound, Inventory, re-VI & re-PIT tagging | Bonneville Hatchery (BOH) Cascade Locks, Oregon |
| Apr 24-28 | 1ST maturity sort - ultra sound, Inventory, re-VI & re-PIT tagging | Manchester Research Station (MRS) Port Orchard, Washington |
| May 22-26 | 2nd maturity sort | BOH & MRS |
| Jun 5 – July 28 | Additional maturity sort if needed | BOH & MRS |
| Jul 25-28 | Inventory, VI tag and 1st maturity sort, & re-vaccinate BKD vaccine fish. Start at BOH | BOH & MRS |
| Aug 14-18 | Collect Lostine River parr & send to WFH | Lostine River |
| Aug 28-Sept 1 | Ripe sort and BEGIN SPAWNING. | BOH |
| Aug 25-Sept. 19 | Spawning ground surveys | Lostine River |
| October 16-20 | PIT tagging F1s | Lookingglass Fish Hatchery |
| Nov 13-17 | PIT tagging captive parr and genetic sampling | WFH |
| Nov 27 – Dec 1 | Sampling | BOH & MML |

Table 2. 2006 Technical Oversight Team Meeting Schedule

| Date | Location | Date | Location | Date | Location |
| --- | --- | --- | --- | --- | --- |
| Jan. 26 | LaGrande | May 4 | Manchester | Sept. 11 | Irrigon |
| February | No Meeting | June 15 | Enterprise | Oct. 26 | LaGrande |
| March 9 | LaGrande | July 24 | Irrigon | Nov. | No Meeting |
| April | No Meeting | August | No Meeting | Dec. 14 | LaGrande |

To answer the specific question about “subobjective 2.2”; the monitoring and evaluation activities associated with this objective are conducted by NPT and ODFW while at Bonneville Fish Hatchery and by NPT, ODFW and NOAA Fisheries when the activities occur at Manchester Research Station.

Reviewer Comment – “The project summary includes work done by this project and others – it is hard to tell who did what.”

Proposer Response – The five tables of cohort data and the six selected performance measures summarized in the proposal (pg 10-15) are results based on monitoring work accomplished by crews from NPT, ODFW, NOAA Fisheries and in some cases CTUIR. As stated above, the work is normally accomplished by a team of individuals from all these agencies. They work side-by-side in cooperation with each other. The collected information is then made available to all the program’s sponsors through the program’s Access database. The data in the tables were generated from querying the database.

Reviewer Comment – “No results are presented on adult returns”

Proposer Response – The Grande Ronde Captive Broodstock Program has produced F1 progeny that have returned as adults for conservation to the treatment streams since 2001. The project is collecting data, evaluating results from these returning fish and providing information consistent with the recommendations of the Council’s draft Columbia River Basin Research Plan (NPCC 2005), the Council’s Artificial Production Review and Evaluation Report (NPCC 2004) and NOAA Fisheries’ Interim Standards for the Use of Captive Propagation Technology in Recovery of Anadromous Salmonids Listed Under the Endangered Species Act (NMFS 1999). The project sponsors believe that the monitoring and evaluation component of this experimental project can provide the indicators and performance measures that help define a successful strategy that the region seeks. Analysis and evaluation have just begun to bear results from these F1 adults. Life history characteristics of these fish (age-at-return, size-at-return, sex ratios, migration timing, distribution, etc.) compare favorably with their wild counterparts. Relative reproductive success of the F1 progeny is encouraging based on preliminary information from DNA pedigree analysis (Moran 2005). More detailed results and performance information of these F1 fish can be found in Hoffnagle et al. 2004, Cleary et al. 2005 and Cleary et al. 2006. The following tables provide specific adult return results from the Lostine River (return numbers, migration timing, age structure, sex ratio, distribution).

Table 3.  Adult Chinook salmon captured at the Lostine River weir from 1997 to 2005 from the captive broodstock program, conventional program and natural origins.

| Year | Natural Origin | Conventional Progeny | Captive Brood Progeny | Total Adult Return |
| --- | --- | --- | --- | --- |
|  | No. | % | No. | % | No. | % |  |
| 1997 | 25 | 93% | NA | 0 | NA | 0 | 27 |
| 1998 | 23 | 100% | NA | 0 | NA | 0 | 23 |
| 1999 | 13 | 100% | NA | 0 | NA | 0 | 13 |
| 2000 | 64 | 70% | 27 | 30% | NA | 0 | 91 |
| 2001 | 344 | 77% | 75 | 17% | 25 | 6% | 444 |
| 2002 | 265 | 49% | 12 | 2% | 266 | 49% | 543 |
| 2003 | 239 | 52% | 28 | 6% | 197 | 42% | 464 |
| 2004 | 297 | 28% | 259 | 24% | 516 | 48% | 1,072 |
| 2005 | 193 | 23% | 285 | 35% | 346 | 42% | 824 |

Table 4. Estimated escapement of returning captive F1s, conventionals and natural adult Chinook salmon to the Lostine River from 1997 to 2005.

| Year | Estimated Natural Escapement | Estimated Escapement for the Conventional Program | Estimated Escapement for the Captive Program |
| --- | --- | --- | --- |
| 1997 | 171 | 0 | 0 |
| 1998 | 180 | 0 | 0 |
| 1999 | 101 | 0 | 0 |
| 2000 | 328 | 82 | 0 |
| 2001 | 529 | 135 | 42 |
| 2002 | 476 | 41 | 446 |
| 2003 | 564 | 66 | 463 |
| 2004 | 428 | 370 | 758 |
| 2005 | 213 | 340 | 413 |

Table 5.  Migration timing of returning captive F1s, conventionals and natural adult Chinook salmon to the Lostine River weir from 1997 to 2005.

| Rearing | Year | Number Captured | Range of Arrival | 10% | 50% | 90% |
| --- | --- | --- | --- | --- | --- | --- |
| Natural | 1997 | 27 | 7/18 – 9/22 | 7/31 | 8/19 | 9/10 |
| Natural | 1998 | 23 | 6/19 – 9/21 | 6/28 | 7/12 | 9/10 |
| Natural | 1999 | 13 | 7/19 – 8/27 | 7/23 | 7/29 | 8/13 |
| Natural | 2000 | 64 | 6/22 – 9/20 | 6/28 | 9/1 | 9/13 |
| Conventional | 2000 | 27 | 7/16 – 9/10 | 7/21 | 9/2 | 9/6 |
| Natural | 2001 | 338 | 6/1 – 9/18 | 6/15 | 6/24 | 9/3 |
| Conventional | 2001 | 79 | 6/5 – 9/11 | 6/19 | 7/8 | 9/4 |
| Captive | 2001 | 25 | 6/11 – 9/15 | 6/14 | 7/15 | 9/5 |
| Natural | 2002 | 265 | 6/14 – 9/16 | 7/5 | 7/19 | 8/29 |
| Conventional | 2002 | 15 | 7/5 – 8/29 | 7/5 | 7/22 | 8/29 |
| Captive | 2002 | 263 | 6/7 – 9/16 | 7/5 | 7/20 | 8/26 |
| Natural | 2003 | 239 | 5/16 – 9/10 | 7/1 | 7/11 | 7/24 |
| Conventional | 2003 | 30 | 6/28 – 9/15 | 7/6 | 7/10 | 7/23 |
| Captive | 2003 | 195 | 5/20 – 9/21 | 7/4 | 7/11 | 7/25 |
| Natural | 2004 | 297 | 5/19 – 9/12 | 6/22 | 7/11 | 8/23 |
| Conventional | 2004 | 254 | 6/14 – 9/16 | 7/4 | 7/16 | 8/3 |
| Captive | 2004 | 521 | 5/22 – 9/10 | 7/2 | 7/14 | 7/25 |
| Natural | 2005 | 193 | 6/9 – 9/16 | 6/25 | 7/12 | 9/1 |
| Conventional | 2005 | 285 | 6/5 – 9/9 | 6/22 | 7/8 | 7/23 |
| Captive | 2005 | 346 | 6/9 – 9/12 | 6/22 | 7/8 | 7/25 |

Table 6.  Sex ratios of returning captive F1s, conventionals and natural adult Chinook salmon to the Lostine River weir from 1997 to 2005.

| Rearing | Year | Males | Females | Female % | Male:Female Ratio |
| --- | --- | --- | --- | --- | --- |
| Natural | 1997 | 13 | 12 | 48.0 | 1.08:1.00 |
| Natural | 1998 | 12 | 11 | 47.8 | 1.09:1.00 |
| Natural | 1999 | 5 | 7 | 58.3 | 1.00:1.40 |
| Natural | 2000 | 43 | 21 | 32.8 | 2.05:1:00 |
| Conventional | 2000 | 26 | 1 | 3.7 | NA |
| Natural | 2001 | 203 | 136 | 40.1 | 1.49:1.00 |
| Conventional | 2001 | 36 | 41 | 53.2 | 1.00:1.14 |
| Captive | 2001 | 20 | 0 | 0 | NA |
| Natural | 2002 | 150 | 115 | 43.4 | 1.30:1.00 |
| Conventional | 2002 | 11 | 4 | 26.7 | 2.75:1.00 |
| Captive | 2002 | 128 | 135 | 51.3 | 1.00:1.05 |
| Natural | 2003 | 121 | 119 | 49.6 | 1.02:1.00 |
| Conventional | 2003 | 28 | 0 | 0 | NA |
| Captive | 2003 | 124 | 72 | 36.7 | 1.75:1.00 |
| Natural | 2004 | 155 | 142 | 48.2 | 1.08:1.00 |
| Conventional | 2004 | 176 | 84 | 32.3 | 2.10:1.00 |
| Captive | 2004 | 270 | 262 | 49.2 | 1.03:1.00 |

Table 7. Age class structure of returning captive F1s, conventionals and natural adult Chinook salmon according to brood year.

| Brood Year | Origin | Cohort Return (n) | Percent of Age Class in Cohort Age 3 Age 4 Age 5 |
| --- | --- | --- | --- |
| 1994 | Natural | 94 | 0.0 | 91.5 | 8.5 |
| 1995 | Natural | 108 | 7.4 | 78.7 | 13.9 |
| 1996 | Natural | 306 | 2.6 | 85.6 | 11.8 |
| 1997 | Natural | 608 | 8.4 | 78.9 | 12.7 |
|  | Conventional | 243 | 33.7 | 55.6 | 10.7 |
| 1998 | Natural | 599 | 2.2 | 63.6 | 34.2 |
|  | Captive | 578 | 7.3 | 74.0 | 18.7 |
| 1999 | Natural | 381 | 4.7 | 87.4 | 7.9 |
|  | Captive | 309 | 10.7 | 80.6 | 8.7 |

Table 8.  The annual percentage of natural Chinook salmon female carcasses per survey section found in the Lostine River from 2001 to 2005.

|  | Survey Section |
| --- | --- |
| Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 2001 | 34.9 | 0.0 | 4.7 | 11.6 | 39.5 | 2.3 | 7.0 |
| 2002 | 31.3 | 6.3 | 6.3 | 12.5 | 43.8 | 0.0 | 0.0 |
| 2003 | 37.8 | 0.0 | 2.2 | 0.0 | 28.9 | 6.7 | 24.4 |
| 2004 | 31.3 | 6.3 | 6.3 | 12.5 | 43.8 | 0.0 | 0.0 |
| 2005 | 14.3 | 14.3 | 0.0 | 14.3 | 42.9 | 0.0 | 14.3 |
| Average | 23.5 | 3.4 | 2.9 | 12.3 | 47.1 | 2.6 | 8.1 |

Table 9.  The annual percentage of hatchery Chinook salmon female carcasses per survey section found in the Lostine River from 2001 to 2005.

|  | Survey Section |
| --- | --- |
| Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 2001 | 57.9 | 0.0 | 5.3 | 5.3 | 31.6 | 0.0 | 0.0 |
| 2002 | 21.7 | 2.2 | 10.9 | 2.2 | 50.0 | 2.2 | 10.9 |
| 2003 | 25.0 | 0.0 | 2.3 | 4.5 | 29.5 | 11.4 | 27.3 |
| 2004 | 21.7 | 2.2 | 10.9 | 2.2 | 50.0 | 2.2 | 10.9 |
| 2005 | 24.1 | 0.0 | 5.2 | 5.2 | 39.7 | 6.9 | 19.0 |
| Average | 30.1 | 0.9 | 6.9 | 3.9 | 40.2 | 4.5 | 13.6 |

# Footnotes

Two hatchery strays were also interrogated at the Lostine weir in 1997.

# Text boxes

Nez Perce Tribe

Department of Fisheries Resources Management

Administration ( Enforcement ( Habitat/Watershed ( Harvest ( Production ( Research ( Resident Fish